## Schedule of Works
0
0
0
0
0
0
0
| CITY COLLEGE PLYMOUTH |  |  |  | 0
| KINGS ROAD |  |  |  | 0
| PLYMOUTH |  |  |  | 0
| PL1 5QG |  |  |  | 0
0
0
| PROJECT DETAILS: |  |  |  | 0
| STEM SECOND FLOOR ROOMS KS227/KS228/KS229 CONVERSION |  |  |  | 0
0
0
0
0
0
0
0
0
0
|  | Qty | Item | Rate | £ p
0
| This specification is to be priced in conjunction with drawings: CCP-AH-ST2-01 CCP-AH-ST2-02 |  |  |  | 0
0
| PROJECT REQUIREMENTS |  |  |  | 0
0
| CONSTRUCTION WORKS |  |  |  | 0
0
1 | Allow to remove existing wall to create larger teaching space as indicated with dashed line, to include making good walls and ceiling. |  |  |  | 0
2 | Allow to set aside section of skirting for re-use on new wall. |  |  |  | 0
3 | Allow to remove existing acoustic ceiling panels and return to CCP Estates. |  |  |  | 0
4 | Allow to construct new metal stud wall c/w Acoustic infill, finished with plasterboard and skimmed, leaving ready to decorate. |  |  |  | 0
5 | Allow to extend existing suspended ceiling in Room KS228 into Room KS227 approx. 27m2, to include all trims and matching tiles. |  |  |  | 0
6 | Allow to uplift existing flooring to Room KS227 and extend existing flooring from Room KS228 into Room KS227 approx. 27m2, to include all preparation works and trims. |  |  |  | 0
7 | Allow to re-fit set aside skirting, leaving ready to decorate. |  |  |  | 0
0
| DECORATION WORKS |  |  |  | 0
0
1 | Allow to remove all pictures, pin boards, wipe boards and notice boards. Do not remove media boards |  |  |  | 0
2 | Allow for preparation works to include filling any holes, sanding, filling, stopping and chalking |  |  |  | 0
3 | Paint walls with Crown Eggshell, colour to be White |  |  |  | 0
4 | Allow to make good skirting following wall removal and paint with Dark Grey undercoat and top coat Satinwood RAL 7016
5 | Allow to paint new and altered pipework |  |  |  | 0
0
| MECHANICAL WORKS |  |  |  | 0
0
1 | Allow to drain down system. |  |  |  | 0
2 | Allow to alter existing steel pipe in Room KS229 to new location. |  |  |  | 0
3 | Allow to relocate existing radiator in Room KS229 to new position. |  |  |  | 0
4 | Allow to remove existing radiator in Room KS228 and dispose and remove pipework back to main flow and return. |  |  |  | 0
0
| ELECTRICAL AND DATA |  |  |  | 0
0
1 | Allow to remove all power, data and services from wall that is to be removed. |  |  |  | 0
2 | Allow to install new twin compartment trunking to each run of workstations to include cable management access. |  |  |  | 0
3 | Allow for 2 no. double electrical sockets per workstation |  |  |  | 0
4 | Allow for 1 no. data point per workstation from existing comms cab located in room. New comms cab to be installed by others. Allow to provide satisfactory data test paperwork on completion allowing for termination at both ends. |  |  |  | 0
5 | Install new lighting to Room KS227 to match lighting in Room KS228 to include switching from the same position in Room KS228. |  |  |  | 0
0
0
| SUB TOTAL |  |  |  | 0
| VAT @ 20% |  |  |  | 0
| TOTAL PROJECT COST |  |  |  | 0