## Schedule of Works
0
0
0
0
0
0
0
| CITY COLLEGE PLYMOUTH |  |  |  | 0
| KINGS ROAD |  |  |  | 0
| PLYMOUTH |  |  |  | 0
| PL1 5QG |  |  |  | 0
0
0
0
| PROJECT DETAILS: |  |  |  | 0
| STUDENT HUB REFURBISHMENT |  |  |  | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
| This specification is to be priced in conjunction with drawings: CCP-AH-SU-01 CCP-AH-SU-02 CCP-AH-SU-03 CCP-AH-SU-04 |  |  |  | 0
0
|  | Qty | Item | Rate | £ p
| NOTES |  |  |  | 0
0
| Allow to move, re-position or protect any equipment to include Pool Tables, Table Tennis, office furniture and reception desk within the work area to avoid any damage. |  |  |  | 0
0
| Allow to remove and set aside all signs, posters, pictures, notice boards, pin boards and wipe boards. Allow to remove all transfers including adhesive. |  |  |  | 0
0
| STRIP OUT WORKS |  |  |  | 0
0
1 | Allow to uplift flooring to work area and dispose. |  |  |  | 0
0
2 | Allow to remove existing electrical supplies to Avon Partition wall and make safe. |  |  |  | 0
0
3 | Allow to remove existing air vents fitted in floor. |  |  |  | 0
0
4 | Allow to dismantle Avon Partition system and dispose. |  |  |  | 0
0
5 | Allow to overboard work defined area withh the exception of the lobby area KIB001A with 6mm plywood. |  |  |  | 0
0
6 | Remove all furniture, set aside ready for re-use |  |  |  | 0
0
| DECORATION WORKS |  |  |  | 0
0
| NOTES |  |  |  | 0
| Do not allow for painting of radiators, pipes, doors or windows |  |  |  | 0
| Allow to remove all door furniture from linings prior to painting. |  |  |  | 0
0
1 | Paint walls and pillars with Crown Eggshell, colour to be White |  |  |  | 0
0
2 | Paint 3 no. feature walls as indicated on drawing. Colour to be Orange RAL 2004. |  |  |  | 0
0
3 | Paint all single door linings and architraves (defined work area side only) with Dark Grey undercoat and top coat of Satinwood RAL 7016 |  |  |  | 0
0
4 | Paint all skirtings with Dark Grey undercoat and top coat of Satinwood RAL 7016 |  |  |  | 0
0
0
| FLOORING WORKS |  |  |  | 0
0
1 | Allow to lay over existing flooring a new 150mm high removable stage c/w with nosing and upstands. |  |  |  | 0
0
2 | To supply and fit new Forbo Vinyl flooring to 4 no. areas as per Drawing CCP-AH-SU-04 |  |  |  | 0
2.1 | To be fully fitted into the corner under the newly installed removable stage. Forbo Vinyl Flooring - Sarlon - Wood XL Modern (Colour - Carbon) |  |  |  | 0
2.2 | Forbo Vinyl Flooring (Sarlon - Cement) (Colour - Chalk) |  |  |  | 0
2.3 | Forbo Vinyl Flooring (Sarlon - Canyon) (Colour - Orange) |  |  |  | 0
2.4 | Forbo Vinyl Entrance Matting (Coral - Coral Classic)(Colour - Mouse Grey) |  |  |  | 0
0
| DECORATION WORKS |  |  |  | 0
0
1 | Paint walls with Crown Eggshell, colour to be White |  |  |  | 0
0
2 | Paint pillars with Crown Eggshell, colour to be White |  |  |  | 0
0
3 | Paint previously painted skirting with Dark Grey undercoat and top coat of Satinwood RAL 7016 |  |  |  | 0
0
4 | Paint door linings and architraves with Dark Grey undercoat and top coat of Satinwood RAL 7016 |  |  |  | 0
0
0
| SUB TOTAL |  |  |  | 0
| VAT @ 20% |  |  |  | 0
| TOTAL PROJECT COST |  |  |  | 0
0