Greater Manchester Health and Social Care Partnership:

Incentivising Delivery Through Payment Reform

Specification of Requirements

Final Version: 1.0

Date: 6 January 2017

# Specification of Requirements

## Background to the requirements

### Greater Manchester Health and Social Care Partnership (GMHSCP) require support to develop their approach for using payment and contract reform to align incentives, to enable health and social care transformation and public service reform in Greater Manchester (GM).  NHS England is procuring this service on behalf of the GM partners.

### GM partners are working together on the radical reform of public services through a series of challenging and ambitious programmes. This is driven by the need to address the forecast £6 billion gap between public spending and income generated in GM and the historic variation in health inequalities across our region.

### The scale of the financial challenge facing GM public services will continue over the coming years and continues to be a driver for change.   However we also have the ambition to improve outcomes for our residents, increasing independence and reducing the rising demand on public services. Devolution to GM provides a unique opportunity for the next phase of GM reform: ensuring all residents are equally connected to and benefit from current and future economic growth across GM.

### Historical opportunities and funding streams have meant that GM has a mixed economy of reform programmes, often structured around services, themes or Government departmental lines.  Devolution provides an opportunity to change that by co-designing with Government a programme of reform covering:

#### Health and Social Care integration:  GM is the first City Region in England to be given the opportunity to demonstrate how powers over health and social care could be devolved to it from national bodies to be effective from April 2016.

#### Complex dependency, work and skills:  Three programmes of reform including ten-fold expansion of Working Well, review of Further Education, and an opportunity to co-commission the next phase of the Work Programme.

#### GM review of services for children: GM is developing a radical programme of reform on services for children jointly with Government, including opportunities for greater collaboration between local authorities and partners.

### The initial focus for this work is health and social care integration:

#### In February 2015, the GM Clinical Commissioning Groups (CCGs), Local Authorities (LAs) and providers signed a Memorandum of Understanding (MoU) with NHS England committing to “the production, during 2015/16, of a comprehensive GM Strategic Plan for health and social care. This aligned with the 5 Year Forward View will describe how a clinically and financially sustainable landscape of commissioning and provision could be achieved over the subsequent 5 years, subject to the resource expectations set out in the 5 Year Forward View, appropriate transition funding being available and the full involvement and support of national and other partners.”

#### The GM Strategic Plan – ‘Taking Charge of our Health and Social Care in Greater Manchester’ (a copy is provided as Appendix A of this document) was built from the work to further integrate health and social care in the 10 locality footprints, the work across our acute providers to deliver reform opportunities and work already underway or developing across the GM footprint.  It recognised that in order to deliver the significant improvements in the outcomes of the people of GM and address the forecast financial challenges, there needed to be a comprehensive programme of transformation that takes place across GM.

### Our vision is “to deliver the greatest and fastest possible improvement to the health and wellbeing of the 2.8 million people of Greater Manchester”.

### Our strategic objectives are to:

#### Create a transformed health and social care system which helps more people stay well and take better care of those who are ill;

#### Align our health and social care system far more widely with education skills, work and housing; and

#### Make sure the system remains safe throughout.

### The outcomes we are trying to achieve are:

#### More GM children will reach a good level of development cognitively, socially and emotionally;

#### Fewer GM babies will have a low birth weight resulting in better outcomes for the baby and less cost to the health system;

#### More GM families will be economically active and family incomes will increase;

#### Fewer people will die early from cardio-vascular disease;

#### Fewer people will die early from cancer;

#### Fewer people will die early from respiratory disease; and

#### More people will be supported to stay well and live at home for as long as possible.

### We have structured our approach to delivery of our vision, objectives and outcomes around 5 Transformation themes and this provides a comprehensive framework for transformation which underpins GM’s Strategic Plan, which is outlined in Figure 1 below:

Figure 1:

### Since the approval of Taking Charge, we have developed and agreed the GM Commissioning for Reform strategy.  This strategy aims to ensure that we commission services at the right spatial level, collaboratively across public services to support community resilience and wellbeing; and ensure a focus on the outcomes we are seeking to achieve for GM.  With local services working together, focused on people and place, we want to transform the role of public services and take a more proactive approach rather than responding to crises.  We will need our mechanisms to contract and pay for services to reflect this approach.

### GM has also secured a £450m health and social care Transformation Fund to support the delivery of transformation in our localities and across GM.  A process is in place to enable proposals for how the Fund can be used to be developed, assessed and monies allocated.  A key part of the process, following the agreement to allocate monies, is the construction and signing of a Transformation Investment Agreement.  This contains key metrics demonstrating how and where monies will be spent and the impacts in terms of population outcomes, finance, activity shifts and decommissioning of the interventions supported by the monies.

### Contracting and payment reform

#### Both the GM plan and its constituent locality, provider and GM work stream plans describe the need to develop new models of care delivery and provision between primary, community, social and acute providers.

#### Whilst there are a number of ways to contract for and pay for services, in GM we believe that there is a case to understand all the existing models and how they can be used to facilitate our new models of care, but also challenge our understanding of new and innovative models to ensure that we deliver a truly integrated health and social care service focused on outcomes and financial balance and sustainability.

#### The current contracting and pricing mechanisms may not be suitable to facilitate the level of change we want to deliver in our timescales, as:

##### They incentivise an activity-based, as oppose to outcome-based approach;

##### They do not address the challenges of risk and benefit share between organisations (especially if the investing agency does not benefit);

##### They do not address the challenges of the delay between investment and investment return, especially when the service models being contracted for are focussed more on early intervention and prevention;

##### They tend to incentivise competitive, not collaborative behaviour and ideally should promote a healthy mixture of both; and

##### They do not support innovative practice and the translation of innovation into mainstream service delivery.

### Therefore in GM we have developed a specific enabling work stream (Incentivising reform) to support the implementation of our GM strategic and 10 locality plans, as we assert that the work to develop payment reform to align incentives and enable health and social care transformation is a key enabler to the successful delivery and implementation of our GM and locality plans.

### In GM, the New Economy (wholly owned by the GM Combined Authority, providing policy, strategy and research support to GM) has developed a Cost Benefit Analysis (CBA) tool, which has been adopted by HM Treasury and can be used in conjunction with the Green Book.  The model enables the appraisal and evaluation of interventions to service models and can support investment decision-making and the appraisal and evaluation to changes to public service provision.  This tool has been used as part of our process to allocate Health and Social Care Transformation Fund monies within GM to assess the ROI and benefits to be delivered of proposed programmes of reform.

### We are keen to use such methodologies in the implementation of new models of care, and understand how they can be used to develop, implement and evaluate the new models of care and how they inform our approaches to contracting and payment mechanisms as we move through implementation.

### The GM Strategic Partnership Board (All of the 37 organisations in GM) has agreed that there is a case for change and approved a small working group (comprised of representatives from commissioning, primary care, social care, community and Mental Health and acute) to develop a Programme plan / roadmap and business case for the work.

### The responsibility to develop a programme plan / roadmap and associated business case for contracting and payment reform will remain with the GM Health and Social Care team and be delivered through the 37 organisations that make up the GM Health and social care system. However external support is required to add specific support and capacity within the identified timeframe, to ensure our approach builds on current and existing work within GM and at a national level, whilst also looks to understand and be challenged by national and international examples of best practice from a range of public and private sector fields.

### The roadmap should also provide a high-level plan of the opportunities to expand these approaches beyond health and social care integration to other areas of public service reform.  This will link to initial work within GM to develop joint commissioning arrangements that are ultimately structured around holistic solutions to the issues people face, not just the commissioning of single services.  It will also align to and inform the new models of care emerging across GM, such as the development of Local Care Organisations, Hospital Groups / Chains and integrated commissioning.

### This approach should be phased to cover the areas highlighted in section 1.4 above (Health and Social Care Integration, Complex Dependency, Work and Skills and GM Review of Services for Children), in particular the services for children review, and complex dependency, employment and skills.  Where there are disincentives in payment reform, commissioning and contracting methods act as barriers to integrating total resources to solve complex problems, such as the organisations that benefit can be different to those that are contributing resources.  It should also be noted that Greater Manchester is a national intensive support site for the new multispecialty community provider (MCP) contract and the successful bidder will need to make some connections on this and how this new contractual vehicle for out of hospital services might connect and facilitate some of this work.

### This assignment provides a unique opportunity to be involved in the implementation of the GM health and social care strategic plan (and its 5 Transformation Programmes) and the 10 locality plans and this is one of our key enablers to reform as part of a devolved health and social care system.

### Therefore we are seeking professional advice and support to develop imaginative ways in which we can deliver the ambition that is set out in the 5 Transformation programmes of the GM plan and that of the 10 locality plans, the health and social care Memorandum of Understanding.

## Scope of the Procurement

### Overview

#### The aim of this phase of work is to develop and then facilitate the agreement across all 37 organisations that make up the GM Health and social care system, of a programme plan and roadmap to facilitate the sign up to the work through a joint statement / business case that will need to be a key deliverable of this work.

#### GMHSCP require proposals from bidders that will offer innovative, structured and evidence based approaches to delivering this programme in the longer term in addition to the programme plan / roadmap and business case.

#### The scope of the work is inclusive of mental health services and should take into account and align to work being undertaken at a national level on Mental Health Payment by Results.

#### Bid proposals should also take into account and align to the GM Primary Care at scale development and our work to move towards Local Care Organisations in each of the 10 GM localities.

#### We also want to ensure the scope of the work extends to contracting and payment mechanisms for social care.  This would ideally cover:

##### How different forms of contract and payment mechanisms can incentivise higher quality in high volume personal care services, such as home care and residential care; and

##### How social care payment mechanisms can incentivise integrated service delivery with health and how both can align to wider public sector.

#### Not included in the scope of this work are nationally-led programmes on MCP contracts through NHS England and Patient Level costing through NHS Improvement.  They will need to be triangulated to the GM work programme as the programme plan is developed, but this work will not seek to duplicate that which has already commenced.

#### We are committed to looking at how we can improve the health outcomes of our residents and deliver the GM priorities of economic growth and the reform of public services.

#### We are seeking support in how we deliver this ambition through an innovative use of current and the development of new models of contracting and pricing mechanisms and ensure we are clear on the financial implications and how the health and social care economy can be put onto a sustainable footing.

### Constraints and Dependencies

#### It should be noted that work has been undertaken to date across GM and in the localities and this work should collate and then build on that, not look to replicate or repeat work that has already commenced. The progress that we have made to date will provide an opportunity for the development and testing of a range of different models through live change programmes, which are at different stages of development and delivery.

#### It should also be recognised that the current payment structure has merits and may not need to be dismantled, but reformed to become more efficient.  This work should consider all options open to us.

#### The external support must utilise information that is available and provided by GM and its localities and build on the extensive work undertaken to date across GM and within localities on payment and contracting reform.

#### Ownership and leadership of the work will be retained by GM Health and Social Care leaders.

#### All data, data models and supporting information must be handed over to the GMHSCP Programme Director on completion of the work.

#### Intellectual property rights will be retained by the GM Local Authorities, Clinical Commissioning Groups and providers.

#### Any identified duplication of existing analysis and or data collection will not be funded through this contract.

#### The successful supplier will need to work within the standard IT infrastructure in operation within the GMHSCP Team.

#### The Programme Director will be the main point of contact for the supplier in the running and management of the contract, but the supplier will also be expected to work with key system leaders and managers as outlined by the GMHSCP Programme Director.

#### The GMHSCP Programme Director will be the main point of contact for the appointed supplier.

#### The base for the appointed supplier will be 3 Piccadilly Place, Manchester, M1 3BN, however the will also be expected to work and travel across the GM geography as the work requires.

#### The work is to be delivered within 12-weeks, as outlined in section 3.3 below.

## Overview of Requirements

### Requirements:

#### GMHSCP are seeking an external consultancy provider (either on a single supplier or consortia basis) with the capability of successfully delivering against the following requirements:

##### Programme plan for a short–term deliverable of the programme and a roadmap outlining the approach that the work stream will need to take over the next 3 years to achieve its objectives.  This will need to include a timetable and implementation plan for the work stream; (note the objectives are yet to be determined, this will be undertaken through a system workshop in February 2017);

##### Joint statement of commitment or business case detailing the rationale, objectives and outcomes for the work to be taken forward and outlining the process and approach that will be taken in the short and longer term (through the programme plan and roadmap) to facilitate support  of the development and delivery of the work stream by all the organisations in GM;

##### Repository of national and international good practice examples relating to incentivising reform through payment and contracting (this will need to be a live repository and should be able to be used as a good practice guide for the GM system as the need for new approaches are identified – see Section 3.7: Deliverable 3);

##### Suggested governance for the future of the work stream; and

##### Proposed capacity / resources needed to deliver the requirements of the work stream.  Both 3.1.1.4 and 3.1.1.5 should be included within the roadmap.

#### The appointed supplier will be awarded a 12 week contract to commence within the financial year 2016/17 and likely run into the next financial year, with key contract deliverables aligned to achieving the key deadlines.

#### The requirement is to deliver the products outlined in section 3.1.1 above, which will form the work package for the GM strategic plan enabling work stream of incentivising reform; describing how GM can use the reform of contract structures and payment systems as a mechanism for aligning incentives to deliver health and social care integration.

#### The project outputs should be fully aligned to the overarching aims of the GM Strategic plan ‘Taking Charge of our health and Social Care in Greater Manchester’ and the priorities and plans of the 10 GM localities.

#### It is important that any potential bidder approaches this with a view of building on the work that is already in place across GM (referenced in section 2.2 above)  and within localities and has experience of working with stakeholders across all of the settings including local authorities as well as the NHS.

#### It must be recognised that this work has to be delivered within challenging timescales and a constrained financial budget/day rate cap (see sections 3.3 and 3.9 below).

### Expected Outcome and Deliverables

#### The Supplier will be expected to support the GM Incentivising Reform Working Group and programme team to develop the deliverables, as detailed in section 3.1.1 as an enabler of health and social care transformation in GM.

#### The key milestones, deliverables and performance measures for the project are outlined in section 3.7 below.

#### External support is required to add capacity to leadership within the GM system, and to support the GM health and social care team to enable the agreed timeline and products to be completed.  It should also challenge our ambition and help us understand the potential alignment to national and international best practice.

#### We anticipate that to do this a combination of specialist skills and previous experience will need to be provided and we expect to receive bids from single suppliers and consortia, who will be able to demonstrate that they will bring together the leading experts in this field.

### Timescales & Implementation

#### To be delivered within the 12 week contract time frame from the agreed contract commencement date with the appointed supplier.

#### The key milestones, deliverables and performance measures in section 3.7, require all to be delivered within 10 weeks, allowing for a two-week flex period.

### Location

#### GMHSCP require flexible support to be based on site on a regular basis at GMHSCP offices at 3 Piccadilly Place, Manchester, M1 3BN so that the consultants can integrate and work with the GM Incentivising Reform Group to meet these deliverables.

#### The appointed supplier will also be expected to travel across the GM geography as the assignment requires.

### Roles and Responsibilities

#### GMHSCP will lead on contract management and arranging progress meeting as and when required. There will either be based at GMHSCP’s offices at Piccadilly Place, Manchester, M1 3BN or via conference call.

#### GMHSCP will have a project management team in place. The appointed supplier will work with the GMHSCP project management team for the duration of the contract.

#### GMHSCP will be responsible for nominating a responsible officer to act as a Contract Manager for this contract.

#### GMHSCP will monitor progress against agreed milestones and help troubleshoot any arising issues

#### The appointed supplier will be responsible for the identification of a Contract Manager to oversee the work and liaise with/report to the nominated GMHSCP Contract Manager

#### The appointed supplier will attend meetings with GMHSCP as and when required in relation to the delivery of this project and/or the resultant Contract.

#### The appointed supplier will be responsible for complying with all performance management requests from GMHSCP as outlined in sections 3.6 and 3.7.

#### The appointed supplier will not undertake any piece of work or provide representatives to attend any meetings without the prior agreement in writing from the GMHSCP Contract Manager.

#### The appointed supplier will be responsible for the overall project management. This will include the production of materials and set up of stakeholder meetings as necessary.

### Management Information & Governance

#### The contract will be held between NHS England and the appointed supplier based upon the terms and conditions set out in Document 4: Form of Contract of the Invitation To Tender documentation.

#### Strategic progress reports are expected on a weekly basis to the GM Incentivising Reform group in a written form.

#### Operational progress reports will be expected on a daily basis with exception reporting escalated to the work stream Senior Responsible Officer as required.

#### Details on the governance of this work stream are provided within the Terms of Reference (see Appendix B).

### Key Milestones, Deliverables and Performance Measures

| Deliverables | Summary | Measurement | Timeframe |
| --- | --- | --- | --- |
| Deliverable 1 – Programme plan / roadmap to include a timetable and implementation plan for the work stream, to include: - Suggested governance - Proposed capacity / resources needed to deliver the requirements | The supplier will work with the GMHSCP SRO, Programme lead and the identified key stakeholders to develop a programme plan for a short term or quick win and then the roadmap for this enabling work stream over the next 3 years. The baseline exercise that will be undertaken will be a key input to this work and it is expected that the supplier will use their knowledge of best practice examples and discussions with national colleagues (NHS England, NHS Improvement, Nuffield etc) to inform the plan. The plan should include a proposed governance and capacity requirements needed to be established to deliver the work programme. | A comprehensive short term programme plan as part of a 3 year roadmap – narrative and deliverables plan (milestone and task specific) that is delivered after 10 weeks. Weekly highlight report to be provided to the GMHSCP programme lead outlining work completed that week, tasks for the coming week, risks and issues that need to be resolved, update on cost of work to date and any decisions that need to be taken. | 10 weeks from contract commencement |
| Deliverable 2 – Joint statement of commitment / Business case | The supplier will work with the GMHSCP SRO, Programme lead and the identified key stakeholders to develop the business case that will outline the rationale, objectives and outcomes for the work to be taken forward and outlining the process and approach that will be taken in the short and longer term. The purpose of the business case is to secure the ownership of the delivery of the plan by all the GMHSCP organisations. This will almost be the GM system MoU for the delivery of the work. | A joint statement of commitment / business case document that can be taken round all the key GMHSCP governance groups for consideration and approval. The joint statement / business case should have been approved within the 12 week timescale by the GM Strategic Partnership Board. Weekly highlight report (as above) | 10 weeks from contract commencement |
| Deliverable 3 – Repository of national and international good practice examples | The supplier will work with the GMHSCP SRO, Programme lead and the identified key stakeholders to develop a repository of national and international best practice examples from both public and private sector that demonstrate the potential of what could be done at a GM level to incentivise the integration of health and social care and wider public sector. | A document (format to be agreed with the Programme lead) outlining good practice examples and any key supporting documentation to provide clarity on the model and impact. This would include a brief analysis on how applicable in the current GM system this model would be. Weekly highlight report (as above) | 10 weeks from contract commencement |

### Contract Term

#### This is a fixed term 12 week assignment of work, which will start on an agreed contract commencement date between GMHSCP and the appointed supplier.

#### GMHSCP may elect to extend or request additional deliverables beyond the initial 12 week fixed term, provided that:

##### The value of the extended or additional work does not exceed more than 10% of the original contract value;

##### The extended and/or additional deliverables are within the specification of requirements scope outlined in section 3 of this document;

##### The extended and/or additional deliverables are delivered by the appointed Providers in accordance with the agreed Fixed Price Rate Cards (including any Discounts) negotiated as part of this procurement process that resulted in the agreed final Contract; and

##### Appropriate GMHSCP/NHS England approvals have been sought and confirmed ahead of the extended deliverables and/or additional works have been commissioned by the GMHSCP Contract Manager.

### Budget, Day Rate Cap and Payment

#### There is a capped budget of £100k (excluding VAT) to deliver this work. Bidders will be required to provide a breakdown of their proposed costs against this amount in Document 6 Commercial Schedule.

#### Bids exceeding £100k (excluding VAT) will not be evaluated by GMHSCP and will be deemed as ‘non-compliant’. Non-compliant tenderers will therefore be eliminated from the procurement exercise immediately.

#### A maximum capped day rate per role will apply. All rates per role are capped at £900 (excluding VAT) per day.

#### Bids that include roles that exceed the £900 (excluding VAT) per day rate cap will not be evaluated by GMHSCP and will be deemed as ‘non-compliant’. Non-Compliant tenderers will therefore be eliminated from the procurement exercise immediately.

#### Payment will be on completion of the services/deliverables outlined in Section 3.7 Key Milestones, Deliverables and Performance Measures.

## Appendices

### Appendix A: GM 5 year strategic plan – Taking Charge

### Appendix B: GM Incentivising Reform Group Terms of Reference

### Appendix C: Examples of work already underway in GM

Both the GM plan and its constituent locality, provider and GM work stream plans describe the need to develop new models of care delivery and provision between primary, community, social and acute providers.

There are a number of approaches already in place and being developed across GM, for example:

- A new contract combining activity and cost reduction incentives, with cost risk share;

- High level outcome-focused cost & volume contract with high level outcome measures; and

- The development of a capitation based contract linked to an Outcome Framework.