Order Schedule 20 (Order Specification)

This Schedule sets out the characteristics of the Deliverables that the Supplier will be required to make to the Buyers under this Order Contract

CONTENTS

1.	PURPOSE	3

2.	BACKGROUND TO THE CONTRACTING AUTHORITY	3

3.	BACKGROUND TO REQUIREMENT	3

4.	DEFINITIONS	4

5.	SCOPE OF REQUIREMENT	5

6.	THE REQUIREMENT	5

7.	KEY MILESTONES AND DELIVERABLES	11

8.	MANAGEMENT INFORMATION/REPORTING	13

9.	VOLUMES	13

10.	CONTINUOUS IMPROVEMENT	14

11.	SOCIAL VALUE AND SUSTAINABILITY	14

12.	QUALITY	14

13.	PRICE	14

14.	STAFF AND CUSTOMER SERVICE	15

15.	SERVICE LEVELS AND PERFORMANCE	15

16.	SECURITY AND CONFIDENTIALITY REQUIREMENTS	17

17.	PAYMENT AND INVOICING	17

18.	CONTRACT MANAGEMENT	18

19.	LOCATION	18

# PURPOSE

## The Office for Equality and Opportunity (OEO) is seeking to commission robust analysis on the upcoming consultation for the Equality (Race & Disability) Bill. The supplier will be required to analyse all responses to open and closed questions on a consultation survey. The project will deliver two final outputs: a set of slides for policy officials, and a short publication-quality report.

# BACKGROUND TO THE CONTRACTING AUTHORITY

  - The Contracting Authority (Cabinet Office) sits at the centre of government, supporting the Prime Minister and ensuring the effective running of government. The Contracting Authority is the corporate headquarters for government, in partnership with HM Treasury, and takes the lead in certain critical policy areas. More information about the Contracting Authority can be found on its website at:

## https://www.gov.uk/government/organisations/cabinet-office

  - The Office for Equality and Opportunity (OEO) sits within the Contracting Authority. It is central to the government’s commitment to ensuring that every person, no matter their background, has access to the opportunities that allow them to thrive and be treated with respect and dignity.

# BACKGROUND TO REQUIREMENT

  - The upcoming Equality (Race and Disability) Bill - (the “Equality Bill”), which was announced in the King’s Speech in July, will deliver the manifesto commitments to:

    - introduce mandatory ethnicity and disability pay gap reporting for large employers; and

    - extend the right to make equal pay claims to ethnic minority and disabled people.

  - The government has committed to publishing the draft Equality Bill in the first parliamentary session.

  - The Contracting Authority will be launching a public consultation on the measures in March 2025      , and the responses will inform the development of the legislation. The consultation will be accessible and open to all for views, particularly those who will be impacted by the proposals, including employers, people in ethnic minority groups and disabled people.

  - The public consultation will consist of 5      open questions, 28      closed questions and 32      demographic questions. These 32 demographic questions cover all types of respondents. Each individual respondent only has to answer between 6 and 9 questions, depending on in what capacity they are responding (for example, on behalf of an employer, or as an individual).

  - There are also 11 comment boxes associated with the closed questions, although we do not expect these to be used to the same extent as the open questions.

  - The consultation will be held on the OEO’s online consultation survey platform. For reasons of accessibility, the consultation is also available for response in a number of alternative formats (e.g. email, EasyRead and hard copy).

# DEFINITIONS

| ## Expression or Acronym | ## Definition |
| --- | --- |
| ## Equality Bill | ## Refers to the upcoming Equality (Race and Disability) Bill, which is described in more detail in ‘3. Background to the Requirement’. |
| ## OEO | ## Office for Equality & Opportunity |
| Open Questions | Open questions are those that allow the respondent to give a free text answer. |
| Comment box | Comment boxes allow respondents to add a free text comment following their response to some of the Closed questions. We do not expect these to be used to the same extent as Open Questions. |
| Closed questions | Closed questions are those that require the respondent to choose from a limited range of options. Some closed questions will allow respondents to select only one option; others may allow them to select multiple options from the list. |

# SCOPE OF REQUIREMENT

## The supplier will conduct the following research activities (all outlined in further detail in Section 6 ‘The Requirement’):

## Data cleaning. This includes checking for duplicate or malicious responses and removing ‘N/A’-type responses.

    - Qualitative analysis of open questions. Robust thematic analysis of all open questions, including by key groups of respondents (e.g. by respondent type)

    - Descriptive quantitative analysis of closed questions. Robust descriptive analysis of all closed questions on the consultation survey, including breakdowns by key groups of respondents (e.g. by key demographics). We also require descriptive analysis of demographic questions, in order to give an overview of respondents.

    - A presentation of findings to OEO researchers and policy makers, accompanied by a detailed slidepack.

    - A final report which provides an overview of the analysis. This will be of publication-quality, in line with OEO accessibility rules, and a maximum of 30 pages in length (excluding annexes, e.g. a data table annex).

    - A full and cleaned dataset and code book containing all responses to the questions as a .csv file.

# THE REQUIREMENT

## Aim:

    - To robustly and objectively analyse the responses received to the Equality Bill consultation, in order to inform ongoing policy development.

  - Scope:

    - Analysis must include all responses to all 28      closed,      all 5      open questions, all 11 comment boxes, as well as descriptive analysis of demographic questions.

    - All questions are optional. As such, we do not expect that all respondents will answer all questions.

    - A consultation is open to whoever wishes to respond. As such, it is not possible to know in advance of the consultation closing how many responses there will be. The successful supplier must be prepared to analyse all responses within the time frame set out below. If response numbers have an impact on price, this must be outlined under volumes. In the event of large response numbers, suppliers may need to use a semi-automated approach (more detail below).

    - The majority of respondents will respond via the consultation survey platform. Responding this way means that responses are uniform, and follow the structure of the consultation survey. However, there are other response mediums on offer. Respondents may also respond via email or hardcopy. Those responding in this way may not follow the structure of the survey (e.g. they may submit a response to the consultation as a whole, without clearly demarcating individual questions). These minority of non-standard

format responses need to be considered equally within the analysis, to the extent that this is possible and robust (e.g. they should be considered under the relevant open questions and/or overarching themes, but responses to closed questions should not be inferred unless explicitly given).

  - Methodology:

    - Data Cleaning:

      - OEO will provide the supplier with a dataset of all responses received via the consultation platform, along with non-standard responses received through email or hard copy.

      - Some cleaning of the dataset is likely to be required by the supplier prior to analysis. For example, it may become evident that there is a significant attempt to deliberately disrupt the consultation with irrelevant or disruptive responses. Alternatively, a single individual may attempt to skew the findings by intentionally submitting multiple identical responses. We envisage this data cleaning to be relatively limited in scale, and it may not be necessary at all.

      - We advise that the supplier should undertake an initial assessment of the quality of the data, with any emerging issues to be dealt with on a case-by-case basis. In order to avoid the risk of discounting any respondents’ views inappropriately, removing responses should be seen as a last resort. Removing responses should only be carried out if objectively justifiable, after discussion with OEO, and should be avoided if at all possible.

      - Data cleaning should involve the following, with both the closed question and open question responses checked to:

- Identify any incomplete responses;

- Detect and remove not applicable/ does not apply responses;

- Identify the number of duplicate responses or extremely similar responses that might either be part of coordinated campaigns, those that fail screening checks, or from the same individual.

      - The open question responses should be checked to:

- Separate individual terms, remove punctuations and numbers;

- Convert upper to lower case (Tokenization);

- Correct spellings, typos and abbreviations using dictionary function;

- Correct US English to British English

- Correct stemming – obtaining base or stem words;

- Detect (and discount from analysis) hate speech, sarcasm and trolling using software such as  HateSonar hate speech detection library within Python.

      - The supplier will need to deliver a short methods paper (within the second week of the contract) which describes the proposed approach to data cleaning, and report on the numbers and proportions that have been affected.

      - As part of the initial assessment of data quality, it may become evident that multiple respondents have submitted very similar or identical responses. These may be part of a coordinated campaign led by an organisation, which has provided template responses or guidance on how the questions should be answered. In these cases, the responses should still be treated and counted as individual cases (as we will assume the respondents agree with the responses they have provided), but we will expect the supplier to provide a summary of the template responses received, and the source of these, if possible.

      - The supplier is also required to conduct analysis on responses inspired or informed by campaign groups, and identify whether and how far this is a feature of the consultation. The supplier should lead and advise on how to treat these responses in the wider data analysis.

    - Analysis of Open Questions

      - We expect the supplier to carry out qualitative analysis of all responses to the 5      open questions.

      - In order to get a head start on analysis to be able to do the Presentation of Findings by the date set out in Section 8 below, OEO anticipates that suppliers will want to begin the coding framework prior to the consultation closing, based on responses received before this date.

      - There are four types of respondents: employers or business, organisations representing employees and/or employers, individuals and other interested organisations (for example academic organisations or charities). We expect the responses from each of these respondent types to be considered separately, with any differences drawn out (if any). We also require all organisational responses to be reviewed manually. Organisational responses will be a small minority of the overall number of responses. There may be instances when more than one response is legitimately provided by the same individual. For example, an individual may submit a response on behalf of their organisation and another response reflecting their own personal views. In these cases, the responses should still be treated and counted separately.

      - We expect that the best balance of robustness and efficiency will be to use hand coding, potentially combined with text analysis in the event of large response numbers. Bidders should propose the method they prefer, and should outline how their approach will ensure robustness of analysis as well as coping with potentially large numbers of responses.

      - The analysis of free-text responses must be accompanied by exemplar quotes.

      - We expect the themes identified to also be accompanied by some assessment of the strength of support for that view.

      - In addition to question-by-question analysis, it is possible that there will be some themes which exist across a number of different consultation questions. If this is identified, these should be drawn out as overarching themes.

    - Analysis of closed questions:

      - The supplier will be required to analyse the 28      closed questions, as well as providing a range of breakdowns based on key demographics. These breakdowns will be agreed with OEO at a start-up meeting, or at a subsequent time prior to analysis.

      - The supplier is required to provide results for individual responses and organisational responses separately.

      - The supplier will also be required to summarise the types of respondents to the consultation questionnaire as a whole, using the closed demographic question responses (covering key demographics and other categorisation information such as whether the respondent is an individual or an organisation).

      - The supplier should provide all code and data tables to enable the analysis to be replicated and quality assured by OEO as required.

    - Analysis of comment boxes:

      - The supplier will be required to analyse the 11 comment boxes associated with the closed questions. We do not expect these to be used to the same extent as open questions.

    - Presentation of Findings:

      - OEO has split the final output of this work into two. The first of these - Presentation of Findings - shares the complete and detailed analysis with OEO officials. This should be via a presentation (1-2 hours, conducted remotely) with a detailed accompanying write-up to be completed 2 weeks later. This detailed presentation will be what informs officials’ ongoing policy development.

    - Final Report:

      - The second element of the final output is the final report. Whereas the presentation of findings provides the full detail required by policy officials, the final report provides the same analysis but with less granular detail.

      - The supplier will be required to write up their findings in a final report, combining all of the analysis and presenting them according to the sections and questions as set out in the consultation document. The final report should be of publication quality.

      - The final report should adhere to the in-house style and accessibility guide, which will be supplied at the commencement of the contract.

      - A draft version of the report will need to be shared with OEO prior to the final report, with OEO providing comments which the supplier will need to consider in their final draft. This process gives OEO officials an opportunity to ask questions and request clarifications and small additions. This drafting process is set out in the milestones in section 8.

      - Once the suppliers have completed the report, OEO’s digital team will do some further work to prepare it for publication. This will not change the content, but will include things like (if necessary) editing the report to reduce the reading age. The supplier will be asked to check and sign-off on this final version of the report.

    - Cleaned dataset and codebook:

      - The final dataset and cleaned codebook will be handed over in a format and standard which will make it easy to interrogate by OEO officials. The exact format will be agreed between OEO and the supplier before the completion of the project but we anticipated that the most usable format would be as .csv file or files. We will require the supplier to provide a user guide. Files will be shared via a dedicated Google Drive folder, which will be created and shared with the supplier by OEO officials. Any data that the supplier will need (e.g. the consultation responses) will be saved in this folder, and the supplier should use this folder to share their work with OEO.

# KEY MILESTONES AND DELIVERABLES

## Please note that the timings for the consultation period could shift slightly. The timeline set out below assumes that the consultation will be launched on 13 March 2025 and close on 5 June 2025. It is possible that the consultation may extend beyond this date, in which case milestones 3 onwards would need to be shifted accordingly. We wouldn’t expect this to shift by more than 1-3 weeks at most, and would require suppliers to be flexible to meet this if required.

## The below Contract milestones are based on the Contract being awarded on w/c 1 April. It is possible that the Contract is awarded before this date, in which case milestones should be shifted accordingly.

## The following Contract milestones/deliverables shall apply:

| ### Milestone/ Deliverable | ### Description | ### Timeframe or Delivery Date |
| --- | --- | --- |
| ### 1 | ### Project start-up meeting (held remotely) | ### Within week 1 of Contract Award or no later than 10th April 2025 |
| ### 2 | Short method paper on approach to data cleaning. Following agreement of this, the contractor can commence an initial review of responses to the consultation received thus far. | ### Within week 2 of Contract Award or no later than 17th April 2025 |
| ### 3 | Contractor to provide an update on progress of initial review of responses received before the consultation closes | ### Within week 7 of Contract Award or no later than than 22nd May 2025 |
| ### 4 | Consultation closes. Final and complete set of responses provided to the contractor by OEO. | ### Within week 9 of Contract Award or no later than 6 th June 2025 |
| ### 5 | Interim presentation of findings to OEO analysts. This presentation should include full analysis of the closed questions, and a preliminary analysis of priority open questions and comments boxes (priority questions having been determined in the start-up meeting). OEO analysts will provide feedback, to incorporate into analysis of remaining questions and the later presentation to all OEO officials (Milestone 6). | ### Within week 12 of Contract Award or no later than 26th June 2025 |
| ### 6 | ### Detailed presentation of findings to OEO officials | ### Within week 15 of Contract Award or no later than 17th July 2025 |
| ### 7 | ### Final presentation write-up to be shared by contractor, incorporating any comments or questions raised during the presentation to OEO officials. | ### Within week 17 of Contract Award or no later than 31st July 2025 |
| ### 8 | ### Delivery of first draft of final report. OEO officials will provide questions and feedback on this draft, for incorporation into the final draft. This will be supplied by OEO within 1 week . | ### Within week 19 of Contract Award or no later than 31st July 2025 |
| ### 9 | - A final, quality-assured dataset, codebook and user guide - A final version of the final report, using the publication template and compliant with OEO style guide and accessibility requirements | ### Within week 22 of Contract Award or no later than 4th September |

# MANAGEMENT INFORMATION/REPORTING

  - The supplier should expect to update and share their work with OEO at each of the milestones set out in section 7 and at weekly meetings, to be held either on a Tuesday, Wednesday or Thursday. The supplier should have availability during normal working hours (9am-5.30pm), for these meetings, and should have some degree of flexibility around the availability of OEO staff.

  - OEO will designate a primary point of contact for this work, and the supplier should update this contact with any significant changes or developments in between regular meetings. Should any questions arise, the supplier should make contact with OEO’s primary contact as needed and at the earliest possible opportunity.

# VOLUMES

  - The supplier will be required to analyse all responses received. As noted above, it is not possible to accurately predict how many responses the consultation will receive. Our best estimate is that the consultation will receive approximately 2,000-4,000 responses. Because of the nature of quantitative analysis, OEO would not expect the cost of analysing closed questions to vary with the number of responses. If the analysis cost for open questions will vary based on response number, suppliers should include their costs for a range of different response numbers in their bids. These must be provided in a uniform way as set out below. Suppliers should indicate their costs for the numbers of responses to free-text questions as set out below. Please note that there may be varying response numbers across the questions, so this number will be calculated as an average across all free text questions:

- Up to 1,999

- 2,000-3,999

- 4,000-5,999

- 6,000-7,999

- 8,000-9,999

- 10,000-11,999

- In the event that the number of responses received exceeds 12,000 you will need to stipulate in Attachment 4 the maximum number of responses that you will analyse, taking into account the timelines stipulated in Attachment 3.

# CONTINUOUS IMPROVEMENT

## Changes to the way in which the Services are to be delivered must be brought to the Authority’s attention and agreed prior to any changes being implemented.

# SOCIAL VALUE AND SUSTAINABILITY

## All meetings will be held virtually in order to cut down on unnecessary travelling.

# QUALITY

  - The analysis and reporting should be completed to a standard of publication quality.

  - The final output should be easy to read and understand by non-specialist users (i.e. a broad audience of people who do not have specialist analytical skills).

  - Review, quality assurance and feedback will be provided by OEO officials at weekly meetings and at designated milestones. This will be used to ensure that the work is being carried out to a suitably high standard.

  - The presentation to OEO officials and the accompanying write-up needs to be suitably robust, clear and detailed in order to inform ongoing policy development. The final report needs to be easy to read by non-specialist users (i.e. a broad audience of people who do not have specialist analytical skills).

  - The outputs need to follow OEO templates and accessibility guidelines, which will be provided to the contractor at the start of the contract.

# PRICE

## Prices are to be submitted via the e-Sourcing Suite (Attachment 4 – Price Schedule) excluding VAT and including all other expenses relating to Contract delivery.

# STAFF AND CUSTOMER SERVICE

## The Supplier shall provide a sufficient level of resource throughout the duration of the Contract in order to consistently deliver a quality service.

## The Supplier’s staff assigned to the Contract shall have the relevant qualifications and experience to deliver the Contract to the required standard. Staff shall have the relevant research and analytical skills to carry out this piece of work, as well as the required project management skills/experience to manage it to the timeline set out.

## The Supplier shall ensure that staff understand the Authority’s vision and objectives and will provide excellent customer service to the Authority throughout the duration of the Contract.

# SERVICE LEVELS AND PERFORMANCE

## The Authority will measure the quality of the Supplier’s delivery by:

|  | Theme | ## KPI / SLA description | SLA/KPI Target |
| --- | --- | --- | --- |
| 1 | Responsiveness | The Supplier is expected to respond to Authority emails and ad-hoc queries within 2 working days of being sent. | 98% |
| 2 | Attendance and reporting at weekly progress meetings | The Supplier is expected to attend weekly progress meetings, and to be on track to meeting milestones and outputs. | 98% |
| 3 | Satisfactory completion of milestone 2 | Satisfactory completion of methods paper to a high quality. The paper should include consideration of methods for all stages of the process (cleaning, analysis, reporting), and should be sufficiently robust and appropriate for the analysis. Milestone to be completed on time, as set out in Schedule 7 (or a later date if by mutual agreement) | 100% |
| 4 | Satisfactory completion of milestone 5 | Satisfactory completion of the interim presentation of findings to OEO analysts. This presentation should include full analysis of the closed questions, and a preliminary analysis of priority open questions (priority questions having been determined in the start-up meeting). Milestone to be completed on time, as set out in Schedule 7 (or a later date if by mutual agreement) | 100% |
| 5 | Satisfactory completion of milestone 6 | ### Satisfactory completion of a detailed presentation of findings to OEO officials. This presentation should be based on thorough, high-quality and robust analysis, and should include overarching themes as well as sufficient detail to support policy development. It should incorporate feedback received at the interim presentation of findings (milestone 5). Milestone to be completed on time, as set out in Schedule 7 (or a later date if by mutual agreement). | 100% |
| 6 | Satisfactory completion of milestone 7 | ### Satisfactory completion of the final write-up of the presentation. This should incorporate any comments or questions raised during the presentation to OEO officials. This report will not be published, so does not need to be publication-ready in its formatting. However, it does need to be publication-quality research, written in a comprehensive and accessible style. Milestone to be completed on time, as set out in Schedule 7 (or a later date if by mutual agreement) | 100% |
| 7 | Satisfactory completion of milestone 9 | Satisfactory completion of both elements of milestone 9. This includes a final, quality-assured dataset, codebook and user guide, and a final version of the final report, using the publication template and compliant with OEO style guide and accessibility requirements The report will be produced to publishable quality, based on robust analysis which has been quality assured by both the supplier and OEO analysts. | 100% |

  - The Authority will measure the quality of the Supplier’s delivery by checking that the Supplier has met all of the requirements set out in section 6, and delivered to the timeline set in section 7.

  - The supplier will work closely with OEO to manage milestones within the specified timeframe. OEO have the right to terminate the contract if the supplier cannot fulfil the criteria and continues to miss milestones.

# SECURITY AND CONFIDENTIALITY REQUIREMENTS

  - The supplier will carry out their work under this contract in confidentiality and in compliance with the Data Protection Act.

  - More information about the Security and Confidentiality requirements can be found in Special Term 1 - Security.

# PAYMENT AND INVOICING

## Payment can only be made following satisfactory delivery of pre-agreed certified products and deliverables.

## Before payment can be considered, each invoice must include a detailed elemental breakdown of work completed and the associated costs.

## Invoices should be submitted to:

## APinvoices-cab-u@gov.sscl.com

## Newport SSCL – Cabinet Office

PO Box 405

Newport

## NP10 8FZ

# CONTRACT MANAGEMENT

  - The supplier shall attend weekly meetings with OEO, as well as additional milestone meetings as set out under ‘Key Milestones and Deliverables’ (Section 8).

  - Attendance at all meetings shall be at the Supplier’s own expense. However, since all meetings will take place virtually (e.g. over Google Meet) we do not expect there to be any significant expenses associated with this.

# LOCATION

## The Services will be carried out at the Supplier’s premises. All meetings and presentations can be carried out virtually over Google Meet or an equivalent platform.