# Annex A

| Title of Project | Ocean Country Partnership Programme: Maldives Review of shark diving practices at Fuvahmulah atoll, Maldives |
| --- | --- |
| Date and Time for Return of Bids | Monday 14 August 2023 @ 09:00 Hours |
| Contract Reference Number | C23-0604-1779 |
| Address for Bid Submission | 1 electronic copy to be sent to TenderResponse@jncc.gov.uk PLEASE DO NOT SEND BIDS DIRECTLY TO JAMIE SMALL, BETH FLAVELL OR DORA IANTOSCA VIA THEIR WORK EMAIL ADDRESSES AS THIS WILL INVALIDATE YOUR BID. Bids must be less than 10 MB in size. On receipt of your bid, you will receive an automated e-mail to confirm receipt by the JNCC Support Co. If you do not receive this automated email, please contact the individuals below, in the following order: Sue Wenlock (00 44 1733 866880) Chris Downes (00 44 1733 866877) |
| Contacts for Technical Information relating to this Project Specification | Joint Nature Conservation Committee Name: Jamie Small Email: Jamie.small@jncc.gov.uk Telephone: (+44) 01733 259687 OR Joint Nature Conservation Committee Name: Beth Flavell Email: beth.flavell@jncc.gov.uk Telephone: +44 (0)1733 866952 |
| Contact for Queries Regarding the Procurement Procedure | Dora Iantosca Finance Team Joint Nature Conservation Committee Email: contractqueries@jncc.gov.uk Telephone: 01733 866894 |
| Proposed Start Date | TBC prior to award of contract with the successful bidder |
| Proposed End Date | 20th March 2024 |

Ocean Country Partnership Programme: Maldives

Review of shark diving practices at Fuvahmulah atoll, Maldives

Contents

1.	Joint Nature Conservation Committee	3

2.	Project Aims	3

3.	Project Background	4

4.	Project Objectives	5

5.	Contractor Requirements	6

6.	Quality assurance	6

7.	Potential Follow-On Work	7

8.	Product Specification	7

9.	Timescale	7

10.	Project Management	8

11.	Instructions for Bid Submission	8

12.	Evaluation Criteria	9

13.	Payment	10

14.	Additional Requirements	11

## Joint Nature Conservation Committee

The Joint Nature Conservation Committee (JNCC) is the statutory adviser to the UK Government and devolved administrations on UK and international nature conservation

Our role is to provide scientific evidence, information, and advice to inform decisions to  protect the natural environment. Our specific role is to work on nature conservation issues that affect the UK as a whole and internationally, by:

advising Government on the development and implementation of policies for, or affecting, nature conservation in the UK and internationally;

providing advice and disseminating knowledge on nature conservation issues affecting the UK and internationally;

establishing common standards throughout the UK for nature conservation, including monitoring, research, and the analysis of results; and

commissioning or supporting research which it deems relevant to these functions.

Background to JNCC can be found on JNCC’s website at: https://jncc.gov.uk/about-jncc/

JNCC co-leads the Biodiversity loss theme of the Ocean Country Partnership Programme (OCPP), a UK government-led programme under the Blue Planet Programme. For the past 2 years, the OCPP has been working in collaboration with the Government of Maldives  providing technical assistance for Marine Protected Areas (MPAs).

This contract is being delivered on behalf of the Government of Maldives Ministry of Environment, Climate Change and Technology (MoECCT).

## Project Aims

Fuvahmulah atoll in the Maldives was declared an UNESCO Biosphere Reserve in 2020 due to its varied biodiversity including diverse coral reef ecosystems and significant populations of sharks. Several protected areas sit within the Biosphere Reserve including Farikede MPA, designated to protect oceanic species that utilise the area including two species of thresher shark; bigeye thresher shark (Alopias superciliosus) and common thresher shark (Alopias vulpinus).

In recent years a valuable shark diving industry has emerged across Fuvahmulah as it has become globally recognised for its dive encounters with an abundance of oceanic megafauna including tiger sharks, whale sharks, oceanic manta rays and schooling hammerhead sharks. Of particular interest is the famous ‘Tiger Shark Zoo’ or ‘Tiger Harbour’ dive site where divers can experience close encounters with multiple tiger sharks, attracted to the site via provisioning.  For the context of this work, the term ‘provisioning’ refers to the use of food, in the form of fish waste from the fishing industry (e.g. tuna heads), to attract sharks to the site.

The Maldives Ministry of Environment, Technology and Climate Change and Fuvahmulah City Council are currently reviewing the management of MPAs and marine industries on Fuvahmulah. To support the evaluation of current management, this contract seeks to commission a review of shark diving activities that take place at Fuvahmulah. The review will focus on two areas;

1) the supplementary feeding of tiger sharks. Summarising current provisioning activities and management in place and providing advice, based on globally recognised best practice, around how current practices and management could be improved.

2) wider shark diving activities that take place in and around Farikede MPA to support the development of a Fuvahmulah tailored shark diving code of conduct that will feed into the management of the Fuvahmulah Biosphere Reserve and MPAs.

The project outputs will aim to provide:

- A summary of Fuvahmulah’s dive industry’s tiger shark diving operations including current and past provisioning practices and how the local dive industry has developed current management measures.

- A review of the impacts current food provisioning activities (including indirect provisioning from fish waste disposal) have or could potentially have on shark populations around Fuvahmulah. This should include information on potential risks that may arise to divers and other sea users as a consequence of provisioning tiger sharks in the area.

- Examples of shark provisioning best practices undertaken at other globally recognised shark diving sites (such as Tiger Beach, Bahamas) and how they compare to the ‘Tiger Harbour’ dive site at Fuvahmulah to gain a better understanding of best practice for shark diving when attractants such as chum or bait are used.

- Best practice on how to address the identified impacts and risks the current tiger shark diving operations may pose, including different management scenarios to manage food provisioning activities in a safe and sustainable manner.

- Best practice and case studies on how to manage fish waste disposal from the fishing industry based on Fuvahmulah in a sustainable manner.

- Guidance on how to tailor a best practice approach for shark diving ecotourism in Fuvahmulah, providing example codes of conducts which could be considered by the Maldives Government when developing a code of conduct for the management of shark diving in Farikede MPA and the wider area.

## Project Background

This contract sits under the “Marine Biodiversity” strand of the Ocean Country Partnership Programme, which aims to:

- Increase understanding of the value of Marine Protected Areas (MPAs) in supporting sustainable livelihoods, food security, health and well-being;

- Increase understanding of MPA theory and practice, including evidence gathering, identification, selection, monitoring and assessment of MPAs;

- Increase support and compliance for MPAs with stakeholders; and

- Enhance capability and drive within countries to sustainably manager, monitor and assess conservation activities in the future.

## Project Objectives

To meet the overall aims of this project (Section 2), the objectives are:

- Produce a report reviewing the current provisioning practices undertaken by the dive industry at the ‘Tiger Harbour’ dive site. The review should include:

- Data on the number of operators using the area, number of dives/divers per day attending the site, estimated number of shark species frequented, average number of sharks encountered per dive. Note – the contractor is not expected to collect their own data but should collaborate with local dive operators to estimate values.

- Detailed review on provisioning techniques used including types of bait used and frequency of use.

- Summary of current health and safety protocols in place for shark divers and snorkellers.

- Identify potential impacts provisioning may have on the behaviour of local shark populations. Also consider indirect provisioning as a result of fish waste disposal at sea by the local fishing industry (prior to the provisioned diving activities tiger sharks were attracted to the area due to it being a fish waste disposal site).

- Identify potential risks current provisioning practices may pose to divers and other sea users in the area.

- Conduct interviews with key stakeholders to fully understand the context of the shark diving industry based on Fuvahmulah. Interviews should focus on both tiger shark diving and general shark diving activities, aiming to identify best practice procedures already in place and views on how management could be improved. A report summarising the outcome of stakeholder conversations should be provided.

- Provide case studies from other key shark ecotourism diving locations where activities are conducted in a sustainable manner, highlighting management measures in place for provisioning to help outline globally accepted approaches to shark diving and to inform best practice options for Fuvahmulah.

- Provide best practice options for ethical and sustainable shark ecotourism based at Fuvahmulah.  This should;

  - Outline suggested actions to improve management for diving with tiger sharks at the ‘Tiger Harbour’ dive site. This may include a roadmap on how to manage a reduction in provisioning practices if current limits are deemed unsuitable at the site.

  - Provide guidance on a shark diving best practice code of conduct tailored to the context of shark diving at Fuvahmulah which could be incorporated into the management measures for MPAs around the Island such as Farikede MPA.

- Provide options on how to sustainably manage fish waste disposal from the fishing industry based on Fuvahmulah in reference to the impacts it may have on local shark populations and risks it poses to local sea users.

## Contractor Requirements

The successful contractor should:

- Have experience of advising the shark ecotourism sector on provisioning methods to attract sharks for tourism purposes.

- Have experience of providing advice on health and safety aspects of shark diving for scuba divers, free divers and snorkellers.

- Have experience in developing best practice shark diving codes of conduct and/or management measures for shark ecotourism in MPAs.

- Have expertise in large predatory shark behaviour.

- Have experience of engaging with and working closely with stakeholders, and be able to actively listen to the range of views of different stakeholders.

- Ideally, have previous experience of diving with sharks at Fuvahmulah. Have no conflicting interests with existing dive operations that take place at Fuvahmulah.

- Be available and willing to visit Fuvahmulah, Maldives to speak to stakeholders. Please note that the contractor will not dive, snorkel or free-dive as part of this OCPP project and contract.

- Be responsible for independently arranging travel to Fuvahmulah including organisation and costs of the travel itinerary and field work e.g., be responsible for arranging any stakeholder workshops or engagement required to meet the needs of the project outputs including associated travel and subsistence costs. The OCPP team, Maldives Ministry of Environment, Climate Change and Technology and Fuvahmulah City Council will be available to assist with introductions to key stakeholders prior to a site visit.

- Be willing to sign a travel risk assessment prepared by JNCC and comply with the necessary requirements of the risk assessment when in country.

- Quotes should be provided in USD or GBP. The quote should cover all costs to successfully deliver the outputs of the contract including all expenses associated with a site visit to Fuvahmulah, Maldives.

## Quality Assurance

The outputs under this contract (section 4) will be subject to an independent external quality assurance review.

Following award of the contract, and dependent on the evaluation scores they achieved, unsuccessful bidders may be invited to undertake the independent external QA aspects of this project. Please indicate in your tender if you do not wish to be considered for this work. Alternatively, if you wish to only undertake the QA aspects of this project clearly indicate this in your tender.

It is the responsibility of the successful contractor to ensure all project outputs are QA’d before their final delivery. Any remedial action required following the QA process must be completed within an agreed timeframe at no extra cost to the project.

All remedial action taken, and associated rationale, are to be recorded and provided as outputs of this contract. The contract shall not be deemed complete until this external QA step has been completed successfully.

## Potential Follow-On Work

Bidders should be aware that there is the potential for the successful bidder to be requested by JNCC to undertake additional work on this contract into the financial year 2024/25.

Please note however that the potential for additional work to be undertaken is subject to a continuing need, availability of funds and satisfactory contractor performance. For the avoidance of doubt, no guarantee can be given that you will be asked to undertake the potential additional work outlined within this Annex A document. Bidders are not asked to provide detailed project plans for these follow-on aspects at this stage.

## Product Specification

JNCC is committed to making its publicly available resources and documents accessible, in accordance with the Public Sector Bodies (Websites and Mobile Applications) (No. 2) Accessibility Regulations 2018.

Making material accessible means making sure it can be used by as many people as possible.  This includes those with:

- impaired vision

- motor difficulties

- cognitive impairments or learning disabilities

- deafness or impaired hearing

The outputs and material that JNCC publishes should be compliant with the Web Content Accessibility Guidelines version 2.1 AA standard.   All reports and other documentation which are to be made publicly available must be produced using an OCPP template (to be provided), unless otherwise stated. All reports (draft and final) should be provided electronically via email both as a Microsoft Word document and an Adobe PDF. Copies of documentation associated with case studies should be provided in electronic format with an associated reference catalogue.

The contractor will not publish any information, by any means of publication, resulting from this contract without written consent from JNCC and the Government of Maldives, Ministry of Environment, Climate Change and Technology.

Collection of personal data to meet the outputs of this contract should be handled in line with JNCC’s OCPP Privacy Notice.

## Timescale

Provisional timings for delivery of the contract outputs are set out below. Exact dates are to be agreed at the start-up meeting based on contractor and JNCC staff availability. It would be preferable for the contractor to visit Fuvahmulah during December 2023 – January 2024. The final products for this contract must be delivered by 20th March 2024 at the latest.

| Output | Provisional Date |
| --- | --- |
| Start-up meeting (via video call) | Month One |
| Proposed workplan provided by contractor | Month One |
| Technical trip to Fuvahmulah to observe and collect data on shark diving practices | Month Two |
| First draft production of outputs for comment by JNCC and Maldives Government | Month Two-Three |
| Second draft production of outputs for comment by JNCC and Maldives Government | Month Three -Four |
| Final products delivered | Month Four |

Information should be provided on milestones to meet the above outputs and timeline.

In agreeing exact dates please note that the potential for work under this contract to be funded into 2024/25 is subject to availability of funds.

## Project Management

The successful Contractor shall nominate a project manager who shall be responsible for ensuring the project is completed satisfactorily and who shall be the main contact point for JNCC.

JNCC’s main contact points will be:

Name: Jamie Small

Email: Jamie.small@jncc.gov.uk

Telephone: +44 (0) 1733 259687

Name: Beth Flavell

Email:  beth.flavell@jncc.gov.uk

Telephone: +44 (0)1733 866952

Government of Maldives, Ministry of Environment, Climate Change and Technology

Name:  Muhusina Abdul Rahman

Email:  muhsina.abdulrahman@environment.gov.mv

## Instructions for Bid Submission

The bid submission should include the following:

A brief summary of the bidder’s experience in relation to the requirements of this contract;

A proposed approach for achieving the objectives of the contract and delivering the detailed tasks identified within each objective. This should be sufficiently detailed to allow assessment against the evaluation criteria (Section 12);

A project plan and an estimate of time required to achieve each objective;

Details of the Project Team including their roles and experience

Overall quote for the contract (in GBP or USD) should include:

  - Attending virtual start-up, interim and final meetings with JNCC project team

  - Costs and time allocation should be clearly allocated to specific tasks within this contract/project including all costs associated with overseas travel and subsistence to undertake a site visit to Fuvahmulah atoll, Maldives.

- Please refer to contractors travel and subsistence rates for all travel (these rates are analogous to the UK civil service rates)

The following documentation:

  - If your company includes more than 5 employees, please provide copies of health and safety policy statements where available or a note regarding such items as lone working, emergency procedures and accident reporting;

  - Copies of current public and employer liability insurance certificates;

In addition, note that the bid submission should provide sufficient information to allow assessment against the evaluation criteria outlined in Section 12.

## Evaluation Criteria

JNCC is not bound to accept the lowest priced or any bid. Having the technical expertise and experience to complete the work to a high standard and being able to complete it within the timescale are of the essence for this contract.

The bid evaluation shall be undertaken by JNCC staff. However, for transparency, JNCC will quality check with the Government of Maldives for their final review before award of contract.

For information on how we handle personal data please see our Privacy Notice at https://jncc.gov.uk/about-jncc/corporate-information/privacy-statement/

Bids will be evaluated using the following criteria:

|  | EVALUATION CRITERIA | Maximum Score | Score |
| --- | --- | --- | --- |
| 1. Quality of Bid |  |  |  |
| 1 | Clarity of proposal particularly work programme and deliverables | 15 |  |
| 2 | Understanding of, and relevance to, the requirements in particular the adequacy of outputs | 15 |  |
| 3 | Soundness and logicality of methods | 10 |  |
| 4 | Identification and proposed solutions to potential risks/issues | 5 |  |
| 5 | Serious weaknesses which threaten success | 5 |  |
|  | Sub Total | 50 |  |
| 2. Details of Contractor |  |  |  |
| 6 | Expertise and experience of contractor including regional experience | 10 |  |
| 7 | Relevant expertise advising the shark diving industry on sustainable practices including provisioning and best practice management. | 20 |  |
|  | Sub Total | 30 |  |
| 3. Cost |  |  |  |
| 8 | Transparency and correctness of presentation | 10 |  |
| 9 | Fairness/reasonableness for the level of work and expertise required | 10 |  |
|  | Sub Total | 20 |  |
| Total Score |  | 100 |  |

## Payment

PLEASE NOTE: All quotes and all payments must be based on British Pounds (£) or US Dollars ($).

Payment will be made on completion of milestones following the submission of invoice(s) and based on the satisfactory undertaking of the contractual elements to the agreed standard of the JNCC Project Officer.

## Additional Requirements

All bidders are requested to carefully read the Terms and Conditions applying to this contract. Payment will only be made upon delivery of key milestones.

It is assumed that all costs associated with the production of figures, reproduction of photographs and the final report are accounted for within the rates/fees given.

The bidder is expected to supply all necessary equipment, software, licences, etc. to carry out the obligations required under the contract.