## Sheet1
Task | 2019 | [7 empty] | 2020 | [47 empty] | 2021
| Nov |  |  |  | Dec |  |  |  | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  | May |  |  |  | Jun |  |  |  | Jul |  |  |  | Aug |  |  |  | Sept |  |  |  | Oct |  |  |  | Nov |  |  |  | Dec |  |  |  | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  | May |  |  |  | Jun |  |  |  | Jul |  |  |  | Aug |  |  |  | Sep |  |  |  | Oct |  |  |  | Nov |  |  |  | Dec
| 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Produce ITT and Project Plan
First meeting of Steering Group
Send out ITT
Deadline for EOI submissions
Presentation to Carers Trust by chosen agencies
Set up meeting with chosen agency
Initial engagement with staff at sites
Initial engagement with carers and staff at sites
Steering Group meeting
Design for research stage finalised
Data collection at sites
Data provided to pilot sites
Steering Group meeting update
First draft of report and data provided
Steering Group review
Set up survey in Survey Monkey and paper version for wider use
Ammends to survey design made
Publication of report - comms to Network
Launch survey offer to Network
Ongoing implentation of survey to wider Network
quarterly data provided to all Network Partners using survey in PowerBI
After Action Review