|  |  |  |
| --- | --- | --- |
| DIO_5115_AW |  |  |
|  |  |  |

**E&M Works Contract**

**DIO RD OS Trg (Kenya)**

**BATUK**

**Required Works: KEN/GE/2303**

**Booklet 2 - Conditions of Contract Lump Sum Price Contract for the GE Department Building Extension works in Nyati Barracks.**

Reference: KEN/GE/2303 (version 4.0)

Dated: 8 Mar 24

**CONDITIONS OF CONTRACT - OPERATIONS**

**CONTENTS**

ADMINISTRATION

1. Definitions / Interpretations

2. Contract Documents

3. Licences

4. Spare

5. Spare

AUTHORITY POLICY

6. Patents

7. Discrimination

8. Corruption

9. Vesting

10. Assignment

11. Subletting

12. Other Works

13. Loss or Damage

14. Rights of Third Parties

15. Russian and Belarusian Exclusion

16. Disclosure of Information

CONTRACT PERSONNEL

17. Delegations and Representatives

18. Contractor’s Agent

19. Contractor’s Employees

20. Personal Data

21. Fair dealing and Team Working

22. Freedom of Information and Transparency

23. Spare

HEALTH, SAFETY & ENVIRONMENT

24. Health, Safety and the Environment

25. Statutory Notices and Construction (Design and Management (CDM)) Regulations

26. Nuisance and Pollution

27. Ozone Depleting Substances

28. Spare

SECURITY

29. Site Admittance

30. Passes

31. Photographs

32. Official Secrets and Confidentiality

33. Contractor’s Personnel – Security

34. Cyber Security

35. Spare

INSURANCE

36. Insurance

37. Spare

38. Spare

39. Spare

40. Spare

THE SITE

41. Occupier’s Rules and Regulations

42. Occupation of Government Premises

43. Use of the Site

44. Spare

45. Spare

THE WORKS

46. Design

47. Technical Guidance

48. Spare

49. Excavations

50. Foundations

51. Covering Work

52. Protection of Works

53. Conditions Affecting Works

54. Spare

55. Spare

MANAGING THE WORKS

56. Returns

57. Records

58. Programme

59. Commencement and Completion

60. Progress Meetings

61. Change Control Procedures

62. PM’s Instructions

63. Valuation of PM’s Instructions – Principles

64. Non-compliance with Instructions

65. Early Possession

66. Acceleration

67. Extensions of Time

68. Prolongation and Disruption

69. Certifying Completion

70. Quality

71. Emergency Work

72. Vehicles, Plant, Tools, & Equipment

73. Authority Supplied Materials

74. Fraud Prevention

75. Spare

FINANCE

76. Price

77. Payment

78. Certifying Payments

79. Final Account

80. Cost Savings

81. Payment of Sub-contractors

82. Recovery of Sums from the Contractor

83. Suspension for Non-payment

84. Bankruptcy

85. Spare

86. Spare

POST COMPLETION

87. Defects in Maintenance Period

88. Spare

89. Spare

DETERMINATION AND ARBITRATION

90. Determination

91. Consequences of Determination for Default

92. Consequences of Other Determination

93. Determination Following Suspension of Works

94. Arbitration

95. Authorisation by the crown for use of third-party intellectual property rights

96. Spare

ANNEXES

A. Change Form.

B. Montreal Protocol Substances.

C. MOD Policy Statement on Fraud & Theft for Construction Industry Suppliers.

D. DEFCON 532A

**ADMINISTRATION**

**1. Definitions / Interpretations**

1.1 In these conditions “the Contract” means the agreement concluded between the Authority and the Contractor including all specifications, plans, drawings and other documents which are relevant to the Contract and also such of these conditions as are included in the terms and conditions of the Contract.

1.2 The following provisions shall have effect with respect to the interpretation of the Contract except where the context otherwise requires:

1.2.1 the ‘Accepted Risks’ means the risks that are retained by the Authority as follows and to the extent that these are not provided for in the Contract Price or are specifically excluded from the Contractor’s policies of insurance:

 1.2.1.1 any alteration of, addition to or omission from the Works or any alteration in the design, quality or quantity of the Works confirmed or authorised by the Authority.

 1.2.1.2 an omission or default of the Authority or any employee, contractor or agent of the Authority (including any errors or omissions in description or in quantity in any draft Pricing Document.

 1.2.1.3 any delay by the Authority in providing any information in accordance with the date or dates for the provision of such information set out in the Programme or any delay in giving decisions, confirmations or consents which he is obliged to provide or give under the Contract, save to the extent that any such delay is caused, or contributed to, by any act, default or omission on the part of the Contractor;

 1.2.1.4 the failure of the Authority to comply with any time limit specified in the Contract or, where the parties agree to vary any such time limit, that time limit as varied, save to the extent that any such failure to comply is caused, or contributed to, by any act, default or omission on the part of the Contractor;

 1.2.1.5 any delay in the carrying out of any work or the supply of any Thing undertaken by the Authority or ordered by the Authority from somebody other than the Contractor unless, and to the extent that, any such delay is caused, or contributed to, by any act, default or omission on the part of the Contractor;

 1.2.1.6 Loss or Damage to the Works or to any Things owned by the Contractor or on the Site for the Contractor’s use which is due to any act, omission or default of the Authority or its employees or agents or any other contractor of the Authority engaged in relation to the Works or any part of the Works or his employees or agents;

 1.2.1.7 any change in any relevant statutory requirements (other than in relation to taxation) after the date of the Contract which affects the Contractor’s carrying out of the Contractor’s Design and/or the Works and which was not reasonably foreseeable at the date of the Contract by a reasonable and prudent contractor undertaking or proposing to undertake the Works;

 1.2.1.8 any delay in being given possession of the Site or part of it;

 1.2.1.9 a breach of the warranty of accuracy contained in condition 53 (Conditions Affecting Works);

 1.2.1.10 any Unknown Artificial Obstruction certified in accordance with condition 53 (Conditions Affecting Works);

 1.2.1.11 any official strike or industrial action which prevents or demonstrably delays the carrying out of the Contractor’s Design and/or the Works and which is outside the control of the Contractor or any of his Supply Chain members or agents;

1.2.1.12 pressure waves caused by the speed of aircraft or other aerial devices;

1.2.1.13 ionising radiations or contamination by radioactivity from any nuclear fuel or from nuclear waste from the combustion of nuclear fuel;

1.2.1.14 the radioactive, toxic, explosive or other hazardous properties of any explosive nuclear assembly (including any nuclear component); and

1.2.1.15 war, invasion, act of foreign enemy, hostilities, (whether war has been declared), civil war, rebellion, insurrection, military or usurped power;

1.2.2 ‘The Authority’ means the UK Secretary of State for Defence;

1.2.3 ‘The Authority’s requirements’ means the statements, drawings, and other documents included in the Contract which define the Authority’s requirements.

1.2.4 ‘CDM Regulations’ means the current Construction (Design and Management) Regulations 2015;

1.2.5 ‘Change Order’ means any Instruction which makes any alteration or addition to, or omission from the Works, or any change in the Design Brief or the Design as approved in accordance with Condition 61;

1.2.6 ‘Company’ means and includes anybody corporate;

1.2.7 ‘Construction Documents’ means any Design Document which the PM has confirmed as satisfactory in accordance with Condition 46 (Design);

1.2.8 ‘The Contract’ means the Conditions of Contract, Design Brief, the Tender, the Authority’s written acceptance and any other documents / advice / instruction issued by the Authority and accepted by the Contractor;

1.2.9 ‘The Contract Agreement’ means the formal agreement executed by the Authority and the Contractor recording the terms of the Contract;

1.2.10 ‘The Contract Price’ means the FIRM PRICE (that is a lump sum price for the whole of the Contract exclusive of VAT) accepted by the Authority when awarding the Contract;

1.2.11 ‘The Contractor’ means the person or persons whose Tender is accepted by the Authority;

1.2.12 ‘The Contractor’s Proposals’ means the statements, drawings, and other documents included in the Contract which define how the Contractor is to implement the Authority’s requirements;

1.2.13 ‘The date or dates for completion’ means the agreed completion date or dates;

1.2.14 ‘Days’ means calendar days;

1.2.15 ‘The Design’ means the design proposals contained in the Contractor’s Tender as accepted by the Authority together with the Construction Documents;

1.2.16 ‘The Design Brief’ means the technical document issued in the Invitation to Tender;

1.2.17 ‘Design Document’ means any plan, sketch, drawing, calculation, specification or any other document whatsoever prepared in the performance of the Contract;

1.2.18 ‘The Final Account’ means the document agreed by the Authority showing the calculation of the Final Sum in accordance with Condition 79 (Final Account);

1.2.19 ‘The Final Sum’ means the amount payable under the Contract by the Authority to the Contractor for the full and entire execution and satisfactory completion of the Design and Works;

1.2.20 ‘Group’ means, and includes, a company and every holding company of that company for the time being, and every subsidiary for the time being of every such holding company;

1.2.21 The ‘Construction Phase Plan’ means, where the CDM Regulations apply, the Principal Contractor will use the Pre-Construction Information Pack provided by the Authority to produce a Construction Phase Plan in accordance with CDM Regulations. Once produced, the Principal Contractor is to submit the Construction Phase Plan to the Principal Designer for approval prior to the start of construction, and on any changes;

1.2.22 ‘Holding company’ shall have the meaning given in Section 1159 of the Companies Act 2006;

1.2.23 'Information' means any information in any written or other tangible form disclosed to one party by or on behalf of the other party under or in connection with the Contract.

1.2.24 ‘Instruction’ means any instruction given in accordance with Condition 62;

1.2.25 ‘The Maintenance Period’ means the period, as specified in Condition 87;

1.2.26 ‘Milestone’ means the satisfactory completion of each of the phases of the Works described in the Milestone Payment Schedule;

1.2.27 ‘The Milestone Payment Schedule’ means the Milestones, the Milestone completion dates and the value of each Milestone to be paid to the Contractor by the Authority during the performance of the Works;

1.2.28 ‘Pricing Document’ means that document submitted as part of the Tender as accepted by the Authority;

1.2.29 ‘Principal Contractor’ means the Contractor, or such other Contractor or organisation as may be appointed as the Principal Contractor for the time being by the Authority pursuant within the CDM Regulations 2015;

1.2.30 ‘Principal Designer’ means the PM, or his appointed representative, or any other such person as may be appointed in that capacity for the time being by the Authority pursuant to CDM Regulations 2015;

1.2.31 ‘Products’ means materials (including naturally occurring materials) and goods (including components, equipment and accessories) intended for permanent incorporation in the works;

1.2.32 The ‘PM’ means the Project Manager, or his locally appointed representative, who is the person employed in that capacity named in the Contract and appointed by the Authority to act on his behalf in carrying out those duties described in the Contract (subject to the exclusions set out therein), or such other person as may be appointed in that capacity for the time being, and advised, by the Authority;

1.2.33 The ‘Programme’ means the programme referred to in Condition 58 (Programme);

1.2.34 The ‘Site’ means the land or place detailed in the Contract, together with such other land or places as may be allotted or agreed by the parties from time to time, for the purpose of carrying out the Contract;

1.2.35 ‘Subsidiary’ shall have the meaning given in Section 1159 of the Companies Act 2006;

1.2.36 ‘Tender’ means the Tender submission of the Contractor including his Design and Pricing Document (including Milestone Payment Schedule if appropriate), and any amendments thereto, agreed prior to the Authority’s acceptance;

1.2.37 ‘Things’ comprise ‘Things for incorporation’, which means goods and materials intended to form part of the completed Works, and ‘Things not for incorporation’ which means goods and materials provided or used to facilitate execution of the Works but not for incorporation in them;

1.2.38 The ‘Works’ means the works described or shown in the Design including all modified or additional works to be executed under the Contract;

1.2.39 The ‘Works Contract Officer’ (WCO) is the commercially delegated officer exercising the Contract Authority on behalf of the Authority. He acts as the focal point for the Contract ensuring that the Contractor performs and delivers the requirements of the Contract Specification and Conditions.

1.3 The headings to these Conditions shall not affect their interpretation. Any reference to legislation shall be deemed to include a reference to any amendment or re-enactment thereof for the time being in force. Words in the singular include the plural, and *vice versa.* Words in the masculine include feminine and neuter.

1.4 Any notices or order to be given under the Contract shall be in writing. They may be given to the Contractor by delivery to his agent or may be posted to the registered office or last known place of business of the Contractor. A postal notice shall be deemed to have been served on the date when in the ordinary course of post it would have been delivered.

1.5 The Contractor shall give the Authority at least 14 days’ notice to consider any action required, or to make any decisions.

1.6 Except in relation to Condition 67 (Extensions of Time), any period of time in these Conditions within which the Authority, the Contractor, or PM, is to take action or decide anything may be extended by agreement, notwithstanding that the period of time has expired.

1.7 For the purposes of this Contract, and for all other purposes, periods of time shall include Saturdays and Sundays, but shall be reckoned as follows;

1.7.1 Where an act is required to be done within a specified period after or from a specified date, the period begins immediately after that date.

**2. Contract Documents**

2.1 In case of discrepancy between these Conditions and other documents forming part of the Contract these Conditions shall prevail.

2.2 In the case of discrepancy between the Design Brief and the Contractor’s Proposal, the Design Brief shall prevail.

2.3 The Authority has, subject to the Provisions of the Contract, accepted the Contractor’s Proposal and Pricing Document but does not by its acceptance warrant to the Contractor that the Contractor’s Proposal is necessarily in accordance in all respects with the Design Brief. The Contractor shall ensure that any Specification, Model, Drawing, Sketch or Plan is in accordance with the Design Brief.

2.4 The Contractor shall provide free to the PM a maximum of up to 6 copies of the Construction Documents when requested. The issue of the Construction Documents by the Contractor shall be made promptly, timely during the progress in accordance with the Programme. The Contractor shall keep one copy of all Construction Documents on the Site and the PM or his representative shall have access to them at all reasonable times.

**3. Licences**

3.1 The Contractor shall have the necessary licence(s) appropriate for the performance of this Contract.

**4. Spare**

**5. Spare**

**AUTHORITY POLICY**

**6. Patents**

6.1 The Contractor shall pay any royalty, licence fee or other expense for the supply or use of any patent, process, drawing, model, plan, invention or information used or necessary for, or in connection with, the design or construction of the Works.

6.2 Where the use or supply of any patent etc in accordance with sub-paragraph 6.1 above gives rise to any claim or proceedings against the Authority, the Contractor shall reimburse the Authority any costs and expenses incurred by the Authority in respect of that claim of proceedings.

6.3 The Authority shall reimburse the Contractor the amount of royalty etc incurred in accordance with paragraph 6.1 which;

6.3.1 was necessarily incurred in order to comply with a Change Order; and

6.3.2 was not reasonably contemplated under the Contract.

**7. Discrimination**

7.1 The Contractor shall not unlawfully discriminate within the meaning and scope of the provisions and meaning of the Race Relations Act 1976 or any statutory modification or re-enactment of it.

7.2 The Contractor shall take all reasonable steps to ensure the observance of the provisions of Paragraph 7.1 by all his servants, agents, Sub-contractors and employees.

**8. Corruption**

8.1 The Contractor shall not by himself or in conjunction with any other person;

8.1.1 Corruptly solicit, receive or agree to receive, for himself or for any other person; or

8.1.2 Offer or agree to give to any person in the Authority’s service, or any consultant or Contractor who has a Contract with the Authority;

any gift or consideration of any kind as an inducement or reward for doing or not doing anything, or for showing favour or disfavour to any person, in relation to this Contract or any other Contract to which the Authority is a party.

8.2 The Contractor shall not enter into this or any other Contract with the Authority in connection with which commission has been paid or agreed to be paid by him or on his behalf or to his knowledge unless, before any such Contract is made, particulars of any such commission, and of the terms and conditions of any agreement for the payment thereof, have been disclosed in writing to the Authority.

8.3 The Authority may by notice determine the Contract if:

8.3.1 He is reasonably satisfied that the Contractor or anyone employed by him or acting on his behalf (whether with or without the knowledge of the Contractor) is in breach of this Condition; or

8.3.2 The Contractor is convicted of any offence under the Prevention of Corruption Acts 1889 to 1916 or the Bribery Act 2010.

and, (without prejudice to any powers conferred by Condition 82 (Recovery of Sums from the Contractor), shall be entitled to recover from the Contractor the amount or value of any such gift or consideration.

8.4 Any decision by the Authority that the Contractor is in breach of this Condition shall be final and conclusive for the purposes of Condition 90 (Determination).

**9. Vesting**

9.1 The Works and any Things on the Site in connection with the Contract, the ownership of which the Contractor is able to transfer, or which vest in him under any Contract, shall become the property of and vest in the Authority.

9.2 Subject to Conditions 13 (Loss or Damage) and 12 (Other Works), the Authority shall not be responsible or chargeable for any Thing lost, stolen, damaged, destroyed or removed from the Site, or which is in any way unfit or unsuitable for its purpose.

9.3 The Contractor shall be responsible for the protection and preservation of the Works and any Things brought on the Site until the completion of the Works or the determination of the Contract.

9.4 No Things shall be removed from the Site before completion of the Works without the written consent of the PM. The PM may instruct or permit the Contractor in writing at any time to remove from the Site any Things which are unused, or which have been rejected by the PM, and the Contractor shall at his own expense forthwith remove them. Once so removed from the Site, the Things shall re-vest in the Contractor.

**10. Assignment**

10.1 The Contractor shall not, without the consent in writing of the Authority, assign or transfer the Contract, or any part, share or interest under it. No sum of money to become payable under the Contract shall be payable to any person other than the Contractor without the Authority’s written consent. The Authority may assign or transfer the benefit of the Contract, or any part, share or interest under it.

**11. Subletting**

11.1 Except where the Authority accepted a sub-letting proposal prior to the award of Contract or the Contract specifies the sub-letting of work, the Contractor shall not sub-let any part of the Contract without the prior consent of the Authority. The Contractor shall provide such details of any Sub-contractor he wishes to engage as the Authority may require.

11.2 The Contractor shall ensure that each sub-contract entered into will enable him to fulfil his obligations under the Contract. To the appropriate extent the Contractor shall require the Sub-contractor to assume towards the Contractor the obligations and responsibilities which the Contractor owes to the Authority under the Contract and give the Sub-contractor rights remedies and redress against the Contractor equivalent to those given to the Contractor against the Authority under the Contract.

11.3 Without prejudice to the obligations of the Contractor under any of the provisions of the Contract, the Contractor shall, whenever requested to do so by the Authority, take any necessary action to ensure that a person who has entered into a sub-contract complies with and performs all obligations imposed upon him.

11.4 Where for any reason a sub-contract is determined or assigned because of the default or failure of the Sub-contractor, the Contractor shall, at his own expense secure completion of the sub-contract Works.

11.5 The Contractor shall be responsible for any Sub-contractor or supplier employed by him in connection with the Works.

11.6 The Contractor shall make good any loss suffered or expense incurred by the Authority by reason of any default or failure, whether total or partial, on the part of any Sub-contractor or supplier.

**12. Other Works**

12.1 The Authority shall have power at any time to execute other Works (whether or not in connection with the Works) on the Site at the same time as the Works are being executed. The Contractor shall give reasonable facilities for these Works.

12.2 The Contractor shall not be responsible for damage done to other Works except for damage caused by the negligence, omission or default of his workpeople, agents or Sub-contractors. Any damage done to the Works in the execution of other Works shall, for the purposes of Condition 13 (Loss or Damage), be deemed to be damage which is wholly caused by the neglect or default of the Authority or of any other Contractor or agent of the Authority.

**13. Loss or Damage**

13.1 This Condition applies to any loss or damage that arises out of, or is in any way connected with, the execution or purported execution of the Contract.

13.2 The Contractor shall without delay and at his own cost reinstate, replace or make good to the satisfaction of the Authority, or if the Authority agrees, compensate the Authority for any loss or damage.

13.3 Where a claim is made, or proceedings are brought against the Authority in respect of any loss or damage, the Contractor shall reimburse the Authority any costs or expenses which the Authority may reasonably incur in dealing with, or in settling, that claim or proceedings.

13.4 The Authority shall notify the Contractor as soon as possible of any claim made, or proceedings brought, against the Authority by a third party in respect of any loss or damage.

13.5 The Authority shall reimburse the Contractor for any costs or expenses, which the Contractor incurs in accordance with sub-paragraphs 13.2 and 13.3 above to the extent that the loss or damage is caused by:

13.5.1 The neglect or default of the Authority or of any Contractor or agent of the Authority;

13.5.2 Any accepted risk; or

13.5.3 Any other circumstances which are outside the control of the Contractor or any of his Sub-contractors or suppliers and which could not have been reasonably contemplated under the Contract, provided that this sub-paragraph shall not apply where the loss or damage is loss or damage falling within 13.6.3 below.

13.6 In this Condition loss or damage includes:

13.6.1 Loss or damage to property;

13.6.2 Personal injury to or the sickness or death of any person;

13.6.3 Loss or damage to the Works or to any Things on the Site; and

13.6.4 Loss of profits or loss of use suffered because of any loss or damage.

**14. Rights of Third Parties**

* 1. Notwithstanding anything to the contrary elsewhere in the Contract, no right is granted to any person who is not a party to the Contract to enforce any term of the Contract in his own right and the parties to the Contract declare that they have no intention to grant any such right.
1. **Russian and Belarusian Exclusion**
	1. The Contractor shall, and shall procure that their Sub-contractors shall, notify the Authority in writing as soon as they become aware that:
		1. the Contractor Deliverables and/or Services contain any Russian / Belarussian products and/or services; or
		2. that the Contractor or any part of the Contractor’s supply chain is linked to entities who are constituted or organised under the law of Russia or Belarus, or under the control (full or partial) of a Russian / Belarusian person or entity. Please note that this does not include companies:
			1. registered in the UK or in a country with which the UK has a relevant international agreement providing reciprocal rights of access in the relevant field of public procurement; and/or
			2. which have significant business operations in the UK or in a country with which the UK has a relevant international agreement providing reciprocal rights of access in the relevant field of public procurement.
	2. The Contractor shall, and shall procure that their Sub-contractors shall, include in such notification (or as soon as reasonably practicable following the notification) full details of the Russian products, services and/or entities and shall provide all reasonable assistance to the Authority to understand the nature, scope and impact of any such products, services and/or entities on the provision of the Contract Deliverables and/or Services.
	3. The Authority shall consider the notification and information provided by the Contractor and advise the Contractor in writing of any concerns the Authority may have and/or any action which the Authority will require the Contractor to take. The Contractor shall be required to submit a response to the concerns raised by the Authority, including any plans to mitigate those concerns, within 14 business days of receipt of the Authority’s written concerns, for the Authority’s consideration.
	4. The Contractor shall include provisions equivalent to those set out in this clause in all relevant Sub-contracts.

**16. Disclosure of Information**

16.1 Subject to paragraph 16.4 and 16.5 each party:

16.1.1 shall treat in confidence all Information it receives from the other;

16.1.2 shall not disclose any of that Information to any third party without the prior written consent of the other party, which consent shall not unreasonably be withheld, except that the Works Contractor may disclose Information in confidence, without prior consent, to such persons and to such extent as may be necessary for the performance of the Contract;

16.1.3 shall not use any of that Information otherwise than for the purpose of the Contract; and;

16.1.4 shall not copy any of that Information except to the extent necessary for the purpose of exercising its rights of use and disclosure under the Contract.

16.2 The Works Contractor shall take all reasonable precautions necessary to ensure that all Information disclosed to the Works Contractor by or on behalf of the Authority under or in connection with the Contract:

16.2.1 is disclosed to its employees and supply chain members, only to the extent necessary for the performance of the Contract; and

16.2.2 is treated in confidence by them and not disclosed except with prior written consent or used otherwise than for the purpose of performing work or having work performed for the Authority under the Contract or any sub-contract under it.

16.3 The Works Contractor shall ensure that his employees are aware of his arrangements for discharging the obligations at paragraph 16.1 and 16.2 before they receive Information and take such steps as may be reasonably practical to enforce such arrangements.

16.4 Paragraph 16.1 and 16.2 shall not apply to any Information to the extent that either party:

16.4.1 exercises rights of use or disclosure granted otherwise than in consequence of, or under, the Contract;

16.4.2 has the right to use or disclose the Information in accordance with other conditions of the Contract; or

16.4.3 can show:

16.4.3.1 that the Information was or has become published or publicly available for use otherwise than in breach of any provision of the Contract or any other agreement between the parties;

16.4.3.2 that the Information was already known to it (without restrictions on disclosure or use) prior to it receiving it under or in connection with the Contract;

16.4.3.3 that the Information was received without restriction on further disclosure from a third party who lawfully acquired it and who is himself under no obligation restricting its disclosure; or

16.4.3.4 from its records that the same information was derived independently of that received under or in connection with the Contract; provided the relationship to any other Information is not revealed.

16.5 Neither party shall be in breach of this Condition where it can show that any disclosure of Information was made solely and to the extent necessary to comply with a statutory, judicial or parliamentary obligation. Where such a disclosure is made, the party making the disclosure shall ensure that the recipient of the Information is made aware of and asked to respect its confidentiality. Such disclosure shall in no way diminish the obligations of the parties under this Condition.

16.6 Nothing in this Condition shall affect the parties' obligations of confidentiality where information is disclosed orally in confidence.

16.7 The Authority shall not be in breach of this condition where it can show that any disclosure of Information was made solely and to the extent necessary to comply with its obligations under the Freedom of Information Act 2000 and the Environmental Information Regulations 2004.

**CONTRACT PERSONNEL**

**17. Delegations and Representatives**

17.1 Any decision to be made by the Authority under the Contract may be made by any person or persons authorised to act for him for that purpose. The PM shall be deemed authorised to act generally for the Authority subject to any exclusions set out in the Contract.

17.2 The PM may expressly delegate in writing to named representatives any of his powers and duties. Where a Clerk of Works or Resident Engineer is appointed, he shall exercise the powers of the PM under Condition 70 (Quality) in respect of the Works and such other powers as the PM may delegate to him.

17.3 The appointment of representatives by the Authority, or PM, shall not prevent them from subsequently exercising directly any of the powers and duties conferred under the Contract.

17.4 The Contractor shall as soon as possible be notified of all powers and duties delegated, and the names of representatives, and of any subsequent changes.

**18. Contractor’s Agent**

18.1 The Contractor shall employ a competent agent or agents to supervise the Design work and execution of the Works. The Works agent shall be in attendance at the Site during all working hours and shall when required to do so attend at the office of the PM. Any Instructions given to the agent so appointed shall be deemed to have been given to the Contractor.

**19. Contractor’s Employees**

19.1 The Contractor shall be responsible for the recruitment, management and payment of suitably qualified and experienced workforce in accordance with the Contract agreement, to fulfil the requirements of the Contract. The Contractor shall ensure that at all times there are sufficient personnel with appropriate competence, qualification and experience engaged in the execution of the Contract.

19.2 The Authority may at any time require the Contractor immediately to cease to employ in connection with the Contract any person, including the Contractor’s agent, whose continued employment is in the opinion of the Authority undesirable. The Contractor shall replace any such person with a suitably qualified person without detriment to performance and at no additional cost to the Authority.

19.3 Other than for causes outside his control, the Contractor shall not make changes in personnel named in his Tender in connection with the Contract without the prior approval of the PM.

**20. Personal Data**

20.1 In connection with the Personal Data received under the contract, each party undertakes to comply with its obligations under Data Protection Legislation and in particular, but without limitation, each Party shall take appropriate technical and organisational measures against unauthorised or unlawful Processing of Personal Data provided to it by the other Party, and against accidental loss, alteration, unauthorised disclosure of or damage to that Personal Data in accordance with DEFCON 532A. Full details of the compliance required to DEFCON 532A is at Annex E.

**21. Fair Dealing and Team Working**

21.1 The Authority and the Contractor shall deal fairly, in good faith and in mutual co-operation, with one another, and the Contractor shall deal fairly, in good faith and in mutual co-operation, with all his Sub-contractors and suppliers.

21.2 Both parties accept that a co-operative and open relationship is needed for success, and that teamwork will achieve this. The project team for this purpose shall include, but shall not be limited to, the PM and his representatives; the Contractor’s agent; and major Sub-contractors and suppliers engaged on the Works from time to time.

21.3 As soon as possible, the PM shall call a project team meeting and agree a programme of regular meetings with the Contractor in accordance with Condition 60 (Progress Meetings). Either the PM or the Contractor may also call additional meetings of the team, and if the other agrees may invite any other person needed for an effective meeting. The PM and the Contractor shall use the meetings jointly to develop proposals for reducing costs by solutions that will, so far as possible, be to the benefit of all affected by potential or actual problems. The meetings shall also consider the issues of advance warning of anything that might raise costs or harm final quality of the Works.

**22. Freedom of Information and Transparency**

22.1 Notwithstanding any other term of this Contract, including Condition 16 of Booklet 2 where applicable, the Contractor gives its consent to the Authority to publish the content of this Contract in its entirety, including from time to time agreed changes to the Contract, and details of any payments made by the Authority to the Contractor under the Contract (“the Transparency Information”) to the general public. The Contractor shall assist and cooperate with the Authority to enable the Authority to publish the Transparency Information.

22.2 Before publishing the Transparency Information to the general public in accordance with clause 22.1 above, the Authority may redact any information that would be exempt from disclosure if it was the subject of a request for information under the Freedom of Information Act 2000 (“the Act”) or the Environmental Information Regulations 2004 (“the Regulations”).

22.3 The Authority may consult with the Contractor before redacting any information from the Transparency Information in accordance with clause 22.2 above. The Contractor acknowledges and accepts that its representations on redactions during consultation may not be determinative and that the decision whether to redact information is a matter in which the Authority shall exercise its own discretion, subject always to the provisions of the Act or the Regulations.

**23. Spare**

**HEALTH, SAFETY & ENVIRONMENT**

**24. Health, Safety and the Environment**

24.1 The Contractor shall carry out the Works in accordance with the Authority’s Health and Safety Requirements and in compliance with any Environmental Law and any legislation repealing or replacing or re-enacting the said requirements and legislation herein referred to.

24.2 The Contractor shall throughout the performance of the Contract have full and proper regard to the health and safety of all persons entitled to enter the Establishment and shall keep the Establishment in such a manner so as to keep to a minimum any danger and / or hazard to such persons including any health and safety and or environmental risks to such persons.

24.3 In the event of a breach of this Condition the Contractor shall fully indemnify the Authority against all claims, losses, demands, costs, expenses and damages.

24.4 The Contractor may be required to attend safety training at the site, which may be arranged from time to time by the Authority. The Contractors attendance will be at no additional cost to the Authority.

24.5 In the event that the Authority is not satisfied that the Contractor is complying with this Condition, the Authority may serve a notice of dissatisfaction specifying the steps that the Contractor should take to comply with this Condition. In the event that the Contractor fails to comply with the Notice of Dissatisfaction within 5 working days from receipt thereof, the Authority shall be entitled to terminate the Contract in accordance with the provisions of Condition 90 (Determination).

24.6 The Contractor shall report any injury, illness, disease or dangerous occurrence arising out of the performance of this Contract, which is required to be reported under the Reporting of Injuries, Diseases and Dangerous Occurrences Regulations 1995 (RIDDOR) to the Authority. This shall be in addition to any report, which the Contractor may be required to submit under RIDDOR to the relevant authority.

24.7 Where the Contractor enters an Establishment for the purpose of performing work under the Contract, he shall notify the Authority of;

24.7.1 Any Health and Safety hazards associated with the work to be performed by him or any of his Employees, Sub-contractors and all other Persons under his control;

24.7.2 Any foreseeable risks to the health and safety of all persons associated with such hazards; and

24.7.3 Any precautions to be taken by him as well as any precautions which, in his opinion, ought to be taken by the Authority in order to control such risks.

24.8 The Authority shall notify the Contractor of;

24.8.1 Any Health and Safety hazards which may be encountered by the Contractor or any of his Employees, Sub-contractors and all other Persons under his control, on the Establishment;

24.8.2 Any foreseeable risks to the health and safety of the Contractor or any of his Employees, Sub-contractors and all other Persons under his control, associated with such hazards; and

24.8.3 Any precautions to be taken by the Authority as well as any precautions which, in his opinion, ought to be taken by the Contractor in order to control such risks.

24.9 The contractor shall notify his employees, sub-contractors and all other persons under his control of the following and, where appropriate, provide adequate related instruction;

24.9.1 The hazards, risks and precautions notified by the Contractor to the Authority under Condition 24.7;

24.9.2 The hazards, risks and precautions notified to the Contractor by the Authority under Condition 24.8;

24.9.3 The precautions which, in his opinion, ought to be taken by his employees, sub-contractors and all other persons under his control in order to control those risks.

24.10 The contractor shall provide the Authority with;

24.10.1 Copies of those sections of his own, and where appropriate, his Employees, Sub-contractors and all other Persons in his control, Safety Policies which are relevant to the risks identified at Conditions 24.7 and 24.8.

24.10.2 Copies of any related risk assessments;

24.10.3 Copies of any notifications and instructions issued by him to his Employees, Sub-contractors and any other Persons under his control under Condition 24.9.

24.11 Any such notification or advice given by the Authority in accordance with this condition shall not in any way affect the Contractor’s liability in respect of health and safety under the Contract and the Contractor, whilst complying with the matters notified by the Authority shall rely upon his own assessment and understanding of such risks. Any such matters so notified by the Authority shall not constitute an accepted risk.

**25. Statutory Notices and Construction Design and Management (CDM) Regulations**

25.1 The Contractor shall give all notices required by any Act of Parliament or by any regulations or byelaws made under any Act which may be required in connection with the Works. He shall pay any fees or charges required to be paid under any Act, regulations or byelaws in respect of the Works and supply all drawings and plans required in connection with any notice.

25.2 The Contractor shall bear full responsibility for compliance, and shall comply in all respects, with the Construction (Design and Management) Regulations 2015.

25.3 The Contractor shall perform all the functions and duties of the Principal Designer and Principal Contractor.

25.4 For the avoidance of doubt, the Contractor shall have no right to claim for any additional time, loss, expense or other financial consequence arising from or in connection with any delay or disruption to the progress of the Works occasioned by activities necessary to comply with the Regulations.

**26. Nuisance and Pollution**

26.1 The Contractor shall take all reasonable precautions to prevent any nuisance or inconvenience to the owners, tenants or occupiers of any other property and to the general public and shall secure the efficient protection of all streams and waterways against pollution.

**27. Ozone-depleting Substances**

27.1 The Contractor shall not, without the prior written consent of the Authority, specify in the Works Contractor’s Design or use in the carrying out of the Works any products or other ozone–depleting substances referred to in the Montreal Protocol on substances that deplete the ozone layer, as amended and updated from time to time.

**28. Spare**

**SECURITY**

**29. Site Admittance**

29.1 The Contractor shall take all steps reasonably required by the Authority to prevent unauthorised persons being admitted to the Site. If the PM gives the Contractor notice that any person is not to be admitted to the Site, the Contractor shall take immediate action to prevent that person being admitted.

29.2 The Contractor shall give to the PM a list of names and addresses of all persons who are or may be at any time concerned with the Works or any part of them, specifying the capacities in which they are so concerned, and giving such other particulars as the PM may reasonably require.

29.3 The decision of the PM as to whether any person is to be admitted to the Site and as to whether the Contractor has furnished the information or taken the steps required of him by this condition shall be final and conclusive.

29.4 The Contractor shall bear the cost of any notice, Instruction or decision of the PM under this Condition.

**30. Passes**

30.1 The Contractor shall arrange for all employees, Sub-contractors and suppliers that require admittance to site to be in possession of a valid security pass to the relevant Establishment. The Contractor is to allow sufficient time in his programme daily for non-pass holders to gain access. The Contractor shall submit to the Authority for his approval a list of the names of the workpeople and any other information the Authority reasonably requires in this respect. Any temporary passes issued specifically for the duration of the Works shall be returned at any time on the demand of the Authority and in any case on the completion of the Works.

**31. Photographs**

31.1 The Contractor shall not at any time take any photographs of the site or the works or any part of them, and shall take all reasonable steps to ensure that no such photographs shall at any time be taken or published or otherwise circulated by any of his employees, agents or Sub-contractors, unless the Contractor has obtained the prior written consent of the PM

**32. Official Secrets and Confidentiality**

32.1 The Contractor shall take all reasonable steps to ensure that all persons employed by him or his Sub-contractors in connection with the Contract are aware of the Official Secrets Act 1989, and that this Act will apply to them during the execution of the Works and after the completion of the Works or earlier determination of the Contract.

32.2 Any information concerning the Contract obtained either by the Contractor or by any person employed by him in connection with the Contract is confidential and shall not be used or disclosed by the Contractor or by any such person except for the purposes of the Contract.

**33. Contractors Personnel – Security**

33.1 All Contractors' personnel may need to be security cleared to an appropriate level. The Authority will retain the right to veto any individual’s employment for reasons of security and has the right to require any member of the Contractors’ staff to be removed from the site or theatre.

**34.** **Cyber Security**

34.1 The Authority will determine and review the level of Cyber Risk applicable to this Contract at regular intervals throughout the life of the Contract.

**35. Spare**

**INSURANCE**

**36. Insurance**

36.1 Without prejudice to its obligation to indemnify or otherwise be liable to the Authority under this Contract, the Contractor shall take out and maintain, or procure the taking out and maintenance of;

36.1.1 Third Party Public and Products Liability Insurance indemnifying the Contractor in respect of all sums that the Contractor may become legally liable to pay (including claimant’s costs and expenses) as damages in respect of accidental death or bodily injury, illness or disease contracted by any person (not an employee of the Contractor) and/or loss or damage to third party property (including property of the Authority) and arising out of or in connection with the Contract. The Third-Party Public and Products Liability Insurance shall have a limit of indemnity of not less than **five hundred thousand USD ($500,000.00)** in respect of any one occurrence, the number of occurrences being unlimited in any annual period of insurance, but **five hundred thousand USD ($500,000.00)** any one occurrence and in the aggregate per annum in respect of products and pollution liability.

36.1.2 Construction "All Risks" Insurance providing insurance cover in respect of "All Risks" of physical loss, damage or destruction to the permanent and temporary works, materials, goods, plant and equipment for incorporation in any relevant works (and all other property used or for use in connection with the works and things associated with the Contract). The Construction "All Risks" Insurance shall have a sum insured at all times in an amount not less than the full reinstatement or replacement value of the works and associated physical property. The Authority shall be named as a co-insured party for its separate interests with attendant non vitiation and waiver of subrogation in favour of the Authority.

36.1.3 And any other insurances required by relevant law or regulation (together the "Required Insurances").

36.1.4 The Contractor shall ensure that the Required Insurances are effective in each case not later than the date on which the relevant risk commences.

36.2 The Required Insurances shall be taken out and maintained with insurers who are of good financial standing and of good repute in the international insurance market.

36.3 The Contractor shall not (and the Contractor shall procure that none of its Subcontractors of any tier shall not) take any action or fail to take any action or, insofar as is reasonably within its power, permit anything to occur in relation to it which would entitle any insurer to refuse to pay any claim under any of the Required Insurances.

36.4 If the Contractor is in breach of clause 36.1, the Authority may elect, but shall not be obliged, to purchase any insurance which the Contractor is required to maintain pursuant to this Contract but has failed to maintain in full force and effect, and the Authority shall be entitled to recover the premium and other reasonable costs incurred in connection therewith as a debt due from the Contractor.

36.5 The Contractor shall, upon the date of this Contract and within fifteen (15) days after the renewal of any of the Required Insurances, provide evidence, in a form satisfactory to the Authority, that the Required Insurances are in force and meet the requirements of this clause 36. The supply to the Authority of any evidence of insurance cover in compliance with the requirements of this clause shall not imply acceptance by the Authority that the extent of insurance cover is sufficient or that the terms and conditions thereof are satisfactory, in either case, for the purposes of this Contract, nor be a waiver of the Contractor's liability under this Contract.

36.6 The Contractor shall notify the Authority at least ten (10) days prior to the cancellation, suspension, termination or non-renewal of any of the Required Insurances.

36.7 Where any Required Insurance requires payment of a premium, the Contractor shall be liable for such premium.

36.8 Where any Required Insurance is subject to an excess or deductible, below which the indemnity from insurers is excluded, the Contractor shall be liable for such excess or deductible which would otherwise be insured but for the excess or deductible. The Contractor shall not be entitled to recover from the Authority any sum paid by way of excess or deductible under the Required Insurances whether under the terms of this Contract or otherwise.

36.9 All insurance proceeds received in respect of the Construction “All Risks” Insurance shall be used to reinstate, repair or replace the insured property in respect of which the insurance proceeds were received.

**37.** **Spare**

**38. Spare**

**39. Spare**

**40. Spare**

**THE SITE**

**41. Occupier’s Rules and Regulations**

41.1 The occupier’s rules and regulations will be advised and clarified by the PM at Contract Award.

41.2 The Contractor shall comply with the occupier’s rules and regulations which have been provided to him or made available to him for inspection, both in respect of the Site and in respect of any larger premises of which the Site forms part. The Contractor shall comply with any changes to those rules and regulations notified to him as an Instruction under Condition 61 (Change Control Procedures) during the execution of the Works.

**42. Occupation of Government Premises**

42.1 Any land or premises (including temporary buildings) made available to the Contractor by the Authority in connection with the Contract shall be made available to the Contractor free of charge and shall be used by the Contractor solely for the purposes of performing this Contract. The Contractor shall have the use of such land or premises as Licensee and shall vacate the same upon termination or completion of the Contract or when requested by the WCO.

**43.** **Use of the Site**

43.1 The Contractor shall not use the areas agreed for performance of the Contract for any other purpose other than to the extent necessary and agreed by the Authority for the performance of the Contract. In this respect he shall comply with any instructions issued by the PM. The Contractor shall not cause any obstruction to normal pedestrian or vehicular movements around the Base. No storage of materials or parking of vehicles or temporary accommodation or any other use of areas beyond this area shall be permitted.

43.2 The Contractor shall be responsible for providing sufficient site office and facilities for all personnel necessary for performance of the Contract. The Authority will not be responsible for providing any other facilities other than those detailed in the Contract.

43.3 The Contractor shall, at all times, keep the Site tidy and free from debris, litter and rubbish and shall, not later than the Works Completion Date, remove from the Site all Things for incorporation which are unused, together with all things not for incorporation. The Contractor shall, by the Works Completion Date, clear and remove all rubbish and deliver up the Site, in all respects, in accordance with the Contract. The Contractor shall comply at his own cost with any PM direction relating to the removal of any Things and Rubbish.

**44. Spare**

**45. Spare**

**THE WORKS**

**46. Design**

46.1 The Contractor shall undertake and be responsible for the Design, which shall comply with the requirements of the Design Brief. The Works shall be executed in accordance with the Design and shall be reasonably fit for the purpose described in the Design Brief (the design requirement as defined within the Outline Design and Specification and the General Specification).

46.2 The Contractor shall provide the PM with up to a maximum of 6 copies of all Design Documents on request. The PM shall notify the Contractor in writing within 72 hours of receiving any Design Document whether or not he considers the document to be satisfactory as a Construction Document. The Contractor shall not commence any work to which such Design Document relates unless the Contractor has been notified by the PM in writing that it is considered satisfactory, and the Contractor shall not alter that design without the further written approval of the PM.

46.3 If the PM considers that a Design Document is not satisfactory as a Construction Document, he shall reject the document concerned and the Contractor shall at his own cost amend it and submit an amended version(s) to the PM satisfaction.

46.4 The PM will only be entitled under paragraph 46.3 to reject Design Documents which he considers would render the Design incapable of complying with the Design Brief or which, if used for construction, would render the Works unfit for their purpose.

46.5 The Contractor shall warrant that the Design will comply with the conditions of any planning consent, the requirements of the Building Regulations and shall comply and continue to comply with MoD Fire Regulations and all other relevant statutory requirements.

46.6 The Contractor shall be liable for the rectification of any defect which occurs during a period of 25 years following the expiry of the Maintenance Period and which is caused by a fault in the design.

46.7 The Contractor’s liability under this condition shall not be affected by any warranty that the Authority may obtain from any Sub-contractor.

46.8 The copyright in all Design and Construction Documents related to this Project will be the property of and will vest in the Authority.

46.9 Nothing in this Condition shall relieve the Contractor of liability under the Contract for any defect in any Design or Construction Document, or for any defect in the Design as a whole.

46.10 In case of any discrepancy between the Authority’s Requirements and any Design Document, the Authority’s Requirements shall prevail, without any adjustment to the Contract Price.

46.11 In case of discrepancy within, or between, Design Documents, the Contractor shall resolve the discrepancy to the satisfaction of the PM, without any adjustment to the Contract Price.

46.12 If the Contractor discovers any of the discrepancies referred to in sub-paragraphs 46.10 and 46.11 above, he shall immediately notify the PM, informing him of the discrepancy.

**47. Technical Guidance**

47.1 The Contractor shall ensure that the constructed Works and Contractor designed Works where applicable comply with all relevant legislation, national or EU standards and any relevant Technical Guidance. For the purpose of this Condition, Technical Guidance means any document published by the Authority as “Defence Estates (DE) Technical Bulletins” and “Defence Works Functional Standards” or any guidance published by the Authority and deemed by the Authority to be extant. DE Technical Bulletins and other technical guidance are available via the World Wide Web (www).

**48. Spare**

**49. Excavations**

49.1 Except as otherwise provided by the Contract, material and objects of any kind obtained from work on the Site (including, without limitation, from excavations, demolition or dismantling) shall remain or become the property of the Authority.

49.2 When the Authority’s property is permitted to be used in substitution for any Things, (whether or not for incorporation), which the Contractor would otherwise have provided, the Authority shall ascertain and agree with the Contractor the amount of any saving in the cost of the execution of the Works. The Contract Price shall be reduced by the value of any saving.

49.3 All objects which are, or appear to be, fossils, antiquities, or likely to have interest or value, found on the Site or in carrying out excavations in the execution of the Works, shall remain or become the property of the Authority. Upon the discovery of any such object, the Contractor shall forthwith:

49.3.1 Take all practicable measures not to disturb the object;

49.3.2 Cease work, if the continuance of work would endanger, or disturb, the object, or prevent or impede its excavation or removal;

49.3.3 Take all necessary steps to preserve the object in the exact position and condition in which it was found; and

49.3.4 Inform the PM of the discovery and precise location of the object.

49.4 Any Instructions issued by the PM in relation to any object mentioned in paragraph 49.3 above, may require the Contractor to permit the examination, excavation or removal of the object by a third party.

**50. Foundations**

50.1 The Contractor shall not lay any foundations until the excavations for them have been examined by the PM. The Contractor shall give the PM a minimum of 5 days’ notice prior to laying any foundations.

**51. Covering Work**

51.1 The Contractor shall give the PM a minimum of 2 days prior notice whenever any work or thing for incorporation is intended to be covered with earth or otherwise. In default of such notice, the Contractor shall, if required by the PM, uncover the work or Thing at his own expense.

**52. Protection of Works**

52.1 The Contractor shall during the execution of the Works take all reasonable measures and precautions needed to take care of the Site and the Works and shall have custody of all Things on the Site against loss or damage from fire and any other cause. The Contractor shall be solely responsible for and shall take all reasonable and proper steps for protecting, securing, lighting and watching all places on or about the Works and the Site which may be dangerous to his workpeople or to any other person.

52.2 The Contractor shall comply with any statutory regulations (whether or not binding on the Crown) which govern the storage and use of all Things that are brought on to the Site in connection with the Works.

**53. Conditions Affecting Works**

53.1 The Contractor shall in relation to the Site be deemed to have satisfied himself as to: -

53.1.1 The existing roads and other means of communication with or access to it;

53.1.2 Its contours and boundaries;

53.1.3 The risk of damage by reason of any work to any property adjacent to the Works and injury to occupiers of that property;

53.1.4 The nature of the soil and material (whether natural or otherwise) to be excavated;

53.1.5 The conditions under which the Works will have to be carried out, including precautions to prevent nuisance and pollution;

53.1.6 The supply of and conditions affecting labour necessary to carry out the Works;

53.1.7 The facilities for obtaining any Things whether or not for incorporation, and

53.1.8 Any survey and investigative works they believe necessary for both the design and safe execution of the Works, and;

53.1.9 Any other matters or information affecting or likely to affect the execution of, or price tendered for, the Works.

53.2 If, during the execution of the Works, the Contractor becomes aware of ground conditions (excluding those caused by weather but including artificial obstructions) which he did not know of, and which he could not reasonably have foreseen having regard to any information which he had, or ought reasonably to have ascertained, he shall, as a condition precedent to any right of remedy in respect of such conditions, by notice immediately;

53.2.1 Inform the PM of those conditions; and

53.2.2 State the measures, which he proposes to take to deal with them.

53.3 If the PM agrees that the ground conditions specified in a notice under Condition 53.2 could not reasonably have been foreseen by the Contractor having regard to any information he should have had in accordance with that Condition, he shall certify those conditions to be ‘Unforeseeable Ground Conditions’. The PM shall notify the Contractor of his decision which shall be final and conclusive.

53.4 If, after ground conditions specified in a notice under Condition 53.2 have been or should have been certified as Unforeseeable Ground Conditions in accordance with this Condition, and, as a result of such Unforeseeable Ground Conditions the Contractor in executing the Works properly carries out or omits any work which he would not otherwise have carried out or omitted, then without prejudice to any instruction given by the PM, the value of the work carried out or omitted shall be ascertained in accordance with Condition 63 (Valuation of PM’s Instructions-Principles) and the Contract sum shall be increased or decreased accordingly.

53.5 No claim by the Contractor for additional payment will be allowed because he has, or claims to have, misunderstood or misinterpreted anything mentioned in paragraph 53.1 above. The Contractor shall not be released from any risks or obligations imposed on or undertaken by him under the Contract for this reason or because he did not or could not foresee any matter which might affect or have affected the execution of the Works.

**54. Spare**

**55. Spare**

**MANAGING THE WORKS**

**56. Returns**

56.1 The Contractor shall provide the PM with a return, in a form the PM shall direct, of the number and description of his workpeople and the plant employed each day on the Works including those employed by Sub-contractors.

**57. Records**

57.1 The Contractor shall for the purposes of the Contract keep such records as may be reasonably necessary for the PM and / or the Authority to ascertain or verify any claims made or to be made by the Contractor or any sums to be paid to the Contractor under, or in connection with, the Contract.

57.2 In order that the PM may discharge his functions under the Contract, the Contractor shall afford him access to the records mentioned in sub-paragraph 57.1 and supply him with the information (including means to interpret the records) that may be required.

**58. Programme**

58.1 The Contractor shall deliver the Works in accordance with the programme and methodology agreed in the Contract. Without prejudice to Condition 60 (Progress Meetings), the Contractor may at any time submit proposals to the PM for amending the agreed programme. Such proposals shall not, however, be included in the Programme unless and until they have been agreed by the PM.

**59. Commencement and Completion**

59.1 Upon receipt of the Authority’s letter of acceptance of his Tender, the Contractor shall immediately commence the performance of the Contract. Possession of the Site shall be given to the Contractor on the date agreed under the Contract and he shall then take possession of the Site or parts of the Site and forthwith commence the execution of the Works and proceed with diligence and in accordance with the Programme or as may be instructed by the PM, so that the whole of the Works or any relevant Section shall be completed to the satisfaction of the PM by the agreed Date or Dates for Completion.

59.2 The Contractor shall, at all times, keep the Site tidy and free from debris, litter and rubbish and shall not later than the agreed date for Completion of the Works, remove from the Site all Things for incorporation in the Works or any relevant Section(s) which are unused, together with all things not for incorporation. The Contractor shall by the agreed date clear and remove all rubbish and deliver up the Site and the Works in all respects to the satisfaction of the PM. The Contractor shall comply at his own cost with any Instructions from the PM relating to the removal of any Things and rubbish.

59.3 When the Contractor considers the Works to be completed, he shall invite the PM to certify that they are complete to the PM’s satisfaction. Before certifying the Works as complete, the PM and Contractor shall jointly inspect the Works. If, in the opinion of the PM, the Works are not complete, the PM shall not certify them as such, and the Contractor must do whatever is necessary to complete the Works. However, if some minor works (“snags”) are still to be completed but in the opinion of the PM the Works are substantially complete, the PM may certify the Works as complete subject to the completion by the Contractor of those snags to the satisfaction of the PM.

**60. Progress Meetings**

60.1 The Contractor shall attend weekly progress meetings at the WCO office (Nyati) **Wednesdays at 1430 hrs** to assess progress and to facilitate satisfactory completion by the agreed date or dates for completion.

60.2 As a minimum a progress meeting shall be held each fortnight subject to any Instructions to the contrary. The PM shall specify the time and place of progress meetings.

60.3 The Contractor shall submit to the PM, at least 3 days before each progress meeting, a written report which shall, as a minimum;

60.3.1 Describe the progress of the Design and execution of the Works by reference to the Programme, and relevant Instructions;

60.3.2 Specify all outstanding requests by the Contractor for information;

60.3.3 Explain any new circumstances arising since the previous meeting which in his opinion have delayed, or may delay, completion of the Works or a Section of them;

60.3.4 Refer to any request for an extension of time under Condition 67 (Extensions of Time) since the previous meeting;

60.3.5 Set out any re-programming proposals to ensure that the completion of the Works or any Section will be achieved by the relevant Date for Completion.

60.3.6 Give any additional details requested by the PM.

60.4 The PM shall, within 3 days of each progress meeting, give the Contractor, a written statement which specifies;

60.4.1 By reference to the Programme the extent to which he considers the project is on time, delayed or early;

60.4.2 The matters that the PM considers have delayed, or are likely to delay, due completion of the Works or any Section or Sections;

60.4.3 The steps that the PM has agreed with the Contractor to reduce or eliminate the effects of any such delay;

60.4.4 The situation in respect of applications for and awards of extensions of time under Condition 67 (Extensions of Time); and

60.4.5 His response to outstanding requests for information.

**61. Change Control Procedures**

61.1 Changes to the Contract (“Changes”) shall for the purpose of this condition mean;

61.1.1 The award of extensions of time in accordance with Condition 67 (Extensions of Time);

61.1.2 The acceptance of proposals for acceleration in accordance with Condition 66 (Acceleration);

61.1.3 The determination of expense arising from the prolongation or disruption of the regular progress of the Works or any part of them in accordance with Condition 68 (Prolongation and Disruption); and

61.2 In event of any conflict or inconsistency between this Condition and the Conditions referred to in Condition 61.1, this Condition shall prevail.

61.3 Either party to the Contract may initiate a Change and shall, subject always to the provisions of paragraph 61.2, follow the procedures laid down in the Condition governing that Change and in accordance with the Change Control Procedure detailed within the Change Proposal Form at Annex A.

61.4 The Contractor shall be responsible for co-ordinating and providing all information necessary for the Authority to assess the proposed Change. Such information should be submitted to the WCO detailed in the Appendix to Contract. As appropriate he will issue any necessary Amendment to Contract. The Contract may only be amended by the WCO.

61.5 If as a result of a Change, the Contract Sum is adjusted, the Milestone Payment Schedule, if appropriate, shall be adjusted by agreement to reflect the effect of the Change as follows;

61.5.1 For Changes in accordance with any PM’s Instruction, the WCO shall advise the Milestone on completion of which price for the Change shall be paid;

61.5.2 For Changes in accordance with Condition 68 (Prolongation and Disruption), the WCO shall advise a separate Milestone to allow payment to be claimed at the earliest opportunity.

61.5.3 For any other Change, which affects the completion of more than one Milestone, the WCO may agree to renegotiate the full Milestone Payment Schedule.

61.6 No payment shall be made in respect of any Change unless and until the Change, and the price for the Change, has been agreed in writing by the WCO detailed in the Appendix to Contract. The Authority may not accept liability for any Change if the Contract procedures for agreeing Changes, detailed on the Change Proposal Form at Annex A, are not strictly adhered to.

**62. PM’s Instructions**

62.1 The Authority may from time to time issue further drawings, details, instructions, directions and explanations all or any of which shall be treated for the purposes of the Contract as PM Instructions, including Change Orders.

62.2 Instructions may be given in relation to all or any of the following matters;

62.2.1 The version or modification of all or any of the specification, drawings or Bills of Quantities, or the design, quality or quantity of the Works;

62.2.2 Any discrepancy in or between the specification, drawings and Bills of Quantities;

62.2.3 The removal from the Site of any Things for incorporation and their substitution with any other Things;

62.2.4 The removal and / or re-execution of any work executed by the Contractor;

62.2.5 The order of execution of the Works or any part of them;

62.2.6 The hours of working and the extent of overtime or night working to be adopted;

62.2.7 The suspension of the execution of the works or any part of them;

62.2.8 The replacement of any person employed in connection with the Contract;

62.2.9 The opening up for inspection of any work covered up;

62.2.10 The amending and making good any defects under Condition 87 (Defects in Maintenance Period(s).

62.2.11 The execution of any emergency work as mentioned in Condition 71 (Emergency Work).

62.2.12 The use or disposal of material obtained from excavations on the Site;

62.2.13 The actions to be taken following discovery of fossils, antiquities, objects of interest or value;

62.2.14 Measures to avoid nuisance or pollution;

62.2.15 Any other matter which the PM considers necessary or expedient.

62.3 All instructions shall be in writing except those under sub-paragraphs 62.2.2, 62.2.4, 62.2.7, and 62.2.11, which may be given orally – these will be confirmed in writing within 7 days of the oral instruction. The decision of the PM that any Instruction is necessary, or expedient shall be final and conclusive. The Contractor shall comply with any PM Instruction.

62.4 The Contractor shall not add to, omit from, or otherwise alter the Works except in accordance with a PM Instruction.

62.5 The PM may include in a Change Proposal a requirement for the Contractor to submit to the QS not later than 21 days from the receipt of that Instruction a written quotation of the lump sum price of complying with it.

**63. Valuation of PM’s Instructions – Principles**

63.1 It is a fundamental principle of this Contract that the price for any alterations or additions to or omissions from the Works, or the Design, where appropriate, shall be agreed by the WCO before the relevant Amendment to Contract is issued.

63.2 The price for any alterations or additions to or omissions from the Works etc will be calculated and agreed using the same prices and rates included in the Contractor’s accepted Tender for the Contract where these are appropriate and available. The Contractor shall provide a full breakdown of the proposed additional or reduced price(s) for consideration, negotiation as appropriate, and agreement with the Authority. The Contractor shall mitigate any additional costs incurred for any Change and shall provide full supporting documentation and explanation in support of any proposed alteration in price and such additional explanation and documentation as the Authority may reasonably require. The price will be agreed on the basis of “fair and reasonableness”.

63.3 In addition to Condition 63.2 above, full details of the Contractor’s proposals relating to alterations or additions to or omissions from the Works are to be provided in the Change Proposal Form enclosed at Annex A.

**64. Non-compliance with Instructions**

64.1 If, after receipt of a notice from the PM requiring compliance with any Instruction within a period specified in the notice, the Contractor fails to comply, the Authority may, without prejudice to the exercise of his powers to determine the Contract, provide labour and / or any Things (whether or not for incorporation), or enter into a Contract for the execution of any work which may be necessary to give effect to that Instruction. Any reasonable costs and expenses incurred by the Authority over and above those, which would have been incurred had the Contractor complied promptly with the Instruction, shall be recoverable by the Authority from the Contractor.

**65. Early Possession**

65.1 The Authority shall be entitled, before the completion of the Works, to take possession of any part of the Works (in this Condition referred to as a ‘completed part’) which is certified by the PM as having been completed in accordance with the Contract and is either;

65.1.1 A Section; or

65.1.2 Any other part of the Works in respect of which the parties agree, or the PM has given an Instruction, that possession shall be given before the completion of the Works or the relevant Section;

and the completed part, on and after the date on which the certificate is given, shall no longer form part of the Works for the purposes of Conditions 13 (Loss or Damage) and 9 (Vesting).

65.2 The provisions of Condition 87 (Defects in Maintenance Periods) shall have effect in relation to a completed part as if the Maintenance Period or Periods in respect of the completed part, or any sub-contract works comprised in it, commenced on the date of certification under Condition 69 (Certifying Completion).

65.3 As soon as possible after certification under Condition 69, the PM shall certify the value of the completed part.

65.4 Any decision of the PM under this Condition shall be final and conclusive.

**66. Acceleration**

66.1 If the Authority wishes to achieve completion of the Works or any relevant Section before the agreed Date or Dates for Completion, he shall direct the Contractor to submit to him within the period specified in the direction;

66.1.1 The Contractor’s priced proposals for achieving the accelerated completion date, together with any proposed consequential amendments to the Programme, or

66.1.2 As appropriate, the Contractor’s explanation why he is unable to achieve the accelerated completion date or such alternative priced proposals and amended programme as he considers appropriate.

66.2 If the Authority accepts the Contractor’s proposals he shall specify;

66.2.1 The accelerated Date for Completion of the Works and / or any relevant Section;

66.2.2 The amendment to the Programme, including any relevant critical paths and any supporting documentation;

66.2.3 The amount(s) by which the Contract Price shall be adjusted;

66.2.4 A revised Milestone Payment Schedule or Schedules, if appropriate;

66.2.5 Any other relevant amendment to the Contract which has been agreed with the Contractor.

66.3 The Contractor may at any time submit to the Authority proposals for completing the Works or any relevant Section, before the agreed Date or Dates of Completion. The Authority undertakes to consider any such proposals and, if he accepts them, to take action as in Condition 66.2.

**67. Extensions of Time**

67.1 Where the PM receives notice requesting an extension of time from the Contractor (which should include the grounds for his request) or where the PM considers that there has been or is likely to be a delay which will prevent or has prevented completion of the Works or any relevant Section by the agreed Date for Completion, he shall as soon as possible and in any event within 7 Days from the date any notice is received notify the Contractor of his final or interim decision regarding an extension of time for completion of the Works or relevant Section. The PM will come to a final decision on any outstanding interim decision(s) within a maximum of 7 days after completion of the work. No requests for extension of time may be submitted after completion of the Works or relevant Section.

67.2 The Authority shall award an extension of time under paragraph 67.1 only if he is satisfied that the delay, or likely delay, is or will be due to;

67.2.1 The execution of any modified or additional work;

67.2.2 The acts, neglect or default of the Authority or the PM;

67.2.3 An accepted Risk or unforeseeable ground conditions;

67.3 The PM shall indicate whether this decision is interim or final. The PM shall keep all interim decisions under review until he is satisfied from the information available to him that he can give a final decision.

67.4 The Authority shall not be entitled in a final decision to withdraw or reduce any interim extension of time already awarded, except to take account of any authorised omission from the Works or any relevant Section, that he has not already allowed for in an interim decision.

67.5 If the Contractor is dissatisfied with any decision under paragraph 67.1 he shall, not later than 7 Days from receipt of the decision, submit a case to the WCO specifying the grounds which in his view entitles him to an extension or further extension of time. The WCO shall notify the Contractor of his decision within 7 Days of the receipt of the case.

67.6 The Contractor must endeavour to prevent delays and to minimise unavoidable delays, and to do all that may be required to proceed with the Works in accordance with the agreed programme. The Contractor shall not be entitled to an extension of time where any delay, or likely delay, is, or would be, attributable to the Contractor.

**68. Prolongation and Disruption**

68.1 If the Contractor properly and directly incurs any expense which he would not otherwise have incurred by reason of;

68.1.1 The execution of Works pursuant to Condition 12 (Other Works); or

68.1.2 Any delay in being given possession of the Site or part of it or in respect of the matters specified in Condition 68.2;

68.1.3 Delay in being given notification as to whether or not a Design Document is satisfactory as a Construction Document under Condition 46 (Design).

which unavoidably results in the regular progress of the Works or of any part of them being materially disrupted or prolonged and which is beyond that provided for or reasonably contemplated by the Contract he should action in accordance with Condition 61 (Change Control Procedures). Except that full details may be submitted after the event but within 14 days of the end of “Other Works“– Condition 12 or the end of any delay under Conditions 68.1.2 and 68.1.3.

68.2 The matters referred to in Condition 68.1.2 are;

68.2.1 The issue of any schedules or other information to be provided by the PM;

68.2.2 The execution of any work or the supply of any Thing by the Authority or ordered from somebody other than the Contractor and which is not undertaken or ordered in consequence of any default on the part of the Contractor;

68.2.3 The issue of any pass to any person’s i.e. beyond the normal period for approval as notified by the PM.

68.3 The Contract Sum shall not be increased under paragraph 68.1 unless;

68.3.1 The Contractor, immediately upon becoming aware that Design work, or the regular progress of the Works or any part of them, has been or is likely to be disrupted or prolonged has given notice to the PM specifying the circumstances causing, or expected to cause, that disruption or prolongation and stating that he is, or expects to be, entitled to an increase in the Contract Sum under that paragraph;

68.3.2 The Contractor, as soon as reasonably practicable, and in any case within 14 Days of the end of any delay, provides full details of all expenses incurred and evidence of the expenses directly resulting from the occurrence of any of the events as appropriate described in Condition 68.1.

68.4 Subject to paragraph 68.3, the Contract Price may be increased in accordance with Condition 68.1.2 only where the Contractor has necessarily incurred additional costs through no fault of his own and the Authority has failed to supply an item or act;

68.4.1 By a date agreed beforehand with the Contractor; or

68.4.2 Within any reasonable period specified in a notice given by the Contractor to the Authority or the PM for the supply of the item or taking the action.

68.5 The Authority shall, not later than 14 Days from receipt of the information referred to in Condition 68.3.2 above, notify the Contractor of his decision under this Condition.

68.6 In this Condition “expense” shall mean money expended by the Contractor but shall not include any sum expended, or loss incurred, by him by way of interest or finance charges however described.

**69. Certifying Completion**

69.1 The PM shall certify the date when the Works, or any Section, or any completed part within the meaning of Condition 65 (Early Possession), are completed in accordance with the Contract. Such completion shall include full compliance by the Contractor with Condition 25 (Statutory Notices and CDM Regulations). After the end of the last Maintenance Period to expire, the PM shall issue a certificate when the Contractor has complied with Condition 87 (Defects in Maintenance Periods).

**70. Quality**

70.1 The Contractor shall execute the Works with in accordance with the Contract and;

70.1.1 With diligence;

70.1.2 In accordance with the programme;

70.1.3 With all reasonable skill and care;

70.1.4 In a workmanlike manner.

70.2 The Contractor shall ensure that any Things for incorporation are of appropriate quality for their intended purpose, and conform to the Specification and the Design and / or agreed by the PM.

70.3 The Contractor shall when requested by the PM demonstrate to the PM’s satisfaction that he is performing his duties under paragraphs 70.1 and 70.2 above. The PM shall have power at any time to inspect and examine any parts of the Works or inspect, examine and test any Thing for incorporation either on the Site or at any factory or workshop or other such place where any such Thing is being constructed or manufactured or at any place where it is lying or from which it is being obtained. The Contractor shall give the Authority the assistance and facilities he may reasonably require for any inspection and examination. The Authority may reject any Thing for incorporation, which he is satisfied, does not conform to the Specification or Design.

70.4 The PM may arrange for an independent expert to test whether any Thing for incorporation is fit for use in the Works and / or conforms to the Contract requirements. All costs incurred by the Authority in arranging for an expert to carry out any test shall be borne by the Contractor if the test results disclose that the Thing tested does not conform to the provisions of the Contract. The Contractor shall also bear the cost of any further tests reasonably required to monitor quality following negative test results.

70.5 The report of the independent expert and to the fitness or suitability of any Thing required to be provided under the Contract shall be final and conclusive.

70.6 The Contractor shall, at his own cost, replace, rectify or reconstruct;

70.6.1 The Works, or any part of them, which do not conform with the Contract or are not to the satisfaction of the PM; and

70.6.2 Any Things for incorporation which do not conform to the Contract or which have been rejected by the PM.

**71. Emergency Work**

71.1 If the Contractor is unable or unwilling to carry out promptly any emergency work required by the PM, the Authority may make arrangements for that work to be carried out. If the work carried out by the Authority shall be such as the Contractor is liable under the Contract to carry out or execute at his own expense, then the Contractor shall reimburse;

71.1.1 any costs reasonably incurred by the Authority under this paragraph; and

71.1.2 any loss suffered by the Authority because the Contractor has not carried out the work.

71.2 In this Condition ‘emergency work’ means any work which becomes necessary during the execution of the Works or during any Maintenance Period;

71.2.1 to prevent, or alleviate the effects of, any accident, failure or other event in connection with the performance of the Works;

71.2.2 to secure the Works, the Site or any adjoining property from damage; or

71.2.3 without prejudice to Condition 13 (Loss or Damage), to repair any damaged or dangerous part of the Works.

**72. Vehicles, Plant, Tools, and Equipment**

72.1 The Contractor shall;

72.1.1 Provide any Vehicles, Plant, MHE, Tools (including Special Tooling) and Equipment required to undertake the requirements of the Contract.

72.1.2 Be responsible for providing necessary insurance for all personnel required to use Vehicles, Construction Plant, and MHE.

72.1.3 Provide all fuel for use under the Contract.

**73. Authority Supplied Materials**

73.1 Where applicable, material will be handed over to the Contractor on site and will thereafter become his responsibility in accordance with Condition 9 (Vesting).

**74. Fraud Prevention**

74.1 The Contractor shall comply, and shall ensure that all members of his Supply Chain comply, with:

74.1.1 The Contractor’s policy for the prevention and detection of fraud as submitted in accordance with his tender for the Contract;

74.1.2 MOD Policy Statement on Fraud & Theft for Construction Industry Suppliers attached to these Conditions of Contract at Annex C.

74.2 Upon the request of the Authority, the Contractor shall carry out an internal audit and an audit of the members of his Supply Chain in relation to their respective compliance with condition 74.1 above and shall report to the Authority on the result of such audit.

**75. Spare**

**FINANCE**

**76. Price**

76.1 All Prices are FIRM i.e. not subject to variation and will be paid in **Kenyan Shillings (KHS)** as identified in the Milestone Payment Schedule.

**77. Payment**

77.1 “As Built” drawings, documents and all related information referred to in Conditions 46 (Design) shall be supplied in 3 hard copies plus 2 electronic copy (Drawings to be in a format compatible with AutoCAD 2015 format and a PDF) prior to submitting / approval of the final claim for payment.

77.2 The Contractor shall be entitled to apply for and be paid advances against the agreed FIRM Contract Price during the period of the Contract for each Milestone certified as being completed to the satisfaction of the PM provided that all preceding Milestones on the agreed extant Payment Schedule have been satisfactorily completed.

77.3 The amount of each advance payable shall be the relevant milestone value detailed in the agreed extant Milestone Payment Schedule less 5%, which the Authority shall withhold as retention from each Milestone Payment. If the final milestone completion date is achieved then the Authority will pay 2.5% of the value of the milestone, with the remaining 2.5% being paid on successful completion of any defects at the end of the 12 months defects liability period (DLP) (or such lesser period decided by the WCO) and on satisfaction by the Authority that all Contractual obligations have been fulfilled subject to Conditions 82 (Recovery of Sums from the Contractor). Failure to meet the final milestone completion date will result in the full 5% being retained until successful completion of the defects in the DLP.

77.4 The Contractor shall submit valid claims for payment of bills following satisfactory completion of the agreed milestones, and which are properly payable under terms and conditions of the Contract, to the PM for certification for payment. The Contractor having received appropriate certification should forward his application for payment on company headed notepaper to the WCO.

**78. Certifying Payments**

78.1 The PM shall certify the sums to which the Contractor is entitled under Condition 79 (Final Account).

78.2 The Authority shall give the Contractor notice not later than 14 Days after receipt of a claim due under the Contract specifying any amount to be withheld, the grounds for withholding payment and the basis on which that amount was calculated.

78.3 Any certificate may be modified or corrected by any subsequent certificate or by the final certificate for payment. No certificate of the PM shall of itself be conclusive evidence that any Works or Things to which it relates are in accordance with the Contract.

78.4 Any dispute about the Contractor’s right to a certificate shall be referred at the request of the Contractor to the WCO named in the Contract whose decision shall be final and conclusive – provided that this paragraph shall not apply to a dispute as to the amount of the balance of the Final Sum due to the Contractor.

**79. Final Account**

79.1 Upon completion of the Works to the satisfaction of the Authority the Contractor may claim the balance of the Contract Price outstanding subject to any previous instruction and / or agreement with the Authority or any action under any other Condition of Contract. The Project Manager’s decision in this matter will be final and conclusive.

79.2 Within 2 months of the certified completion of the Works to the satisfaction of the Authority the Contractor shall forward one copy of the final account to the PM. The PM shall within 10 Days of receipt of the final account notify any disagreement to the Contractor along with full details for his disagreement.

79.3 If before the end of the Maintenance Period, or where there is more than one the end of the last Maintenance Period, the Final Price has been calculated and agreed, or in default of agreement has been determined by an Arbitrator appointed under Condition 94 (Arbitration), then:

79.3.1 If the Final agreed Price exceeds the sum of any amount already paid plus any amount withheld by the Authority, then the Authority shall pay the difference to the Contractor, and

79.3.2 If the total amount already paid to the Contractor exceeds the Final agreed Price then the Contractor shall pay the excess to the Authority immediately on request.

**80. Cost Savings**

80.1 The Contractor may at any time during the Contract submit to the PM a written proposal which in the Contractor’s opinion will reduce the cost of the Works or the cost of maintenance or increase the efficiency of the completed Works. Any proposal shall clearly state that it is submitted for consideration under this Condition and shall include an estimate, for consideration by the Authority, of the amount to which the Contractor may be entitled on the basis that he and the Authority shall share equally the savings in the cost of carrying out the Works as determined in accordance with Condition 63 (Valuation of PM’s Instructions-Principles).

80.2 The Contractor shall provide any further information relating to his proposal which the Authority may require.

80.3 The Contractor, having submitted any proposal under Condition 80.1, shall continue with the expeditious completion of the Works as previously agreed by the Authority. If appropriate the WCO will formally advise any changes to the Contract.

**81. Payment of Sub-contractors**

81.1 Where the Contractor enters into a sub-contract with a supplier or Sub-contractor for the purpose of performing the Contract, he shall cause a term to be included in such sub-contract which requires payment to be made to the supplier or Sub-contractor within a specified period not exceeding 30 days from receipt of a valid invoice as defined by the sub-contract requirements.

**82. Recovery of Sums from the Contractor**

82.1 Any sum that is recoverable from or payable by the Contractor under the Contract may be deducted from or reduced by any sum(s) then due, or which may thereafter become due to the Contractor under or in respect of the Contract or any other Contract with the Authority

**83. Suspension for Non-payment**

83.1 Where a sum due under the Contract (as determined by agreement between the parties, certification and invoicing, adjudication, arbitration or litigation) is not paid in full by the final date for payment and no effective notice to withhold payment has been given under Condition 78 (Certifying Payments), the person to whom the sum is due has the right (without prejudice to any other right or remedy) to suspend performance of his obligations under the Contract to the party by whom payment ought to have been made (‘the party in default’).

83.2 The right may not be exercised without first giving to the party in default at least 7 days’ notice of intention to suspend performance, stating the ground or grounds on which it is intended to suspend performance.

83.3 The right to suspend performance ceases when the party in default makes payment in full of the amount due or alternatively gives effective notice to withhold payment under Condition 82 (Recovery of Sums from the Contractor).

83.4 Any period during which performance is suspended in pursuance of the right conferred by this Condition shall be disregarded in computing, for the purposes of any Contractual time limit, the time taken, by the party exercising the right or by a third party, to complete any work directly or indirectly affected by the exercise of the right. Where the Contractual time limit is set by reference to a date rather than a period, the date shall be adjusted accordingly.

**84. Bankruptcy**

84.1 Should the Contractor be adjudged bankrupt, or should the Contractor make a general assignment for the benefit of his creditors, or should a Receiver be appointed on account of the Contractor’s insolvency, the Authority may, without prejudice to any other right or remedy he may have under the terms and conditions of the Contract, terminate forthwith the Contract. Such termination shall be without liability, arising howsoever, to the Authority.

**85. Spare**

**86. Spare**

**POST COMPLETION**

**87. Defects in the Maintenance Period**

87.1 The Contractor shall without delay make good at his own cost to the satisfaction of the Authority any defects in the Works resulting from what the Authority considers to be default by the Contractor or his agent or Sub-contractor which appear during the Defects Liability Period.

87.2 After completion of the remedial Works by the Contractor the Authority shall reimburse the Contractor for any reasonable costs the Contractor has incurred to the extent that the Authority is satisfied that any defects were not caused by: -

87.2.1 A fault in the Design;

87.2.2 The Contractor’s neglect or default, or the neglect or default of any agent or Sub-contractor of his; or

87.2.3 By any circumstances within his or their control.

87.3 If the Contractor fails to comply with this Condition the Authority may do anything necessary to make good any defects notified to the Contractor. All the costs and expenses incurred by the Authority in doing so shall be recoverable from the Contractor.

87.4 When the cost of making good defects under this Condition are not reimbursed by the Authority under paragraph 87.2 then the relevant defects shall apply to the remedial Works in full from the date of making good.

87.5 The Defects Liability Period for the Works shall be 12 months, or such lesser period as decided by the WCO, and shall apply from the day after that on which the Works are certified as complete by, and to the, satisfaction of, the PM.

**88. Spare**

**89. Spare**

**DETERMINATION AND ARBITRATION**

**90. Determination**

90.1 Without prejudice to any other power of determination, the Authority may at any time determine the Contract by notice to the Contractor. Upon receipt of the notice the Contract shall be determined.

90.2 The Authority shall specify in a notice of determination, which, if any, of the grounds mentioned in paragraph 90.7 apply.

90.3 The Authority may give directions in relation to the performance or completion of any work and any other matters connected with the Works, the Site and any other Contract or sub-contract.

90.4 Any direction under paragraph 90.3 shall be given not later than 7 Days from the date of notice of determination or the Date or Dates for Completion whichever is the sooner.

90.5 The Contractor shall comply promptly with any directions given by the Authority under paragraph 90.3. The Contractor shall be paid for any work so performed as if the directions were PM Instructions.

90.6 When requested by the Authority the Contractor shall promptly pass to the Authority all drawings, plans and other design information that have been prepared or are in the process of being prepared.

90.7 Condition 91 (Consequences of Determination for Default) shall have the effect where notice of Determination is given for any of the following reasons, namely;

90.7.1 The failure of the Contractor to comply with the content of a PM Instruction within a reasonable period of its issue;

90.7.2 The failure of the Contractor to proceed with the Design or to execute work in an efficient, workmanlike or proper manner, or to proceed regularly and diligently with the Works, or the suspension by the Contractor of the Design or the Works, so that in the opinion of the Authority the Contractor has not completed or will be unable to secure the completion of the Works or any relevant Section by the agreed Date or Dates for completion;

90.7.3 Where the Contractor is an individual, the insolvency of that individual, or, where the Contractor is a partnership, the insolvency of any partner. In this sub-paragraph insolvency shall include the making of any voluntary arrangement under Part VIII, and the presentation of any bankruptcy petition under Part IX, of the Insolvency Act 1986, or the making of any conveyance or assignment of the benefit of creditors;

90.7.4 Where the Contractor is a registered company, the passing of any resolution or the making of any application to the Court for the winding up of the company, the making of any arrangement with creditors, the appointment of a receiver or manager on behalf of a creditor, or in the occurrence of any circumstances which will entitle any creditor to appoint a receiver or manager or the Court to make a winding up order;

90.7.5 Failure by the Contractor to comply with Condition 29 (Site Admittance) where the Authority determines that such failure is prejudicial to its interests;

90.7.6 Any breach by the Contractor of Condition 8 (Corruption); or

90.7.7 Any breach of the conditions mentioned in the Invitation to Tender relating to the Contract.

90.8 Condition 92 (Consequences of Other Determination) shall have the effect where notice of determination is given for any reason not mentioned in Condition 90.7.

90.9 All Things not for incorporation which are brought onto the Site at the Contractor’s expense shall (whether damaged or not) be removed by him as and when they cease to be required in connection with any directions given by the Authority under Paragraph 90.3. From the date of determination, the Authority shall be under no liability to the Contractor in respect of any loss or damage to any such Things howsoever caused including by any of the Accepted Risks.

90.10 Under this Condition the decisions of the Authority shall be final and conclusive.

**91. Consequences of Determination for Default**

91.1 If the Authority shall determine the Contract for any reason mentioned in Condition 90.7 (Determination) the following provisions shall apply;

91.1.1 All sums of money that may then be due or accruing due from the Authority to the Contractor shall cease to be due or accrue due;

91.1.2 The Authority shall hire any person, employ other Contractors, use any Things on the Site, and may purchase or do anything necessary for the completion of the Design and of the Works. The Contractor shall have no claim whatsoever in respect of any such action by the Authority.

91.1.3 The Contractor shall when requested, except where determination occurs by reason of any of the circumstances described in Condition 90.7.3 and 90.7.4, assign to the Authority without further payment, when requested, the benefit of any sub-contract or Contract for the supply of any Thing for incorporation which he may have made in connection with the Contract.

91.1.4 The Authority shall ascertain and certify the cost of completing of the Works.

91.2 If the total of the following sums, i.e. sub-paragraphs 91.2.1, 91.2.2 and 91.2.3 - (hereafter called ‘the first amount’) - exceeds the total of all payments paid to the Contractor (or to which he is entitled) to the date of determination (hereafter called the ‘second amount’), the Authority shall, subject to Condition 91.3, hold the amount of the excess. If the second amount exceeds the first amount the Contractor shall, be liable to pay the Authority the amount of the excess.

The individual sums making up the ‘first amount’ are;

91.2.1 The value of all the work carried out to the satisfaction of the PM up to the date of determination;

91.2.2 The value of any work carried out or other actions carried out in accordance with any direction given under Condition 90.3 (Determination);

91.2.3 The value (ascertained on the basis of fair and reasonable prices) of all Things for incorporation brought onto Site or in the course of preparation or manufacture off the Site which the Authority elects to keep.

91.3 If the total cost of completing the Works as certified under Condition 91.1.4 and the first amount determined in accordance with Condition 91.2 exceeds the sum that would have been payable to the Contractor for due completion then the Contractor shall pay the Authority the amount of the excess.

**92. Consequences of Other Determination**

92.1 If the Authority shall determine the Contract for any reason not mentioned in Condition 90.7 (Determination) the following provisions shall apply.

92.2 If the total of the following sums (hereafter called the ‘third amount’) exceeds the second amount i.e. the total of all payments paid to the Contractor (or to which he is entitled) to the date of Determination (see Condition 91.2 (Consequences of Determination for Default)), the Authority shall be liable to pay the Contractor the amount of the excess. If the second amount exceeds the third amount the Contractor shall be liable to pay the Authority the amount of the excess immediately on request. The individual sums are;

92.2.1 The value of all the design and construction work carried out to the satisfaction of the PM to the date of determination;

92.2.2 The value of any work carried out or other things done in accordance with any direction given under Condition 90.3 (Determination);

92.2.3 The value (ascertained on the basis of fair and reasonable prices) of any Things for incorporation brought onto the Site or in the course of preparation or manufacture off the Site which the Authority elects to keep;

92.2.4 Any sum necessarily and reasonably expended by the Contractor because of the determination of the Contract in respect of;

92.2.4.1 The uncompleted part of any sub-contract and other Contracts (including those for the hire of plant, services and insurance), and

92.2.4.2 Any unavoidable Contract of employment, entered into in connection with the Contract.

92.3 If, in the period from the date of determination to the date on which any directions under Conditions 90.3 (Determination) are to have been complied with, the Works or any part of them, or any Things for incorporation which the Authority elects to keep, are lost or damaged by reason of any of the Accepted Risks, and the loss or damage was not occasioned by any failure on the part of the Contractor to perform his obligations under Condition 52 (Protection of Works), the amount payable to the Contractor under this Condition shall be ascertained as if no loss or damage occurred.

92.4 If the Contractor is of the opinion that any unavoidable loss or expense directly due to determination has not been fully reimbursed by sums paid or agreed then he shall refer the circumstances to the WCO, for referral to Commercial Branch who shall make such allowance, if any, as is considered reasonable.

**93. Determination Following Suspension of Works**

93.1 Without prejudice to any other power of determination, either the Authority or the Contractor may determine the Contract by notice to the other of them in the event of the suspension of the execution of the whole or substantially the whole of the Works, other than the making good of defects in the Works under Condition 87 (Defects in the Maintenance Period), for a continuous period of 30 Days, provided that such suspension for the relevant period was not due to any act, neglect or default of the party giving notice of such determination.

93.2 The party giving notice of determination under paragraph 92.1 shall specify in the notice the grounds for such determination.

**94. Arbitration**

94.1 The Authority and the Contractor will comply with the following procedures to resolve any dispute or disagreement arising in the performance of the Contract. Any dispute or disagreement arising should be resolved by discussion and agreement between the Contractor’s nominated site representative and the PM. Either party may give a written notice of a dispute or disagreement to the other. If the issue cannot be resolved satisfactorily within 48 hours of receipt of written notification, then it should be referred to the WCO for further action.

94.2 The PM and the Contractor’s nominated site representative shall each prepare a submission on no more than 1 x A4 page outlining their case and submit this to the WCO for consideration. The WCO will consult further as he considers appropriate and will give a written decision to each party within 7 calendar days.

94.3 If either party to the dispute refuses to accept the WCO’s decision then the WCO will forward a copy of all correspondence relating to the dispute or disagreement to Assistant Director Commercial 1 / DIO Operations International and the Contractor’s Managing Director for consideration and discussion. They will aim to agree a resolution within 14 calendar days of receipt. Failure to reach a decision will result in the formal Arbitration Procedures detailed in paragraph 94.4 being followed.

94.4 Any dispute, difference or questions between the Authority and the Contractor arising out of or relating to this Contract, other than a matter as to which a decision is expressed to be final and conclusive, and having followed the initial process described in paragraphs 94.1 to 94.3 shall, after notice by either party to the other, be referred to arbitration by a single arbitrator mutually agreed for that purpose or, in default of agreement on a single arbitrator within a reasonable period, appointed at the request of the Authority by the Chairman or any other of the Vice Presidents of the Chartered Institute of Arbitrators.

94.5 Unless the parties otherwise agree;

94.5.1 No reference shall be made under paragraph 94.4 until after the completion, alleged completion or abandonment of the Works or the determination of the Contract;

94.5.2 The arbitrator will hold a meeting with the parties forthwith on his acceptance of office and will fix a timetable for the delivery of points of claim and defence or counter claim, for the discovery and inspection of documents, for the inspection of the Works (if necessary) and for the hearing of any oral evidence, if necessary, which timetable shall not exceed a period of six months from the date of that preliminary meeting without the consent of both parties;

94.5.3 The parties shall ensure that any evidence whether oral or written and any document or argument required to be submitted to the arbitrator is submitted to him in accordance with the agreed timetable;

94.5.4 The arbitrator shall give his award not later than three months from the end of the period mentioned in sub-paragraph 94.5.2.

94.5.5 All reasonable costs and expenses incurred by each party in pursuing the Arbitration process shall fall to be the responsibility of the parties to the extent decided by the Arbitrator or, in the absence of such decision; the unsuccessful party shall be responsible for all costs incurred by both parties or to the extent agreed between the parties.

94.6 A reference to arbitration in accordance with this Condition shall be a reference to which the Arbitration Act 1996 applies, and this Act shall have effect subject to the provisions of this Condition.

**95. AUTHORISATION BY THE CROWN FOR USE OF THIRD-PARTY INTELLECTUAL PROPERTY RIGHTS**

95.1 Notwithstanding any other provisions of the Contract and for the avoidance of doubt, award of the Contract by the Authority and placement of any contract task under it does not constitute an authorisation by the Crown under Sections 55 and 56 of the Patents Act 1977 or Section 12 of the Registered Designs Act 1949. The Contractor acknowledges that any such authorisation by the Authority under its statutory powers must be expressly provided in writing, with reference to the acts authorised and the specific intellectual property involved.”

**96. Spare.**

APPENDIX TO CONTRACT

|  |  |
| --- | --- |
| 1. **Works Contract Officer:**

 **WO2 Gurung RE** Works Contract Officer DIO REGIONAL DELIVERY BATUK Nyati Bks, Nanyuki BFPO 680 | 1. **The Authority Project Manager shall be:**

 **Capt Browne RE** GE Department DIO REGIONAL DELIVERY BATUK Nyati Bks, Nanyuki BFPO 680 |
| **3. The Certifying Officer for the purposes of this Contract shall be:** The Project Manager (See Box 2 above) |
| **4. Claims for Payment:**All claims for payment shall be submitted to the Works Contract Officer (See Box 1 above) for certification.  |
| **5. For the purposes of this Contract, the Quality Assurance Authority (QAA) shall be:** DIO REGIONAL DELIVERY |
| **6. Project Manager’s Site Representative(s) / Supervising Officer(s) shall be:**Mr Patrick Munene – Clerk of Works (Electrical & Mechanical)Mr Mbilo Mutinda – Clerk of Works (Civil)Mr Emmanuel Kanda – Clerk of Works (Electrical & Mechanical) |
| **7. For official use:** |  |

 Annex A to

 Booklet 2

 Dated 8 Mar 24

**CHANGE PROPOSAL**

**Contract Number: KEN/GE/2303**

**Project Title:** **GE DEPARTMENT BUILDING EXTENSION IN NYATI BARRACKS.**

To the Works Contract Officer / Works Contractor1:

Works Contract Officer’s / Works Contractor’s1

address:

**PROPOSED CHANGE**

 I / we1 propose the following alteration of, addition to, or omission from, the Works Contractor’s Specification and / or the following change in the design, quality or quantity of the Works:

 The reason for this Change is:

 as supported by the documentation attached to this Proposal (where appropriate).

**CHANGE QUOTATION2**

**Option 1:** I attach my Change Quotation in respect of the above Change.

**Option 2:** Please forward a Change Quotation for the above Change as soon as possible and, in any event, within the next 14 days.

Works Contract Officer / Works Contractor’s1

Signature:

Name (in capitals):

Name of company / firm:

Date:

*1Delete as appropriate 2Delete the option that does not apply*

Distribution: Works Contract Officer, Works Contractor, GE Project Manager, and GE Task Officer

PROJECT TITLE: **GE DEPARTMENT BUILDING EXTENSION IN NYATI BARRACKS.**

To the Works Contract Officer: **WO2 Gurung RE**

Works Contract Officer’s address: **Defence Infrastructure Organisation**

 **Regional Delivery (Kenya)**

 **British Army Training Support Unit Kenya**

 **Nyati Barracks, Nanyuki**

 **British Forces Post Office 680**

**DETAILS OF CHANGE**

Change Proposal / Notification1 dated and numbered

Action required / no longer required1 as a result of the above Change:

Further information is provided in the documentation attached to this Quotation.

**FINANCIAL IMPLICATIONS OF CHANGE**

The direct price of / direct saving from1 the Change is: KSH (excluding VAT)

The price (if any) of any disruption to, or prolongation of, the

Works / the saving directly consequential upon the Change1 is: KSH (excluding VAT)

The credit (if any) for any amount(s) previously paid in respect

of any disruption to, or prolongation of, the Works resulting from

any extension of time previously granted in respect of the whole

or part of the period covered by a proposed acceleration: KSH (excluding VAT)

The total lump sum price / saving is1: KSH (excluding VAT)

A breakdown of the above lump sum price / saving1 is attached to this Quotation.

Works Contractor’s signature:

Name (in capitals):

Name of company/firm:

Date:

*1Delete the option that does not apply*

Distribution: Works Contract Officer, Works Contractor, GE Project Manager, and GE Task Officer

 Annex B to

 Booklet 2

 Dated 8 Mar 24

**MINISTRY OF DEFENCE**

**TENDER FOR LUMP SUM FIRM PRICE CONTRACT FOR**

**KEN/GE/2303**

**GE DEPARTMENT BUILDING EXTENSION IN NYATI BARRACKS.**

**CFCs**

Production of controlled CFCs has stopped.

CFC-11 (trichlorofluoromethane) CFC-211

CFC-12 (dichlorodifluoromethane) CFC-212

CFC-13 CFC-213

CFC-111 CFC-214

CFC-112 CFC-215

CFC-113 (trichlorotrifluorethane) CFC-216

CFC-114 (dichlorotetrafluoroethane) CFC-217

CFC-115 (chloropentafluoroethane)

The above substances are also used in blends. For example: CFC-500 (CFC-12/HFC152a) and CFC-502 (CFC-115/HCFC-22)

**Halons**

Production of controlled Halons has stopped.

Halon-1211 (bromochlorodifluoromethane - BCF)

Halon-1301 (bromotrifluoromethane - BTM)

Halon-2402

**HBFCs**

No production after 31 December 1995

CHFBr2 C2H2F2Br2 C2HF4Br5 C3H3F2Br3 CHF2BrC2H2F3Br

C3HF5Br2 C3H3F3Br2 CH2FBr C2H3FBr2 C3HF6BrC3H3F4Br

C2H3F3Br C3H2FBr5 C3H4FBr3 C2HFBr4 C2H4FBrC3H2F2Br4

C3H4F2Br2 C2HF2Br3 C3H2F3Br3 C2H2F2Br2 C2HF3Br2 C3HFBr6

C3H4F4Br2 C3H5FBr2 C2HF4BrC3HF2Br5 C3H2F5BrC3H5F2Br

C2H2FBr5 C3HF3Br4 C3H3FBr4 C3H6FBr

**HCFCs**

The use of the following HCFC refrigerants is no longer acceptable (See Note 1). Please therefore complete and sign below, in doing so you are confirming that none of the refrigerants listed are being proposed within your Tender.

HCFC-21 HCFC-141 HCFC-225ca HCFC-243

HCFC-22\* HCFC-141b HCFC-225cb HCFC-244

HCFC-31 HCFC-142 HCFC-226 HCFC-251

HCFC-121 HCFC-142b HCFC-231 HCFC-252

HCFC-122 HCFC-151 HCFC-232 HCFC-253

HCFC-123 HCFC-221 HCFC-233 HCFC-261

HCFC-124 HCFC-222 HCFC-234 HCFC-262

HCFC-131 HCFC-223 HCFC-235 HCFC-271

HCFC-132 HCFC-224 HCFC-241

HCFC-133 HCFC-225 HCFC-242

**CARBON TETRACHLORIDE (CCI4)** Production has stopped

**1,1,1 – TRICHLOROETHANE (C2H3Cl3)** – No production after 1st December 1995.

**METHYL BROMIDE (CH3Br)** – Production limits apply.

**SIGNED**: …………………………………………………

Name (in CAPITALS).……………………………………

in the capacity of.…………………………………………

duly authorised to sign Tenders for and on behalf of (in CAPITALS):

…………………………………………………………………………

Address (including postcode):

…………………………………………………………………………

…………………………………………………………………………

…………………………………………………………………………

…………………………………………………………………………

Date: ………………………………………

Note:

1. The total ban applies to new equipment (MoD Policy requires that new designs of equipment and installations are not to use or incorporate HCFCs). For new installations, seek guidance from Defence Works Functional Standards - "Design and Maintenance Guide 07", which may be purchased from The Stationery Office Bookshop.

2. It is accepted that during the course of this Contract that HCFC-22 (R-22) will continue to be in common use in Oman, and that the existing installations on this site contain HCFC-22. The Contractor may replace this Refrigerant only like for like until such time as such action shall be banned under the terms of the Montreal Protocol or shall be deemed unlawful under Omani law. Following either event HCFC-22 shall be banned on this site.

3. Should a unit containing HCFC-22 come to the end of its economic life it is to be replaced with a unit compliant with the Montreal Protocol.

 Annex C to

 Booklet 2

 Dated 8 Mar 24

**MOD POLICY STATEMENT ON FRAUD & THEFT FOR CONSTRUCTION INDUSTRY SUPPLIERS**

**Introduction**

This document sets out the MOD Construction Industry policy in relation to Fraud and Theft. It is intended to ensure that all Construction Industry Suppliers employed on the MOD Estate understand the MOD's policy on the detection and deterrence of fraud and what is expected of them.

Fraud includes dishonest acts committed by the employees of the Department, by external individuals or groups, or by employees and external parties working together, to gain a financial advantage from the Department. Corruption involves external parties or anyone else making payments to, or bestowing benefits on, an employee with the intention of influencing them to act in a way that is against the interests of the Department. Where corruption is involved there may not be any immediate loss to the Department, but positions of trust may have been abused. For the purposes of this paper, fraud and corruption are considered together.

|  |
| --- |
| ***The Ministry of Defence's policy on fraud******The Ministry of Defence has stated that dishonest and illegal activity will not be tolerated under any circumstances, irrespective of any loss or gain to the Department or others. Furthermore, the Department undertakes to investigate all cases of suspected fraud, theft and irregularity and, where appropriate, to prosecute cases or take disciplinary action.*** |

**What are fraud and corruption?**

**Fraud** has no precise legal definition. The Theft Acts of 1968 and 1978 cover the offences generally referred to as fraud and it is for the court to determine in a particular instance whether fraud has occurred. The Government Internal Audit Manual defines fraud as the use of deception with the intention of obtaining an advantage, avoiding an obligation or causing loss to another party.

**Corruption** Is defined in the Prevention of Corruption Act, 1906, S.1 (1) and is the offering, giving, soliciting or acceptance of an inducement or reward which may influence a person to act against the interests of the organisation. The Act of 1906 applies to Crown Servants and employees of local authorities. The Prevention of Corruption Act, 1916 and the Criminal Justice Act, 1967 increased the penalties for corruption.

Principal differences between civil and criminal fraud cases relate to the burden of proof and the sanctions available. Generally, the burden of proof required in a civil case is lower than that required in a criminal case.

**Procurement Fraud**

**Procurement Fraud** is the term used by the Department to cover cases of fraud and corruption which involve a contractor or supplier (or potential contractor or supplier); this definition is deemed to include any companies or organisations that are, or are potentially, Supply Chain members of such contractors or suppliers. Some examples of procurement fraud are:

* Submission of false or duplicate invoices
* Submission of claims for interim payment before entitlement
* Supply of sub-standard items, sometimes in forged maker's packs
* False certification of quality or quantity of goods
* False statements at price meetings or on quotation
* Submission of rigged bids in competition (secret cartels)
* Obtaining inside information on rival bids or MOD procurement plans
* False accounting or cross-contract cost transfers
* False claims for Supply Chain members’ or suppliers' costs
* Unauthorised use of government furnished stores or equipment
* Rigging of specifications in favour of one contractor
* Underbidding with a view to recouping costs unfairly later
* Corruption or attempted corruption of MOD personnel

**Action required of Construction Industry Suppliers by the MOD**

The MOD expects and requires all civilian and Service Personnel, described collectively as “Crown Servants”, to observe high standards of personal honesty and integrity and to ensure all Departmental business is carried out in a manner that conforms to the same high standards. In particular:

* Dishonest activity will not be tolerated.
* The Department will cause all suspected or attempted fraud to be investigated by the relevant authorities in order that prosecution or civil action can be undertaken where appropriate.
* Under the Prevention of Corruption Act 1916, any money, gift or other consideration (including hospitality) received by a Crown Servant from a person or organisation holding or seeking to obtain a government contract will be deemed by the Courts to have been received corruptly unless proved to the contrary by the defendant.

The Department must be able to demonstrate the same level of confidence in Construction Industry Suppliers that it has in its Crown Servants. It needs this because it has a responsibility for safeguarding public funds, including the prevention and detection of fraud

in all areas. That level of confidence does not presently exist.

The MOD spends substantially in excess of £1Bn each year on its estate. It believes that a significant element of this expenditure is at risk of fraud (that is, spent in ways that are inadequately controlled, audited and monitored).

It will take a period of time to establish the level of confidence required in suppliers' procedures, and it will only come about by the efforts of suppliers themselves. These efforts are not viewed by the MOD as new or onerous; indeed, in seeking the following information, the MOD is merely asking to see what it is entitled to assume already exists, as a matter of good business practice.

|  |
| --- |
| **The contractor's anti-fraud measures*****As a minimum, these should include:**** ***A statement of commitment to ethical business behaviour***
* ***A fraud policy statement***
* ***A fraud response plan***
 |

In future each supplier will be required to provide detailed information covering the totality of its anti-fraud measures. As a minimum, these measures are expected to include:

* **A statement of commitment to ethical business behaviour** (laying down parameters of what is, and is not, considered acceptable behaviour on the part of staff)
* **A fraud policy statement**, which should address, inter alia:
* Allocation of responsibilities for the overall management of fraud,
* The procedures which all staff, Supply Chain members and suppliers should follow if a fraud or suspected fraud is
* Guidance on training for the protection and prevention of fraud
* Reference to the response plans that have been devised to deal with and minimise the damage caused by any fraud or attempted fraud
* **A fraud response plan**, whose objective is to ensure that timely and effective action can be taken to:
* Prevent losses of funds or other assets where fraud has occurred and to maximise recovery of losses
* Minimise the occurrence of fraud by taking rapid, appropriate and effective action at the first sign of fraud or possible fraud
* Identify the fraudsters and maximise the success of any disciplinary/legal action taken
* Identify any lessons which can be acted upon in managing fraud in the future
* Reduce any adverse impacts on the contractor and the MOD

The **fraud response plan** should address the following areas:

* The Director to whom the fraud or suspicion of fraud and cases of sharp practice and poor performance should be reported in the first instance
* The contact point in the MOD to whom the fraud or suspicion of fraud should be reported by that Director; all fraud, suspected fraud and cases of sharp practice and poor performance must be reported to the contact point: -

Fraud Prevention Unit,

DE Fraud Focal Point

Defence Estates,

St. Georges House,

Kingston Road, Sutton Coldfield, West Midlands, B75 7RL

Telephone 0121 3113840

* How the Contractor should investigate the fraud or suspected fraud together with what steps should be taken to minimise or eliminate the potential loss from the fraud or suspected fraud
* How to ensure that any evidence is secured in a legally admissible form
* If, when and how to contact the police (which is patently easier if arrangements are already in place)
* How to initiate recovery action
* Who else needs to be contacted?
* How to disseminate lessons learned to interested parties
* How to protect informants from reprisals whilst at the same time ensuring adequate arrangements are in place to protect individuals from unfounded or malicious allegations
* How the supplier will ensure that his Supply Chain comply with all aspects of his fraud response plan

A **fraud response plan** is, by definition, a complex document, because the subject it deals with is potentially very complex, with a large number of possible variations and permutations. It should ensure that each situation is dealt with in the most appropriate fashion.

In providing copies of the above 3 documents (and any other document considered relevant), the contractor should state for each document:

* Date of issue
* Nature & extent of its dissemination
* Frequency of updates

**Conclusion**

The deterrence and detection of fraud issue of fraud involving expenditure on its estate is a very high priority for the Department. The robustness of suppliers’ anti-fraud measures will be examined increasingly thoroughly now and in the future, and the MOD will seek to protect the public purse by only doing business with suppliers who satisfy it that they take fraud as seriously as it does.

8th March 2001 approved by Fraud Prevention Steering Group (FPSG), name changed to Construction Fraud Initiative Steering Group (CFISG) on 2nd November 2001.

Annex D to

 Booklet 2

 Dated 8 Mar 24

|  |
| --- |
| **DEFCON 532A** **Edn 04/20** **Protection of Personal Data (Where Personal Data is not being processed on behalf of the Authority)**  1. In this Condition, the expressions “Controller”, “Data Subject”, “Personal Data”, Personal Data Breach and “Processor” shall have the same meanings as in Article 4 of the GDPR. 2. Data Protection Legislation means: a. the General Data Protection Regulation (Regulation (EU) 2016/679); * 1. b. the Data Protection Act 2018 to the extent that it relates to processing of Personal Data and privacy; and
	2. c. all applicable laws about the processing of personal data and privacy.

3. Both Parties acknowledge that there is no processing of Personal Data associated with or intrinsic to the performance of the Contract. The incidental exchange of Personal Data for the purpose of communication to give effect to the Contract or the business relationship is not considered to be processing of Personal Data by either Party on behalf of the other. 4. The Contractor shall notify the Authority promptly if it considers that any of the Authority’s instructions obligate the Contractor to take on the role of Processor under the Data Protection Legislation beyond that which is contemplated in clause 3. The Authority agrees that the Contractor shall not be required to provide legal advice to the Authority and that such notification (or absence of notification) by the Contractor will not be construed as legal advice or representation by the Contractor. 5. Should the Contract be amended to require the Contractor to process Personal Data as a Processor on behalf of the Authority as a result of clause 4 or otherwise the Contract will be amended to include DEFCON 532B and DEFFORM 532 in accordance with the provisions of DEFCON 503. Where the Contract is amended to include processing of Personal Data as a Joint Controller, the Parties agree that they shall amend the Contract to include appropriate contractual clauses, including but not limited to clauses dealing with notification in the event of a Personal Data Breach and requests from Data Subjects for access to their Personal Data. 6. Notwithstanding clause 3, each Party undertakes to comply with its obligations as Controller under the Data Protection Legislation. |