
	[image: image1.jpg]@ HM Revenue
& Customs





	
	

	
	
	     

	
	
	Newcastle Upon Tyne




	
	
	

	
	Ipsos MORI

London,

E1W 1YW

	

	
	
	Tel
	     

	
	
	     

	
	
	

	
	
	

	
	
	Fax
	     

	
	
	

	
	
	www.hmrc.gov.uk

	
	Date
	11 April 2017 
	

	
	Our Ref
	 
	DX: 
	     

	________
	Your Ref
	 
	
	

	
	
	Commercial - In Confidence
	


	


	[image: image2.png]Awarded for excellence






Dear 
Service Order: PTA Campaign Qualitative Research
Assignment under the Market Research Framework MR130001
I refer to the Market Research MR130001 Framework Agreement contract. This letter is to formally issue an order / award an assignment under this framework titled ‘PTA Campaign Qualitative Research’. The assignment is detailed in the following documents:

· HMRC’s specification of requirements of (6 April 2017) for this assignment.

· Your revised proposal of (13 April 2017).

· the Market Research MR130001 Framework Contract (which comprises HMRC’s specification and ITT, your final proposal, plus the terms and conditions of the contract). Unless specifically amended by the assignment specification or proposal, in all other regards the terms and conditions of the framework agreement apply. For the purpose of this assignment the ‘notice period’ shall be 2 weeks’.
The formal start date of this assignment is the date of this letter. The assignment is estimated to be completed by end of June. 

The total cost of the assignment is fixed at £32,402.50 (excluding VAT which will be charged at the appropriate rate). The invoice schedule is as follows:

	Invoice Schedule



	Approximate

Date
	% a
	Amount to be invoiced
	Milestones a 

	13/04/2017
	30%
	 £9,720.75 + VAT
	Following initiation meeting.   

	01/05/2017
	30%
	 £9,720.75 + VAT
	Commencement of fieldwork.

	19/06/2017
	40%
	 £12,961  + VAT
	On satisfactory completion of project.

	Total
	100%
	 £32,402.50 + VAT
	

	Notes

a   According to those agreed under the Framework Agreement. 



To note the final invoice is subject to the satisfactory (to the Department) completion of all aspects of the work. The Department’s nominated officer for the project is.
Could you please ensure that the following PO Number is quoted on all invoices for this project: PO Number = xxx
Could you please e-mail to confirm agreement with the terms of this assignment under the Market Research MR130001 Framework Agreement.
Yours faithfully,

NB ‘Personal’, ‘Confidential’ and ‘Commercial’ sensitive information has been redacted according to the provisions in the FOI Act (sections 40, 41 & 42).
	

	Information is available in large print, audio and Braille formats.

Type Talk service prefix number – 18001 
	
	[image: image3.png]




	
	
	[image: image3.png]


PAGE  
2

