Order Schedule 20 (Brief)

This Schedule sets out the characteristics of the Goods or Services that the Agency will be required to make available to the Client under this Order Contract

As issued at tender:

# PURPOSE

## The Cabinet Office requires a delivery partner to support the delivery of the Civil Service Awards, the government’s annual celebration event. The event is due to be held in London in December 2024 with approximately 350 guests.

## Previously, this tender has been issued to agencies in Lot 1, Events Planning, Delivery and Related Services' Framework RM1049.

## This contract is initially for a period from 01 March 2024 up to 19 April 2025 with no options to extend. This tender is subject to CCS rights of early termination under the terms and conditions of the CCS Framework Agreement.

## This will be the 19th year of Civil Service Awards; it is a high-profile staff celebration event in the Civil Service calendar. The successful agency must be able to provide a highly professional and proactive team to deliver this tender and have the flexibility to manage changing requirements with ease and professionalism.

## Event objectives

## The overarching objectives of the Civil Service Awards are to:

## celebrate success and recognise the contribution of civil servants

## promoting and enhance the reputation of the Civil Service

## Showcase best practice examples of innovation to inspire civil servants to apply these approaches to their work

## inspire civil servants to strive for continuous improvement in everything they do.

## engage civil servants by making them feel part of A Modern Civil Service

## The categories of the awards will be agreed upon the Awards Champion and Awards SRO, with approval from the Chief Operating Officer of the Civil Service. The successful delivery partner will be consulted on the categories to advise on the commercial viability of the categories.

## Event Format: Scope of the awards ceremony:

## c350 delegates

## 6pm - 9pm

## Arrival drinks and canapes, post ceremony drinks and canapes (to include management of dietary requirements); or a banquet-format ceremony

## High profile venue in central London

## One room for the ceremony and one room for arrival and post ceremony drinks, canapes and networking, or one large space that can be sectioned.

## Area for registration

## Staffing

## Cloakroom

## Toilets

## Compliant with DDA best practice

## AV (stage, laptop, AV technician x 2, screens x 2, PA system, lectern and lectern mics x 2, switcher, stage for film crew, all necessary filming equipment and videographers. Green room with additional videographer, backdrop, mics, and video equipment.)

## Lighting and decorations

## Date in early December 2024; preferably the first week.

# BACKGROUND TO THE BUYER

## The Buyer (Cabinet Office) supports the Prime Minister, and ensures the effective running of government. The Buyer is also the corporate headquarters for the government, in partnership with HM Treasury, and takes the lead in certain critical policy areas.

# BACKGROUND TO REQUIREMENT/OVERVIEW OF REQUIREMENT

## An event agency is required to deliver the following:

## Securing sponsorship to cover the event costs

## The delivery partner would be responsible for securing sponsorship to cover the event costs. It is anticipated that the successful delivery partner would need to secure over £150,000 in guaranteed sponsorship, and that this would be a capped cost for the event. Any sponsorship secured over and above the agreed guaranteed total would be split 50/50 between the delivery partner and the client. The client would maintain sign-off for all sponsorship packages and sponsors, but would expect the delivery partner to handle all communication with the sponsors, and agree sponsorship packages.

  - Any surplus sponsorship from the programme which the Authority receives will offset costs for other cross Government events, such as Civil Service Live.

## All event management activities organising catering, staffing, drinks, running orders, online registration, on the night delivery, AV, lighting, decorations, photography and filming of the ceremony, filming and interviews of award winners, certificates, trophies, security, glassware, linen-hire, music, licences, insurance, legal advice where necessary, production of a privacy policy and accessibility policy, project management, risk management, budget management, liaison with the venue, liaison with the client, attendance at client meetings (monthly for 6 months, weekly for 3 months, and ad-hoc meetings as requested) including readouts after each meeting, evaluation.

## Communications Event communications (joining instructions, invitations (both electronic and hardcopy), social media activity, thank you communication, communication with judging panels, communication with sponsors, progress updates. The client would handle promotion of the awards and would require sign-off of any and all comms the delivery partner produced.

## Management of the judging process staffing, project management, over-seeing the sifting process, editorial of shortlisted entries, developing briefing packs, overseeing the assurance of the shortlisted entries, and communications with judging panels.

## Website hosting developing, hosting, and updating a public-facing website, a web-based application form, compliance with DDA best practices, and data protection best practices. The client would require sign-off of any website content, and own the rights to the website domain and intellectual property.

## The successful agency must be able to provide a highly professional and proactive team to deliver this tender and have the flexibility to manage changing requirements with ease and professionalism. It will need to have proven experience in putting together not only large-scale events but experience in sponsorship generation to deliver events. The agency will be able to outsource aspects of delivery but will be held responsible for ensuring the quality and timing of service provision.  You will be expected to work with the venue regarding AV provision and we will be looking for innovative and creative proposals with cost-effective solutions demonstrating value for money.

## A summary of the required services follows:

## Event Project Management

## Sponsorship Generation and management

## Financial Management and Settlement

## Web design and Management

## Speaker and Sponsor Liaison and coordination

## Advance and on-site delegate & database management including registration

## Advance and on-site venue and catering management including risk assessment

## Advance and on-site technical, design and production services

## Production of event materials

## Advance and on-site venue surveys, health and safety/risk assessments

## Post-event research and evaluation.

# definitions

| ## Acronym | ## Definition |
| --- | --- |
| ## OGC | ## Other Government Department |
| ## CO | ## Cabinet Office |
| ## HMT | ## His Majesty’s Treasury |
| ## HMG | ## His Majesty’s Government |
| ## SCS | ## Senior Civil Servant |
| ## SRO | ## Senior Reporting Officer |

# scope of requirement

## You are invited to tender for the provision and delivery of HMG’s annual staff celebration event.

## The day-to-day project management will be the supplier, working closely with the CO Event Manager in the CO Communications Team. This team is very small; therefore, the appointed agency must be able to provide a fast and flexible approach with stringent attention to detail and initiative that maintains the success of the event.

## The successful agency will be required to work closely with the CO Communications Team, wider planning group, venues, sponsors, and stakeholders to design and construct an inspiring event; to provide all materials and key staff necessary to deliver this programme of work. The agency will be able to outsource aspects of delivery but will be held responsible for ensuring the quality, timing, and overall service provision.

## The brand may need to be refreshed to reflect the new year. The successful agency will work closely with the planning team and venue to ensure that there is adequate branding that reflects the guidelines for the events. The agency will also provide wing banners to dress the stage, filming area, and major footfall areas.

## Sustainability should be factored into your proposal.

## Sponsorship

## Bidding agencies should note that the successful agency will be required to offer a guaranteed sponsorship amount as part of the overall cost of the project.

## Your tender should include suggestions for appropriate sponsorship revenues that will not cause any reputational risk to HMG or act as a pure sales platform.

## Sponsorship may be through the provision of goods and services in kind and/or monetary. Civil servants cannot be charged to attend this event.

## There will be no paid-for communications activity.

## Sponsorship packages and sponsors will require pre-approval from the CO planning team. It should however be noted that CO requires a light touch approach to the manner in which potential sponsors are contacted and communicated with – a hard sell approach is not appropriate.

## The successful agency will be required to manage all administration activities associated with the sponsorship activity, including but not limited to:

## Providing a long list of potential sponsors for sign off by CO

## Keeping a contact report database of communications with potential sponsors which are shared with the client

## Contracting the sponsors

    - Due diligence of all sponsors (including assessing financial and reputational risks associated with their involvement)

## Securing the sponsorship package from sponsors (cash or in kind)

## Invoicing the sponsors on a cost recovery basis

## Keeping a transparent and detailed audit trail

## Updating the overall event budget to reflect financial sponsorship income against costs

## Regular full budget updates to CO Event Manager

## Bidding agencies must show a tangible track record in securing sponsorship and the ability to work with other stakeholder organisations involved in the process as described in this tender.

## Bidding agencies should note that if they wish to engage sub–contractors for this project these will need to be identified in your proposal and agreed in advance by CO. The agency will need to identify the skills, experience and their relationship to the sub-contractor. The agency will also need to demonstrate how they will manage the sub–contractor and they may be required to attend a schedule of meetings.

## Costs regarding the management and administration for sponsorship must be identified separately within your budget.

## Website

## The website will incorporate the branding and design. Online registration will be managed by the successful agency. The website should enable registrants to book to attend the event, provide venue information and should be accessible for all users.

## The website or associated registration portals will need to:

## be able to cope with spikes in visitors

## comply with website accessibility standard WCAG 2.1 Level AA, or higher specification

## incorporate (but not be limited to) the following:

## An introduction to the event

## Registration pages (meeting all data protection rules and best practice)

## Venue information, accessibility information and travel details

## Event programmes

## Sponsors’/Exhibitors’ page

## Host social media/videos

## Contact details

## FAQs

## reporting functionality including analytics reports which can be scheduled on a weekly basis, or on request.

## Please state in your tender how many pages your core website includes. Your tender will need to provide explanations on how you will mitigate downtime for updates/amendments to delegates and creative ways in which the technology can be used during the event.

## Delegate and Database Management

## The event will be advertised on the event website, with links to the registration pages from and promoted through departmental intranets.

## The online registration system should:

## allow delegates to book, amend and cancel their registration

## have waiting-list functionality to address cancellations

## issue electronic confirmation of individuals’ bookings

## safely store individuals’ data

## be able to cope with spikes in visitors to the site.

## Your tender should include proposals and costs to deliver the following for all events:

## Manage the delegate and sponsor registration,

## Online registration with option to revise booking; receive confirmation of the booking and travel details

## Provide a telephone helpline and email address.

## Provide weekly reports on registration figures, specific requests, as well as post-event attendance reports to the CO Team

## Information regarding public transport including accessibility information both at and getting to the venue will need to be provided

## Liaison with venues and CO team to organise specific requirements including accessibility, dietary etc.

## Collection of sponsor/exhibitor fees

## On-site registration at all venues

## Catering

## Food and drinks options should be agreed with the organising team. Dietary requirements should be catered for.

## An after party for delegates and sponsors will be considered by the organising team.

## Event Materials

## We wish to minimise paper-based delegate materials. Your tender should include costs for:

## Production of hardcopy invitations if applicable to the venue

## Production of delegate badges

## Speaker/presenter confirmation and information packs

## A Powerpoint Presentation

## Video footage from the awards ceremony to be used to create a highlights film, and for promotion of the event in future years; short 30-60 seconds “Reels” comprising of video footage from the ceremony and awards branding that can be used on social media

## Signage

## Speaker Liaison

## As well as sharing information regarding room requirements, timings, travel etc with speakers, you may also be required to issue invitations to internal and external speakers and follow-up correspondence. You will also cover rehearsals and script preparation.

## Technical/Production

## The appointed agency will be responsible for full creative and innovative event production, ensuring compliance with relevant guidelines. Flexible and imaginative use of venues is essential.

## You will be required to liaise with the venue/suppliers to obtain value for money for AV production to help mitigate cost.

## The provision of equipment may change depending on room size/style and session required, however for the purpose of the tender, please base your costs for each venue on the following:

## Each venue will require AV in the main ceremony room (c400 delegates) and should include as a minimum:

    - Lighting

    - Stage dressing

    - Screen(s) suitable for the audience size

    - Comfort monitors for speakers

    - Lecterns x 2 with fixed mics

    - Roving Mics

    - Staging to accommodate up to 25 people

    - Staging for camera crew

    - Camera crew to record the ceremony

    - Second camera crew to conduct post awards interviews

    - PA system

    - Sound/AV technicians

    - Remote mouse/clicker x 2

    - Laptops x 2

    - Music licence

    - Auxiliary equipment e.g. cabling,

    - Radio headsets for the organising teams

    - Install and de-rig,

    - Transport, travel and subsistence/expenses.

  - On-site management

  - The agency will be required to provide costs for all events for:

    - Event & Technical Production Management, Full management of the registration process,

    - Management of presenters and sponsors,

    - Staffing of the event

    - All co-ordination, e.g. dealing with enquiries, main point of contact for all parties involved, stage management and speaker liaison,

    - Act as lead agency for other sub-contractors,

    - Ensuring that arrangements have been made for delegates with any specific requirements/disabilities including access, induction loops, signers, etc.

  - Accessibility

  - HMG expects the very highest standards of accessibility. Disabled access in set, staging, signage, print and all pre-event communication MUST be exemplary.

  - Evaluation

  - The successful agency will be required to provide creative ideas for a system of gathering feedback from attendees. Please include this as a separate line item within your costs to include production of a post event report.

  - Event briefs

  - The appointed agency with be expected to work with CO to input into a number of briefing/communication products including:

    - Website copy

    - Speakers’/presenters’ briefs

    - Media Sales pack

  - Email correspondence from the agency

    - Delegate joining instructions/invitations

    - Delegate/speaker communications

    - Registration instructions

    - Updates on changes to the programme

# The requirement

# There are no training or skills transfer requirements to be delivered by the supplier, other than upskilling their own team on how to use agreed event technology such as the event website build, and registration sites.

  - We would like to review key suppliers of website delivery, registration providers, polling options and app suppliers for functionality and compatibility and adherence to GDPR best practice.

# key milestones and Deliverables

## The Potential Provider should note the following project milestones that the Authority will measure the quality of delivery against:

## The following Contract milestones/deliverables shall apply:

| ### Milestone/Deliverable | ### Description | ### Timeframe or Delivery Date |
| --- | --- | --- |
| Proposal | Venue options explored, planning meetings commence | March 2024 |
| Proposal | Event proposals to go to Awards Champion, Awards SRO and CEO to secure agreement | March 2024 |
| Website | Website built | April 2024 |
| Application process | Nominations open | May 2024 |
| Application process | Nominations close | July 2024 |
| Judging | Sifting period | August - September 2024 |
| Judging Due diligence | Winners agreed by Awards Champion and final judging panel Due diligence on shortlisted nominees carried out | September 2024 |
| Invitations Communication | Nominees invited to the awards Shortlist announcement | October 2024 |
| Ceremony | Awards ceremony | December 2024 |
| Communication Evaluation | Week of Winners campaign Evaluation, after action review, budget confirmation. | January 2025 |

# MANAGEMENT INFORMATION/reporting

## The appointed agency will be expected to work to the reporting procedures as stated below:

## Provision of a comprehensive project management plan, detailing milestones,

## Provision of detailed risk register to be produced for every aspect of the event, along with contingency plans for all high impact and high likelihood risks. This register should be produced as part of the initial planning for the event, in consultation with CO planning team and should be monitored and updated as required throughout the planning process.

## Weekly nomination and registration figures.

## Monthly budget updates to CO Event Manager, to include summary of sponsorship achieved.

## Analytics for the website and registration pages.

## Database management in line with all data protection rules and regulations.

## The provision of privacy policies in line with GDPR.

## Due diligence reports for sponsorship volumes

## For CS Awards 2024 we anticipate

## 1,300 - 2500 applications; we received 1,962 nominations in 2023.

## 300 - 400 attendees at the ceremony

## 12 awards and 15+ presenters

## 2 hosts.

  - Venue specifications

  - A suitably high-profile venue should be secured for the ceremony. Lancaster House has been secured for the Awards in previous years at no cost, however it is anticipated that this would not be the case for 2024. Initial conversation estimated the dry hire of Lancaster House at £16,000.

  - We would welcome suggestions for a similar venue suggestion to be put forward if the decision was reached to move the event to another venue in London or in the North of the UK (e.g. Manchester/Liverpool/Newcastle). Sponsorship should be secured to cover all venue costs.

# continuous improvement

## The Supplier will be expected to continually improve the way in which the required Services are to be delivered throughout the Contract duration.

## The Supplier should present new ways of working to the Authority during quarterly Contract review meetings.

## Changes to the way in which the Services are to be delivered must be brought to the Authority’s attention and agreed prior to any changes being implemented.

# SUSTAINABILITY / SOCIAL VALUE

## The Supplier must ensure best practice in terms of sustainability is adhered to and demonstrated in their response. Whilst not essential, the Supplier’s adherence with ISO2012 and other relevant policies should be included as evidence where applicable.

## There are no specific sustainability requirements applied to this contract, due to its overarching nature, however the Contracting Authority expects the Supplier to comply with all current legislation regarding sustainability and legislation introduced or amended during the period of the contract pertaining to this.

## This must include compliance with the Modern Slavery Act 2015 and Climate Change Act 2008 and that any chosen sub-contracted suppliers have sustainability accreditation.

## The Supplier must consider their carbon footprint in allocating and deploying resources to undertake requirement.

## Procurement Policy Note (PPN) 6/20 – Taking Account of Social Value in the Award of Central Government Contracts. ‘Social value should be explicitly evaluated in all central government procurement, where the requirements are related and proportionate to the subject-matter of the contract, rather than just ‘considered’.

## PPN 06/20 guidance documents can be found at: https://www.gov.uk/government/publications/procurement-policy-note-0620-taking-account-of-social-value-in-the-award-of-central-government-contracts .

## ‘Social Value for Commercial Success’ - an e-learning course accessed through the Government Commercial College that can be found via the ‘Social Value Mandatory eLearning’ link. It takes less than one hour to complete and will help you to better understand what social value is, why it is important and how to implement it.

# quality

## The agency is required to hold or be working to complete ISO9001 within 6 months of Contract Award.

# PRICE

  - Please complete the attached price schedule and submit all costs as excluding VAT, indicating where VAT will be applicable.

## Prices are to be submitted via the e-Sourcing Suite Attachment 4 – Price Schedule excluding VAT and including all other expenses relating to Contract delivery.

# STAFF AND CUSTOMER SERVICE

## The Supplier shall provide a sufficient level of resource throughout the duration of the Contract in order to consistently deliver a quality service.

## The Supplier’s staff assigned to the Contract shall have the relevant qualifications and experience to deliver the Contract to the required standard.

## The Supplier shall ensure that staff understand the Buyer’s vision and objectives and will provide excellent customer service to the Buyer throughout the duration of the Contract.

# service levels and performance

  - The contract to be agreed with the appointed agency will be based on optimum value for money across all events to deliver the specified objectives.

  - The Authority will measure the quality of the Supplier’s delivery by:

    - Level of sponsorship and value for money achieved;

    - Attention to detail and timing;

    - Managing Stakeholder relationships effectively; and

    - Delivery against tender requirements and agreed milestones.

  - This is not exhaustive and other service levels and KPIs may be agreed at the beginning of the project

| ## KPI/SLA | ## Service Area | ## KPI/SLA description | ## Target |
| --- | --- | --- | --- |
| ## 1 | ## Service delivery | ## The Agency shall meet all proposed Milestones outlined in Section 6.31 | ## 99% |
| ## 2 | ## Sponsorship | ## Sponsorship to be guaranteed as part of the tender exercise. | ## £150k + |
| ## 3 | ## Website | ## To be delivered in May 2024 as described in this document, and updated in April to host all event content and manage delegate registration. To host all post-event content until CS Awards 2024. | ## April |
| ## 4 | ## Attention to detail | ## All event materials and online content to be checked for accuracy prior to being shared with the client and meet a minimum of 90% accuracy. | ## 90% of materials to be accurate. |

## Mechanisms for remedies for poor Supplier performance may include service credits or liquidated damages.

## Where performance is not consistent with expectations outlined in this Contract or in other writing from the Client, and after written warning, the Client reserves the right to initiate early termination of the Contract.

# SECURITY AND CONFIDENTIALITY REQUIREMENTS

## Security checks for both delegates and suppliers should be completed in line with the Met Police’s advice and the threat level at that time in the UK.

## It is anticipated that all delegates will be expected to show their Civil Service Pass or photo ID on arrival to be permitted entry to the events.

## All suppliers should be security checked ahead of being awarded the contract.

# PAYMENT AND INVOICING

## As this is a nil-value contract, no formal invoicing schedule is needed, but the supplier should indicate what their invoicing terms are for subcontractors and for payment of the excess sponsorship.

## Surplus profit from sponsorship following reconciliation of this project is to be divided 50/50 between the successful agency and CO. Regular reports on sponsorship generation and full budget breakdown and updates will need to be provided to the CO event manager.

## Your budget must clearly show the individual roles involved in delivery and the number of days/hours against these roles. Any/all invoices and receipts may be requested for auditing and FOI purposes and should be provided when requested; this will include any third-party suppliers you contract. The contract will be published on the Contracts Finder website as part of HMG transparency agenda, however the Cabinet Office will agree to reasonable redactions with you prior to publication.

## A full breakdown for travel and subsistence should be included in your budget (standard rates of public transport should be used and the use of taxis avoided).  Any travel and subsistence costs should be met by the delivery partner and within the limits set in Cabinet Office policy. A copy of the policy can be provided on request. Payment terms will be in accordance with the Framework Agreement.

## Payment can only be made following satisfactory delivery of pre-agreed certified products and deliverables.

## Before payment can be considered, each invoice must include a detailed elemental breakdown of work completed and the associated costs.

# CONTRACT MANAGEMENT

## Attendance at Contract Review meetings shall be at the Supplier’s own expense.

  - As per Order Schedule 15 (Contract Management).

## Senior project staff must be available to attend an agreed schedule of regular update meetings pre-and post-event. Please state in your proposal how many meetings are included.

# Location

## All meetings will take place virtually, at 70 Whitehall, 9 Downing Street, or a location close to Westminster.