Crown Commercial Service

___________________________________________________________________________

CONSTRUCTION PROFESSIONAL services framework schedule 5

template call off agreement (INCORPORATING THE nec3 professional services contract APRIL 2013) AND contract data

___________________________________________________________________________

TABLE OF CONTENTS

- Form of Agreement

- Contract Data – Part one (Data provided by the Employer)

- Contract Data – Part two (Data provided by the Consultant)

Date 18th September 2025

FORM OF AGREEMENT

Incorporating the NEC3 Professional Services Contract April 2013

Between

Medicines and Healthcare products Regulatory Agency

And

WSP UK Ltd

For the provision of

Professional Services and Project Management of the South Mimms Decarbonisation Project

THIS AGREEMENT is made the 18th day of September 2025

PARTIES:

1.	Medicines and Healthcare products Regulatory Agency whose offices are located at 10 South Colonnade, Canary Wharf, London E14 4PU acting as part of the Crown (the "Employer"); and

2.	WSP UK Ltd which is a company incorporated in and in accordance with the laws of England and Wales (Company No. 01383511 whose registered office address is at WSP House 70 Chancery Lane, London, United Kingdom WC2A 1AF (the "Consultant").

BACKGROUND

- The Minister for the Cabinet Office (the "Cabinet Office") as represented by Crown Commercial Service, a trading fund of the Cabinet Office, without separate legal personality (the "Authority"), established a framework for construction professional services for the benefit of public sector bodies.

- The Consultant was appointed to the framework and executed the framework agreement (with reference number RM6165) which is dated 1 October 2021 (the “Framework Agreement”).  In the Framework Agreement, the Consultant is identified as the “Supplier”.

- On the 30th June 2025 the Employer, Medicines and Healthcare products Regulatory Agency invited the Consultant along with other framework suppliers to tender for the Employer’s construction professional services requirements in accordance with the Call Off Procedure (as defined in the Framework Agreement).

- On the 26th July 2025 the Consultant submitted a tender response and was subsequently selected by the Employer to provide the services.

- The Consultant has agreed to Provide the Services in accordance with this agreement and the Framework Agreement.

IT IS AGREED AS FOLLOWS:

            - The Employer will pay the Consultant the amount due and carry out his duties in accordance with the conditions of contract identified in the Contract Data and the Contract Schedules.

            - The Consultant will Provide the Services in accordance with the conditions of contract identified in the Contract Data and the Contract Schedules.

            - This contract incorporates the conditions of contract in the form of the NEC3 Professional Services Contract April 2013 and incorporating the following Options:

- Main Option A

- W2 - The adjudicator is Royal Institute of Chartered Surveyors, 12 Great George Street, London, SW1P 3AD. Email – contactrics@rics.org

- Option  X1, X2, X5

- which together with the additional conditions of contract specified in Option Z, and the amendments specified in Option Z, form this contract together with the documents referred to in it.  References in the NEC3 Professional Services Contract April 2013 Edition to "the contract" are references to this contract.

            - This contract and the Framework Agreement is the entire agreement between the parties in relation to the services and supersedes and extinguishes all prior arrangements, understandings, agreements, statements, representations or warranties (whether written or oral) relating thereto.

            - Neither party has been given, nor entered into this agreement in reliance on any arrangements, understandings, agreements, statements, representations or warranties other than those expressly set out in this agreement.

            - Nothing in clauses 4 or 5 shall exclude liability in respect of misrepresentations made fraudulently.

Executed under hand

Signed by for and on behalf of WSP UK Ltd

...............................

Operations Director – Building Specialists and Architecture

Date:……………………….

Signed by Lawrence Tallon for and on behalf of MHRA

…………………………………………..

Chief Executive Officer

Date:…………………….

Professional Services Contract

Contract Data

| ## Part one – Data provided by the Employer |  |  |  |
| --- | --- | --- | --- |
| 1 General | The conditions of contract are the core clauses and the clauses for main Option A, dispute resolution Option W2 and secondary Options X1, X2, X5 and Z of the NEC3 Professional Services Contract (April 2013). |  |  |
|  | - The Employer is Medicines and Healthcare Products Regulatory Agency. 10 South Colonnade, Canary Wharf, London E14 4PU |  |  |
|  | - The Adjudicator is the person agreed by the Parties from the list of Adjudicators published by the Royal Institute of Chartered Surveyors or nominated by the Adjudicator nominating body in the absence of agreement. |  |  |
|  | The services are Professional and Project Management services to support the South Mimms decarbonisation Project. |  |  |
|  | - The Scope is in Schedule 1 and is comprised of the following documents in order of priority as follows: - MHRA – Doc 5 Technical Questionnaire – Professional Services and Project Management to support South Mimms Decarbonisation Project dated July 2025; - Professional Services and Project Management to support South Mimms Decarbonisation Project – C362828 – Clarifications No. 13 Date: 18/07/2025; - Document 3 – Specification Professional Services and Project Management to support South Mimms Decarbonisation Project. |  |  |
|  | - The language of this contract is English. - The law of the contract is the law of England and Wales, and the Courts of the country selected above, shall have exclusive jurisdiction with regard to any dispute in connection with this Agreement and the Parties irrevocably agree to submit to the jurisdiction of those courts. The period for reply is Three weeks. The period for retention is 6 years following Completion or earlier termination. |  |  |
|  | The Adjudicator nominating body is the Royal Institute of Chartered Surveyors - The tribunal is arbitration |  |  |
|  | - The following matters will be included in the Risk Register To be developed in the first risk review meeting between the Parties. |  |  |
| 2 The Parties' main responsibilities | - The Employer provides access to the following persons, places and things access to access date The site at South Mimms, EN6 3QG 22nd September 2025 Dedicated Share Point Site 22nd September 2025 |  |  |
| 3 Time | - The starting date is 22nd September 2025. - The Consultant submits revised programmes at intervals no longer than one month. |  |  |
| 4 Quality | The quality policy statement and quality plan are provided within Four weeks of the Contract Date. - The defects date is 52 weeks after Completion of the whole of the services. |  |  |
| 5 Payment | The assessment interval is 30 Days. - The currency of this contract is the pound sterling (£). - The interest rate is, 3% per annum above the Bank of England base rate in force from time to time. |  |  |
| 8 Indemnity, insurance and liability | - The amounts of insurance and the periods for which the Consultant maintains insurance are |  |  |
|  | event | cover | Period |
|  | failure of the Consultant to use the skill and care normally used by professionals providing services similar to the services | in respect of each claim, without limit to the number of claims except for claims arising out of pollution or contamination, where the minimum amount of cover applies in the aggregate in any one period of insurance and except for claims arising out of asbestos, fire safety, where a lower level may apply in the aggregate | from the starting date until 6 years following completion of the whole of the services or earlier termination |
|  | death of or bodily injury to a person (not an employee of the Consultant) or loss of or damage to property resulting from an action or failure to take action by the Consultant | As required under Framework Agreement | from the starting date until all notified Defects have been corrected or earlier termination |
|  | death of or bodily injury to employees of the Consultant arising out of and in the course of their employment in connection with this contract | As required under Framework Agreement | from the starting date until all notified Defects have been corrected or earlier termination |
|  | - The Consultant's total liability to the Employer for all matters arising under or in connection with this contract, other than the excluded matters, is limited to |  |  |
| Optional Statements | - DBS checks on Consultant staff by 22nd September 2025. |  |  |
|  | - If the Employer has decided the completion date for the whole of the services - The completion date for the whole of the services is 31st March 2028. - If no programme is identified in part two of the Contract Data - The Consultant is to submit a first programme for acceptance within 4 weeks of the Contract Date. |  |  |
|  | - If the Employer has identified work which is to meet a stated condition by a key date - The key dates and conditions to be met are |  |  |
|  | Description; Proposed Delivery Date. Stage 0 review / project validation; October 2025. Decarbonisation Options Appraisal (RIBA S2); February 2026. RIBA Stage 3 / 4 EC & DHN Design & Procurement Documentation Complete; October 2026. Completion of Contractor Procurement Technical Support (Contract Award); January 2027. Completion of the Construction Works; March 2028. |
|  | - If the period in which payments are made is not three weeks and Y(UK)2 is not used The period within which payments are made is 30days from date of invoice. |  |  |
|  | - If the tribunal is arbitration - The arbitration procedure is the London Court of International Arbitration Rules; - The number of arbitrators shall be one. - The place where arbitration is to be held is London. - The language to be used in the arbitration proceedings shall be English - If the parties cannot agree the identity of the arbitrator then the nominating body shall be: Royal Institute of Chartered Surveyors. |  |  |
|  | - If Option A is used: - The Consultant prepares forecasts of the total expenses at intervals no longer than 4 weeks. |  |  |
| Option X1 | - If Option X1 is used - The index is the Consumer Price Index (CPI) - as published by the Office for National Statistics. |  |  |
| Option X2 | - If Option X2 is used - The law of the project is the law of England and Wales. |  |  |
| Option X5 | - If Option X5 is used - The completion date for each section of the services is as stated in the Activity Schedule in Schedule 2 of this contract. |  |  |
| Option Z | - The additional conditions of contract are as selected below and as detailed in the appended Standard Boilerplate Amendments: |  |  |

| Option Z2 | - Identified and defined terms - applies |
| --- | --- |
| Option Z4 | - Admittance to Employer’s Premises - applies |
| Option Z5 | - Prevention of fraud and bribery - applies |
| Option Z6 | - Equality and diversity - applies |
| Option Z7 | - Legislation and Official Secrets - applies |
| Option Z10 | - Freedom of information - applies |
| Option Z8 | - Conflict of interest - applies |
| Option Z9 | - Publicity and Branding - applies |
| Option Z13 | - Confidentiality and Information Sharing - applies |
| Option Z14 | - Security Requirements - does not apply |
| Option Z16 | - Tax Compliance - applies |
| Option Z22 | - Fair payment |
|  | - applies |
| Option Z26 | - Building Information Modelling - does not apply |
| Option Z42 | - The Housing Grants, Construction and Regeneration Act 1996 - does not apply |
| Option Z44 | - Intellectual Property Rights - applies |
| Option Z45 | - HMRC Requirements - does not apply |
| Option Z46 | - MoD DEFCON Requirements - does not apply |
| Option Z47 | - Small and Medium Sized Enterprises (SMEs) - does not apply |
| Option Z48 | - Apprenticeships - does not apply |
| Option Z49 | - Change of Control - applies |
| Option Z50 | - Financial Standing - does not apply |
| Option Z51 | - Financial Distress - applies |
| Option Z52 | - Records, audit access and open book data - applies |
| Option Z100 | - Data Protection - does not apply |
| Option Z101 | - Cyber Essentials - applies |

| ## Part two – Data provided by the Consultant |  |
| --- | --- |
| 1 Statements given in all contracts | The Consultant is Name WSP UK Limited Address WSP House, 70 Chancery Lane, London WC2A 1AF. |
|  | The key people are Name Job Director, Head of Energy Solutions Responsibilities Project Director Name Job Associate Director Responsibilities Project Manager |
|  | - The staff rates are: - Job title Rate - Item; - Day rate £ excl. VAT. - Project Management (RLB). - Cost Management (WSP Lexica). - Principal Designer (CDM & BSA). - Planning Consultancy. - Architecture. - BIM. - Geotech. - Structures. - Civils / Drainage. - Flood Risk Assessment. - Acoustics. - Ecology. - Fire. - Process Engineering. |
|  | - The following matters will be included in the Risk Register N/A…………………………………. |
| Optional statements |  |
|  | - If the programme is to be identified in the Contract Data - The programme identified in the Contract Data is as stated in the Activity Schedule in Schedule 2 of this contract. |
| Include where expenses are being stated by the Consultant | - If the Consultant states any expenses The expenses stated by the Consultant are item; amount. [ ]; [ ]. |
| [Include if the Consultant requires additional access] | - If the Consultant requires additional access - The Employer provides access to the following persons, places and things access to access date - …TBA……………………………….…………………TBA…………. |
|  | - If Option A or C is used The activity schedule is …… set out in Schedule 2 ……………………………. The tendered total of the Prices is |

Schedules

# Schedule 1 - Scope

# Schedule 2 – Activity Schedule