## Sheet1
Tender Questions and Answers |  |  | Revision: C
Client: | Croydon College |  | Revision date: 05/07/2024
Project Name: | CC-T423 West End Entrance
Tender released: | 2024-06-11
Tender clarification deadline: | 2024-07-05
Tender submission deadline: | 2024-07-08
Clarification No. | Date Query Issued | Query | Response | Answered by | Date Answer Issued | Query Status (Open / Closed)
1 | 2024-06-17 | Will the external signage features be supplied by the college and a fit only product? | The bidder is to supply and install. Further, the bidder is to refer to the following signage fabricator to obtain a price. However it is expected that the bidder will also provide a competitive cost from their own supply chain for this element of the works. Web: arcola.co.uk Address: Arcola House, Staplehurst Road, Sittingbourne, Kent, ME10 2NH. | ACG | 2024-06-18 | Closed
2 | 2024-06-17 | The finishes and fittings and furnishings sections in the CSA document have no details. However, they are not down as N/A's - can you advise the works required for this section. | Although not indicated as “N/A’s” there is no works itemised under these sections. | WCLLP | 2024-06-18 | Closed
3 | 2024-06-27 | Can you confirm where a storage area for the works where we will be able to store a skip and have access for a grab lorry to remove the arisings from the ramp removal. | Skip storage area will be located in the College's underground car park which has a maximum height of 10ft 10". | Fusion | 2024-06-28 | Closed
4 | 2024-07-03 | Could you please elaborate on the scaffold access for this site. Will we be able to set scaffold up on the slab at the front entrance? | Loadings on the ground floor roof at the West End are unlikely to be sufficient or Scaffold to sit directly on it. The contractor will need to satisfy themselves that their proposal is suitable, and any proposal will be at the contractor's risk. | Fusion | 2024-07-05 | Closed
5
6
7
8
9
10