ProCure22 Framework Agreement

P22 Framework Instruction 7: P22 NEC3 Contract Templates - Building Information Modelling (BIM)

Employers Information Requirements (EIR) Explanatory Notes

Introduction.

The notes below relate directly to Appendix 5 in the P22 NEC 3 Option C Templates B/D/F Under the Government Construction Strategy use of BIM is mandatory on all public sector capital schemes.  The notes are provided for guidance in the application of the EIR but do not take precedent to or overrule the text of Appendix 5.

There is a Jargon Buster (set of Definitions) at the end of this document to assist with some of the new terms that incorporation of BIM can bring.

The P22 Works Information EIR is to provide the Client with comprehensive contractual BIM requirement that defines the BIM specification and process for a project. The EIR provides for the Client that does not have in house BIM expertise but requires the implementation of BIM in line with Government Requirements. It is designed to be a robust minimum that can be elevated in scope in agreement with the PSCP.  The EIR is designed to be cost neutral, deviation may have cost implications therefore implementation must be discussed and agreed with the PSCP prior to production of a BIM Execution Plan.

The benefits of BIM are detailed in the P22 BIM Executive Summary that can be downloaded from the P22 Club website Guidance Section.

Before considering the EIR the Client should consider the P22 BIM Benefits Matrix to determine their high level BIM requirement for the project.  The Benefits Matrix has been jointly developed with the PSCPs and represents a standardised view of BIM deliverables for P22 projects.  All PSCPs have all signed up to the content and implementation of the EIR to deliver the benefits stated, albeit the method with which they do so will be unique to them.

If you have any comments on the EIR please contact your P22 IA and/or DH. _________________________________________________________________________________

- Overview

The EIR requires editing to confirm project-specific requirements for each of the sections. Standard responses have been included and in many cases these can be adopted without amendment. However, all EIR content requires review and confirmation prior to issue.

If BIM is not to be used on the project the Client Project Manager will cross out Appendix 5.

The EIR assumes PSCP appointment at Stage 2 OBC, with the first BIM output (Data Exchange) being at stage 2.

The EIR is an evolving document to be updated as BIM Level 2 standards evolve.

Areas where project specific adjustments are likely to be required include:

- Type of asset. This document is prepared on the assumption that the asset is the construction and/or refurbishment of a capital asset on the Major/Small Works Contract Templates;

- Project stages. Data exchanges and associated information requirements are to be mapped against the P22 project stages. Where implemented in a Small Works Scheme guidance is to be sought from P22 Helpdesk for Data exchanges at the 2 key stages of each Task.

- Information requirements. Data exchanges are to be aligned against the needs of the project – e.g. new-build vs. on-going asset management;

- Procurement strategy. Data exchanges are to be aligned with the procurement strategy as noted;

- IT requirements. Collaboration tools and other employer-specific requirements are to be specified. Client IT tools referred to in the EIR are indicative and not a requirement to use specific products e.g. a collaboration site provided by the employer or PSCP;

- Terminology is to align with P22 terminology and refer to P22 Guidance / Contractual documents where required;

- Project specific adjustment may be required in response to specific data requirements to be handed to the Client or input into an existing CAFM system at the end of the project.  However a robust minimum requirement is included in the EIR;

- Nothing in the EIR  overrides the requirements of the P22 National Framework Agreement and its Appendices;

Note:  The Client is to ensure the above requirements are applied throughout the contract.

1.1 BIM Strategic Objectives

Before completing this section the Client should refer to the P22 Benefits Matrix the and replicate the selections within the EIR.

1.2 Project Specific Challenges

The Client summarises the BIM status at the point the PSCP is selected and any qualifications on its administration. For example Client restrictions and limitations - supplier input / liaison required such as Computer Aided Facilities Management (CAFM) requirements, limits on the geometric or Level of Detail / Level of information required.

2.1 Standards

This specifies the BIM Task Group standards to be applied to the scheme. Additional standards used by the PSCP are to be defined within the BEP.  The stated BS/PAS standards have been developed by the BIM Task Group and represent a robust standard for BIM Implementation across the public sector. The standards are subject to continual development by the BIM Task Group; such development is to be incorporated in the project specific EIR.

2.2 Roles and Responsibilities

The purpose of this section in the EIR is to bring to the attention of the project team the allocation of roles associated with the management of the BIM model and project information. It’s important to note that this is not necessarily additional information being produced for BIM specifically, just a change in format of the project information already produced normally.

The roles are envisaged as being undertaken by individuals as part of their normal duties within the Project team and are not seen as additional roles for additional staff.

Details of the scope of services of the Information Manager are as prepared by the Construction Industry Council. An outline version suitable for incorporation with any appointments is published on the BIM Task Group website http://www.bimtaskgroup.org/wp-content/uploads/2013/02/Outline-Scope-of-Services-for-the-Role-of-Information-Managment.pdf

PAS 1192-2 section 7.5 table 2 provides a useful cross-tabulated summary of the roles as they apply across Project Team Members.

The PSCP is to consider these standards and adopt them for the project in context with the EIR for inclusion in the BIM Execution Plan.

2.3 Planning the Work and Data Segregation

This section sets out requirements for the management of the modelling process.  The PSCP will respond in their BEP.

Where the employer has specific requirements for work management, this should be identified and discussed with the PSCP prior to submission of the BEP.

The PSCP BEP includes recommendations on:

- Model Management:

  - Details for procedures required.  The expectation is that this will be co-ordinated by the Information Manager (PSCP).

- Volumes, Zones and Areas:

  - Requirements in connection with the definitions of zones and the management of adjacency within the model.

  - Requirements in connection with the definition of the project volume structure.

- Naming Conventions:

  - Definition of the requirement for a single project convention.

2.4 Security

Record Client specific security measures required in order to secure the data and model.

2.5. Coordination and Clash Detection

This section defines the required co-ordination process, together with requirements for quality control. This should be aligned with design development meetings where the latest version of the BIM model is used.

2.6 Collaboration Process

Defines how the Client, PSCP and Supply-Chain will collaboratively develop the model.  The  requirements will be reflected in the PSCP’s BEP.  The Client needs to ensure that they have the latest version of the model available to them in periodic design development meetings and at key decision points.  If possible amendments should be made directly  to the live version of the model in a Common Data Environment.

2.7 Health and Safety / Construction Design Management

The PSCP states how BIM based working will support H&S/CDM monitoring.

Clients should consider their requirement for H&S/CDM information to be provided in the BIM model, during design and construction stages. The Client should require access to this information in whatever format it feels best to receive it rather than requiring it to be part of the BIM model specifically.

Consideration should be given as to how post-construction Health and Safety information is to be recorded where Client does or does not require the BIM model to be used post construction for FM.

2.8 Systems Performance

Requirement is for the PSCP to ascertain whether or not the Client IT system has BIM capability. If the answer is no then PSCP proposes suitable measures.

2.9 Compliance Plan

The PSCP records and communicates how the integrity of the model and other data sources are to be maintained.

2.10 Delivery Strategy for Asset Information

This section defines the information exchange standard for Asset Information delivery into the employer’s FM system for ongoing FM Management at the end of the project.

Clients should consider carefully the information they require and how they may use it.  The P22 Standard Core Data-set provides a basic level of information that offers the following information for each component.  If the Client requires more information, they should discuss this with the PSCP in development of the EIR.

- Name

- Description

- Reference Number

- Use Classification

- Material and Finish Information

- Manufacturer

- Serial Number

- Technical information for Mechanical or Electrical Equipment

- Location

- FM Asset Number

- O+M Reference

- Residual Risks /Health and Safety Information

The requirements could be extended to identify specific requirements for cleaning, renewable assets, life expiry dates, statutory compliance certificates etc, if required. However Clients need to be mindful that asking for more information can lead to a very large data set and file size that can be difficult to operate.  Expanding the range of information requirements may increase the cost of delivery.

The Client should identify their CAFM system in Section 1.2.

- Technical Requirements

This section establishes technical information requirements, including the available Client software, data exchange contents and required level of detail.

The PSCP consults with the Project Manager identifying additional hardware/software the Client may need to implement BIM for the project

  - Software Platforms

It is necessary to ascertain at an early date in the application of BIM which software the Client has available and whether it is compatible with that operated by the PSCP. Final decisions on compatibility are to be recorded for avoidance of doubt.

  - Data Exchange Format

This section defines the formats used to deliver data at data exchanges.

Government (BIM Task Group) specifies the requirement for information in a COBie format. This is the most commonly used and understood format.  The Construction-Operations Building Information Exchange (COBie) format facilitates the delivery of Asset Information during planning, design, construction, and commissioning for delivery to facility owners and operators.  It is commonly delivered in an MS Excel spreadsheet.

  - Co-ordinates

A common co-ordinate system is stipulated for all BIM data with consistent adoption for all models. It ensures that all building components are located relative to an agreed point of origin. The PSCP uses a common co-ordinate system for all BIM data which is to be described within the BEP. If project-specific co-ordinate requirements exist, these should be inserted.

  - Level of Definition

Defines the requirements for information submissions/data exchanges at project stages. This information is used to develop the Master Information Delivery Plan (MIDP) and also defines, for the purposes of the contract, the levels of detail used for the various phases of the project.  As the project develops, increasing levels of detail can be included in the model.

3.5. Training

The PSCP provides training in application of the software and process required for the operation of BIM for Client staff.

The PSCP is required to provide trained personnel to operate and deliver the BIM process.

4. Data Exchanges and Project Deliverables

Defines the content of data exchanges and how the exchanges are aligned to work stages.

P22 PSCPs have agreed a standard minimum data set that to be supplied with all BIM projects,

To plan the development of the model and the design, the PSCP provides a Model Production Delivery Table (MPDT) in their BEP that specifies who will produce the information, when and in what detail.

- Jargon Buster

Data Exchanges – sets of data to be uploaded to the model at key decision points in the process.  Under P22 these are at SOC, OBC, FBC, and Completion.  See Section 6 in the EIR for the P22 standard Client requirements for data exchanges. Data Exchanges were previously known as ‘Data Drops’.

BEP – BIM Execution Plan.  The PSCP develops the BIM Execution Plan to describe in detail how they execute BIM on the scheme. Client engages with the PSCP in its development and acceptance.

MPDT – Model Production Delivery Table (MPDT).  The PSCP supplies this in their BEP and sets out all the models that will be developed and at high level who is responsible for the supply of discipline based information, and when.

MIDP – Master Information Delivery Plan.  The PSCP develops this plan with their suppliers to organise the delivery of asset data to the model. It specifies all the information deliverables on the project including but not limited to drawings, specifications, equipment and room data sheets. It records who, what, how and when information is to be supplied by linking it to the design and the programme.

COBie – Construction Operations Building Information Exchange.  This is the data format recommended by Government for the recording and communicating asset data.  It is usually in MS Excel format and supports the Federated BIM Model.  It can be exported from the BIM model and used in a CAFM system.

IFC – Industry Foundation Classes. An open file format that facilitates the interoperability of different BIM software for different disciplines.  BIM software can export models in IFC format that can then be imported by different software to federate the models.  The Government are supporting the use of IFC as standard, however there are issues with compatibility in some cases which the PSCP is to resolve for the project.

Federated Model – A BIM Model is collection of several different discipline based models that are Federated together to create a single interface for the Client.  When the models are federated the software checks for clashes and other inconsistencies and provides a report.