## Sheet1
CLARIFICATION LOG
Tender: | Landscaping Development work, Kerrier Way, Camborne
Tender Reference: | 01-24
Published Date: | 22.03.2024
Version number: | 0.3
Number | Clarification | Response | Reply date
1 | We are interested in bidding for the Landscaping Development Work for Kerrier Way however, we will struggle to meet the current deadline due to in-house capacity. May we kindly request a two week extension please? | Thanks for the interest in Kerrier Way tender. At present, we feel that it would be better for our programme to allow the tender to run as it is currently listed. The programme is scheduled to align with council committee meetings in order to enable the approvals for us to progress. | 2024-03-07
2 | Please would it be possible to provide the Bills of Quanties as an Excel document. | Yes, we will provide this via a further document upload on Contracts Finder - please ensure you look out for this document and download for completion. Please note when filling in the Excel documents not to amend any of the preset formulas. | 2024-03-07
3 | Are there further details in relation to the ground / site conditions etc.? | Additional document added: Phase II Ground Investigation | 2024-03-22
4 | Bills of Quantities update | An Excel version of the Bills of Quantities is now uploaded. Please note there have been some amends to a small amount of quantities. We will accept for evaluation responses against the original published Bill of Quantity and / or the revised Excel version. As part of evaluation we will compare on Unit cost where different quantities have been specified | 2024-03-22
Clarifications will be published against the Contract Notice on Contracts Finder.
If interested in tendering for this project please ensure you add a "watch this notice" for alerts as from time to time additional information or clarifications may be published related to this tender.
It will be the responsibility of Bidders to ensure they are aware of all published clarifications and ensure that their bid has taken these into account.
In the event of any queries please contact: