## Price Schedule
Revision 1
Pricing Schedule - Refurbishment Works at Penhill Bowls Club
|  | £ |  | £
PRELIMINARIES |  |  | £
1.1 | Site Management: Allow for all necessary site management including a designated site foreman.
1.2 | Health and Safety: Provide written risk assessments before commencing any work. Allow for carrying out all the work in accordance with current health and safety regulations.
1.3 | Fencing and access: Form a secure construction site area with temporary fencing to prevent unauthorised access to the site including building, footpaths and car parking area to side of the building during the carrying out of the works. Clear away all temporary fencing on completion of the works. Allow for maintaining access to the building during the carrying out of the works.
1.4 | Signage: Allow for all site health and safety signage for both the public and the workforce to be in accordance with current health & safety regulations.
1.5 | Goods & Materials: Allow for all goods and materials to be supplied new in accordance with the contract specification and drawings or equal approved, in good condition and only brought to site as and when needed. Allow for protection and security of all goods and materials until the completion of the works.
1.6 | Workmanship: Allow for all workmanship to be in accordance with the contract specification and to approved construction industry standards and codes of practice.
1.7 | Plant, tools and equipment: Allow for all neccesary small plant, tools and equipment for the carrying out of the works including arranging for power as required. Note the community centre may be used for power provision during the carrying out of the works.
1.8 | Welfare facilities: Allow for all necessary temporary welfare facilities to be in accordance with current health and safety regulations including arranging for power, water and sanitation as required. Note the changing rooms may be used for welfare provision during the carrying out of the works.
1.9 | Waste and Cleaning: Allow for removing all waste from site to approved tips as the work proceeds including the use of covered skips as required. Leave the site clean and tidy on completion of the works.
1.10 | Insurances: Allow for public and employers liability insurances to the levels of imdemnity as required.
MAIN ROOM / CAFÉ |  |  | £
2.1 | Walls: Remove fire damaged plaster from walls (return to brick) and either skim or plasterboard. Supply & fit new skirting boards.
2.2 | Ceilings: Remove fire damaged materials. Repair fire damaged ceiling joists, supply & fit new plasterboard, skim to make good.
2.3 | Floor Covering: Remove any existing coverings and make make good sub-floor. Provide and lay latex screed ready to receive new coverings. Provide and lay new Altro Walkway 20 or similar approved vinyl safety flooring fixed with low emmision adhesive all in accordance with manufacturer's recommendations. Heat weld all joins. Allow for formimg joints at door openings to existing remaining floor finishings, abutments to skirtings and for all necessary cutting and fitting around obstructions.
2.4 | Redecoration: Prepare and decorate plaster walls with 2coats agreed colour vinyl matt emulsion paint. Prepare and decorate plasterboard ceilings with 2coats white vinyl matt emulsion paint. Prepare and redecorate all other surfaces including skirtings, doors with frames and window boards with 2coats agreed colour gloss paint.
OFFICE |  |  | £
3.1 | Walls: Remove fire damaged plaster from walls (return to brick) and either skim or plasterboard. Supply & fit new skirting boards.
3.2 | Ceilings: Remove fire damaged materials. Repair fire damaged ceiling joists, supply & fit new plasterboard, skim to make good.
3.3 | Floor Covering: Remove any existing floor coverings and make make good sub-floor. Provide and lay latex screed ready to receive new coverings. Provide and lay new carpet fixed in accordance with manufacturer's recommendations. Allow for formimg abutments to skirtings and for all necessary cutting and fitting around obstructions.
3.4 | Redecoration: Prepare and decorate plaster walls with 2coats agreed colour vinyl matt emulsion paint. Prepare and decorate plasterboard ceilings with 2coats white vinyl matt emulsion paint. Prepare and redecorate all other surfaces including skirtings, doors with frames and window boards with 2coats agreed colour gloss paint.
MULTI USE ROOM |  |  | £
4.1 | Walls: Remove fire damaged plaster from walls (return to brick) and either skim or plasterboard. Supply & fit new skirting boards.
4.2 | Configuration: Create DDA compliant accessible opening between 2 rooms, with finishes. Including installation of lintel. Close off 1 x door opening and make good walls.
4.3 | Ceilings: Remove fire damaged materials. Repair fire damaged ceiling joists, supply & fit new plasterboard, skim to make good.
4.4 | Redecoration: Prepare and decorate plaster walls with 2coats agreed colour vinyl matt emulsion paint. Prepare and decorate plasterboard ceilings with 2coats white vinyl matt emulsion paint. Prepare and redecorate all other surfaces including skirtings, doors with frames and window boards with 2coats agreed colour gloss paint.
4.5 | Floor Covering: Remove any existing coverings and make make good sub-floor. Provide and lay latex screed ready to receive new coverings. Provide and lay new Altro Walkway 20 or similar approved vinyl safety flooring fixed with low emmision adhesive all in accordance with manufacturer's recommendations. Heat weld all joins. Allow for formimg joints at door openings to existing remaining floor finishings, abutments to skirtings and for all necessary cutting and fitting around obstructions.
KITCHEN / STORE ROOM |  |  | £
5.1 | Walls: Remove fire damaged plaster from walls (return to brick) and either skim or plasterboard. Supply & fit new skirting boards.
5.2 | Ceilings: Remove fire damaged materials. Repair fire damaged ceiling joists, supply & fit new plasterboard, skim to make good.
5.3 | Redecoration: Prepare and decorate plaster walls with 2coats agreed colour vinyl matt emulsion paint. Prepare and decorate plasterboard ceilings with 2coats white vinyl matt emulsion paint. Prepare and redecorate all other surfaces including skirtings, doors with frames and window boards with 2coats agreed colour gloss paint.
5.4 | Floor Covering: Remove any existing coverings and make make good sub-floor. Provide and lay latex screed ready to receive new coverings. Provide and lay new Altro Walkway 20 or similar approved vinyl safety flooring fixed with low emmision adhesive all in accordance with manufacturer's recommendations. Heat weld all joins. Allow for formimg joints at door openings to existing remaining floor finishings, abutments to skirtings and for all necessary cutting and fitting around obstructions.
TOILET |  |  | £
6.1 | Walls: Remove fire damaged plaster from walls (return to brick) and either skim or plasterboard. Supply & fit new skirting boards.
6.2 | Configuration: Create new DDA compliant accessible opening. Installation of lintel. Supply and fit door and all frame work. Close off 1 x door opening and make good walls.
6.3 | Ceilings: Remove fire damaged materials. Repair fire damaged ceiling joists, supply & fit new plasterboard, skim to make good.
6.4 | Redecoration: Prepare and redecorate existing plaster walls with 2coats matt emulsion paint. Prepare and decorate existing textured paint ceilings with 2coats white vinyl matt emulasion. Allow for skimming existing textured paint ceilings if necessary. Prepare and redecorate existing timber surfaces including skirtings, doors with frames and window boards with 2coats agreed colour gloss paint.
6.5 | Floor Covering: Remove any existing coverings and make make good sub-floor. Provide and lay latex screed ready to receive new coverings. Provide and lay new Altro Walkway 20 or similar approved vinyl safety flooring fixed with low emmision adhesive all in accordance with manufacturer's recommendations. Heat weld all joins. Allow for formimg joints at door openings to existing remaining floor finishings, abutments to skirtings and for all necessary cutting and fitting around obstructions.
6.6 | Supply and fit all new DDA approved facilities, including Ceramic Sink (hand basin), Ceramic Toilet, Hand Dryer, hand hold rail and safety holds. Allow for testing appliances and reporting findings.
WINDOWS / DOORS & SHUTTERS |  |  | £
7.1 | All internal Doors: Remove all existing doors and frames, complete and make good. Provide and fit new 30 minute fire resistant wood door frame to fit existing opening with appropriate intumescent/smoke seals within the frame to comply with current fire regulations. Provide and fix new 30 minute fire resistant wood doors to match existing sizes with rectangular fire resistant glazed panel in each together with anti-finger trap mechaism and appropriate intumescent/smoke seals to comply with current fire regulations. Provide and fit satin anodised aluminium ironmongery to both sides of each door leaf. Provide and fit 2nr door opening safety barriers with either disabled opening push plate or PIR sensor both sides. Allow for providing door power supply in concealed or surface fixed conduit from adjacent double power socket.
7.2 | External Door: Remove existing double doors and frame, complete and make good. Provide and fit new 30 minute fire resistant alluminium double door frame to fit existing opening with appropriate intumescent/smoke seals within the frame to comply with current fire regulations. Provide and fix new 30 minute fire resistant alluminium double doors to match existing sizes with anti-finger trap mechaism and appropriate intumescent/smoke seals to comply with current fire regulations. Provide and fit satin anodised aluminium ironmongery to both sides of each door leaf. Provide and fit 2nr door opening safety barriers with either disabled opening push plate or PIR sensor both sides. Allow for providing door power supply in concealed or surface fixed conduit from an adjacent double power socket.
7.3 | Windows: Remove all damaged material and repair all window surrounds. Supply & fit all new FENSA rated compliant window frames and glazing.
7.4 | Windows: Remove all damaged material and repair all window surrounds. Supply & fit all new FENSA rated compliant window frames and glazing.
7.5 | All windows frames, external doors, shutters and security bars to be supplied in RAL6005
ELECTRICAL INSTALLATIONS |  |  | £
8.1 | Whole Building: Full electrical rewire including data cabling, power sockets and light switches.
8.2 | Main Room / Café: Remove all existing light fittings. Provide and install new non-dimmable LED light fittings. Provide and install new emergency light fitting. Allow for amending terminal blocks and new wiring and cabling as required.
8.3 | Office Lighting: Remove all existing light fittings. Provide and install new non-dimmable LED light fittings. Provide and install new emergency light fitting. Allow for amending terminal blocks and new wiring and cabling as required.
8.4 | Multi Use Room : Remove all existing light fittings. Provide and install new non-dimmable LED light fittings. Provide and install new emergency light fitting. Allow for amending terminal blocks and new wiring and cabling as required.
8.5 | Klitchen & Store Lighting: Remove all existing light fittings. Provide and install new non-dimmable LED light fittings. Provide and install new emergency light fitting. Allow for amending terminal blocks and new wiring and cabling as required.
8.6 | Disabled Toilet Lighting: Remove all existing light fittings. Provide and install new non-dimmable LED light fittings. Provide and install new emergency light fitting. Allow for amending terminal blocks and new wiring and cabling as required.
8.7 | Smoke Alarms: Installation of smoke & fire detection.
8.7 | Provisional Sum: Allow a £1,000 provisional sum for carrying out any recommended work to existing electrical installations | 1000
8.8 | CCTV: Supply and Install Closed Circuit TV system.
8.9 | Electrical Specification: Carry out all electrical work in accordance with all current Electrical Regulations and Codes of Practice of The Chartered Institute of Building Services, The Institute of Electrical Engineers, British Standards including B7671 (Requirements for Electrical Installations) and any amendments and The Current IEE Wiring Regulations for Electrical Installations. Install all equipment in accordance with manufacturers recommendations.
8.10 | Testing & Commissioning: Carry out all necessary labelling and testing and certification to comply fully with NIC EIC BS7671.
8.11 | Documentation: Provide and hand to employer 2nr Hard Copies and 1nr Electronic Pdf Copy of all necessary Health and Safety (H&S) and Operation and Maintenance (O&M) Manuals together with 'As Installed' Drawings in AutoCAD 2011 format
MECHANICAL INSTALLATIONS |  |  | £
9.1 | Existing Boiler & Controls: Existing heating system is to be replaced. Review & report recommendations for bringing existing heating system up to current regulations. Allow for new point of use water heater. Visual inspection and full demonstration of all plant and controls.
9.2 | Main Room / Café: Design, supply and install new sufficiently sized low surface temperature (LST) electric panel radiators. Allow for test and reporting.
9.3 | Office: Design, supply and install new sufficiently sized low surface temperature (LST) electric panel radiators. Allow for test and reporting.
9.4 | Kitchen: Design, supply and install new sufficiently sized low surface temperature (LST) electric panel radiators. Allow for test and reporting.
9.5 | Multi Use Room: Design, supply and install new sufficiently sized low surface temperature (LST) electric panel radiators. Allow for test and reporting.
9.6 | Kitchen / Store: Design, supply and install new sufficiently sized low surface temperature (LST) electric panel radiators. Allow for test and reporting.
9.7 | Toilet: Design, supply and install new sufficiently sized low surface temperature (LST) electric panel radiators. Allow for test and reporting.
9.8 | Toilet Mechanical Ventilation: Remove existing extract fan. Design and provide and install new sufficiently sized fresh air supply and extract air mechanical ventilation system. Form new fresh air suppy ducting sytem to the outside. Allow for connecting extract air to existing ducting. Allow for all necessary new wiring and controls.
9.9 | Provisional Sum: Allow a £1,000 provisional sum for carrying out any recommended work to existing mechanical installations | 1000
9.10 | Cleaning & Chlorination: Allow for cleaning and chlorination of all mechanical installations.
9.11 | Testing & Commissioning: Carry out all necessary labelling and testing and certification to comply fully with current water and gas regulations (if required).
9.12 | Documentation: Provide and hand to employer 2nr Hard Copies and 1nr Electronic Pdf Copy of all necessary Health and Safety (H&S) and Operation and Maintenance (O&M) Manuals together with 'As Installed' Drawings in AutoCAD 2011 format
EXTERNALLY |  |  | £
10.1 | Provisional Sum: Allow a £1,500 provisional sum for cutting back and removing overgrown shrubs and vegetatin (Landscaping). | 1500
10.2 | Roof and guttering: Remove and dispose of existing felt roof. Supply & fit new insulation. Supply & fit new EPDM rubber roofing to total roof area. Supply and fit new guttingering, chanels and downpipes.
10.3 | Drainage: Clearance of all gullies and drains.
10.4 | Connection: Allow for connection to exisiting services (Waste / Water)
10.5 | Redecoration: Replace and decorate timber fascias and soffits to single storey roof only with 2coats agreed colour gloss paint. Allow for cleaning out gutters and valleys to single storey roofs only.
10.6 | Graffiti Removal: Jet wash all external brickwork.
10.7 | Hardstanding: Ground Scan, design 57m2 area of hard standing. Excovate topsoil from bowls green lawn (spoil to be relocated on site). Insert drainage chanels to feed in to existing. Reduce level ground to correct formation and roll material. Supply and lay terram 1000 on formation Supply and lay 225mm Type 1 stone and compact Supply and lay 150mm Type 1 to make up final levels Supply and Machine lay 80mm AC 20 dense bit macadam binder Supply and Machine lay 30mm AC10 surface course
10.8 | Carpark: Allow for minor resurfacing works to exisisting carpark.
10.9 | Fencing: Supply and install 35m of 1.8m high accoustic sound fencing.
10.10 | Path: Install 1.6m wide, up to 10m lime dust path with board edging.
10.11 | Access: Design, supply and Install DDA complient slope/ramp access in to main room.
10.12 | Patio: Make good existing patio area surfacing and bridge small gap from patio to bowling green area.
CONTINGENCIES
11.1 | Provisional Sum: Allow a £10,000 provisional sum for unforeseen problems. | 10000 | £ | 10000
---------------------
TOTAL PRICE (excluding VAT) to APPENDIX A (Form of Quotation): |  | £
---------------------
Signed:
Print Name:
Date:
Position:
Note on C32: Andrew Briggs: New Steal Beam Close 1 x door opening
Note on C45: Andrew Briggs: New door opening