## Sheet2
Specification Holocaust Memorial and Learning Centre - Architectual Peer Review Services
2020-02-20
Stage 4 Technical Design Audit Services
Core Service Discipline 1 - Peer Reviewer / Design Auditor
Ref | The Supplier is required to deliver the following Scope of Services
1 | General Services
1.1 | Carry out a technical design audit of the RIBA Stage 4 design to assess completeness of the design, design coordination, buildability, statutory compliance and project design risks, compliance with Client Brief
1.2 | The audit brief includes review of all interfaces, and compliance issues including planning and building regulations as well as compliance with the Client's Brief. The audit shall highlight any missing information normally provided at RIBA Stage 4 Technical Design phase.
1.3 | Information for review shall be provided in CAD/Revit format.
1.4 | glass replacement strategy
1.5 | maintenance and cleaning strategy
1.6 | opportunities for cost savings / value engineering / efficiency in design
1.7 | opportunities for improvement / efficiency in design
1.8 | area check calculations (GIA / NIA)
1.9 | Maintenance / detailing strategy e.g. key component servicing or replacement, façade access
1.10 | Request and attend meetings in order to complete the Stage 4 design audit review.
1.11 | Liaise through usual communication media (phone, e-mail, ad-hoc meetings if necessary) with the Client, Project Manager, Lead Designer, Consultant Engineers, Cost Manager and Principal Designer as necessary to complete the Stage 4 design audit review.
1.12 | Attend one interim two hour meeting at mid-point of study to review progress with client team.
2 | RIBA Stage 4 - Technical Design
2.1 | The Stage 4 design audit review shall cover all consultant services (including architectural (Learning Centre and Memorial), landscape architect and all engineering services). {Note: the review shall not include review of the UKHM Learning Centre Content}
2.2 | Overview of the completeness and coordination of the RIBA Stage 4 and equivalent ICE / CIBSE work stage standards) design as provided in the consultant team information (drawings, technical specifications, reports etc.)
2.3 | Review to include all Stage 4 reports, drawings and technical specifications, appropriateness of specification and highlighting any areas of unnecessary complexity or expense, where more efficient specification would meet brief
2.4 | Review BREEAM reporting and assessment.
2.5 | Review statutory compliance (Building Regs, CDM) except planning
2.6 | Technical Design (material specifications, compliance with statutory regulations, services strategy, integration of servicing)
2.7 | Buildability / ease/efficiency of construction / fabrication
2.8 | Access and Servicing
2.9 | Design for Access (including compliance with Equality Act)
2.10 | building services (MEP) strategy
2.11 | robustness and tolerance allowances inherent within the design and detailing
2.12 | comment on assumptions about visitor numbers and suitability of design for flow / dwell time, Note, this isn't an expert view on visitor flows but an assessment as experienced architects of the size, scale and configuration of the spaces, and ability to accommodate up to 500 visitors
2.13 | Identify key areas of conflict / discrepancies. If applicable (i.e. if prepared at the time of review) review consultant team Stage 4 statements of conformance including lists of 'outstanding items' and items identified to be carried out during Stage 5. Provide comments. Highlight areas or concern such as tolerances, need for more detailed specification
2.14 | Provide comment(s) on the adequacy of the design compliance with the Client's Brief.
2.15 | Check area schedules and provide comments on any discrepancies to the information provided.
2.16 | Carefully assess coordination status of the Stage 4 design; coordination between all design disciplines - architects, landscape architect and engineering disciplines. Provide detailed comments as to whether the coordination is at a level commensurate with what could be expected for RIBA Stage 4 Technical Design.
2.17 | Provide comment(s) on ease of information navigation between documents, drawings, reports etc,
3 | RIBA Stage 4 - Optional Services
All the above shall include review of, but not limited to:
3.1 | detailed review of building services, checking of calculations, capacity, sizing and location of equipment. Suitability of components within building services to meet design specification
3.2 | Fire Strategy
3.3 | Lighting
3.4 | civil and structural reports
3.5 | acoustic performance (analysis of design to the acoustic report)
3.6 | vertical transportation
3.7 | comment on CDM Risk Assessments
4 | Report and Meetings
4.1 | Collate all review and findings into a full Stage 4 Design Audit Report and issue to the Client. This will identify, amongst other issues, areas of design risk, lack of completeness, coordination and compliance with statutory regulations, identifying potential risk issues as Red, Amber, Green in terms of risk to delivery cost and programme.
4.2 | Allow for 2 information gathering meetings during the study, and 2 presentations at conclusion of study, 1 to present findings consult design and 2 to present findings to client team. (Five meetings in total)