| Pirbright CVIM Contract Pirbright Innovations Limited And [Contractor] in relation to the CVIM (Centre for Veterinary Vaccine Innovation and Manufacturing) Facility at The Pirbright Institute, Ash Road, Woking, Surrey, GU27 0NF |  |
| --- | --- |

CVIM Contract based on the NEC4 Engineering and Construction Contract (June 2017 Edition) incorporating the January 2019, October 2020, and January 2023 amendments as modified and supplemented in the manner indicated in this Agreement and the Appendices hereto.

THIS AGREEMENT is made on                                                                               2024

BETWEEN:-

Pirbright Innovations Limited (Company number 04394007) whose registered office is at The Pirbright Institute Ash Road, Pirbright, Woking, Surrey, GU24 0NF

- (the "Client”, which expression shall include its successors in title and permitted assigns);

- and

[CONTRACTOR] [Company number (No. [•])] whose registered office is at [•]

- (the "Contractor").

RECITALS

The Client has agreed to employ the Contractor to carry out and complete the design of certain works as contained in the ITT documents.

The Client and the Contractor have agreed to enter into this Agreement for the purpose of recording the terms and conditions of such employment.

IT IS HEREBY AGREED AS FOLLOWS:-

- Interpretation

In this Agreement (including the recitals) words and expressions shall have the meanings as are respectively assigned to them in the conditions of contract referred to below. Clause headings are for information purposes only and do not affect the interpretation of the contract. Unless the context otherwise requires:

any word or term beginning with a capital letter has the meaning given to it in the conditions of contract;

any italicised term has the meaning given to it in the Contract Data; and

Agreement

  - The Contractor will Provide the Works in accordance with this contract and the conditions of contract.

  - The Client will pay the Contractor the amount due and carry out their duties in accordance with this contract and the conditions of contract.

References in the conditions of contract to "the contract" are references to this contract.  The contract consists of the following and if there is any ambiguity or inconsistency in or between the documents comprising this contract, the priority of the documents is in accordance with the following sequence:

this Agreement;

the conditions of contract, as referred to in clause 3 below, including the annexures thereto, as follows:

the core clauses of the NEC4 Engineering and Construction Contract (June 2017 edition) incorporating the January 2019, October 2020, and January 2023 amendments;

the clauses for Main Option A: Priced contract with activity schedule;

dispute resolution Option W2;

Secondary Options X4 (Parent Company Guarantee), X7 (Delay Damages), X8 (Collateral warranties), X10 (Information Modelling), X11 (Termination by the Client), X13 (Performance Bond), X16 (Retention), Y(UK)2 (The Housing Grants, Construction and Regeneration Act 1996), Y(UK)3 (The Contracts (Rights of Third Parties) Act 1999);

the Z clauses annexed at Annex 2 of this Agreement, which take precedence over the remaining conditions of contract;

the Contract Data Part One set out in Annex 1 of this Agreement and (excluding the conditions of contract) all the documents referred to in such part;

the Contract Data Part Two set out in Annex 1 of this Agreement and all the documents referred to in such part;

the Scope and Preliminaries are annexed at Annex 3 of this Agreement;

the Preconstruction Information annexed at Annex 4 of this Agreement; and

the Activity Schedule annexed at Annex 5 of this Agreement.

3 	NEC conditions

The conditions of contract are based on the NEC4 Engineering and Construction Contract (June 2017 edition) main Option A, dispute resolution Option W2 and secondary Option clauses X4, X7, X8, X10, X11, X13, X16, Y(UK)2, Y(UK)3 together with the amendments set out in the ‘January 2019 Amendments’, ‘October 2020 Amendments’ and ‘January 2023 Amendments’ published by the NEC and the modifications, additions and amendments set out in Annex 2 to this Agreement (the ‘Z clauses’).

4	Appointment

The Client appoints the Contractor to Provide the Works in accordance with this Agreement and the Contractor accepts such appointment.

5	Payment

The Client pays the Contractor in consideration of it Providing the Works and remedying the Defects the amount due in accordance with this contract.

EXECUTED AS A DEED and delivered on the date above written

| Executed (but not delivered until the date hereof) as a deed by Pirbright Innovations Limited (Company number 04394007) whose registered office is at The Pirbright Institute Ash Road, Pirbright, Woking, Surrey, GU24 0NF in the presence of: |  | ) ) |  |
| --- | --- | --- | --- |
| Director |  |  |  |
| Witness/Company Secretary/Director |  |  |  |

| Executed (but not delivered until the date hereof) as a deed by [CONTRACTOR] in the presence of: |  | ) ) |  |
| --- | --- | --- | --- |
| Director |  |  |  |
| Witness/Company Secretary/Director |  |  |  |

ANNEX 1

CONTRACT DATA

| Part one - Data provided by the Client |  |  |  |  |
| --- | --- | --- | --- | --- |
|  |  | General |  |  |
|  |  | The conditions of contract are the core clauses of the NEC4 Engineering and Construction Contract (June 2017 edition, together with the amendments set out in the January 2019, October 2020, and January 2023 amendments) and the clauses for Main Option A (Priced Contract with Activity Schedule), Dispute Resolution Option W2 (used in the UK when the Housing Grants, Construction and Regeneration Act 1996 applies) and Secondary Options X4 (Parent Company Guarantee), X7 (Delay Damages), X8 (Collateral warranties), X10 (Information Modelling), X11 (Termination by the Client), X13 (Performance Bond), X16 (Retention), Y(UK)2 (The Housing Grants, Construction and Regeneration Act 1996), Y(UK)3 (The Contracts (Rights of Third Parties) Act 1999), Z (Additional conditions of contract). |  |
|  |  | The works are as listed in Annex 3. |  |
|  |  | The Client is Pirbright Innovations Limited Name: Joan Shadwell Address for communications: The Pirbright Institute Ash Road, Pirbright, Woking, Surrey, GU24 0NF Address for electronic communications: joan.shadwell@BBSRC.ukri.org |  |
|  |  | The Project Manager is Currie & Brown UK Limited Name: James Morgan Address for communications: 40 Holborn Viaduct, London, EC1N 2PB Address for electronic communications: james.morgan@curriebrown.com |  |
|  |  | The Supervisor is Scitech Engineering Ltd Name: Jonathan Harriss Address for communications: Scitech House, Mill Lane, Godalming, Surrey, GU7 1EY, UK Address for electronic communications: Jonathan.Harriss@scitech.com The ‘principal designer’ for the purposes of the CDM Regulations is [The Contractor] The ‘principal contractor’ for the purposes of the CDM Regulations is the Contractor. The ‘principal designer’ for the purposes of the Building Regulations is The Contractor The ‘principal contractor’ for the purposes of the Building Regulation is the Contractor. |  |
|  |  |  | The Scope and Preliminaries document is in Annex 3. |  |
|  |  |  | The Preconstruction Information is in Annex 4. The Activity Schedule is in Annex 5. |  |
|  |  |  | The boundaries of the site are set out in Annex 3 and Annex 4. |  |
|  |  |  | The language of this contract is English. |  |
|  |  |  | The law of the contract is the law of England. |  |
|  |  |  | The period for reply is 2 weeks. The following matters will be included in the Early Warning Register: Time risks, cost risks, quality risks or any factors that impact the Works. Early warning meetings are to be held at intervals no longer than: [monthly] Risk reduction meetings will be done as EWN’s arise. |  |
| 2. |  | The Contractor’s main responsibilities | The key dates and conditions to be met are: Contract commencement 28th August 2024 RIBA Stage 4 Commencement 16th September 2024 Start on Site 18th March 2025 Completion and Handover 9th January 2026 Please refer to Annex 3 and Annex 4 |  |
| # 3. |  | Time |  |  |
|  |  |  | The starting date is 28 August 2024 |  |
|  |  |  | The access date is 18 March 2025 |  |
|  |  |  | The Contractor submits revised programmes at intervals no longer than one month. The completion date for the whole of the works is 9 January 2026. The Client is willing to take over the works before the Completion Date. |  |
| # 4. |  | Quality Management |  |  |
|  |  |  | The period after the Contract Date within which the Contractor is to submit a quality policy statement and quality plan is 4 weeks. The period between Completion of the whole of the works and the defects date is 8 January 2027. The defect correction period is 12 months. |  |
| # 5. |  | Payment |  |  |
|  |  |  | The currency of this contract is the pound sterling. |  |
|  |  |  | The assessment interval is monthly. |  |
|  |  |  | The interest rate is 2 % per annum above the base rate of the Bank of England. [The Contractor’s applications for payment shall always include the following details: The activity schedule linked to pricing document. Instructed compensation events indicating a percentage complete and associated costs. Any application for payment submitted without all the above information shall be invalid and have no contractual effect. |  |
| # 6. |  | Compensation Events |  |  |
|  |  | - the place where weather is to be recorded is the South Farnborough nr 2 weather station - the weather measurements to be recorded for each calendar month are: - the cumulative rainfall (mm) - the number of days with rainfall more than 5 mm - the number of days with minimum air temperature less than 0 degrees Celsius - the number of days with snow lying at 09:00 hours GMT - the weather measurements are supplied by the automated monitoring station at the location above. - the weather data are the records of past weather measurements for each calendar month which were recorded at South Farnborough nr 2 weather station. These are additional Compensation Events: Not Applicable |  |  |
| # 8. |  | Liabilities and insurance |  |  |
|  |  |  | The minimum amount of cover for insurance against loss of or damage to property (except the works, Plant and Materials and Equipment) and liability for bodily injury to or death of a person (not an employee of the Contractor) arising from or in connection with the Contractor Providing the Works for any one event is £10,000,000. |  |
|  |  |  | The minimum amount of cover for insurance against death of or bodily injury to employees of the Contractor arising out of and in the course of their employment in connection with the contract for any one event is £10,000,000. The minimum limit of indemnity for professional indemnity insurance caused by activity in connection with this Contract for any one event (as required under clause 84.3) is £5,000,000 (Five million pounds). Clause 87 refers. The insurance against loss of or damage to the works, Plant and Materials is to include cover for Plant and Materials provided by the Client for an amount of £10,000,000. |  |
| Resolving and avoiding disputes |  |  |  |  |
|  |  |  |  | The tribunal is: Adjudication |
|  |  |  |  | The Senior Representatives of the Client are: Name (1): Bryan Charleston Address for communications: The Pirbright Institute Ash Road, Pirbright,Woking, Surrey, GU24 0NF. Address for electronic communications: Bryan.charleston@pirbright.ac.uk |
|  |  |  |  | Name (2): [Joan Shadwell] Address for communications: The Pirbright Institute Ash Road, Pirbright,Woking, Surrey, GU24 0NF. Address for electronic communications: Not Applicable The Adjudicator nominating body is The Royal Institute of Chartered Surveyors. |
|  |  |  | X7: Delay damages Delay damages for Completion of the whole of the works are £1500 per day. X13: Performance bond - The amount of the performance bond is 10% of the Prices. X16: Retention The retention free amount is Nil. The retention percentage is 3%. The Contractor may not give the Client a retention bond. Y(UK)2: The Housing Grants, Construction and Regeneration Act 1996 The period for payment is 30 days after the date on which payment becomes due. Y(UK)3: The Contracts (Rights of Third Parties) Act 1999 term beneficiary [•] [•] Z: Additional conditions of contract - The additional conditions of contract are contained in Annex 2. |  |

Part two - Data provided by the Contractor

| 1. General |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | The Contractor is Name: [•] Address for communications: [•] Address for electronic communications: [•] |  |  |
|  |  |  |  |  | The fee percentage is [•] % |  |  |
|  |  |  |  |  | The working areas are [•]. |  |  |
|  |  |  |  |  | The key persons are |  |  |
|  |  | (1) |  | Name: [•] Job: [•] Responsibilities: [•] Qualifications: [•] Experience: [•] |  |  |
|  |  | (2) |  | Name: [•] Job: [•] Responsibilities: [•] Qualifications: [•] Experience: [•] |  |  |
|  |  | (3) |  | Name: [•] Job: [•] Responsibilities: [•] Qualifications: [•] Experience: [•] |  |  |
|  |  | (4) |  | Name: [•] Job: [•] Responsibilities: [•] Qualifications: [•] Experience: [•] |  |  |
| 2. The Contractor’s main responsibilities |  |  |  |  |  |  |  |
|  |  |  |  |  | The Scope provided by the Contractor for its design is referenced in Annex 3. |  |  |
| 3. | Time |  |  |  |  |  |  |
| 5. | Payment |  |  |  | The programme identified in the Contract Data is [•]. |  |  |
|  |  |  |  |  |  | The activity schedule including detailed analysis is in Annex 5. |  |  |
|  | 6. Resolving and avoiding disputes |  |  |  |  | The tendered total of the Prices is [•] |  |  |
|  |  |  |  |  |  | The Senior Representatives of the Client are: Name (1): Bryan Charleston Address for communications: The Pirbright Institute Ash Road, Pirbright, Woking, Surrey, GU24 0NF. Address for electronic communications: Bryan.charleston@pirbright.ac.uk |
|  |  |  |  |  |  | Name (2): Joan Shadwell Address for communications: The Pirbright Institute Ash Road, Pirbright, Woking, Surrey, GU24 0NF. Address for electronic communications: Joan.shadwell@BBSRC.UKRI.Org |

ANNEX 2

additional conditions of contract

Option Z: Additional conditions of contract

Z	The core clauses and clauses for Options are amended and added to as follows:

Core Clauses

11.	Identified and defined terms

11.2(1B)	Insert a new clause 11.2(1B):

"Beneficiary means

(i) any person providing finance in connection with the works (or any part thereof) and/or any person having or acquiring a mortgage or charge over the works or any part thereof; and/or

(ii) any purchaser acquiring a freehold or long leasehold interest in the whole or any part of the works; and/or

(iii) any tenant of the whole of any part of the site upon which the works are situated; and/or

(iv) the Biotechnology & Biological Sciences Research Council of Polaris House, North Star Avenue, Swindon, SN2 1UH.”

11.2(1C)	Insert a new clause 11.2(1C):

“The Building Regulations are the Building Regulations 2010 as amended from time to time”.

11.2(1D)	Insert a new clause 11.2(1D):

“The BR Principal Contractor is the entity identified in the Contract Data Part One as the principal contractor for the purposes of the Building Regulations or treated as appointed pursuant to regulations 11D(1) or 11D(2) or such replacement as may be appointed by the Client in connection with the works from time to time.”

11.2(1E)	Insert a new clause 11.2(1E):

“The BR Principal Designer is the entity identified in the Contract Data Part One as the principal designer for the purposes of the Building Regulations or treated as appointed pursuant to regulations 11D(1) or 11D(2) or such replacement as may be appointed by the Client in connection with the works from time to time.”

11.2(1F)	Insert a new clause 11.2(1F):

"The CDM Regulations are the Construction (Design and Management) Regulations 2015)."

11.2(1G) 	Insert a new clause 11.2(1G):

“The CDM Principal Contractor is the entity identified in the Contract Data Part One as the principal contractor for the purposes of the CDM Regulations or such replacement as may be appointed by the Client in connection with the works from time to time.”

11.2(1H)	Insert a new clause 11.2(1H):

“The CDM Principal Designer is the entity identified in the Contract Data Part One as the principal designer for the purposes of the CDM Regulations or such replacement as may be appointed by the Client in connection with the works from time to time.”

11.2(2)	Delete the second bullet point and replace with the following:

- “demonstrated that the works have successfully completed all of the tests specified in the Scope to be completed before Completion provided that, for the avoidance of doubt, where the works have not successfully completed any of the tests specified in the Scope due to a  fault in the design provided by the Client (other than in the design for the Contractor's Designed Portion) or due to an instruction from the Project Manager changing the Scope, this shall be treated as a compensation event under clause 60.1(14);

- provided all collateral warranties required under clause 26.4 and Option X8;

- provided copies of all documents and other deliverables and information which under this contract it is to supply by the Completion Date or as set out in the Scope, including all relevant as-built drawings and operation and maintenance manuals;

- corrected Defects which would have prevented the Client from fully and conveniently using the works without impediment, and Others from doing their work without impediment;

- where the Contractor is acting as the BR Principal Designer and/or the BR Principal Contractor, provided to the Client a written statement forming part of the completion notice issued pursuant to regulation 16(4) of the Building Regulations that the Contractor has fulfilled its duties as a principal contractor and/or principal designer (as applicable) under Part 2A of the Building Regulations, duly signed by the Contractor;

- where regulation 16(5) of the Building Regulations applies and where the Contractor is acting as the BR Principal Designer and/or the BR Principal Contractor, provided to the Client a written statement forming part of the notice issued pursuant to regulation 16(5) of the Building Regulations that the Contractor has fulfilled its duties as a principal contractor and/or principal designer (as applicable) under Part 2A of the Building Regulations, duly signed by the Contractor;

- provided to the Client the information required pursuant to or referred to in regulation 38 of the Building Regulations 2010 together with the fire strategy current at the Completion Date together with written and signed confirmation from the fire engineer that the information provided meets the requirements of regulation 38 to the extent applicable to the works.”

11.2(3A)	Insert a new clause 11.2(3A):

“Consents means any planning permission(s) referred to and/or included in any other document forming part of this contract, approval of reserved matters or details pursuant thereto, building regulations approval and any other consents, permissions, approvals, certificates and licences of a public or private nature that may be necessary for the execution of the works and if they are destroyed or damages the reinstatement of the works.”

11.2 (4)	Delete and substitute:

"The Contract Date is the date of the Agreement."

11.2(4A)	Insert a new clause 11.2(4A):

“The Contractor’s Team is the director and other personnel of the Contractor, including, without limitation, the key persons as set out in the Contract Data Part Two and the designated individuals who are tasked with managing the Contractor’s functions as the principal designer and/or principal contractor pursuant to Part 2A of the Building Regulations in accordance with regulations 11G(2) and 11H(2) of the Building Regulations respectively, to the extent that the Contractor is the BR Principal Designer or the BR Principal Contractor.”

11.2 (6)	At the end of the first bullet point insert:

“the Contractor’s obligations under this contract or”

11.2(7A)	Insert a new clause 11.2(7A) as follows:

"An Event of Force Majeure is an event or circumstance:

which is beyond a Party's reasonable control;

which such Party could not have reasonably provided against before entering into this contract;

which having arisen such Party could not reasonably have avoided or overcome;

which is not substantially attributable to the other Party; and

which prevents the relevant Party from complying with its obligations under the contract.

For the avoidance of doubt but without limitation an Event of Force Majeure shall not include any inability on the part of the Contractor (and all other persons employed or engaged by the Contractor on or in connection with the works or any part of them) for reasons beyond their control or which could not reasonably have been foreseen to secure such labour, goods or materials as are essential to the proper carrying out of the works.

The following will not constitute an Event of Force Majeure: labour strikes which are specific to the Site or the Contractor or any of its Subcontractors, and weather conditions regardless of severity.”

11.2(20A)	Insert the following new definitions:

“Group Company means a company or companies of the Client or its subsidiary or subsidiaries (of any tier) or holding company or companies (of any tier) or any subsidiary (of any tier) of any such holding company or companies and “subsidiary” shall bear the meanings given to it in section 1159 Companies Act 2006 but on the basis that the holding of not less than one quarter of voting rights shall be deemed to satisfy the condition in section 1159(1)(a).”

“Statutory Agreements means any agreement entered into or to be entered into by the Client affecting the Site or the carrying out of the works details of which have been or will provided to the Contractor prior to or after the date hereof.”

"Statutory Requirements means any statute, statutory instrument, regulation, rule or order made under any statute or directive having the force of law or any regulation or bye-law of any local authority or Statutory Undertaker which has any jurisdiction with regard to the works and any notices or permissions (excluding planning permissions) served or granted under any such statute, statutory instrument, regulation, rule or order or bye-law."

“Statutory Undertaker means any local authority or statutory undertaker or equivalent or relevant public body or any private utility service provider who executes work in pursuance of its statutory obligations and persons employed, engaged or authorised by it upon or in connection with that work.”

“Third Party Agreements means any agreement now or hereafter made between the Client and any third party relating to the works.”

11.2 (23)	Delete and substitute:

"Defined Cost for people directly employed by the Contractor, whether or not they are working in the working areas, is calculated using the rates in the Contract Data, Part 2.

Other than the rates for people directly employed by the Contractor referred to in the Contract Data, Part 2, the Defined Cost is an open market or competitively tendered price rate or amount. These items include, but are not limited to: subcontractors, plant, operators, supervisors, equipment, materials, surveying, testing (including laboratory analysis undertaken by the Contractor), security, specialist consultancy, any third party design, accommodation, welfare, utilities, fees due to public authorities, and travel and subsistence for people directly employed by the Contractor."

12		Interpretation and the law

12.4		Delete and replace with:

“Except where expressly provided in this contract, this contract constitutes the entire agreement between the Parties in connection with its subject matter and supersedes all prior representations, communications, negotiations and understandings concerning the subject matter of this contract.”

12.5		Insert a new clause 12.5:

“References to a statute or statutory instrument include any amendment or re-enactment of it from time to time and any subordinate legislation or code of practice made under it.”

12.6		Insert a new clause 12.6:

“The invalidity, illegality or unenforceability in whole or in part of any of the terms of this contract does not affect the validity of any other term or the remainder of any affected term.”

12.7		Insert a new clause 12.7:

“If the Contractor comprises two or more companies or other entities acting in joint venture, consortium, partnership, unincorporated grouping or otherwise, each such company or other entity is jointly and severally liable to the Client for the performance of the works and all of the Contractor’s obligations under this contract. The Contractor does not alter its composition or legal status without the prior consent of the Client. These companies or entities notify the Client of the identity of the company or entity who has authority to bind the Contractor and in the absence of such notification the Client is entitled to rely upon each such company or other entity as having authority to bind the Contractor and each of them.”

13		Communications

13.7		At the start of the clause delete ‘A’ and replace with: ‘Save in respect of notification and instruction under clauses 61.1. and 61.2, a’

13.8		In line 2 after “of contract” add “or any other reasonable reason”.

14.	The Project Manager and the Supervisor

14.5	Insert a new clause 14.5:

“No approval, acceptance, inspection, certificate, report or test carried out by or communicated by the Client or Project Manager or Supervisor to the Contractor or any Subcontractor or otherwise in connection with the works shall remove, diminish or otherwise affect the Contractor’s obligations or liabilities under this contract.”

14.6	Insert a new clause 14.6:

“The Client’s and the Contractor's respective rights and remedies under this contract are cumulative and do not exclude any rights or remedies provided by law or otherwise.”

17.	Ambiguities and inconsistencies

17.2	Delete and replace with the following:

“17.2.1	Save to the extent expressly provided for in the Scope, the Client makes no warranty as to the accuracy, consistency or sufficiency, legality or feasibility of any information contained within the documents that are part of this contract.

17.2.2	The Contractor has thoroughly examined each part of the contract documents and satisfied itself that there are no mistakes, inaccuracies, omissions, inconsistencies, discrepancies, divergencies or conflicts within or between any documents that are part of this contract.

17.2.3	Where such mistakes, inaccuracies, omissions, inconsistencies, discrepancies, divergences or conflicts within or between any documents that are part of this contract may subsequently come to light, the Contractor shall immediately give notice with appropriate details to the Project Manager, who shall issue instructions in that regard but such instructions shall not be treated as a compensation event.

17.2.4	Any mistake, inaccuracy, omission, inconsistency, discrepancy, divergence or conflict within or between the documents that are part of the contract shall be corrected by the Contractor but without any entitlement to claim any additional payment (whether by way of an addition to the Prices or otherwise) and/or without any entitlement to claim for any delay to the Completion Date and/or to any Key Date and/or without constituting a compensation event.”

19.	Prevention

19.1		Delete and replace with the following:

"If a Party is or will be prevented from performing any of its obligations under this contract by an Event of Force Majeure (the "affected Party") the affected Party shall give notice to the other Party and by copy to the Project Manager of such event and shall specify the obligations the performance of which is or will be prevented.  Such notice shall be given as soon as reasonably practicable and in any event within 14 days after the affected Party became aware or should have become aware of the Event of Force Majeure."

Insert new clauses 19.2 to 19.4 as follows:

19.2	"From the date of receipt by the other Party and the Project Manager of the notice given pursuant to clause 19.1 the affected Party shall be excused performance of such obligations as are affected by the Event of Force Majeure for so long as such event prevents the affected Party from performing the obligations, provided that each Party has used reasonable endeavours to minimise the effects of any such delay in performance of the obligations.

19.3	If the affected Party is the Contractor the Project Manager gives an instruction to the Contractor stating how they are to deal with the event.

19.4	The affected Party shall give notice to the other Party and by copy to the Project Manager when it ceases to be affected by the Event of Force Majeure.

20	Providing the Works

Insert new clauses 20.2, 20.3, 20.4, 20.5, 20.6 and 20.7 as follows:

“20.2	The Contractor is deemed to have inspected and examined the Site and its surroundings, the form and nature of the Site, the extent, nature and difficulty of the work and materials necessary for the completion of the works, the means of communication with and restrictions of access to the Site, the accommodation they may require and in general to have obtained for themselves all necessary information as to risks, contingencies, and all other circumstances influencing and affecting the works (and to have satisfied themselves in respect of the same). Insofar as clause 60.1 does not apply, the Contractor is not entitled to any change to the Completion Date or any Key Date or to any change to the Prices on grounds of any misunderstanding or misinterpretation of any such matter and nor is such misunderstanding or interpretation a compensation event pursuant to clause 60.1 nor is the Contractor to be released from any of the risks accepted or obligations undertaken by them under this contract on the ground that they did not or could not have reasonably foreseen any matter which might affect or have affected the execution of the works.

20.3	The Contractor has satisfied themselves as to the correctness and sufficiency of the Prices and unless otherwise stated in this contract, the Prices cover all the Contractor's obligations under and in connection with this contract and all things necessary for the proper execution and Completion of the works and completing the design of the whole of the works in accordance with the Scope and the remedying of any Defects.

20.4	The Contractor warrants and undertakes to the Client that the works will when completed comply with the Scope and with the Statutory Requirements and any Consents.

20.5	The Contractor warrants and undertakes that the works have been or will be carried out and completed using the best practice in a good and workmanlike manner and using only good quality and sound materials of satisfactory quality and consistent with the intended use of the works.

20.6	The Contractor warrants and undertakes that the works comprise or will comprise only materials and goods which are new and of good and satisfactory quality and all workmanship, manufacture or fabrication will be to the standards necessary for completion of the works in accordance with this contract, save for free issue material provided by the Client and site won material from the works.

20.7	The Contractor is responsible for appointment (where required), management and performance of any Statutory Undertakers who are required to carry out work in relation to the works.  In particular (but without implying any limitation) the Contractor is responsible for any delays caused by the carrying out by a Statutory Undertaker of work in pursuance of its statutory obligations, or any failure to carry out such work.”

21.	The Contractor's design

21.1		Delete clause 21.1 and replace with the following:

“21.1.1 	Notwithstanding any approval by the Project Manager under clauses 21.2, 21.3 and/or 23.1:

(a) the Contractor shall be fully responsible in all respects for the entire design of the works and shall adopt and take responsibility for any design work in relation thereto may be carried out or which may have been carried out by professional consultants or specialist subcontractors or by any other person engaged by the Client. Any reference to the design which the Contractor has prepared or shall prepare or issue for the works shall include a reference to any design which the Contractor had adopted or shall adopt or has caused or shall cause to be prepared or issued by others;

(b) The Contractor accepts entire responsibility for the design of the works, including all design work prepared before or after the date hereof (and whether or not carried out by or on behalf of the Client or the Contractor);

(c) The Contractor accepts entire responsibility for any design work contained in the Scope (and whether or not carried out by or on behalf of the Client or the Contractor);

(d) Without prejudice to the foregoing, the Contractor accepts entire responsibility for any design work contained in the ‘Enhanced RIBA Stage 3’ level of design’ (and whether or not carried out by or on behalf of the Client or the Contractor); and

(e) Notwithstanding any other provision of this contract the Contractor accepts entire responsibility for the design and integration of the design for all parts of the works and for any mistake, inaccuracy or discrepancy in the design for the works and is not entitled to any compensation event or additional payments (whether by way of addition to the Prices or as damages for breach of contract or tort (including negligence)) and/or for any change to the Completion Date and/or any Key Date in respect of the same or any actions required to be taken by the Contractor to deal with the same.

21.1.2 	The Project Manager’s (or Client’s) acceptance of the Contractor’s design (or any part of it) does not change or remove the Contractor’s responsibility to Provide the Works or its liability for the entire design of the works.

21.1.3 	The Contractor warrants and undertakes to the Client that the works will when completed comply with any performance specifications or requirements included or referred to in the Scope  or in any instruction changing the Scope and will be adequate for the intended use of the works.

21.1.4 	The Contractor shall ensure that the various elements of the design for the works are properly co-ordinated and integrated with each other.

21.1.5 	The warranties and undertakings contained in this clause 21.1 shall be without prejudice to any warranties implied by common law or statute.”

21.2		In line 3 delete “applicable law” and replace with “Statutory Requirements”.

21.4		Insert a new clause as follows:

"The Contractor's obligation in respect of the entire design of the works is to use the standard of skill, care and diligence to be expected of an appropriately qualified design and build contractor who hold themselves out as being competent in designing works of a similar size and scope to the works."

22.	Using the Contractor's design

22.1		Delete and substitute clause 22.1 as follows:

"The Contractor hereby grants to the Client with full title guarantee to the extent required by the Client for any purpose whatsoever connected with the works including (without limitation) the construction, completion, maintenance, dismantling, reassembly, repair, alterations and adjustment of the works a royalty-free irrevocable non-exclusive licence to copy use and reproduce all drawings, details, plans, sketches, manuals, models, estimates, analyses, budgets, specifications, schedules, reports, calculations, computer programs, software, graphical and non-graphical information  and other materials and the designs contained in them (the “Documents”) which have been or are hereinafter written originated or made by or through the Contractor in the course of performing their duties in connection with the works, provided always that the Contractor shall have no liability under this clause 22.1 other than for the use for which such materials were originally prepared. Such licence shall carry the right to grant sub-licences and shall be freely transferable to third parties.”

Add new clauses 22.2 – 22.4 as follows:

“22.2		If the use of the Documents for the purposes of the works and/or completed works is found to infringe the rights of any third party then the Contractor shall be responsible for all costs, damages and expenses incurred or to be incurred by the Client.

22.3 		Without prejudice to any other obligations under this contract to provide documents (or other materials) or copies thereof to the Client, the Contractor shall upon the written request of the Client provide to the Client copies of the Documents and such other information in relation to the works, as the Contractor can reasonably supply.

22.4		The Contractor irrevocably waives, and procures that each of its Subcontractors and suppliers irrevocably waives, any rights it or they may have under Chapter IV (Moral Rights) of Part I of the Copyright, Designs and Patents Act 1988 in relation to the Documents.”

24. 	People

Insert new clauses 24.3 – 24.5 as follows:

“24.3		The Contractor shall at all relevant times engage an adequate number of competent and suitably qualified and experienced personnel in the performance of the works and allocate adequate resources to enable the Contractor to carry out and complete the works in satisfaction of the competence requirements of the CDM Regulations and Part 2A of the Building Regulations.

24.4		The Contractor shall not remove any of the persons comprised in the Contractor’s Team or any permitted replacement without the Client’s prior written approval. For the avoidance of doubt, it shall be reasonable for the Client to withhold approval on the ground that the substitution of the relevant person(s) will result in the Contractor ceasing to satisfy the competence requirements of either the CDM Regulations or Part 2A of the Building Regulations as applicable to the duties thereunder to the discharged by the Contractor in the performance of the whole or any part of the works.

24.5		The Contractor shall remove any persons in the Contractor’s Team or any permitted replacement if reasonably required to do so by the Client and replace such personnel with other suitably qualified and experienced personnel at no further cost to the Client and subject to the Client’s prior approval under clause 24.4.

26.	Subcontracting

26.1A	Insert a new clause 26.1A as follows:

“26.1A.1 	The Contractor shall not sub-contract the whole of the works.

26.1A.2 	The Contractor shall not without the prior written consent of the Client (which consent shall not be unreasonably withheld or delayed) sub-contract any portion of the works.

26.1A.3 	Subject to clause 26.1A.2, the Client may attach to any such consent such conditions as they may reasonably require, and the Contractor shall comply with or procure compliance with such conditions.

26.1A.4 	Where, pursuant to clause 26.1A.2, the Contractor seeks the written consent of the Client in relation to a subcontractor or sub-consultant providing works or services to enable the Contractor to discharge its duties as the principal designer and/or the principal contractor pursuant to the CDM Regulations or Part 2A of the Building Regulations (where applicable) whether in an advisory capacity or otherwise, or enables the Contractor to satisfy the whole or any part of the competence requirements in the CDM Regulations or Part 2A of the Building Regulations imposed on the Contractor as referred to in clause 27.10.1, the Contractor shall notify the Client of this fact as part of the Contractor’s application for consent.

26.1A.5 	The Contractor shall satisfy itself that the person to whom the Contractor sub-lets the design and/or the construction of any part of the works has the skills, knowledge and experience and, if they are an organisation, the organisational capability, necessary to fulfil the role that they are to undertake, in a manner that:

(a) with regard to the CDM Regulations, secures the health and safety of any person affected by the works for the purposes of complying with the duties of a designer or contractor, as applicable, under the CDM Regulations and any other relevant Statutory Requirements prior to their engagement; in so satisfying itself the Contractor shall seek and take into account the advice of the CDM Principal Designer and the CDM Principal Contractor to the extent that the Contractor is not responsible for those roles under this contract; and

(b) with regard to Part 2A of the Building Regulations, ensures compliance with the duties of a designer or contractor, as applicable, under the aforementioned Part 2A of the Building Regulations and, in so satisfying itself the Contractor shall seek and take into account the advice of the BR Principal Designer and the BR Principal Contractor to the extent that the Contractor is not responsible for those roles under this contract.”

26.2		Delete the second sentence and replace with the following:

“The Contractor shall in relation to any subletting of any portion of the works (or the design thereof):

- procure that the relevant sub-contract shall, in all respects be compatible with the terms of this contract;

- procure that all relevant sub-contracts shall be executed and delivered as a deed;

- provide to the Client on demand certified copies of any sub-contract (save for particulars of the cost of such sub-contract works).”

26.3		Delete ‘or’ from the end of the penultimate bullet point, and insert at the end of the clause:

- “the proposed Subcontractor has not been procured in accordance with the Scope,

- the proposed subcontract conditions are not consistent with the Scope,

- the proposed subcontract works represent too large a proportion of the total works, or

- the proposed subcontract does not include an obligation on the Subcontractor to novate or otherwise transfer the subcontract to the Client if required to do so in accordance with the contract.”

26.4		Insert a new 26.4 as follows:

“The Contractor (on the Client’s request) shall procure from any Subcontractor appointed by the Contractor in connection with the works a deed or deeds of collateral warranty within four weeks of the date of such request in favour of the Client or any Beneficiary in the form set out in Schedule 2 to the Additional Conditions of Contract.”

26.5		Insert a new 26.5 as follows:

“In no case shall any consent under this clause 26 or any sub-contracting in any way affect the Contractor’s obligations under any other provision of this contract including, without limitation to the foregoing, the Contractor’s duties under Part 2A of the Building Regulations, and the Contractor shall be responsible for the acts and omissions of any subcontractor as if they were those of the Contractor.”

27.	Other responsibilities

27.5		Insert new clause 27.5 as follows:

“Where necessary to comply with their obligations under this contract and to Provide the works in accordance with the Scope, the Contractor shall as soon as reasonably practicable make all applications for any necessary permissions, licences and approvals for the purposes of the works, save in relation to any temporary traffic orders which shall be procured by the Client.”

27.6		Insert new clause 27.6 as follows:

“Notwithstanding the Contract Date, any work forming part of the works (including any design, enabling, temporary or other preliminary or permanent works) carried out by or on behalf of the Contractor prior to the Contract Date shall be subject to the terms of this contract. Where the Contractor has subcontracted, delegated or entered into any arrangement in respect of the carrying out of the works (before or after the Contract Date), the Contractor shall remain wholly responsible for carrying out and completing the works in all respects as if they had been carried out by the Contractor.”

27.7	Insert a new sub-clause 27.7:

“The Contractor does not use or specify for use in relation to the works and does not authorise or approve the specification or use by Others of any products or materials not in conformity (or which incorporate substances which are not in conformity) with relevant British or European Standards or Codes of Practice or which at the time of specification or use are widely known to builders or designers of the relevant discipline within the construction industry to be dangerous or hazardous to health and safety or deleterious to the integrity or durability of buildings and/or for other structures and/or finishes in the particular circumstances in which they are used or which are otherwise not in accordance with Statutory Requirements and/or the guidelines contained in the edition of the publication ‘Good Practice in the Selection of Construction Materials’ published by The British Council for Offices current at the date of this contract.

If in the performance of its duties under this contract, the Contractor becomes aware of it or any other person has specified or used, or authorised or approved the specification or use by Others of, any such products or materials, the Contractor notifies the Client in writing forthwith. This sub-clause does not create any additional duty for the Contractor to inspect or check the work of Others which is not required by this contract.”

27.8	Insert new clause 27.8 as follows:

“The Contractor shall at all times take all reasonably practicable precautions to prevent any public or private nuisance or other interference with the rights of any adjoining or neighbouring landowner, tenant, or occupier or any Statutory Undertaker arising out of the carrying out of the works or of any obligation under clause 44 and will assist the Client in defending any action or proceedings which may be instituted in relation to the same. The Contractor is responsible for and indemnifies the Client from and against any and all expenses, liabilities, losses, claims and proceedings whatsoever to the extent that the same arises or results from any such nuisance or interference except only where such nuisance or interference is the result of the carrying out of the works in accordance with the contract and which could not have been avoided by the Contractor using all reasonably practical precautions in accordance with this clause.”

27.9	Insert new sub-clause 27.9 as follows:

27.9.1	“The Contractor:

- performs all the functions and duties and exercises the powers of the ‘principal contractor’ as defined in the CDM Regulations and the ‘principal contractor’ as defined in the Building Regulations,

- to the extent that it is in control of the Site or any part of it within the meaning of section 4 of the Health and Safety at Work etc Act 1974 keeps the Site, the access thereto and the egress therefrom safe and without risk to the health of persons using it, and

- co-operates at all times, so far as is reasonably practicable, with all parties having health and safety responsibilities on or adjacent to the Site for the effective discharge of those responsibilities.”

27.10	Insert new sub-clause 27.10 as follows:

“27.10	Competence

27.10.1 	With regard to the competence requirements imposed in the CDM Regulations and Part 2A of the Building Regulations, it is a condition of the contract that:

(a) 	the Contractor has the requisite skills, knowledge and experience and, if the Contractor is an organisation, the organisational capability necessary to fulfil the competence requirements of the role(s) of contractor and designer and, to the extent that the Contractor is responsible for providing such roles under the contract, principal designer and principal contractor for the works pursuant to the CDM Regulations and Part 2A of the Building Regulations, and

(b) 	the information provided by the Contractor and the representatives given by the Contractor in making its assessment of the competence of the Contractor are accurate.

27.10.2	The Contractor shall immediately notify the Client on:

(a)	the occurrence of any disciplinary action at any time during the performance of the works against the Contractor or any of its personnel which could raise concerns with regard to the satisfaction of the applicable competence requirements under the CDM Regulations or Part 2A of the Building Regulations, or

(b) 	the Contractor ceasing to satisfy the competence requirements under the CDM Regulations or Part 2A of the Building Regulations as a contractor or designer or, to the extent that the Contractor is responsible for performing such roles under the contract, the principal designer or the principal contractor pursuant to the CDM Regulations and Part 2A of the Building Regulations, in the performance of the whole or any part of the works, whether by virtue of a change in personnel or for any other reason.

27.10.3	The Client may at any point during the term of the contract require the Contractor to provide details and evidence of the competence (with regard to skills, knowledge and experience) of any of the Contractor’s employees and agents, and all other persons employed or engaged by the Contractor on or in connection with the works or any part of them, to ensure that such persons have the requisite skills, knowledge and experience and, for any organisations employed or engaged on or in connection with the works or any part of them, the organisational capability necessary to fulfil the role(s) of the applicable dutyholder pursuant to the CDM Regulations and Part 2A of the Building Regulations, and the Contractor agrees to provide all reasonable assistance to the Client and any person authorised by the Client, as may be required from time to time in this regard.

27.10.4	A breach of clause 27.10.1 or clause 27.10.3 or the occurrence of a reason to notify the Client of any of the circumstances set out in clause 27.10.2 shall entitle the Client to issue a notice under clause 90.1 and entitles the Client to terminate the Contractor’s employment under the contract.”

27.11	Insert a new sub-clause 27.11:

“27.11	Dutyholders (Part 2A of the Building Regulations)

27.11.1 	“Each Party undertakes to the other that in relation to the works and the Site they will duly comply with their respective duties under Part 2A of the Building Regulations. In particular but without limitation:

27.11.1.1	where the Contractor is not the BR Principal Designer, the Client shall appoint the BR Principal Designer to carry out those duties of a principal designer pursuant to Part 2A of the Building Regulations and, where the Contractor is not the BR Principal Contractor, the Client shall appoint the BR Principal Contractor to carry out those duties of a principal contractor pursuant to Part 2A of the Building Regulations;

27.11.1.2 	where the Contractor is and while he remains the BR Principal Designer, he shall comply with the duties of a principal designer pursuant to Part 2A of the Building Regulations;

27.11.1.3	where the Contractor is and while he remains the BR Principal Contractor, he shall comply with the duties of a principal contractor pursuant to Part 2A of the Building Regulations;

27.11.1.4 	the Contractor shall comply with the duties of a designer and a contractor under Part 2A of the Building Regulations;

27.11.1.5	whether or not the Contractor is the BR Principal Contractor or the BR Principal Designer, compliance by the Contractor with his duties under Part 2A of the Building Regulations shall not entitle the Contractor to apply for an extension of time and shall not entitle the Contractor to any adjustment to the Prices including any loss and expense save as expressly provided to the contrary in clauses 60 to 66 (inclusive).

27.11.1.6	if the Client appoints a replacement for the BR Principal Designer or the BR Principal Contractor, the Client shall immediately upon that appointment notify the Contractor with details of the new appointee.”

27.12	Insert new clause 27.12 as follows:

"The Contractor shall ensure that there is no trespass over any adjoining or neighbouring property arising out of the works or of any obligation under clause 44. If the carrying out of the works or of any obligation under clause 44 is likely to necessitate interference with the rights of adjoining or neighbouring owners or occupiers, then the Contractor, at no cost to the Client, obtains the prior written agreement of such owners and/or occupiers to the work, and such agreement will be subject to the approval of the Client before execution. The Contractor shall comply in every respect with any conditions in any such agreement."

27.13	Insert new clause 27.13 as follows:

“The Contractor shall at their own cost use reasonable endeavours to ensure that the Site is cleared of any rubbish, refuse or waste placed on or emanating from the Site at reasonable intervals and/or as often as may be necessary and that the Site is left clean and tidy immediately upon Completion of the works.’’

27.14	Insert new clause 27.14 as follows:

“27.14.1 	The Client and the Contractor undertake that they will not do, and warrant that prior to the Contract Date they have not done, the following:

(a) offer, promise or give, or accept, agree to accept or receive any gift or financial or other advantage of any kind as an inducement or reward for doing or not doing (or for having done or not having done) any act in relation to the obtaining or execution of this contract or any other agreement between the Parties; or

(b) offer, promise or give, or accept, agree to accept or receive any gift or financial or other advantage of any kind as an inducement or reward for showing or not showing favour or disfavour to any person in relation to this contract or any other agreement between the Parties.

27.14.2    	Each Party will, in relation to this contract, abide by and comply with all applicable laws relating to anti-bribery and anti-corruption including, without limitation, the UK Bribery Act 2010 and the U.S. Foreign Corrupt Practices Act 1977.

27.14.3    	Each Party warrants to the other that at the effective date of this contract there is no proceeding (pending or threatened) relating to any fraud, bribery or corruption which to its knowledge may have a material adverse impact on this contract or its ability to comply with its obligations under this contract."

27.15	Insert new clause 27.15 as follows:

“27.15.1 	The Contractor shall perform its obligations under this contract in such a manner as not to constitute, cause or contribute to any breach by the Client of its obligations under any Third Party Agreement and/or any other agreement entered into by the Client in connection with the works, provided that copies or relevant extracts of such agreements have previously been provided by the Client to the Contractor.  If any Third Party Agreements (or relevant parts of the same) are provided to the Contractor after the date hereof: (a) the Contractor shall (subject to the Contractor having a reasonable opportunity to review such Third Party Agreements or relevant parts thereof) so carry out the works with due regard to such Third Party Agreements so that (so far as is reasonably attainable) no action or omission by the Contractor causes or contributes towards a breach of the duties and obligations of the Client under such Third Party Agreements; and (b) to the extent that any duties or obligations within the relevant Third Party Agreement(s) impose additional or more onerous obligations on the Contractor than would otherwise have been the case under the terms of this Contract or the Scope, then this shall be treated as a compensation event.

27.15.2 	The Contractor indemnifies the Client against any claims, proceedings, compensation and costs due to a breach of clause 27.15.1.

27.15.3 	For the avoidance of doubt the Third Party Agreements forming part of the contract are as follows: [Not Applicable].

27.16	Insert new clause 27.16 as follows:

“27.16 	The Contractor shall, without any entitlement to claim any additional payment (whether by way of an addition to the Prices or otherwise) and/or without any entitlement to claim for any delay to the Completion Date and/or to any Key Date and/or without any of the following constituting a compensation event:

27.16.1 	comply with the obligations on the part of the Client under any Statutory Agreement and/or Consent in so far as they relate to the carrying out and completion of the works and that have been listed in the Scope;

If any Statutory Agreement and/or Consent (or relevant parts of the same) are provided to the Contractor after the date hereof:

(a) the Contractor shall (subject to the Contractor having a reasonable opportunity to review such Statutory Agreement and/or Consent or relevant parts thereof) so carry out the works with due regard to such Statutory Agreement and/or Consent so that (so far as is reasonably attainable) no action or omission by the Contractor causes or contributes towards a breach of the duties and obligations of the Client under such Statutory Agreement and/or Consent; and

(b) to the extent that any duties or obligations within the relevant Statutory Agreement(s) and/or Consent(s) impose additional or more onerous obligations on the Contractor than would otherwise have been the case under the terms of this contract or the Scope, then this shall be treated as a compensation event.

27.16.2 	obtain and/or satisfy all those consents that the Scope states that the Contractor is responsible for obtaining and that are necessary from any relevant authority for the carrying out of works required under any Statutory Agreement and/or Consent; and

27.16.3 	carry out all works in full compliance with the requirements of any relevant authority under any Statutory Agreement and/or Consent.”

27.16.4 	For the avoidance of doubt the Statutory Agreements and/or Consents forming part of the contract are as follows: Refer to Annex 4 – Appendix 5 Preconstruction Information with particular reference to MOPA Decision Notice and MOPA_Pirbright_DESIGN CODE-01s

28.	Assignment

28.1		Delete clause 28.1 and replace with the following:

“28.1		The Client shall be entitled to assign any and all of the benefits of this contract on two occasions without the consent of the Contractor provided that an assignment by the Client to a Group Company or to or from any party providing finance in connection with the works shall be excluded from this limit of two occasions. Any further right to assign shall be subject to the prior written approval of the Contractor.

28.2	Insert new clause 28.2 as follows:

“The Contractor is not entitled to assign the benefit of this contract.”

28.3		Insert new clause 28.3 as follows:

“The Contractor agrees that it shall not at any time assert that any permitted assignee of this contract is precluded from recovering any loss resulting from any breach of this contract by reason that such assignee is not an original party to this contract or that the original party or a prior assignee has suffered no loss or a different loss from that suffered by the assignee.’’

29	Disclosure

29		Delete clause 29 and replace with:

“29.1		The Contractor does not, without the prior written approval of the Client:

(a) take or permit to be taken any photographs of the works for use in any publicity or advertising; and/or

(b) publish or authorise the publication of any articles, photographs or other illustrations of the works.

29.2 		The Contractor and its agents and employees do not, without the prior written approval of the Client, disclose to any other person (other than any person to whom disclosure must be made in order for the Contractor to fulfil their duties under this contract, the Contractor’s lawyers, auditors and other professional advisers subject to a duty of confidence or as may be required by statute or by a court of competent jurisdiction) any information about the works or otherwise including, without limitation, any information about the Client or their business and/or any information about any person in whose favour the Contractor is obliged under this contract to execute a warranty or their businesses and/or any information relating to methods and techniques of construction proposed by the Client  and/or any financial information relating to the works and/or the contents of any drawings details documents or other information prepared by or on behalf of the Client, nor does the Contractor exploit any such information for their own benefit or the benefit of any other person. The Contractor’s obligations under this clause 29 do not apply to any information which is already in the public domain or to any information which came to them otherwise than in connection with their involvement in relation to the works except where such entry into the public domain or such coming to the Contractor was as a result of a breach of any contractual obligation by the Contractor or any other person for whom the Contractor is responsible.

29.3  		The Contractor ensures that similar provisions are included in their contracts with Subcontractors and shall enforce such provisions.”

30. 	Starting, Completion and Key Dates

30.4		Insert new clause 30.4 as follows:

"The Contractor proceeds regularly and diligently to Provide the Works in accordance with this contract and uses all reasonable endeavours to prevent and/or reduce any delay in the progress of the works."

30.5		Insert new clause 30.5 as follows:

“30.5		The Project Manager at their discretion may certify Completion notwithstanding that:

(a) minor items of work and/or minor defects remain to be completed; and/or

(b) any planting or landscaping works remain to be completed but cannot be completed until the next planting season,

in which event details of such incomplete work and/or minor defects and/or landscaping planting works shall be included in an appropriate schedule and issued forthwith to the Contractor who shall complete the works and rectify the defects under 30.5(a) as soon as possible but in any case not later than 14 days from the date of Completion, and the works under 30.5(b) not later than the date specified by the Project Manager in such schedule.  Where work and/or rectification of defects under clauses 30.5(a) and/or (b) have not been completed within the time period stated under this clause 30.5 the Client may employ others to carry out such work and/or rectify any minor defects and deduct the cost of the same from any monies due and owing to the Contractor (or the Client shall be entitled to recover such cost from the Contractor as a debt).”

31.	The programme

31.3		In sub-clause 31.3 after ‘Scope’ in bullet 4 insert ‘or other requirement of the contract’.

34.	Instructions to stop or not to start work

34.1		Add at the end of this clause as a new hanging paragraph:

“During any period in which any work is so stopped or not started, the Contractor keeps secure and protects the Site and the works and all Equipment, Plant and Materials against any deterioration, loss, damage or theft.”

41.	Tests and inspections

41.7		Add a new clause 41.7:

“The Contractor allows the Client and any Beneficiary and their respective representatives to inspect the works at any reasonable time, provided they give the Contractor reasonable notice prior to any such inspection.”

46.	Uncorrected Defects

46.1		In line 2 after “period,” delete the remainder of the clause and replace with:

“the Client shall be entitled to employ other people to correct the Defect and all costs consequent thereon or incidental thereto shall be determined by the Project Manager and shall be paid by the Contractor.”

50.	Assessing the amount due

50.3(A)	Insert new clause as follows:

"All amounts due under this contract are exclusive of any VAT that may be due to the Contractor in respect of the works.  The Client shall pay the amount of any VAT properly chargeable in respect of VAT provided that the Contractor provides the Project Manager with a corresponding VAT invoice and any other documentation reasonably necessary in order to permit such payment to be properly made."

50.7		Insert a new clause 50.7 as follows:

“In the event of the Contractor becoming insolvent (as defined within section 113 of the Housing Grants, Construction and Regeneration Act 1996), no further sum shall become due to the Contractor under this contract other than any amount that may become due to them under clause 93 and the Client need not pay any sum that has already become due either:

50.7.1	insofar as the Client has given or gives a pay less notice under clause Y2.3; or

50.7.2	if the Contractor, after the last date upon which such notice could have been given by the Client in respect of that sum, has become insolvent within the meaning of section 113 of the Housing Grants, Construction and Regeneration Act 1996.”

51.	Payment

51.4	Delete "and is compounded annually".  Insert at the end: "The Parties agree that the provisions of this contract for the payment of the interest rate constitutes a substantial remedy for late payment of any amount due under this contract in accordance with s.8(2) of the Late Payment of Commercial Debts (Interest) Act 1998."

60.	Compensation events

60.1	In line 1, after the words “compensation events” insert: “except where the event in question is caused by the negligence, fault, error, breach of contract, breach of statutory duty or omission of the Contractor or any of its employees or agents or a Subcontractor or any person for whom the Contractor or a Subcontractor is responsible”.

60.1 (1) 	Insert a new bullet point at the end of clause 60.1(1) as follows:

“where it is stated elsewhere in this contract that the instruction is not a compensation event.”

60.1 (5)	Add “(save for Statutory Undertakers)” after “Others” in line 1.

60.1 (6)	Insert “except where such communication relates to a notice under clause 17 of this contract.”

60.1 (9)	In line 1 after “Project Manager” add “unreasonably” and in line 2 delete “for a reason not stated in this contract”.

60.1 (12)	Delete and insert “Not Used”.

60.1 (13)	Delete and insert “Not Used”.

60.1 (18)	Delete and substitute with:

“A breach of contract or other act of prevention by the Client or any person for whom the Client is responsible, the Project Manager or the Supervisor which is not one of the other compensation events in this contract.”

60.1(19)	Delete and substitute:

"The Contractor is or will be prevented from performing any of its obligations under this contract by an Event of Force Majeure. The Contractor shall be entitled to claim an extension of time but shall not be entitled to recover additional cost in respect of any such prevention."

60.1 (20)	Delete and insert “Not Used”.

60.3		Delete and insert “Not Used”.

60.4	Insert new clause 60.4 as follows:

“The Contractor takes reasonable steps to mitigate the effects of any compensation event.”

61.	Notifying compensation events

61.4	Delete “arises from a fault of the Contractor” and replace with: "arises from a fault, error, omission, negligence, default, breach of contract or breach of statutory duty of the Contractor or any of its employees or agents or of any Subcontractor or their employees or agents."

61.4	Delete the final sentence.

62.	Quotations for compensation events

62.6		Delete the third sentence.

63.	Assessing compensation events

63.1	Insert at the end:

“In assessing any change to the Prices, the Project Manager takes into account the effect of any act, omission, breach or other default of the Contractor which contributes to an increase in the cost of providing the works and makes an appropriate deduction from the assessment of any change to the Prices.”

63.3A   	Insert a new clause 63.3A as follows:

“Assessments are, in addition, based on the Contractor complying with the time periods for submitting or replying to a communication set out in clauses 61 and 62.  If the Contractor does not comply then they  are not entitled to any adjustment to the Prices or to any change to a Key Date or the Completion Date for a compensation event in respect of the period for which the submission or reply to a communication is delayed.”

63.7	Add at the end of this clause the following:

“and had taken such actions as the Project Manager (acting reasonably) decides should have been taken to mitigate, avoid or reduce any increase to the total of the Prices or any delay to Completion or any impairment of the performance of the works in use”.

64.	The Project Manager’s assessments

64.4	Delete the third sentence.

73.	Objects and materials within the Site

73.3		Insert a new clause 73.3 as follows:

"Notwithstanding any other provision in this contract to the contrary, all recyclable materials and any materials produced or extracted as a by-product of the works (including materials stockpiled within the boundaries of the site on the Contract Date) remain the property of the Client provided the Contractor can use such materials on the Site in connection with the works."

80.	Client’s liabilities

80.1	Delete the third bullet point.

81.   Contractor’s liabilities

81.1 	Add to the end of the clause, “Any other liabilities not stated to be Client’s liabilities are Contractor’s liabilities”.

82.	Recovery of costs

82.	Delete clause 82 and replace with the following:

“82.1 		The Contractor indemnifies keeps indemnified and holds harmless the Client from and against all suits, actions, administrative proceedings, claims or demands brought or made, and any and all losses, damages, costs, charges and expenses of whatsoever nature incurred or suffered or arising directly or indirectly as a result of any:

(a) personal injury to or death of any person arising out of or in the course of or by reason of the design, execution and completion of the works and the remedying of any Defects;

(b) event which is at its risk; or

(c) loss of or damage to any property, other than the works which is due to or arises out of or in consequence of the performance by the Contractor of, or the failure by the Contractor to perform, any of its obligations under the contract except to the extent that the same results solely from any act or neglect of the Client.

82.2 		For the purposes of clause 82.3 the following definitions apply:

“Environment” means in respect of onshore and offshore, any and all living organisms (including man), ecosystems, property and the media of air (including air in buildings, natural or manmade structures, below or above ground), water (including drains and sewers), land (including under any water as described above and whether above or below the surface).

“Environmental Law” means any rule of common law, statute, code of practice, circular, guidance note, by-law or regulation having the force of Law or any consent, license, permit, order notice, recording, registration or judgement whose breach can give rise, whether immediately or not, to criminal, civil or administrative, damages, sanctions or penalties for the failure to meet obligations relating to the presence, release, spillage, treatment, handling, deposit, escape or other mode of existence of any substance, the carrying out of any activity, or the existence of any condition or any phenomenon which has or could have a detrimental impact on the Environment and which in any such case has as its primary purpose or effect the protection of the Environment generally or in any particular locality.

82.3.1 	The Contractor warrants and undertakes that with respect to the design and carrying out of the works, construction and operation of the Plant and Materials forming part of the works and the remedying of Defects, there is and will be no breach of Environmental Law.

82.3.3 	If Contractor commits a breach of this clause 82.3, the Contractor immediately at its own expense, alters repairs or replaces any affected works or part of the works, or otherwise remedies the breach and indemnifies the Client from any and all losses caused by such breach.”

83.	Insurance Cover

83.3	In line 1 after “Parties” insert:

“(and any party whom the Client requires to be composite insured and who has an insurable interest in the works)”.

83.3A	Insert new clause 83.3A as follows:

"The insurance requirements under this contract do not relieve the Contractor from any of its other obligations and liabilities under this contract."

86.	Insurance by the Client

86.3	Delete clause 86.3.

87.    Professional indemnity insurance by the Contractor

87	Insert a new clause 87 as follows:

"The Contractor takes out from the Contract Date and maintains for a period of 12 years from the date of Completion professional indemnity insurance in respect of the duties and obligations in this contract with insurers of repute in an amount of not less than Five Million Pounds (£5,000,000.00) for any one claim, provided always that such insurance is available at commercially reasonable rates and terms. The Contractor immediately informs the Client if such insurance ceases to be available at commercially reasonable rates in order that the Contractor and the Client can discuss the means of best protecting the respective positions of the Client and the Contractor in respect of the works in the absence of such insurance.  As and when reasonably required to do so by the Client, the Contractor produces for inspection documentary evidence that its professional indemnity insurance is being maintained."

90.	Termination

90.2	In the Termination Table, in row 1 column 2, after “or R22”, insert: “or R23”.

90.2	In the second row of the Termination Table, replace “R10” with “R10A”.

91.	Reasons for termination

91.1	In R10, after “arrangement”, insert “compromise or composition in satisfaction of its debts (including but not limited to any restructuring plan)”

At the end of the clause, delete ‘.’ and replace with ‘,’

Add to the end of the clause:

- become subject to a moratorium under Part A1 of the Insolvency Act 1986, including but not limited to where a monitor is appointed or any document filed at court to obtain or apply for a moratorium or an order is made for a moratorium to come into force (R10A),

91.1A	Add a new sub-clause 91.1A as follows:

“The Contractor shall immediately notify the Client if they make any proposal, give notice of any meeting or become the subject of any proceedings or appointment relating to any of the matters referred to in clause 91.1.”

91.1B	Add a new sub-clause 91.1B as follows:

“The Contractor’s right to terminate for reasons R1–R10A does not arise unless and to the extent that:

- in the case where the Client has entered administration, an administrative receiver of the company has been appointed (otherwise than in succession to another administrative receiver), has gone into liquidation and/or a provisional liquidator of the Client is appointed (other than in succession to another provisional liquidator), the administrator, receiver or liquidator (as relevant) consents to the termination,

- in any other case, the Client consents to the termination,

- the court is satisfied that the continuation would cause the Contractor hardship and grants permission for the termination, or

- the termination is otherwise permitted pursuant to s. 233B of the Insolvency Act 1986 as amended by the Corporate Insolvency and Governance Act 2020.”

91.2	In the first bullet point delete the word "Substantially".

91.3	Delete and insert: "The Client may terminate immediately if the Contractor has broken a health or safety regulation or a health or safety requirement of this contract and/or if the Contractor breaches clauses 27.10.1 or 27.10.3 and/or where there is a reason to notify the Client of any of the circumstances set out in clause 27.10.2 has occurred (whether or not the Contractor has duly notified the Client)(R15).

91.3A	Insert new clause 91.3A as follows: "The Client may terminate immediately if the Contractor has substantially hindered the Client or Others (R14) and not stopped such hindrance within 2 weeks of a notification by the Project Manager to the Contractor of such hindrance."

91.3B	Insert new clause 91.3B as follows: "The Client may terminate immediately if the Contractor has failed to proceed regularly or diligently with their work (R23) and not stopped such failure within four weeks of a notification by the Project Manager to the Contractor of such failure."

91.4	Insert the following at the end before “(R16)”: "provided always that the Contractor has given written notification to the Client of such intention to terminate at least four weeks prior to the expiry of this thirteen week period and the Client has not paid the amount due within that period".

91.5		Delete and insert “Not Used”.

91.6		Insert the following at the beginning of the second bullet point: "provided the Contractor has given written notification to the Client of an intention to terminate at least four weeks prior to expiry of the above 13 weeks and no instruction allowing the work to restart or start has been given within that period,".

Insert the following at the beginning of the third bullet point: "provided written notification of an intention to terminate is given to the other Party at least four weeks prior to expiry of the above 13 weeks and no instruction allowing the work to restart or start has been given within that period,".

91.7		Delete and replace with:

“The Client may terminate if an Event of Force Majeure occurs (R21).”

91.9		Add a new sub-clause 91.9 as follows:

“The Contractor’s right to terminate for reasons R16, R17, R19 or R20 does not arise where the Client is subject to any of the events listed in R1–R10A on or before the date the termination takes effect and the right to terminate had arisen before the Client is insolvent, in each case unless the exceptions in 91.1B apply.”

92	Procedures on termination

92.1	Insert at the end before “(P1)”: "and the Contractor shall give the Client all information, documents, models, and all other items of any kind whatsoever relating to the works in the Contractor's control, custody or possession and the Contractor shall liaise, co-operate and co-ordinate with the replacement principal designer and replacement principal contractor for the purposes of the CDM Regulations and Part 2A of the Building Regulations to ensure a smooth handover of any obligations and duties.".

92.3	Add a new clause 92.3 as follows:

“Where amount A3 is taken into account in calculating the amount due on termination, the Project Manager’s certification of the final payment may be expressed to be provisional until four weeks following final ascertainment of the Client’s additional cost of Completion of the whole of the works and in the meantime the Project Manager shall not be obliged to certify any interim final payment to the Contractor.”

93.	Payment on Termination

93.2	Insert at the end of A3: "together with the amount of any loss or expense or additional cost incurred or suffered by the Employer arising out of the termination, including a forecast of the damages for delay to Completion and the additional costs of remedying any breaches or failures by the Contractor, whether forming grounds of termination or otherwise.”

100.  Public Contracts Regulations 2015

100		Add new clause 100 as follows:

“100.1 	The Contractor’s obligation to Provide the Works may be terminated by the Client if any of the provisions of paragraph 73(1) of the Public Contracts Regulations 2015 (PCR 2015) apply.

100.2 	Where the Client terminates under paragraph 73(1)(b) of the PCR 2015 as a result of information not disclosed by the Contractor at the Contract Date, the procedures and amounts due on termination are as if clause 91.2 (R11) applies. Where the Client otherwise terminates under paragraph 73(1) PCR 2015, the procedures and amounts due on termination are as if clause 91.5 (R17) applies.

100.3 	The Contractor does not engage a Subcontractor or supplier if there are compulsory grounds for excluding such party under regulation 57 of PCR 2015.

100.4 	The Contractor includes in any subcontract awarded by it provisions requiring that:

- payment to the Subcontractor/supplier under such subcontract is made no later than 30 days from receipt of a valid and undisputed invoice, unless the terms of this contract require the Contractor to make such payment earlier

- the Contractor considers and verifies invoices for payment submitted by the Subcontractor/supplier in a timely fashion

- undue delay in considering and verifying invoices is not sufficient justification for failing to regard an invoice as valid and undisputed and

- any sub-sub-contract awarded by the Subcontractor/supplier for work under this contract includes provisions to the same effect as these provisions.’

Option X4.	Delete Option X4 and replace with the following:

“X4 Parent Company Guarantee

X4.1	Upon the Contract Date, the Contractor shall deliver to the Client a parent company guarantee in the form set out in Schedule 3 to the Additional Conditions of Contract, executed as a deed and delivered by the [ultimate holding company of the Contractor].  Notwithstanding any other provisions of this contract, no payments shall become due to the Contractor under this contract while the Contractor remains in default of this clause X4.”

Option X7.2

In line 2, insert a full stop after “overpayment of damages” and delete the words “with interest”.  Delete the second sentence.

Option X8.	Delete Option X8 and replace with the following:

"Option X8: Collateral warranties and Materials Guarantees

X8.1	The Contractor shall, as a condition precedent to any obligation on the part of the Client to make any payment (or further payment) under this contract, within 14 days of a written request from the Client to do so, enter into deeds of collateral warranty with any Beneficiary in the form set out in Schedule 1 to the Additional Conditions of Contract.”

X8.2	The Contractor shall give to the Client duly executed insurance backed guarantees in a form accepted by the Client from each manufacturer or supplier where stated in the Scope or if instructed by the Client. Each such guarantee is provided for the benefit of the Client, enforceable for the period set out in the Scope or otherwise instructed by the Client and given to the Client by no later than Completion of the whole of the works.

Option X10.

Amend Option X10 as follows:

In Option X10.7(1), replace the first bullet with the following:

“A fault in the Information Model not caused by a Defect in the Project Information.”

In Option X10.7(2), in the first line replace the words “fault or error” with “Defect”.

Option X13.

Amend Option X13 as follows:

In line 3 delete ‘the Scope’ and replace with ‘Schedule 4 to the Additional Conditions of Contract’.

At the end of this clause add the following:

“Notwithstanding any other provision of this contract no payments shall become due to the Contractor under this contract while the Contractor remains in default of their obligations under this clause X13.1.”

Option X16.

Renumber X16.3 as X16.5, and insert a new Clause X16.3:

"X16.3	The Client’s interest in the amount retained shall not be fiduciary, either as trustee for the Contractor or any other person, or in any other capacity; the relationship of the Client and the Contractor with regard to the amount retained shall be solely that of debtor and unsecured creditor, subject to the terms hereof; and the Client shall have no obligation to invest the amount retained or any part thereof.  Any right of the Client to deduct or to set off any amount (whether arising under any express term or under any rule of law or of equity) shall be exercisable against any sums due or become due to the Contractor, whether or not such sums consist of or include any amount retained."

Clause X16.4	Insert a new Clause X16.4:

"X16.4	The Client shall have no obligation to segregate the amount retained or any part thereof in a separate banking account, or in any other manner whatsoever; and shall be entitled to the full beneficial interest in the amount retained and every part thereof (and, without limitation, interest thereon and income arising therefrom) unless and until the amount retained is paid to the Contractor pursuant to this contract."

Option Y(UK)2	In clause Y2.3 replace “seven days” with “one day”.

SCHEDULE 1

Deed of Collateral Warranty by

the Contractor in favour of

Beneficiary

Contractor's Warranty Pirbright Innovations Limited And [Contractor] And [Beneficiary] Relating to the [Name of Contract]

THIS DEED is made the		day of						20[  ]

BETWEEN:

- [CONTRACTOR] [Company Number (No. [•])] whose registered office is at [•] ("Contractor");

Pirbright Innovations Limited (Company number 04394007) whose registered office is at The Pirbright Institute Ash Road, Pirbright, Woking, Surrey, GU24 0NF

# and

- [BENEFICIARY] (Company Number (No. [•]) whose registered office is at [•] ("Beneficiary")

WHEREAS:

- [The Beneficiary [has entered into an agreement to [purchase] [provide funding for the purchase of] [lease] the property known as [definition of Site only to cover that part of the site which is being sold/let]] ("Site")]

# OR

# [The Beneficiary is the Biotechnology & Biological Sciences Research Council and has an interest in the property known as [definition of Site only to cover that part of the site which is being sold/let]] ("Site")]

- By a contract dated [•] ("Construction Contract") made between [the Client] ("Client") and the Contractor, the Contractor has agreed to construct certain works for [•] ("Works").

- Under the terms of the Construction Contract, the Contractor has agreed to enter into this Deed for the benefit of the Beneficiary.

- Capitalised terms defined in the Construction Contract shall insofar as the context permits bear the same meaning when used in this Deed unless otherwise defined in this Deed.

NOW IN CONSIDERATION OF THE PAYMENT OF ONE POUND (£1) BY THE BENEFICIARY TO THE CONTRACTOR (RECEIPT OF WHICH THE CONTRACTOR ACKNOWLEDGES) IT IS HEREBY AGREED as follows:

- The Contractor warrants and undertakes to the Beneficiary that it has performed and will continue to perform all of its duties and obligations under the Construction Contract in accordance with the terms and provisions thereof.

- The Contractor hereby grants to the Beneficiary with full title guarantee for any purpose whatsoever connected with the Works including (without limitation) the construction, completion, maintenance, dismantling, reassembly, repair, alterations and adjustment of the Works a royalty-free irrevocable non-exclusive licence to copy use and reproduce all drawings details plans specifications schedules reports calculations and other materials and the designs contained in them which have been or are hereinafter written originated or made by or through the Contractor in the course of performing their duties in connection with the Works provided always that the Contractor shall have no liability under this clause 2 other than for the use for which such materials were originally prepared and provided further that the Beneficiary shall be entitled to use such documents for reference in connection with an extension of the Works but shall not be entitled by virtue of this licence to replicate the designs contained within the documents for any extension to the Works or additional works.

- The Contractor shall be entitled in any action or proceedings by the Beneficiary to rely on any limitation in the Construction Contract and to raise the equivalent rights in defence of liability as it would be entitled to raise as if in all cases the Beneficiary had been named as joint employer with the Client under the Construction Contract (excluding set-off and counterclaim).

- The obligations of the Contractor under or pursuant to this Deed shall not be released or diminished by the employment of any person by the Beneficiary to carry out any independent enquiry into any relevant matter.

- Save to the extent required by virtue of the applicable law the Contractor will use the reasonable skill and care required by clause 21.4 of the Construction Contract not to bring onto the Site any materials which are generally known to be deleterious to health and safety or durability in the particular circumstances in which they are used or any other substances not in accordance with relevant British Standards and Codes of Practice or which is published in the Building Research Establishment Digests as being deleterious at the time of incorporation within the Works and the Contractor will notify the Beneficiary if and when the Contractor becomes aware that any of them have been or are being brought onto the Site for use or are being used in the Works.

- The Contractor shall maintain up to 12 years from the date of Completion professional indemnity insurance in accordance with the Construction Contract with insurers of substance and repute in an amount of not less than [•] million pounds (£[•],000,000) for any one claim, provided always that such insurance is available at commercially reasonable rates and terms.  The Contractor shall immediately inform the Beneficiary if such insurance ceases to be available at commercially reasonable rates and terms in order that the Contractor and the Beneficiary can discuss means of best protecting the respective positions of the Beneficiary and the Contractor in the absence of such insurance.  As soon as reasonably practicable following a request to do so by the Beneficiary or its appointee the Contractor shall produce for inspection documentary evidence that its professional indemnity insurance is being maintained in accordance with this clause.

- No actions for breach of this Deed shall be commenced after the date which is twelve (12) years from the date of Completion of the Works (as defined in the Construction Contract).

- [Step-in rights [CLAUSES 8.1 – 8.6 TO BE USED FOR A FUNDER WARRANTY ONLY AND "FUNDING AGREEMENT" AS REFERRED TO IN CLAUSE 8.3 TO BE DEFINED]

- 8.1	[The Contractor agrees that it shall not, without first giving to the Beneficiary not less than 21 days' prior notice in writing, exercise nor seek to exercise any right it may have to terminate its employment under the Construction Contract or to treat the Construction Contract as having been repudiated. Any period stipulated in the Construction Contract for the exercise by the Contractor of a right of termination shall nevertheless be extended as may be necessary to take account of the period of notice required by this clause 8.1.

- 8.2	The Contractor shall give notice to the Beneficiary forthwith upon exercising any right to suspend or discontinue the performance of any of its obligations under the Construction Contract.

- 8.3	If, the Beneficiary or its appointee gives a notice which complies with clause 8.7 to the Contractor that the Beneficiary has become entitled under the Funding Agreement to step-in to the Construction Contract or if within the period of 21 days referred to in clause 8.1 above or within a period of 21 days of the Contractor giving notice pursuant to clause 8.2 above (but in any event prior to the date of completion of the Works), the Beneficiary or its appointee gives the Contractor a notice which complies with clause 8.6 then:

- (a)	any right of the Contractor to terminate its employment under the Construction Contract or to treat the Construction Contract as having been repudiated or, to suspend or discontinue the performance of any of its obligations under the Construction Contract shall cease and the Construction Contract shall continue in full force and effect as if such right had not arisen and, in all respects, as if the Construction Contract had been entered into between the Contractor and the Beneficiary or its appointee in the place of the Client;

- (b)	the Contractor shall accept the instructions of and be liable to the Beneficiary or its appointee to the exclusion of the Client in respect of the performance of the obligations of the Client in accordance with the terms and conditions of the Construction Contract;

- (c)	the Beneficiary shall become bound by the terms and conditions of the Construction Contract in respect of all obligations and duties of the Client thereunder which fall to be performed after the date of such notice;

- (d)	the Client shall be released from further performance of the duties and obligations of the Client under the Contract after the date of such notice, but without prejudice to any rights and remedies of the Beneficiary or the Contractor against the Client in respect of any matter of things done or omitted to be done by the Client on or before the date of such notice; and

- (e)	upon the Beneficiary’s request, the Contractor shall enter into an agreement for the novation of the Contract by the Client to the Beneficiary or to its appointee, such agreement to be in terms reasonably required by the Beneficiary (subject to the requirements of this clause 8.3 and clause 8.6).

- 8.4	The Contractor and the Client agree that the Contractor shall be entitled to rely on any notice given by the Beneficiary or its appointee under clause 8.3 as conclusive evidence for the purposes of this Deed of the occurrence of such event.

- 8.5	The Contractor shall not be acting in breach of the Construction Contract or of this Deed by complying with any such notice under clause 8.3 or by entering into any such novation under clause 8.3.

- 8.6	It shall be a condition of any notice given under clause 8.3 that:

- (a)  	the Beneficiary or its appointee assumes all the obligations of the Client under the Construction Contract from the date of such notice; and

- (b)	the Beneficiary or its appointee accepts liability for payment of any amounts payable to the Contractor under the Construction Contract including payment of any amounts properly due to the Contractor at the date of such notice.]

- 8.7	The Beneficiary has and shall have no authority to issue any direction or instruction to the Contractor in relation to the performance of its obligations under the Construction Contract nor any liability to the Contractor in respect of sums due under the Construction Contract [unless and until the Beneficiary has given notice under clause 8.3.]

- This Deed may be assigned by the Beneficiary by way of absolute legal assignment on two occasions without the Contractor’s consent being required after which no further assignments will be permitted without the Contractor’s consent, such consent not to be unreasonably withheld or delayed.

- This Deed (and any non-contractual obligations arising out of or in connection with it) shall be governed by and construed in according with English law.

- Any disputes arising out of or in connection with this Deed shall be subject to the exclusive jurisdiction of the English Courts.

- The parties to this Deed do not intend that any of its terms will be enforceable by virtue of the Contracts (Rights of Third Parties) Act 1999 by any person not a party to it.

IN WITNESS whereof this Deed was executed and delivered the day and year first before written

SIGNED AS A DEED by

[CONTRACTOR]

Acting by

Director

Director / Secretary

SIGNED AS A DEED by

[BENEFICIARY]

Acting by

Director

Director / Secretary

SIGNED AS A DEED by

Pirbright Innovations Limited

Acting by:

Director

Director / Secretary]

sCHEDULE 2

Form of Subcontractor Warranty

Deed of Collateral Warranty by

a Subcontractor in favour of

the Client or a Beneficiary

| Subcontractor’s Warranty [Subcontractor] And [Beneficiary] [Client] |  |
| --- | --- |
| relating to the [Name of Contract] |  |

THIS DEED is made on []

BETWEEN:-

1.	[SUBCONTRACTOR] (Company No: []), whose registered office is at [] (the “Subcontractor”);

2.	[BENEFICIARY / CLIENT] (Company Number: []), whose registered office is at [] (the “Beneficiary”), which expression shall include its successors and assigns).

RECITALS:

- By a building contract dated [insert date] (the “Construction Contract”), [insert name of Contractor] (the “Contractor”) has been appointed by Pirbright Innovations Limited (Company No. 04394007) in respect of [insert works] (the “Works”) at [insert development] (the “Development”).

- By a subcontract dated [insert date] (the “Subcontract”) the Contractor has engaged the Subcontractor to carry out the [insert description of works/services carried out by the relevant subcontractor or sub-consultant] (the “Subcontract Works”).

- [The Beneficiary [has entered into an agreement to [purchase] [provide funding for the purchase of] [lease] the property known as [definition of Site only to cover that part of the site which is being sold/let]] ("Site")]

# OR

# [The Beneficiary is the Biotechnology & Biological Sciences Research Council and has an interest in the property known as [definition of Site only to cover that part of the site which is being sold/let]] ("Site")]

# OR

# [The Beneficiary has an interest in the property known as [definition of Site only to cover that part of the site which is being sold/let]] ("Site")]

- The Subcontractor has agreed to enter into this Deed for the benefit of the Beneficiary and his successors in title and assigns.

- Capitalised terms used in this Deed have the same meaning as given to them in the Subcontract, unless otherwise defined herein.

- Any reference to a document is a reference to that document as may be varied or novated (in each case) at any time.

IT IS HEREBY AGREED as follows in consideration of the payment of one pound (£1.00) by the Beneficiary to the Subcontractor receipt of which the Subcontractor hereby acknowledges:

EXERCISE OF SKILL AND CARE

The Subcontractor warrants and undertakes to the Beneficiary that it has executed and will execute and complete the Subcontract Works in a good and workmanlike manner and in accordance with the Subcontract.

The Subcontractor further covenants with the Beneficiary that:

        - 1.2.1	it has exercised and will exercise all reasonable skill and care in:

          - (a)	the design of the Subcontract Works and of any other part or parts of the Development to the extent that the Subcontractor has been or will be responsible for such design; and

          - (b) 	the selection of goods and materials for the Subcontract Works or any part or parts of the Development to the extent that such goods and materials have been or will be selected by or on behalf of the Subcontractor;

        - 1.2.2	the Subcontract Works will, on completion of the Development, be fit for the purposes for which they are intended to the extent that the Subcontract Works or any part or parts of them have been or will be designed by or on behalf of the Subcontractor;

        - 1.2.3	it has complied and will continue to comply with its obligations under the Subcontract;

        - 1.2.4	it has carried out the Subcontract Works in a good and workmanlike manner;

        - 1.2.5	the Subcontract Works and all materials and goods comprised in them will correspond as to description, quality and condition with the requirements of the Subcontract and will be of sound manufacture and workmanship; and that

        - 1.2.6	the Subcontract Works will on completion of the Development, comply with all applicable statutory requirements.

Insofar as the Subcontractor has performed a part of its obligations under the Subcontract before the date of the Subcontract, the obligations and liabilities of the Subcontractor under this Deed shall take effect in all respects as if the Subcontract had been dated prior to the performance of that part of its obligations by the Subcontractor.

In any action brought by the Beneficiary regarding an alleged breach of this Deed it is agreed that:

        - 1.4.1	the Subcontractor shall have available to it the right of all defences as may have been available to it under the Subcontract as if the Beneficiary were the employer under the Subcontract other than in respect of set-off, deduction and counterclaim under the Subcontract; and

        - 1.4.2	notwithstanding any other provision of this Deed, the Subcontractor shall not be entitled to contend in defence of proceedings under this Deed or otherwise that its liability to the Beneficiary is reduced or affected by virtue of the fact that the employer under the Subcontract has suffered no loss or a different loss from the Beneficiary as a consequence of any breach by the Subcontractor.

[NOVATION

In the event that the Construction Contract or the employment of the Contractor thereunder is determined for any reason whatsoever including, but without prejudice to the generality of the foregoing, the insolvency or winding-up of the Contractor (voluntary or otherwise) the Subcontractor shall, without allowing any break or intermission to occur in the performance of his duties:

continue to observe and carry out his obligations under the Subcontract and this Deed;

if so required by notice in writing from the Beneficiary, treat the Beneficiary as employer under the Subcontract to the exclusion of the Contractor whereupon all rights and obligations of the employer under the Subcontract shall thereafter be exercisable and performed by the Beneficiary; and

accept and enter into any deeds and other documents as are required to put into legal effect any further novation of the Subcontract reasonably required by the Beneficiary, subject to an undertaking by any person taking such a novation to pay all sums due and payable to the Subcontractor under the Subcontract.

Subject to clause ‎3, the Beneficiary shall from the date of such determination until any further novation of the Subcontract be responsible for the payment of all sums properly payable to the Subcontractor under the Subcontract whether accruing due before or after such determination but subject to the same right to deduct retentions as would have applied to the Contractor under the Subcontract.

The Subcontractor shall have no claim whatsoever against the Beneficiary in respect of any damage, loss or expense howsoever arising out of or in connection with any determination of the Construction Contract or the Subcontract.]

[NOTICE OF NOVATION

Notwithstanding anything contained in this Deed and notwithstanding any payments which may be made by the Beneficiary to the Subcontractor, the Beneficiary shall not be under any obligation to the Subcontractor unless the Beneficiary shall have given written notice to the Subcontractor pursuant to sub-clause ‎2.1.2 of this Deed.]

INSURANCE

The Subcontractor shall maintain up to 12 years from the date of Completion professional indemnity insurance in accordance with the Subcontract with insurers of substance and repute in an amount of not less than [•] million pounds (£[•],000,000) for any one claim, provided always that such insurance is available at commercially reasonable rates and terms.  The Subcontractor shall immediately inform the Beneficiary if such insurance ceases to be available at commercially reasonable rates and terms in order that the Subcontractor and the Beneficiary can discuss means of best protecting the respective positions of the Beneficiary and the Subcontractor in the absence of such insurance.  As soon as reasonably practicable following a request to do so by the Beneficiary or its appointee the Subcontractor shall produce for inspection documentary evidence that its professional indemnity insurance is being maintained in accordance with this clause.

LICENCE TO USE DOCUMENTS

The Subcontractor grants and agrees to grant to the Beneficiary an irrevocable, royalty-free, non-exclusive licence to use and reproduce all designs, drawings, models, plans, specifications, design details, photographs, brochures, reports, notes of meetings, CAD materials and any other materials prepared by or on behalf of the Subcontractor in connection with the Development or the Subcontract Works (whether in existence or to be made) and all amendments and additions to them and any works, designs or inventions of the Subcontractor incorporated or referred to in them for all purposes relating to the Development or the Subcontract Works including (without limitation) the construction, completion, reconstruction, modification, extension, repair, reinstatement, refurbishment, redevelopment, maintenance, use, letting, promotion and advertisement of the Development such licence carrying the right to grant sub-licences and to be transferable without the prior consent of the Subcontractor.

The Subcontractor agrees:

on request at any time to give the Beneficiary or any persons authorised by the Beneficiary access to the material referred to in clause ‎5.1, and at the Beneficiary’s expense to provide copies of it; and

at the Subcontractor’s expense to provide the Beneficiary with a set of all such material on Completion.

[All royalties or other sums payable in respect of the supply and use of any patented articles, processes or inventions required in connection with the Subcontract Works shall be paid by the Subcontractor and the Subcontractor shall indemnify the Beneficiary from and against all claims, proceedings, damages, costs and expenses suffered or incurred by the Beneficiary by reason of the Subcontract infringing or being held to infringe any intellectual property rights in the course of or in connection with the Subcontract Works.]

DELETERIOUS MATERIALS

The Subcontractor warrants to the Beneficiary that the Subcontractor has only and will only use or specify for use or permit to be used by or on behalf of the Subcontractor, in relation to the Development or the Subcontract Works or any part or parts of them, materials which:

accord with any relevant recommendations contained or referred to in the latest version of “Good Practice in the Selection of Construction Materials” produced and sponsored by the British Council for Offices current at the date of use or selection;

are in accordance with British Standards and Codes of Practice; and

are not generally known to be deleterious at the time of incorporation in to the Subcontract Works.

COMMUNICATIONS

Except as otherwise provided for in this Deed, all notices or other communications under or in respect of this Deed to either party shall be deemed to be duly given or made when delivered to the party addressed to him at the address set out at the beginning of this Deed (or at such address as the party may hereafter specify for this purpose to the other).

A notice or other communication received on a non-working day or after business hours in the place of receipt, shall be deemed to be given or made on the next following working day in that place.

[CONCURRENT LIABILITIES

The rights and benefits conferred upon the Beneficiary by this Deed are in addition to any other rights and remedies it may have against the Subcontractor including, without prejudice to the generality of the foregoing, any remedies in negligence.]

ASSIGNMENT

# This Deed may be assigned by the Beneficiary by way of absolute legal assignment on two occasions without the Subcontractor’s consent being required after which no further assignments will be permitted without the Subcontractor’s consent, such consent not to be unreasonably withheld or delayed.

LIMITATION PERIOD

- No actions for breach of this Deed shall be commenced after the date which is twelve (12) years from the date of Completion of the Works (as defined in the Construction Contract).

LAW AND JURISDICTION

This Deed shall be governed by, and construed in accordance with, English law.

The parties to this Deed irrevocably agree that the Courts of England shall have jurisdiction to hear and determine any suit, action or proceeding and to settle any dispute, which may arise out of or in connection with this Deed, and for such purpose the parties irrevocably submit to the jurisdiction of the Courts of England.

THIRD PARTIES

The parties to this Deed do not intend that any term of this Deed should be enforceable, by virtue of the Contracts (Rights of Third Parties) Act 1999, by any person who is not a party to this Deed.

Executed as a deed and delivered on the date specified at the beginning of this document.

| EXECUTED as a DEED by [SUBCONTRACTOR] acting by the signature of a director and the company secretary or of two directors of the company: | ) ) ) ) Director Director/Company Secretary |
| --- | --- |

| EXECUTED as a DEED by [BENEFICIARY] acting by the signature of a director and the company secretary or of two directors of the company: | ) ) ) ) Director Director/Company Secretary |
| --- | --- |

sCHEDULE 3

Form of Parent Company Guarantee

DATED 20

[GUARANTOR] Pirbright Innovations Limited

PARENT COMPANY GUARANTEE relating to the [Name of Contract]

THIS DEED is made the                              day of                                                            20

BETWEEN:

[GUARANTOR] (Company No. [•]) whose registered office is at [•] (the “Guarantor”, which expression shall include its successors in title and permitted assigns); and

Pirbright Innovations Limited (Company number 04394007) whose registered office is at The Pirbright Institute Ash Road, Pirbright, Woking, Surrey, GU24 0NF

- (the “Employer”)

RECITALS:

The Employer is undertaking [•] (the “Project”).

The Employer has entered into a contract (the “Contract”) dated [date] with [•] (the “Contractor”) for works for [•] (the “Works”) for the Project upon and subject to the terms and conditions therein set out.

The Contractor is a wholly owned subsidiary of the Guarantor.

The Guarantor has agreed to guarantee the performance of all of the Contractor’s obligations relating to the Contract in the manner appearing below.

IT IS HEREBY AGREED as follows:

- Guarantee

  - The Guarantor hereby irrevocably guarantees to the Employer, subject to the terms of this Guarantee, the due and punctual performance, observance and compliance by the Contractor of each and all of its obligations, duties and undertakings under or pursuant to the Contract (the “Obligations”).

  - Without prejudice to the generality of clause 1.1, if, at any time, any default is made by the Contractor in the performance of any of the Obligations, the Guarantor shall:

    - perform or cause to be performed each and every one of the Obligations; and/or

    - pay and discharge  all such sums of money and liabilities due, owing or incurred or payable and unpaid by the Contractor (whether to the Employer or otherwise) pursuant to the Obligations or as a result of any breach thereof.

  - As a separate, additional, continuing and primary obligation, the Guarantor agrees, on demand, to indemnify and hold harmless the Employer from and against any and all losses, damages, expenses, liabilities, claims, costs and/or proceedings which the Employer may suffer or incur, from time to time, as a result of the non-performance or breach by the Contractor of any of the Obligations.

- Addendum or Variation to the Contract

The Guarantor hereby authorises the Contractor and the Employer to make any addendum or variation to the Contract the due and punctual performance of which addendum or variation shall be likewise guaranteed by the Guarantor hereunder in accordance with the terms of this Guarantee and the obligations of the Guarantor under this Guarantee shall in no way be affected by any such addendum or variation to the Contract.

- Extent of Liability

  - The Guarantor shall not be discharged nor shall its liability be affected by anything which would not discharge it or affect its liability if it were the sole, principal obligor under the Contract including, but not limited to:

    - the insolvency, bankruptcy, winding-up, dissolution, administration, incapacity, amalgamation, reconstruction, re-organisation or any analogous proceedings relating to the Contractor;

    - any time being given to the Contractor by the Employer;

    - any amendment, modification, waiver, consent or variation (express or implied) to the Contract or to any related documentation;

    - the enforcement, absence of enforcement or release of the Contract or of any security, right of action or other guarantee or indemnity;

    - the illegality, invalidity or unenforceability of any part of the Contract;

    - any termination of the Contract;

    - any compromise, settlement or arrangement between the Employer and the Contractor or with any other person;

    - any failure of supervision to detect or prevent any fault of the Contractor;

    - any assignment of the benefit of the Contract; and/or

    - any other act, event or omission (other than full performance of the Contract by the Contractor) which (but for this provision) might exonerate or otherwise affect the Guarantor’s liability or any of the rights, remedies or powers conferred upon the Employer hereunder.

  - Any money judgment of the Court or decision of an adjudicator or any other competent tribunal against the Contractor in favour of the Employer under the Contract shall be conclusive evidence for the purposes of this Guarantee as to any liability of the Contractor to which such judgment or award or decision relates (unless and until the same is set aside by any competent tribunal).

- Continuing Guarantee

  - This Guarantee is a continuing guarantee and accordingly:

    - shall remain in operation until all Obligations now or hereafter to be carried out or performed by the Contractor shall have been satisfied or performed in full;

    - is in addition to and not in substitution for any other security which the Employer may at any time hold for the performance of the Obligations;

    - may be enforced against the Guarantor without first having recourse to any such security and without taking any steps or proceedings against the Contractor; and

    - no delay or omission of the Employer in exercising any right, power or privilege under this Guarantee shall impair or be construed as a waiver of such right, power or privilege nor shall any single or partial exercise of any such right, power or privilege preclude any further exercise of such right, power or privilege or the exercise of any other right, power or privilege.  The rights and remedies of the Employer provided for in this Guarantee are cumulative and not exclusive of any rights or remedies provided by law.

- Recovery against THE Contractor

So long as any liability incurred by the Contractor to the Employer under or in connection with the Contract remains unsatisfied, the Guarantor shall not, in respect of  any payment made or liability arising pursuant to this Guarantee, by any means or on any ground, claim or recover, by the institution of proceedings or the threat of proceedings or otherwise, such sum from the Contractor or claim any set-off or counterclaim against the Contractor or prove in competition with the Employer to claim or have the benefit of any security which the Employer holds or may hold for any money or liabilities due from or incurred by the Contractor to the Employer.

- Setting Aside

If the Guarantor is discharged or released in any way as a result of any payment or performance by the Contractor or any other person which is then set aside under insolvency legislation or for any other reason, the Guarantor’s liability hereunder shall be deemed to be reinstated as if such payment or performance had not occurred.

- Assignment

The benefit of this Guarantee may be assigned by the Employer by way of absolute legal assignment to any permitted assignee of the benefit of the Contract without the prior written consent of the Guarantor being required and the Guarantor’s obligations and responsibilities pursuant to this Guarantee will not be affected. No further or other assignment shall be permitted. Any further assignment shall require the prior consent of the Guarantor which consent shall not be unreasonably withheld or delayed.

- Third Party Rights

The parties hereto acknowledge and agree that it is not their intention for any term or provision of this Deed to confer or purport to confer on any third party any benefit or any right to enforce any provision of this Guarantee, whether pursuant to the provisions of the Contract (Rights of Third Parties) Act 1999 or otherwise.

- Notices

  - Any notice or other communication required to be given under this Guarantee shall be in writing and shall be delivered personally or sent by recorded delivery to each party required to receive the notice or communication at its address:

      - GUARANTOR:

- [NAME OF GUARANTOR] [Registered office address of guarantor] marked for the attention of the Company Secretary

      - COMPANY:

- [NAME OF CLIENT], [Registered office address of client] marked for the attention of ([ADD CONTACT NAME/TITLE])

- or as otherwise specified by the relevant party by notice in writing to each other party.

  - Any notice or other communication shall be deemed to have been duly received:

- (a)	if delivered personally, when left at the address and for the person referred to in this clause;  or

- (b)	if sent by recorded delivery, at 9.00 am on the second Business Day after posting.

  - A notice or other communication required to be given under this Guarantee shall not be valid unless it is given in accordance with clause 9.1 and clause 9.2.

  - This clause 9 shall not apply to the service of any proceedings or other documents in any legal action.

- Interpretation

In this Guarantee, “Working Day” shall mean any day from Monday to Friday inclusive excluding any day which is a recognised public holiday.

- Severability

Each provision of this Guarantee is severable and distinct from the others.  If a provision of this Guarantee is or becomes to any extent illegal, invalid or unenforceable in any jurisdiction, it shall not affect the legality, validity or enforceability of any other term of this Guarantee.

- Proper Law and Jurisdiction

The construction validity and performance of this Guarantee shall be governed by and construed in accordance with English Law and any disputes or differences between the parties shall be referred to the non-exclusive jurisdiction of the English Courts.

- Expiry

  - This Guarantee shall remain valid until 12 years after the date that the Project Manager certifies Completion for the whole of the Works under clause 30.2 of the Contract (the “Expiry Date”) upon which the obligations and liabilities of the Guarantor shall be released and discharged absolutely, save that subject to clause 6 the expiration of this Guarantee shall not in any way affect the validity of any claim served upon the Guarantor pursuant to the terms of this Guarantee prior to the Expiry Date.

- LIMIT OF LIABILITY

  - The Company may not recover any more under this Guarantee in respect of any matter than the Company would be entitled to recover from the Contractor in respect of that matter under the Contract.

  - The Company may not start proceedings against the Guarantor under this Guarantee in respect of any claim if any proceedings against the Contractor in respect of that claim would be statute-barred.

Executed as a deed and delivered on the date specified at the beginning of this document.

| EXECUTED as a DEED by [GUARANTOR] by the signature of a director in the presence of: | ) ) ) Director |
| --- | --- |
| Witness Signature: |  |
| Witness Name: |  |
| Witness Address: |  |
| Occupation: |  |

| EXECUTED as a DEED by [CLIENT] by the signature of a director in the presence of: | ) ) ) Director |
| --- | --- |
| Witness Signature: |  |
| Witness Name: |  |
| Witness Address: |  |
| Occupation: |  |

SCHEDULE 4

Form of Performance Bond

DATED 	20

- [CONTRACTOR]

- [GUARANTOR]

- Pirbright Innovations Limited

MAIN CONTRACT BOND

relating to [Insert name of contract]

THIS DEED is made the                              day of                                                            2024

This Guarantee Bond is made as a deed between the following parties whose names and registered office addresses are set out in the Schedule to this Guarantee Bond (the “Schedule”):

- The “Contractor” as principal,

- The “Guarantor” as guarantor, and

- Pirbright Innovations Limited (the “Employer”)

RECITALS:

- By a contract (the “Contract”) entered into or to be entered into between [CLIENT] (Company No. [•]) (the “Employer”) and the Contractor (particulars of which are set out in the Schedule) the Contractor has agreed with the Employer to execute works (the “Works”) upon and subject to the terms and conditions therein set out.

- The Guarantor has agreed with the Employer at the request of the Contractor to guarantee the performance of the obligations of the Contractor under the Contract upon the terms and conditions of this Guarantee Bond subject to the limitation set out in clause 3.

Now this deed witnesses as follows:

- The Guarantor guarantees to the Employer that in the event of a breach of the Contract by the Contractor or in the event that the Contract or the employment of the Contractor is terminated by the Employer by reason of any one or more of the events set out in clauses 91.1, 91.2, 91.3, 91.6 (R18) or 91.8 of the Contract (including without limitation the “Insolvency” (as defined in the Schedule) of the Contractor), the Guarantor shall subject to the provisions of this Guarantee Bond satisfy and discharge the damages sustained by the Employer as established and ascertained pursuant to and in accordance with the provisions of or by reference to the Contract and taking into account all sums due or to become due to the Contractor.

- The damages payable under clause 1 of this Guarantee Bond shall include (without limitation) any debt or other sum payable to the Employer under the Contract following the Insolvency of the Contractor.

- The maximum aggregate liability of the Guarantor under this Guarantee Bond shall not exceed the sum set out in the Schedule (the “Bond Amount”) but subject to such limitation and to clause 5 the liability of the Guarantor shall be co-extensive with the liability of the Contractor under the Contract.

- The Guarantor shall not be discharged or released by any modification, variation, amendment or supplementation of any of the terms conditions and provisions of the Contract and/or or in the extent or nature of the Works and/or by the appointment of a receiver and/or by the liquidation, administration or dissolution of the Contractor, and/or by any disclaimer of the Contract by a liquidator of the Contractor and no allowance of time or other forbearance or indulgence by the Employer under or in respect of the Contract or the Works shall in any way release reduce or affect the liability of the Guarantor under this Guarantee Bond.

- Whether or not this Guarantee Bond shall be returned to the Guarantor the obligations of the Guarantor under this Guarantee Bond shall be released and discharged absolutely upon “Expiry” (as defined in the Schedule) save in respect of any breach of the Contract which has occurred and in respect of which a claim in writing containing particulars of such breach has been made upon the Guarantor before Expiry.

6 	The Contractor having requested the execution of this Guarantee Bond by the Guarantor undertakes to the Guarantor (without limitation of any other rights and remedies of the Employer or the Guarantor against the Contractor) to perform and discharge the obligations on its part set out in the Contract.

- This Guarantee Bond and the benefit thereof may be assigned by the Employer without the prior written consent of the Guarantor and the Contractor to any party to whom the benefit of the Contract is assigned and may further be assigned by way of security to any bank or other institution providing finance in connection with the Works, but not otherwise. (The Employer should notify in writing to the Guarantor and the Contractor in case the bond is assigned)

- The Guarantor shall not be entitled to contend that any person to whom this Guarantee Bond is assigned in accordance with clause 7 is precluded from recovering under this Guarantee Bond, any or all loss incurred by such assignee resulting from any breach of this Guarantee Bond (whenever happening) by reason that such person is an assignee and not a named promisee under this Guarantee Bond or by reason that the Employer or any intermediate assignee has not suffered any or as much loss as such assignee.

- The parties to this Guarantee Bond do not intend that any of its terms will be enforceable by virtue of The Contracts (Rights of Third Parties) Act 1999 or otherwise, by any person not a party to it.

- This Guarantee Bond shall be governed by and construed in accordance with the laws of England and Wales and, subject to clause 11, only the courts of England and Wales shall have jurisdiction hereunder.

11

  - The parties agree that any dispute under this Guarantee Bond may be referred by any party to adjudication such adjudication to be in accordance with the Technology and Construction Solicitors’ Association (“TeCSA”) rules 2018 version 3.2.2 save that rule 12 and any analogous rule will be deemed to be deleted and that the adjudicator shall be a person nominated by the then President of TeCSA.

The parties shall be entitled to refer any decision of an adjudicator reached in an adjudication as provided for in clause 11.1 above for further or final determination by the courts of England and Wales.

THE SCHEDULE

| The Contractor: | [CONTRACTOR] (Company No. [•]) whose registered office is at [•]; |
| --- | --- |
| The Guarantor: | [GUARANTOR] (Company No. [•]) whose registered office is at [•]; |
| The Employer: | Pirbright Innovations Limited (Company number 04394007) whose registered office is at The Pirbright Institute Ash Road, Pirbright, Woking, Surrey, GU24 0NF [CLIENT] |
| The Contract: | A contract dated the [day] day of [month] between the Employer and the Contractor in an amended form of the NEC4 Engineering and Construction Contract, Option A, Edition June 2017 (together with the amendments set out in the ‘January 2019 Amendments’, ‘October 2020 Amendments’ and ‘January 2023 Amendments’ published by the NEC) for the construction of [•] located at [full address and postal number] for the original contract sum of £( ); |
| The Bond Amount: | the sum of £ ( ); |
| Expiry: | upon the date that the Project Manager certifies Completion for the whole of the Works under clause 30.2 of the Contract which shall be conclusive for the purposes of this Guarantee Bond; and |
| Insolvency: | has the meaning defined within section 113 of the Housing Grants, Construction and Regeneration Act 1996. |

IN WITNESS whereof the Contractor, the Guarantor and the Employer have executed and delivered this Guarantee Bond as a Deed this                  day of                                 20

| EXECUTED as a DEED by [CONTRACTOR] by the signature of a director in the presence of: |  | ) ) ) ................................................................. Director |  |
| --- | --- | --- | --- |
| Witness Signature: |  | ................................................................. |  |
| Witness Name: |  | ................................................................. |  |
| Witness Address: |  | ................................................................. ................................................................. ................................................................. |  |
| Occupation: |  | ................................................................. |  |
| EXECUTED as a DEED by [GUARANTOR] by the signature of a director in the presence of: |  | ) ) ) ................................................................. Director |  |
| Witness Signature: |  | ................................................................. |  |
| Witness Name: |  | ................................................................. |  |
| Witness Address: |  | ................................................................. ................................................................. ................................................................. |  |
| Occupation: |  | ................................................................. |  |
| EXECUTED as a DEED by [CLIENT] by the signature of a director in the presence of: |  | ) ) ) ................................................................. Director |  |
| Witness Signature: |  | ................................................................. |  |
| Witness Name: |  | ................................................................. |  |
| Witness Address: |  | ................................................................. ................................................................. ................................................................. |  |
| Occupation: |  | ................................................................. |  |

ANNEX 3

Scope

Refer to Appendix 4 – Works information and Prelims

- ANNEX 4

- Preconstruction Information

- Refer to Appendix 5 – Preconstruction Information

ANNEX 5

- Activity Schedule

- [Insert activity schedule]

To be inserted.

To be confirmed

Delete as appropriate, depending on whether this a Subcontractor warranty in favour of the Client or of a Beneficiary.

Include, as appropriate, if the warranty is in favour of a “Beneficiary” (as defined under the Contract)

Include, as appropriate, if the warranty is in favour of a “Beneficiary” (as defined under the Contract)

Include if the warranty is in favour of the Client.

Include if this is a warranty in favour of the Client only.

Include if this is a warranty in favour of the Client only.

Include if the warranty is in favour of the Client only.

Include if this is a warranty in favour of the Client only.