Order Schedule 20 (Order Specification)

This Schedule sets out the characteristics of the Deliverables that the Supplier will be required to make to the Buyers under this Order Contract

### Research Specification to HMRC Individuals, Customer and Perception customer survey 2024-26

CCS Research and Insights

Invitation to Tender

February 2024

Contents

Overview of Requirements	3

1.	Introduction	3

2.	Context	4

3.	Research Aims and Objectives	10

4.	Methodology and Scope	11

5.	Timetable	21

6.	Length of Contract	23

7.	Quality and Risk Management	24

8.	Outputs	25

9.	Expertise and Capability	29

10.	Project Management and Contract Administration	30

11.	Social Value	31

12.	Queries on this research specification	32

Submission of Tenders	32

13.	Information on how and when to return tenders	32

14.	Summary of requirements	34

15.	Alternative Bids	35

Evaluation Criteria	36

16.	Tender Evaluation approach	36

17.	Quality criteria and how we assess quality	36

18.	Security	47

19.	Price and how we assess price	47

20.	Summary of Evaluation Criteria	49

21.	HMRC eTrading System	50

22.	Data security and protection	51

23.	Other Ethical Issues	51

24.	Procurement Transparency	52

25.	Group Bids	52

26.	Access to Government Information	52

27.	Commissioning Conditions	53

Contract Award	53

28.	Acceptance of Offers	53

29.	Financial Capacity	53

30.	Accessibility Requirement	53

# Overview of Requirements

## Introduction

  - HM Revenue & Customs (HMRC) invites suppliers from the Research & Insights Marketplace agreement (RM6126) to undertake the HMRC Individuals, Customer Experience and Perceptions 2024-26 Survey.

  - The research will consist of three annual waves (commencing 2024). The stated duration of the contract is four years to allow for sufficient set-up, reporting, and contingency time for all three waves. HMRC intends for this contract to be in place by April 2024, with first outputs expected by May 2025 and final outputs expected by June 2027, although the contract will run until March 2028 to allow for changes to the timetable.

  - From 2024, we are seeking to have a single annual survey with Individuals focused on customers’ experience with, and perceptions of, HMRC. This is a change of approach to previous customer surveys where individuals were surveyed through HMRC’s Individuals, Small Businesses and Agents Survey. HMRC has also surveyed the UK population to ask about their customer experience and have asked more extensive questions on their perceptions of HMRC through HMRC’s Annual Perceptions Tracking Research (Perceptions).

    - This is an opportunity to review the current questionnaire to identify questions that require the continuation of tracking and questions that need redeveloping.

  - The primary focus of this research will be a quantitative survey with respondents selected using a random probability approach. Qualitative research will be used to gain more detailed insight into the views of our customers. We encourage suppliers to suggest innovative approaches that will deliver actionable insights and provide methodological robustness.

  - HMRC will maintain the overall management of the project.

  - The contract will be awarded to the organisation that is deemed to have submitted the most economically advantageous tender (MEAT). Assessment will be based on the factors outlined in sections 16 to 20.

  - To ensure fairness all tenderers are required to submit their tenders in accordance with these instructions and any further requirements contained in the invitation letter. Failure to comply could invalidate your tender.

## Context

Customer Focus in HMRC

  - HMRC uses different frameworks to help keep their focus on their customers. The chart below shows how all of these elements interconnect.

  - HMRC’s purpose is to collect the money that pays for the UK’s public services and give financial support to people.

  - Our vision is to run a trusted, modern tax and customs department – one that fits with how taxpayers run their lives and businesses and keeps the tax gap low.

  - To achieve our purpose and deliver our vision we’ve set ourselves five strategic objectives:

    - Collect the right tax and pay out the right financial support.

    - Make it easy to get tax right and hard to bend or break the rules.

    - Maintain taxpayers’ consent by treating everyone fairly and protecting society from harm.

    - Make HMRC a great place to work.

    - Support wider government economic aims through a resilient, agile tax administration system.

  - The published 10-year Tax Administration strategy for building a trusted, modern tax administration system sets out some of the key reforms we will need to deliver to successfully achieve our vision.

    - Our aim is for everyone to pay the tax that is legally due, no matter who they are. The most effective way of achieving that is through the overall design of the tax system. We are guardians of a system that relies on customer trust and consent.  To maintain their trust, honest taxpayers want to know that we will step in to enforce the rules where necessary. They want the tax system to be fairly operated, but to take account of their circumstances, and be easy to navigate. And they want us to respond quickly and transparently if we make a mistake. We’ll always be on the side of our customers when they’re trying their best to get things right, while tackling the small minority who set out to cheat the system.

  - The 10 year Tax Administration Strategy also identifies the fundamental aim for customers experience: the government wants people and businesses to be able to pay the right tax as they live their lives and go about their business. It should be easy for people to pay any tax due, and for the vast majority of people the calculation and payment of tax should be effortless. For the majority of businesses, tax should be straightforward and hard to get wrong.

    - Effortless:  For the vast majority of taxpayers, the calculation and payment of tax will be effortless, as they will rely on an employer or another third party. As is currently the case for many individuals in Pay-As-You-Earn (PAYE), taxpayers with straightforward tax affairs will need to take no action to pay the right tax at the right time. Taxpayers will be able to view their tax position whenever they want using their online account.

    - Straightforward:  For the majority of businesses, tax will be made more straightforward and harder to get wrong. HMRC will introduce increasingly integrated processes, drawing on information from business systems and validated third parties. This approach minimises opportunities for error and avoids the problems faced by both taxpayers and HMRC in seeking to assemble tax records long after the original business transactions.

    - For those with complex financial affairs and more extensive use of tax planning, such as wealthy individuals and large businesses, a modern, digital tax system should enable HMRC to assess the impact of tax planning choices in order to ensure the correct tax is paid. A modernised tax system will offer businesses and taxpayers greater certainty over their tax position by bringing all their records together into one place.

  - Digitisation is a key part of building a trusted, modern tax administration system and our 10-year Tax Administration strategy identifies digitalisation as a key component of transforming our tax system to enhance customer experience.

  - This digitisation has a fundamental impact on how our customers interact with us. It will help us deliver effortless and straightforward experiences for our customers.

  - Increased digitisation will also help HMRC to deliver the HMRC Charter.  The HMRC Charter supports HMRC to achieve our customer experience aims. It sets out the relationship HMRC wants with its customers, what customers can expect from us, and the behaviours we expect of them. Digitisation can, for example, help by creating and improving services to make it easier for customers.

  - There are seven Charter standards:

    - Getting things right

    - Making things easy

    - Being responsive

    - Treating you fairly

    - Being aware of your personal situation

    - Recognising that someone can represent you

    - Keeping your data secure.

  - This customer experience should help maintain trust and confidence in HMRC and help minimise the tax gap. The importance and continued relevance of achieving this ambition is highlighted in our most recent annual report and accounts.

  - Understanding customer experience and perceptions of the full range of our services, including digitisation, is a key requirement for this research. These are likely to vary by different factors such as familiarity with and/or perceived complexity of tax obligations.

  - Having a robust, independent understanding of customers’ experiences with and perceptions of HMRC over time is essential to help us evaluate how these are changing, particularly as we transform delivery of tax and payments. The survey findings will also provide a means of assessing and demonstrating progress on HMRC Charter commitments. These ongoing needs can only be met via a large-scale survey.

  - We anticipate the 2024-26 surveys will have some differences to those conducted in 2021-23 and welcome critical thinking to ensure the survey questions meet HMRC needs.

How HMRC will use evidence from the survey

  - This survey will be a key source of robust, balanced evidence on customer experience and perceptions of HMRC and the tax system.

  - The findings provide a means of assessing performance over time against:

    - Our 10-year Tax Administration strategy for building a trusted, modern tax administration system, including measures against services being effortless and straightforward.

    - Our Charter Standards

    - Our Vision and Strategic Objectives.

  - The survey is used internally to direct senior decision making, for example providing strategic insight regarding where HMRC should focus effort to improve customer experience. The primary purpose of the surveys is to provide key high-level metrics to act as indicators of how well HMRC is meeting its objectives. If there is space in the survey, a secondary interest is whether we can provide more nuanced information on customer experience (for example, segmenting results by tax type or by journey type).

  - HMRC will also continue to undertake customer surveys with other key customer groups such as Agents, Small, Mid-size and Large businesses. These surveys will be used alongside this contract to provide a single cohesive view of our customers’ experience and perceptions of HMRC.

  - Findings will be used alongside feedback from stakeholders and transactional level feedback (for example, exit surveys across HMRC’s digital and other channels, and social media monitoring), along with other commissioned research to provide a holistic picture of HMRC customer experience.

  - Externally, the published findings report will provide information on HMRC’s performance to the general public, Parliament, and other external stakeholders (for example, the National Audit Office). For example, some metrics are reported in our annual report and accounts.

  - For reporting against the Charter, the Customer Experience Committee assists the Commissioners of HMRC in their statutory obligation to report annually on the extent to which HMRC has demonstrated the standards of behaviour and values included in the HMRC Charter. The Charter Annual Report provides an assessment of HMRC’s performance against the Charter standards, which includes evidence gained through the HMRC customer surveys.

  - Tracking customer experience and perceptions over time is also of importance. The survey should continue the annual time series of data for some core questions which began with the updated Individuals, Small Businesses and Agents Survey in 2018. The 2024 survey will provide a baseline for new questions.

Background to the research need

  - HMRC’s surveys with Individuals have provided robust, objective measures of customer experience and perceptions of HMRC for this key customer group.

  - The annual surveys are a key source of insight into customer experience and perceptions. They provide topline customer metrics and are used alongside operational data to provide a holistic picture of HMRC customer experience.

  - Previously, Individuals have been surveyed through HMRC’s Individuals, Small Businesses and Agents Survey. HMRC has also surveyed the UK population to ask about their customer experience and more extensive questions on their perceptions of HMRC through HMRC’s Annual Perceptions Tracking Research (Perceptions).

  - From 2024, we are seeking to have a single survey with Individuals in the UK population aged 16 and above, focused on customers experience with, and perceptions of, HMRC.

  - For the 2024 survey we require:

    - A set of core questions to be asked every year to fulfil HMRC’s requirement to report our progress in relation to the Strategic Objectives, the HMRC Charter, HMRC’S vision and the 10-year Tax Administration Strategy. As a guideline, the core questions will account for around 75-80% of the survey.

    - We anticipate questions from the 2024 survey will be reviewed in Wave 2 and 3, with some changes in content. This will enable us to gather detailed evidence related to a strategic priority topic which will be set each year. As a guideline, we anticipate around 20-25% of the survey will change each year.

  - The core purpose of the survey will continue to be providing robust evidence on overall customer experience and perceptions of HMRC and observing change over time. This should include capturing the changing relationship customers have with HMRC through the digitisation of services.

  - This digitalisation of services will lead to increasingly straightforward interactions. We must ensure we reflect these changing experiences in our survey design and in the communication of findings. This will be a key focus of the 2024 survey and subsequent waves, ensuring these adapt to the changing landscape.

  - The surveys are unique in asking customers to consider their overall experiences across our full range of services over the previous 12 months, rather than a single interaction, and in surveying our customers who have not needed to interact with HMRC directly (all UK taxpayers are customers of HMRC).

  - The proportion of customers with an “effortless” experience is expected to increase and where customers do interact with HMRC their experience will become increasingly straightforward. We must ensure we reflect these changing experiences in our survey design and in the communication of findings. This will be a key focus of the 2024 survey.

  - We are also interested in exploring whether and how we could use the surveys to provide more nuanced information on customer experiences, in addition to the top tier metrics (described in clauses 2.29 to 2.31), within our budget.

    - For example, we are aware that experiences may be impacted over time – an individual needing to complete a self assessment will affect a customer’s tax liability. Capturing whether customer needs change would help HMRC understand what additional support may be required.

  - The current suite of surveys covers five core themes. We anticipate these remaining broadly consistent for the 2024 survey, albeit with a need to review the questions used and assess their suitability moving forwards:

    - Reputation and trust – reviewing perceptions of HMRC and drivers of trust.

    - Attitudes towards compliance – perceptions of compliance and attitudes towards non-compliance

    - High level interaction with HMRC over the past 12 months – what is the awareness and use of channels / products / services, including those who have not needed to interact with HMRC.

    - Direct experience with HMRC – for those who have completed a task / action, how did they rate their experience? Including self-serve experiences, use of guidance and interactions with HMRC staff.

    - Overall assessment of customer experience – assessment of HMRC at a total level for the past year, including ease and responsiveness when dealing with HMRC and appropriateness of experience for those who have not needed to interact.

  - There is a need to balance the importance of tracking survey results over time, from the 2018 Individuals survey baseline, with refreshing some of the survey questions to ensure continued relevance. Proposals should include details of how the tenderer will ensure sufficient comparisons to earlier waves can be made, whilst also incorporating prioritisation to include new or amended questions to meet changing departmental needs.

  - The research will be supported by an additional qualitative stage. This will be used flexibly and developed to gain more detailed insight into the views of HMRC customers on strategic priority topics.

## Research Aims and Objectives

  - The research aims for the project are to:

    - Provide a high-level readout of key customer metrics over the past 12 months to measure progress against HMRC’s Strategic Objectives, the HMRC Charter, HMRC’s vision and the 10-year Tax Administration Strategy, highlighting where HMRC are improving / need to focus efforts.

    - Develop measurements to assess progress in delivering the effortless and straightforward HMRC customer experience.

    - Enable customer scores to be tracked over time to identify changes.

  - The research objectives are to:

    - Assess HMRC’s reputation, perceptions of HMRC, including trust in HMRC, highlighting drivers of positive associations and identifying where improvements can most increase customer experience.

    - Understand attitudes towards compliance and identify how HMRC can assist customers to ensure they remain compliant.

    - Understand the high-level customer interaction with HMRC across channels and measure awareness and use of products and services, including those who have not needed to interact with HMRC.

    - Capture the direct experience of those interacting with HMRC when completing tasks or actions, assessing the various components used, for example guidance, self-service or direct engagement with HMRC staff.

    - Provide an overall assessment of customer experience across a range of metrics, including ease and responsiveness when dealing with HMRC and identifying where improvements can most increase customer experience.

## Methodology and Scope

Overview

  - HMRC is seeking a supplier that can work flexibly, and deliver robust, workable approaches that will maximise the quality of data within the new HMRC Individuals, Customer Experience and Perceptions Customer Survey design. Tenderers should outline their sampling and fieldwork strategies detailing organisational capacity to undertake fieldwork within the given timeframes, quality control procedures and methods to maximise response rates and minimise bias.

  - The target population of Individuals for this research is the general UK population aged 16 and over, including those who don’t directly interact with HMRC.

  - Tenderers are invited to propose a detailed methodology that will fully address the aims of this research project. The research will be conducted using:

    - A quantitative survey with respondents selected using a random probability approach. This will be the primary focus of this research.

    - Qualitative research to gain more detailed insight into the views of our customers on strategic priority topics. This will be used where it adds the most value.

  - We are open to methodological change (further detail provided in clauses 4.29 to 4.36) where deemed beneficial. We would like tenderers to identify an approach that will deliver the aims of the research and provide actionable insights in the most robust way possible – which may continue the current approach or suggest an alternative.

  - Proposals should outline the benefits and challenges of their chosen methodological approach. This may include outlining impacts on the ability to track data over time. Further details on requirements linked to methodological change are highlighted in section 4.35 below.

  - The Supplier will be required to review and redesign the existing questionnaire for wave 1 of the survey (2024). The questionnaire will need to be updated according to HMRC’s needs and priorities – keeping some questions the same and developing new questions. Further waves will also require the questionnaire to be reviewed for appropriateness. Further details on requirements linked to questionnaire change are highlighted in section 4.17-4.29 below.

  - The research methodology should:

    - Track changes in overall customer experience and perceptions over time, enabling continuity with data from 2018 where needed, whilst ensuring new questions enable tracking from 2024 onwards.

    - Be a highly robust, representative survey using random probability sampling methods.

    - Help HMRC identify where to focus effort to improve customer experience and perceptions.

    - Provide sufficient coverage to fulfil HMRC’s requirement to report on progress against HMRC’s Strategic Objectives, the HMRC Charter, HMRC’s vision and the 10-year Tax Administration Strategy, along with exploring ‘Effortless’ and ‘Straightforward’ for customers.

    - Provide robust, transparent evidence to the general public and external stakeholders.

    - Provide an in-depth qualitative stage to inform quantitative survey development and/or add depth to the quantitative findings.

    - Be flexible and able to respond to any changes in HMRC’s services and requirements between 2024 and 2026 without exceeding an appropriate length of questionnaire.

    - Provide value for money.

Sampling and Recruitment

  - Respondents for the survey will be selected using random probability to ensure HMRC captures the views of a representative sample of our customers and so changes over time can be measured statistically. A survey using non-probability sampling approach, for example a quota based sampling approach, will not be acceptable for meeting the research aims and objectives.

  - The Address Based Online Surveying (ABOS) method has been used for the Individuals survey since 2018. In 2021, the ABOS sample was supplemented with a sample from Kantar Public’s (Verian) own random sample panel Public Voice. It was introduced to improve the representativeness of responses to the Individuals survey, such as age groups, household occupancy, marital status and ethnicity. A base weight was generated and applied to each sample.

Sample Requirements

  - We invite tenderers to propose the most appropriate sampling framework. This should include:

    - The random probability sampling approach.

    - How the tenderer will conduct recruitment.

    - Expected achieved sample size.

    - Maximising how representative the achieved sample is of the general UK 16+, tax paying population, considering factors such as response rates and sample profile, and minimising bias.

    - Consideration and comment to the key risks of their chosen approach and how these will be mitigated.

  - Please note HMRC does not have the contact details for the full population of interest so will not supply a sample of Individuals to the Supplier for both the quantitative and qualitative elements of this research. Any proposed approach and mode will need to take account of this.

  - Tenderers should implement strategies to ensure a representative sample and outline what their proposed approach is expected to achieve to maximise the precision of findings for sub-groups of interest. Quality in the representativeness of the achieved sample is critical for the robustness of findings as we need to be able to identify change in results over time.

  - HMRC is committed to ensuring customer surveys are inclusive. The Supplier will be expected to monitor and ensure a balance of demographic characteristics are reflected in the sample. This should include gender, age, ethnicity, disability, location and employment status.

    - Tenderers should also consider the need to gather views from those more/less digitally able.

  - We would accept a modest value incentive for the Individuals survey. Tenderers should include a description of the type of incentive to be used, the total cost and clear evidence of the beneficial impact of using incentives for the proposed methodology in your tender if included (See section 14.2.1.2). All costs associated with such an approach must be included in the costs submitted in the Cost Model.

    - Response rates achieved as part of the 2022 ISBA survey are provided below and full details are available in the technical annex. We would welcome ideas on how this could be maximised. The 2023 Survey ABOS sample had 1,167 online completes and 207 paper questionnaires received but response rates for 2023 are not currently available. There were 897 Public Voice online completes.

| Outcome | ABOS | Public Voice |
| --- | --- | --- |
| Completed questionnaires online | 1289 |  |
| Completed questionnaire on paper | 330 |  |
| Data quality algorithm (removed cases) | 218 |  |
| Final sample size | 1401 | 872 |
| Interactions with HMRC | 935 | 654 |
| Response rate | 7.9% | 44% |
| Weighted response rate | 8.6% |  |

  - HMRC require the survey design to enable a statistically significant year on year change of 3.5% to be identified at the 95% confidence level for key questions about customer experience and perceptions. The Supplier should ensure that the sampling framework is robust to allow for comparing results between waves.  The Supplier should highlight any proposed revisions with justification to our suggested sample size based on these requirements. Change from the current approach may require a methodology to calibrate the data to form a quasi-time series. If relevant, please include a proposal for modal testing or parallel running of the fieldwork detailing, why the proposed approach is appropriate, the relative benefits and risks with the scale of the proposed testing and how these risks could be mitigated. We will be able to supply full, anonymised datasets including demographic information for the 2018 to 2023, to the successful tenderer to facilitate this. We welcome strategies in the tender for maximising the sample and thus reducing the percentage point difference at which significant changes year on year can be identified.

Questionnaire development

  - The way HMRC operates is changing, whilst our customers’ needs have also developed. Consequently, we anticipate there being a tension between collecting data to continue the current time series for questions in the current ISBA and Mid-sized business surveys and the development of new questions. Further details are outlined below in sections 4.21 to 4.27.

  - The Supplier will be required to review and redesign the 2023 questionnaires for the 2024 survey (wave 1 of the project). The questionnaire will need to be updated according to HMRC’s needs and priorities – both keeping some questions the same and developing new questions. Tenderers should assume that the questionnaire for 2024 will be built from the ground up, as opposed to making amendments to the 2023 questionnaire.

  - We would like tenderers to identify how they propose working with a complex stakeholder landscape to develop the questionnaire content, paying particular attention to:

    - Managing demand for questions in the survey across the five core themes (see section 2.33), ensuring they’re covered in sufficient depth. For example, to measure performance against our Charter standards. These will be further discussed with the Supplier during questionnaire development.

    - The need to specifically consider how we measure key metrics, for example perceptions of HMRC such as trust and straightforward.

    - The desire for greater granularity of information, for example being able to explore perceptions based on particular customer journeys or interactions with tax regimes within HMRC.

    - Increased digitisation and in particular how views to digital services may change with increased experience (for example initial trepidation replaced by positive experiences with increased use / familiarisation)

  - The Supplier will also need to factor in routing, timings, and sample sizes for each question.

Cognitive testing

  - The full questionnaire will need to be tested to ensure appropriate participant understanding. This could include cognitive testing. The tenderer’s intended approach should be outlined in the tender submission proposal.

    - We anticipate that sufficient changes will likely be made to the questions to require full cognitive testing of the entire questionnaire for the first wave in 2024. For subsequent waves we anticipate cognitive testing will only be required for amended and new questions.

Providing comparability to the ISBA

  - The current Individuals survey has run for many years with a well-established time series of data.

  - We want to be able to compare results for key questions from the 2024-26 surveys to those from the previous ISBA surveys, where it is appropriate.

  - HMRC’s needs and requirements have changed since the surveys were established, and consequently some questions that were previously asked may no longer be appropriate. Questions may also require standardising across the customer groups, including those asked of Agents, Small, Mid-size and Large businesses (covered in separate surveys). HMRC will work with the appointed Supplier/s across the Customer Survey contracts where standardisation is required.

  - Therefore, the surveys for 2024 will incorporate a mix of questions comprised of those needed to maintain the time series (i.e. kept the same) and questions we need to develop to increase the relevance of findings to departmental needs, accepting we will lose some ability to compare against previous surveys.

  - We appreciate the continuation of a time series can pose challenges and anticipate these will be amplified with the inclusion of new / different questions.

  - We will work with the appointed Supplier to identify where we wish to continue to track against previous surveys and where we will adapt and amend questions. HMRC reserves the right to have the final say on the content of each questionnaire for each survey/wave.

  - In responding to this ITT, please identify the risks you anticipate with the above approach to redeveloping the questionnaire, along with actions you propose to mitigate these risks. Proposals should identify where HMRC stakeholder input and decisions will be necessary.

Fieldwork

  - In their response to this ITT, the Supplier must propose a fieldwork strategy to ensure timely completion of all fieldwork. This should include appropriate steps to maximise response rates and ensure high quality in data collection.

  - It is expected that delivery of the quantitative survey will take place across three annual waves, with fieldwork taking place each Autumn in 2024, 2025 and 2026.

  - The Supplier will be required to collect representative data on HMRC customers’ overall experience and perceptions using the HMRC-approved questionnaire.

  - The Supplier will be responsible for developing all fieldwork tools (for example, questionnaires), and for scheduling sufficient time for multiple rounds of review by HMRC.

  - The Supplier will need to give sufficient consideration to the effective application of sampling procedures, including respondent selection, cleaning and enhancing of samples (for example supplementing available telephone numbers), administration of any advance letters, invitations to participate (including any reminders) and opt-out procedures.

  - Quantitative fieldwork has previously been conducted with participants either online or via post.

  - In their response to this ITT, proposals for the methodological approach for quantitative fieldwork should indicate:

    - Whether the tenderer intends to proceed with the current approach, along with the benefits and challenges of doing so.

    - Whether the tenderer would use a different methodological approach. This should be accompanied with full justification for the chosen approach, along with an outline of the possibility of and steps taken to preserve consistency with the time series of results developed using the previous approach.

    - Should the fieldwork method change from the current approach, a methodology to calibrate the data via a quasi-time series will need to be developed. Please include a proposal for modal testing and / or parallel running of the fieldwork detailing why the proposed approach is appropriate, the relative benefits and risks with the scale of the proposed testing and how these risks could be mitigated. We will be able to supply full, anonymised datasets including demographic information for the 2018 to 2023 surveys, to the Supplier to facilitate this.

  - In previous years, each survey lasted around 20 minutes and consisted of a core set of questions and a smaller flexible module. This year we will be looking to set the proportion of core and flexible questions as follows:

    - We would have a set of core questions to fulfil HMRC’s requirement to report progress on our Strategic Objectives and Charter. This section will be around 15 minutes. We will work with the Supplier to develop questions that allow us to meet our reporting requirements and maintain continuity.

    - An additional flexible module of questions will be included, which are likely to change annually. This will allow us to gather detailed evidence related to strategic priority topics, which will be set each year. We would expect this section to be approximately 5 minutes, ensuring that the overall survey is no more than 20 minutes.

  - The Supplier must ensure the quantitative approach is fully accessible, for example, including screen reader compatible online platforms, alternative response modes for those that need them (see section 30 for more detail), and Welsh translation (see section 4.61 - 4.68 for more detail) for those that request it.

Analysis and Reporting

  - Agreed analysis plans will be needed to help HMRC get most value from the results. A short turnaround summary reporting of results should be included after each wave of fieldwork. Information on headline measures will need to be presented in an agreed format, suitable for use internally by HMRC.

  - HMRC would like to understand how we can improve customer experience, so we would welcome innovative suggestions for achieving this. In previous iterations of research, this has included:

    - Using analysis to uncover drivers of customer experience, ease, satisfaction, and trust in HMRC, to support HMRC to focus efforts to improve customer experience efficiently.

    - Cross-sectional analysis of HMRC customer experiences over the previous 12 months based on a range of relevant customer variables (for example, tax complexity, etc.).

    - Trend analysis including comparisons with previous waves of customer research to help HMRC track progress in key performance indicators (for example, trust, overall customer experience, ease, etc.).

  - The Supplier will need to provide HMRC with both weighted and unweighted data to evidence and support analysis. Tenderers should provide details of their experience in weighting data to be representative and their proposed approach for this contract.

  - The Supplier will need to develop effective and insightful methods/formats for communicating survey results both internally within HMRC and externally for publication on GOV.UK. This should draw on innovative approaches and industry best practice to generate engaging outputs. This should include fast turnaround reporting of headline results, a written report to be produced in an accessible format of publishable standard and more in-depth reports, including sub-group analysis, in annual PowerPoint presentations. These will all be delivered within timelines agreed between HMRC and the Supplier.

  - In-depth results should be reported annually through presentations, and any other outputs recommended by the Supplier. Outputs need to be accessible, attractive, and insightful.

  - Tenderers should provide details of how their presentations would provide:

    - Compelling outputs that will engage HMRC senior leaders.

    - Strategic insights from the results that would enable us to measure and assess HMRC’s high-level performance in relation to customer experience and perceptions of HMRC over time.

    - Key insights that will allow internal stakeholders to understand the impact of findings on their area of work, including highlighting action to be taken to provide future improvements.

    - Analysis that enables HMRC to gain a deeper understanding of the individuals customer group, identifying for example difference amongst sub-groups of populations that provides more nuanced insight.

One Customer Narrative

  - Whilst this contract covers the Individuals population, contracts will also be awarded covering customer surveys with the Agents, Small and Mid-size business populations and Large business populations.  The three contracts may be awarded to different suppliers following completion of competitive processes.

  - Although it is important to understand the experiences and perceptions by different customer groups, providing a single cohesive view of our customers is also valued. For example, the ability to standardise questions and create a high-level narrative presentation that covers all customer groups in one document (in addition to the deeper reporting for each contract).

  - We would like tenderers to highlight both their willingness to work with others to create a singular headline customer narrative. We are interested specifically in understanding how they propose this would work, along with risks and how these would be mitigated, as well as any prior experience in working in such a way.

Future Waves

  - The research will consist of three annual waves (2024-2026). The timeline below is for wave 1 (2024-2025) of this project, which HMRC commits to:

    - Continuation to wave 2 will be subject to HMRC’s satisfaction with the completion of wave 1 and evidence needs remain.

    - Continuation to wave 3 is dependent on the same factors as described in 4.48.1.

    - HMRC envisages similar timescales to those outlined below for wave 1 being required for waves 2 and 3.

  - A questionnaire review will be required for the start of waves 2 and 3, to make sure that the questionnaire remains fit for purpose.

  - Proposed methodologies should ensure that robust comparison is possible between waves. Any changes to the approach or research materials between waves should be thoroughly tested by the Supplier to ensure continuity and approved in writing by HMRC.

  - We require that the survey design allows for robust significance testing between annual waves. HMRC expects the Supplier to adopt a probability approach to sampling and survey design. A survey using a non-probability based sampling approach, for example quota sampling, will not be acceptable for meeting the aims and objective.

  - Tenderers must state whether they would replicate wave 1 methods for wave 2 and 3 or take an alternative approach.

Qualitative Stage

  - An additional qualitative element will allow us to further explore reasons for experiences and perceptions as measured in the quantitative stage, add depth on key strategic topics, and/or to inform development of the quantitative questionnaire.

  - We would welcome recommendations from tenderers about the qualitative element of the research, including the best approach for meeting the research objectives. We anticipate flexibility in the qualitative stage and how it is used may be required both within and across waves. Tenderers should provide a full justification for their proposed approach which should be fully costed within their cost model.

  - Qualitative approaches to meeting the research objectives may include:

    - Exploring findings from the quantitative stage in more detail.

    - Exploring strategic priority topics identified by HMRC.

    - Exploring themes in detail to support design of the quantitative survey.

    - Other robust qualitative approaches proposed by the Supplier and approved by HMRC to meet the research objectives.

  - Although proposals are not limited to only considering depth interviews, the qualitative component of the research should be approximately equivalent to 20 depth interviews annually in scope.

  - Recommendations for the qualitative element should be accompanied by a full justification for the proposed approach which should be fully costed.

  - We will work with the Supplier to develop topic guides for the qualitative element to fulfil the research objectives. We expect that this will require multiple rounds of review by HMRC and redrafting by the Supplier. The Supplier will need to schedule accordingly to account for this.

  - We are open to proposals regarding how the qualitative research will be reported. Qualitative findings may be included with the quantitative outputs in presentations and final reports, if appropriate. However, some qualitative approaches may require reporting separately. For example, should the qualitative stage be used to inform quantitative survey development, this may need to be reported separately. HMRC reserves the right to make the final decision regarding this. Tenderers must ensure all costs relating to their proposals are included within the Cost Model.

  - Tenderers should provide details of the feasibility of providing the qualitative research and reporting within the timescale outlined in section 5 including an accompanying explanation if the timescale is deemed insufficient.

Welsh translations

  - To ensure HMRC meets its offer to Welsh customers, Welsh customers must be able to participate in Welsh, if they choose.

  - Online platforms for research participation must support Welsh orthography.

  - Participants completing surveys online in Welsh must be able to toggle between Welsh and English at any given point in the survey without being routed back to the beginning, and the language choice should be retained.

  - Similarly, the Supplier must ensure any qualitative research can be completed in Welsh, if requested by a participant.

  - HMRC anticipates the Supplier may need to partner with specialists should this be requested by a participant. Any associated costs should be included within the Supplier’s completed Cost Model

  - Communications, such as invitations to participate sent to potential respondents in Wales must also be in Welsh.

  - HMRC can support the Supplier with translation of communications and the survey, and will quality assure any Welsh translations provided by the supplier.

## Timetable

  - The timeline provided below is indicative of the timelines expected by HMRC.  Tenderers are required to demonstrate in their tenders they will be able to complete the research within the timelines below or sooner.

  - The timeline provided represents HMRC’s minimum expectation. If appropriate, we welcome proposals that indicate how the timeline could be reduced while still allowing time to deliver to a high standard with quality assurance.

  - The timetable below only reflects the first year’s dates. It is likely that waves 2 and 3 would follow to similar timings.

  - The Supplier will be expected to attend a set-up meeting in the week commencing 29 April 2024. This date may be subject to change.

  - The Supplier must suggest an appropriate fieldwork timetable.

  - In their proposal, tenderers must include a project plan and time schedule for the work that identifies the main tasks and key milestones that will be used to monitor progress, detailing clearly where HMRC is expected to contribute.

  - Following review by HMRC if the research is continued beyond Wave 1, Wave 2 and 3 timetables are likely to require delivery of full findings by May in 2026 and 2027 respectively.

  - There will likely be a general election in 2024, however, the date is unknown and the pre-election period could coincide with the fieldwork period for this research. It’s not currently clear whether this project would be impacted by pre-election restrictions therefore the Supplier needs to consider the implications of a pause in fieldwork and account for this in the timetable as well as considering the implications of this in delivery of the project.

| Indicative timetable for wave 1 |  |
| --- | --- |
| Activity | Date |
| Set-up meeting | w/c 29 April 2024 |
| Quantitative research tools development | May – July 2024 |
| Cognitive testing | July 2024 |
| Quantitative fieldwork | September – November 2024 |
| Clean, weighted dataset | December 2024 |
| Data tables | December 2024 |
| Presentation of headline findings | February 2025 |
| Presentation of findings | March/April 2025 |
| Draft report of findings | April 2025 |
| Qualitative research tools development | TBC |
| Qualitative fieldwork | TBC |
| Qualitative findings | TBC |
| Confirm if proceeding to Wave 2 | April 2025 |
| Final outputs signed off for wave 1: Full PowerPoint reports findings presentation, written report and technical report for publication on GOV.UK | June 2025 |

## Length of Contract

  - The contract term will be for four years. This is to take into account three waves of fieldwork, one per year and time for project set-up and the reporting of findings. Key timelines are outlined above.

  - HMRC intends for this contract to be in place by the week starting 29th April 2024, with final quantitative outputs for the first year delivered by the end of May 2025. Final outputs for the second and third waves of quantitative research should be delivered by the end of May 2026 and May 2027 respectively.

    - Year one of research is expected to run from April 2024 – May 2025, year two is expected to run from May 2025 – May 2026, year three is expected to run from May 2026 to May 2027.

    - The deadlines at 6.2 are fixed with no room for adjustment as results are published in HMRC’s Annual Reports and Accounts and Charter Annual Report. Tenderers should state in their submission if they can meet these deadlines.

  - Tenderers are required to set out a detailed timetable covering the duration of the contract. This will be agreed with HMRC following award of the tender and is likely to be subject to minor changes during the contract.

  - Where HMRC opts to continue with waves 2 and 3, all stages of the three waves must be completed by the end of July 2027. Tenderers should state if they can meet this deadline.

  - HMRC intends the Supplier will deliver the requirement for the first year as a minimum, however HMRC reserves the right to hold an annual review of the Supplier’s progress and performance, as well as other external or internal factors to decide whether to proceed with the second and third wave of research under this call off Contract. Following a review HMRC reserves the right to decide at its discretion whether to re-compete for the second and third wave of requirements. This may lead to termination of the Contract with the Supplier.

Years Two and Three

  - If HMRC chooses to proceed with the further research and is interested in delivering it within the scope of this contract, then the Supplier will work with HMRC to discuss and clarify the research needs and potential research approaches, issues and timescales. It is not expected that these will differ significantly from the Specification provided for the first wave.

  - Should HMRC wish to proceed with the Supplier’s proposals as a result of these discussions, the Supplier will then provide a detailed written work plan for the subsequent wave. The Supplier will commit to proposing a strategy which delivers the greatest value for money to HMRC in terms of time, cost and quality and with minimum deviation from their Cost Model for that wave that was submitted at tender stage.

  - HMRC will review the work plan and then decide whether to proceed with that approach or not. HMRC reserves the right to make suggestions or amendments to the proposed strategy in agreement with the Supplier. If HMRC decides to proceed with the written work plan (whether amended or not), then this will form the basis of the requirements for that wave. The Supplier shall submit an amended Cost Model for that wave, where an amended approach has been agreed with HMRC.

  - If HMRC agrees to the Supplier’s proposal (whether amended or not), this, together with the amended Cost Model shall be incorporated into the Contract using RM6126 DPS joint schedule 2: Variation Form v.1.0 HMRC shall notify the Supplier of the invoicing dates.

  - Should HMRC wish to proceed with the second and third waves under the scope of this contract and there are no amendments to HMRC’s requirements, then the costs submitted by the successful Supplier during the tender for the second and third year will be fixed within the subsequent statement(s) of work.

  - Any cost amendments required as a result of potential changes to HMRC’s requirements will be calculated using the Rate Card tab of the Supplier’s submitted Cost Model.

## Quality and Risk Management

  - Tenderers must include a quality control plan with their proposal, which should demonstrate their internal procedures for quality assurance, including a named person responsible for quality assurance at each stage of delivering outputs including setup and sampling, fieldwork completion, data processing and delivery of PowerPoint and written reports.

  - Proposals must also include an assessment of the key risks to this project. This should identify the most significant risks to successful completion of the programme of work, assess the degree of risk (likelihood and impact), and set out strategies for minimising these risks and managing the consequences if problems occur. A risk register template is at Annex F.

## Outputs

  - We will work closely with the Supplier on the outputs. The deliverables required for this project are:

Meeting and updates

  - An initial meeting with the Supplier and main HMRC stakeholders at the start of the project.

  - The Supplier must work with the HMRC project team to take appropriate steps to make sure the questionnaire meets HMRC and stakeholder needs.

  - An annual review at the end of each wave of the project.

  - Regular meetings with the HMRC project team during the project, (for example, a weekly half-hour video call). These will be used to update on progress towards key milestones and to decide on actions needed by the Supplier and HMRC. The frequency shall be agreed at the initial meeting and may be subject to change.

  - Ad hoc meetings where appropriate, for example when providing feedback on key documents, or when specific issues arise.

  - A detailed project plan that includes important dates, milestones and any actions for HMRC. This should specify dates for actions for both HMRC and the Supplier. This should be updated and reviewed weekly as the surveys progress.

  - For important times in the project, such as reporting deadlines and set up times, the project plan needs to be broken down into a daily plan. The Supplier must keep this updated as the project progresses.

  - Weekly updates provided via email throughout the project lifecycle covering key elements such as material development, fieldwork updates and key action points.

Research drafting

  - All research materials should be provided to HMRC for approval in advance. Time should be built into timelines for multiple drafts based on HMRC feedback. Research materials should include (but is not limited to):

    - Quantitative survey questionnaires in Microsoft Word

    - Qualitative topic guides or equivalent in Microsoft Word

    - Any recruitment materials

  - The Supplier should take into consideration within their timing plans that multiple stakeholder groups may be consulted and should factor in a minimum of one week for feedback on research materials to be received.

  - A final version of all research tools including their content, structure, and routing for questionnaires agreed by the HMRC project team and key stakeholders.

  - The Supplier must ensure the availability of a Welsh speaker for the qualitative research and for telephone interviewing if requested. Additionally, the Supplier must ensure any online or postal surveys can be completed in Welsh. Tenderers should state in their proposal that they can meet this requirement.

  - HMRC will send Welsh translations to the department’s Welsh Language Service for quality assurance. It can take up to two weeks for documents to be checked, so all timelines should allow for this. The Supplier should also provide their own quality assurance.

Raw data

  - An analysis plan for quantitative analysis, including all the fields and logic used to produce the quantitative reporting outputs and an agreed approach for the qualitative analysis. This must be agreed with the HMRC project team.

  - HMRC requires an anonymised copy of any dataset produced as part of the project. This should include a clean, fully coded SPSS data file for the quantitative data. This would need to include all of the cases, variables, clear labelling, correct bases and coded responses. Syntax must be provided for derived variables. If the Supplier would prefer to use R with data stored in CSV files, that would also be acceptable.

  - The Supplier should provide HMRC with both weighted and unweighted data.

  - All open-ended responses are to be provided separately in an Excel file and to include selected analysis variables.

  - Full data tables must include all analysis variables, including coded open-ended responses, and relevant cross-breaks.

  - For qualitative research, the Supplier must send a selection of the anonymised transcripts from the interviews/focus groups or equivalent for alternative qualitative methods.

  - Anonymised qualitative data must be organised in an analysis framework, for example thematically in Excel.

  - Tenderers are also invited to suggest any additional outputs they consider would be relevant to this research.

Quality Assurance

  - A quality assurance checklist must be provided and agreed with HMRC before fieldwork begins. This should cover fieldwork processes, data processing and presentation and reporting standards.

  - As part of the quality assurance processes, the Supplier must provide an analysis decision log which should cover, as a minimum, decisions about data cleaning, grouping data, weighting and analysis methods, as well as decisions taken in collaboration with HMRC.

  - The Supplier must provide a fully coded data file for the quantitative data. This must include all cases, variables (including all analysis variables), clear labelling, correct bases and all coded responses, including coded open-ended responses. Syntax must also be provided for any derived variables.

  - HMRC expects all data to undergo quality assurance ahead of being sent to HMRC for our internal quality assurance processes. This must include a named quality assurer or proof-reader for each output.

  - Representatives from the HMRC project team must be invited to observe interviewer briefings and at least one analysis workshop for each wave of qualitative research.

  - The Supplier must provide a framework for qualitative analysis. This must provide sufficient detail for HMRC to be able to identify how themes and / or recommendations have been established.

  - The Supplier must provide anonymised qualitative data, including a proportion of anonymised transcripts (assume a requirement of 20%).

Analysis, presentation and reports of findings

  - HMRC requires a Supplier who can present complex information in a clear and concise manner, highlighting strategic insights and providing consideration of the so what.

  - The Supplier must provide an analysis plan which details the qualitative and quantitative analysis to be completed and information on how the results will be presented.

  - The Supplier must also provide interim reporting of results after each fieldwork period delivered to a timetable agreed in the initial meeting.

  - Draft copies of all presentation slide decks must be provided for HMRC to provide comments on. These should be shared at least three weeks before the presentation. There are likely to be at least two or three drafts before they are finalised.

  - All summaries, reports, data outputs and presentations should be provided in an electronic format, compatible with Microsoft Office applications. All presentations and reports should be concise and written in plain English. They should be of a high (publishable) standard suitable for online publication. A style guide for GOV.UK publication has been made available as annex G.

  - Presentations shall be made by the Supplier at the end of each wave detailing annual results. These must be delivered virtually with accompanying slide decks as described in section 4.42 to 4.44 and 4.60. These would include reporting of the qualitative and quantitative findings in the most robust way. Previously we have required:

    - Headline quantitative findings presentation to the HMRC project team.

    - Quantitative findings presentation to wider stakeholders.

    - Qualitative findings presentation to wider stakeholders.

We are open to the Supplier’s suggestions of the most impactful way to report the findings.

  - Each presentation would be expected to last around 40 minutes, with at least 20 minutes for Q&A.

  - It should be assumed that presentations in year 2 and 3 will be tailored according to departmental needs and will not necessarily replicate the previous presentation.

  - Other customer groups such as Agents, Small, Mid-size and Large businesses are surveyed separately. We would be open to proposals about how collaboration with the supplier(s) for these contracts when reporting these surveys could better achieve the research objectives for HMRC.

  - Tenderers must provide separate costs for 3 presentations in the reporting stage. In case HMRC requires additional presentations, these shall be costed on an hourly basis or pro-rata’d for half-hour presentations using the Additional Services table included in the Cost Model.

  - PowerPoint slide decks are required for each presentation.

  - HMRC require a written report to be produced in an accessible format for publication on GOV.UK each year in line with the standard Government publication process.

  - All presentations and the full report must be engaging with clear recommendations for further actions for internal stakeholders.

  - In addition to the written report, a full technical report for the survey will be required annually. This must include the details of the survey methodology, sampling approach and actual weighting used. It must also include non-response bias analysis and response rates and, thus, the effective sample size.

  - HMRC may require additional analyses to be conducted. These will be agreed with the Supplier. At the end of this contract, all materials, outputs and final deliverables must be collated for handover to HMRC and any new supplier.

  - The Supplier should assume that reports, questionnaires and presentations will need to be amended in response to comments made by HMRC. It is likely that at least two drafts, sometimes more will be required before agreeing a final version. The Supplier must be certain to allow time for this in the proposed timetable for the research. HMRC will strive to provide timely comments to make this possible.

  - The Supplier must ensure that any research reports to be published on www.gov.uk meet the accessibility requirements for public sector bodies’ publications.

  - HMRC expects all documents to have been proof-read before delivery and for data in the documents to have been quality assured.

  - All reports and presentations should be quality assured by a senior member of the Supplier’s project team before delivery.

  - HMRC may arrange for any final reports produced to be peer-reviewed, either in-house or externally.

## Expertise and Capability

  - HMRC acknowledges that considerable resources are required for the successful delivery of this project to the required timescales. It is possible that tenderers have the skills and ability within their organisation to undertake all or part of this research but do not have sufficient resources required to successfully deliver the whole research requirement. We therefore encourage tenderers to consider the use of subcontractors to ensure that they are fully capable of undertaking this work.

  - HMRC is looking for a Supplier who can demonstrate their proposed team incorporates those with:

    - The ability to look at research within a broader strategic context.

    - Experience of delivering large-scale customer research including actionable research that has been used to improve customer experience.

    - Expertise in question development and testing for quantitative research.

    - Experience recruiting individuals using random probability sampling.

    - Experience in survey design.

    - Experience in designing a sampling approach and discussion guide development for the qualitative research proposed.

    - Expertise in advanced analytical techniques and data weighting.

    - Experience quality assuring qualitative and quantitative analysis.

    - The ability to utilise expertise and experience to apply industry best practice through all phases of the research.

    - Experience of presenting to varied audiences including presenting technical issues in an accessible and engaging manner and drawing out strategic insights from complex research findings.

    - Experience (in-house, with freelancers and/or with sub-contractors) of conducting research in Welsh.

  - Proposals should summarise the skills and expertise (relevant to this requirement) that staff members will bring to the team and clearly identify the proposed project manager. A Curriculum Vitae (CV) must be included as an annex for each staff member, which should not have any pictures of members of staff. Each CV should not exceed 1 page.

  - Proposals should also include a resource table for each wave that details the proposed team composition including the staff grade of each member of the team and the number of days allocated to each key stage of the project per team member. The resource tables must not include any cost information. This resource table can be found at 17.5.7.

  - The proposal should specify details of which parts (if any) of the project will be sub-contracted, the name of the sub-contractor who will work on the project, their experience of related research, and their responsibilities within the project. If it is proposed to sub-contract any of the work, the same details as those provided by the Supplier should be given about the qualifications, experience and responsibilities of sub-contractor staff who will be involved along with a description of their respective roles and the management arrangements put in place. The Supplier shall be responsible for the performance of any sub-contractor and needs to demonstrate within their tender their confidence to successfully manage sub-contractors. This should also be considered for any joint submissions, as the second supplier will be treated as a sub-contractor.

## Project Management and Contract Administration

  - [Redacted]is HMRC Manager for this project. She will be responsible for the day-to-day management of the contract. Once the contract has been awarded, all contact with HMRC concerning the project should be made through her. The Supplier will be required to appoint a contract manager who will act as the principal point of contact for HMRC.

  - The Supplier will be expected to work closely with the HMRC project manager and through them, with internal customers within HMRC throughout the duration of the Contract. The project manager must be kept informed of progress and be involved in key decisions. Proposed changes in project staffing (at all levels) or deviations from the agreed work programme must be discussed with the project manager at the earliest possible time and agreed in writing in advance. [Redacted]is responsible for all decisions that involve funding.

  - In costing your tender you should allow for attendance at a minimum of 5 formal meetings in addition to weekly project meetings. Most meetings are expected to take place online. These might include the following:

    - Project set-up meeting.

    - A briefing to discuss the initial findings.

    - A mid-point review meeting.

    - Ad hoc meetings when deemed necessary.

    - An analysis meeting and

    - Presentations of key findings and final analysis each year.

## Social Value

  - In September 2020, the Cabinet Office issued PPN 06/20, outlining that from 1st January 2021 all new above threshold tenders must cover social value as part of the tender evaluation process and ongoing contract performance reviews.

  - As part of your tender submission, you must provide firm social value commitments you would deliver as a direct result of being successfully awarded the contract resulting from this procurement exercise, which are over and above any existing social value policy/incentives you may already have in place within your organisation. As such, your response should not focus on existing social value policy/incentives you may already operate.

  - Any social value deliverables the Supplier commits to provide within their tender response will be incorporated as contractual commitments within the contract prior to signing. In addition, suitable Key Performance Indicators (KPIs) to monitor the Supplier’s performance against such commitments will be agreed between HMRC and the successful tenderer prior to contract signature.

  - Tenderers must suggest KPIs appropriate to their social value deliverables within their tender response. HMRC will review the suggested KPIs and targets and if satisfactory to HMRC, these will form the contractual social value KPI’s to be incorporated into the contract should you be successful at tender award. HMRC reserves the right to suggest amendments to such KPIs or agree alternative KPIs with the successful tenderer prior to contract award should the KPIs/targets be unsatisfactory to HMRC. Tenderers must provide suggested KPI’s and targets as part of their response, however these are for information only and will not form part of the tender evaluation.

  - Annex D details the Social Value Outcome (SVO) that you must deliver through award of this contract.

## Queries on this research specification

  - Tenderers with any queries about the research specification should contact [Redacted] on e-mail: [Redacted] copying in [Redacted] and [Redacted]

  - The deadline for queries is 5pm on 16 February 2024. Responses will be sent to all tenderers by 5pm on 22 February 2024.

  - Please note that if HMRC considers any clarification to be of material and general significance, both the query and the response will be communicated to all tenderers.

# Submission of Tenders

## Information on how and when to return tenders

  - Tenderers should provide notification of their intention to submit a proposal by email to [Redacted] copying in [Redacted] and [Redacted] by 5pm on 26 February 2024.

  - You should send a PDF or read-only electronic copy of your proposal (excluding costs information which will be sent separately as per 13.3) by e-mail to arrive at the following addresses [Redacted] [Redacted]  copying in [Redacted] and [Redacted] no later than 5pm on 4 March 2024 (unless the date is subsequently amended in writing by HMRC). No hard copies of the tender are required.

  - Costs information should be submitted separately from the proposal to the following email address [Redacted] and [Redacted] by the same time as stated in 13.2. You should not send this to the other contacts named in 13.2.

  - HMRC will safeguard all tenders received and action them once the tender deadline has expired.

  - All late tenders will be rejected. It is your responsibility to ensure your tender is received on time.

  - You must not alter any of Tender documents.

  - Tenders may not be considered if any of the information requested is not supplied with the tender or the tender is otherwise non-compliant or incomplete.

  - You must not tell anyone else, even approximately, what your tender price is or will be, before the date of the contract award. The only exception is if you need an insurance quotation to calculate your tender price – in which case you may give your insurance company or brokers any essential information they ask for, provided you do so in strict confidence.

  - You must not try to obtain any information about anyone else’s tender or proposed tender before the date of contract award.

  - You must not make any arrangements with anyone else about whether they should tender, or about their or your tender price. The only exception is where tenderers are considering joint or team bids, which will be allowed providing all participants to the discussions surrounding the bid are clearly stated in the tender response. (See also section 25 ‘Group Bids’).

  - Tender documents must not be transferred to anyone (other than the organisation named in the Invitation to Tender email) without the prior specific approval of HMRC in writing.

  - You must ensure your tender is completely legible, in English, with all prices in Pound Sterling (exclusive of VAT) rounded up to the nearest pound.

  - In summary, Tenderers should note the following timeline:

| Action | Start date | End date | Contact |
| --- | --- | --- | --- |
| ITT Live | 05/02/24 | 04/03/24 | [Redacted] |
| Suppliers to confirm receipt of ITT | 05/02/24 | 16/02/24 | [Redacted] |
| Submit queries | 05/02/24 | 16/02/24 | [Redacted] |
| Answers to queries provided by HMRC | 19/02/24 | 22/02/24 | [Redacted] |
| Notify your intention to submit a proposal | 05/02/24 | 26/02/24 | [Redacted] |
| Submit read only tender via email | 05/02/24 | 04/03/24 | [Redacted] |
| Submit read only cost proposal via email | 05/02/24 | 04/03/24 | [Redacted] |
| Evaluation & Governance | 05/03/24 | 17/04/24 |  |
| Clarification period | 22/03/24 | 26/03/24 | [Redacted] |
| Contract award completed | 22/04/24 | 26/04/24 |  |
| Unsuccessful providers noted of outcome | 22/04/24 | 26/04/24 |  |

  - The dates listed above are subject to change by HMRC if required.

  - Tenders must remain open for acceptance for a minimum of 120 days from the Tender Deadline.

  - If your tender is submitted in the name of one company or organisation but you intend submitting invoices in the name of another, or require payments to be made to another, please give full details in your response. Otherwise, there may be delay in payment.

## Summary of requirements

  - Tenders should not exceed 40 pages for the main body, as detailed in section 14.2. below – which need to answer all assessment criteria. The requirements for the annexes are detailed in section 14.2.2 below.

  - Tenders must include the following information:

    - A written proposal in a read-only pdf including:

      - A detailed written proposal detailing how you will meet the requirements, aims and objectives as outlined in Sections 3-9 of the ITT and summarised in section 17. This should also include the proposed team composition including the staff grade of each member of the team and the number of days given to each key stage of the project per team member in this section (excluding costs).

      - Where incentives are proposed, you should include a description of the type of incentive to be used and their total cost in your written proposal (no other cost should be contained within your written proposal).

      - A detailed timetable for the proposed research, including the information outlined in Section 5.

    - Annexes should include:

      - A quality control plan as requested in section 7.1 to demonstrate the procedures that will be implemented to assure quality control.

      - A fully completed ‘ANNEX F Risk Register’ as outlined in section 7.2 which outlines in detail the risks to the project and methods for mitigating them.

      - The Curriculum Vitae (CV) of key personnel, their status within the company and area of expertise. Individual CVs should not exceed 1 page each nor include any pictures of the personnel.

      - A fully completed ‘ANNEX B Security Questionnaire’. The purpose of this is to outline the tenderer’s security arrangements. This will be evaluated as per sections 22.1 and 22.3 of this ITT. Each tenderer will need to complete this in full and responses may be subject to further clarification.

      - A fully completed ‘ANNEX C Compliance Check Form’ which provides the information necessary for HMRC to undertake the appropriate tax compliance checks. By providing the details requested on this form the tenderer consents to HMRC completing tax compliance checks on their organisation.

      - A response to the ‘ANNEX D Social Value Document’

      - A response to the ‘ANNEX H Capability Assessment document’

    - A fully completed Cost Model (exclusive of VAT) in a read-only excel document as detailed in Section 19. This should be sent separately from the proposal as per 13.3 above. It should include:

      - A fixed price for the first wave and

      - A fixed price detailing project costs for waves two and three, subject to any amendments to approach approved by HMRC as detailed in 6.6 to 6.11 above.

      - Details of key individual personnel’s chargeable day rates.

      - Chargeable rates for other personnel proposed. Where these can be identified as groups (e.g. administration, support etc.) then a group rate will suffice.

      - Any further costs identified.

## Alternative Bids

  - HMRC will not allow tenderers to submit alternative bids.

# Evaluation Criteria

## Tender Evaluation approach

  - HMRC will evaluate the contract based on Most Economically Advantageous Tender (MEAT). Quality forms 70 per cent and price 30 per cent of our assessment of MEAT.

  - As referred to in the Tendering Instructions, the Authority reserves the right to request clarification questions with those Tenderers where further clarification of their tender response is needed to ensure that all aspects of the Contract requirements will be met.

    - Should any clarification questions be required, these will be sent via email between 22/03/2024 - 26/03/2024. These dates may be subject to change.

    - Tenderers must be available to answer questions during the Clarification Period.

## Quality criteria and how we assess quality

  - A tenderer’s written proposal will be evaluated to determine their Quality score.

  - Quality will be assessed separately to cost. Quality criteria will be evaluated on a scale from 0 to 100 (where 0 = totally fails to meet the criteria and 100 = fully meets the requirement, with detailed explanation/evidence in support). A detailed breakdown of the evaluation methodology is as follows:

| Score | ‘Open’ Question Criteria |
| --- | --- |
| 100 | The response is excellent and completely relevant. The response is comprehensive, unambiguous and demonstrates an excellent understanding of, and meets, the requirements in all aspects, with no clarification required. The response is well thought out and/or provides - highly credible examples; - benefits; - or innovation |
| 80 | The response is good and highly relevant. The response indicates a good understanding of the requirements and provides sufficient detail across all areas. The response demonstrates how the requirements will be met in the main, which may require minor clarification only. |
| 60 | The response is satisfactory and relevant. The response indicates a satisfactory understanding of the requirements in most aspects, although may lack detail in certain areas. The response suggests that the requirements would be met satisfactorily but may require some clarification. |
| 40 | The response is limited and partially relevant. The response indicates partial understanding of the requirement. The response contains ambiguities which suggests that the requirements would not be met unless clarified. |
| 20 | The response is poor and only partially relevant. The response addresses some aspects of the requirements but contains insufficient/limited detail or explanation. The response demonstrates only limited understanding of the requirement. The response contains deficiencies which suggest the requirements would not be met. |
| 0 | The response is not considered relevant. The response is unconvincing, flawed or otherwise unacceptable. Response fails to demonstrate an understanding of the requirement. |

  - HMRC reserves the right to not consider for award a tender that scores below 60 in any of the quality criteria as listed at 17.5, excluding Social value.

  - Capability Assessment (Pass / Fail)

    - Tenderers must complete the Capability Assessment at Annex H to help HMRC establish whether they have the capability to carry out HMRC's requirement. Tenderers must be able to answer 'Yes' to all of the questions asked within the Capability Assessment in order for their bid to be considered further.

    - The Capability Assessment will be evaluated first.

    - Any Tenderer who is unable to answer 'Yes' to all of the questions within the Capability Assessment or does not submit a fully completed Capability Assessment will not progress any further during the evaluation stage and their bid will be rejected.

  - Tenderers must submit a written proposal demonstrating how they can best meet HMRC’s research and service delivery requirements as set out within sections 3-9 of this ITT. Tenders will be evaluated on:

    - Addressing Aims & Objectives (7.5%)

      - How well the tenderer demonstrates that they have understood the context and key issues for the project as specified in section 2.

      - The extent to which the proposed approach demonstrates that it will deliver in full the aims and objectives as specified in Section 3.

      - How well the tenderer has presented an approach which has been tailored to meet HMRC’s requirements.

    - Sampling and recruitment (12.5%)

      - The tenderer’s approach to recruitment and sampling that will deliver the requirements in full as specified in sections 4 and also specifically at 4.1, 4.8, 4.9, 4.10, 4.11, 4.12, 4.13, 4.14, 4.15 and 4.16.

      - The tenderer’s proposal for an appropriate and effective recruitment strategy for the specified research participants utilising a random probability approach.

      - How well the data collection strategies maximise successful contact with the sample.

      - The tenderer’s approach to maximising the representativeness of the sample.

      - How well the tenderer can demonstrate their approach includes proven methods to maximise response rates and manage recruitment risk, including opt out and incentive approaches.

    - Questionnaire development (5%)

      - The tenderer’s approach to questionnaire design that will deliver in full the requirements as specified in section 4 and also specifically at 4.18.

      - The tenderer’s approach to reviewing the existing questionnaire and developing the 2024-26 questionnaire with HMRC stakeholders. It should be identified where HMRC stakeholder input and decisions will be necessary.

      - The extent to which the proposed approach to questionnaire development balances the requirement for a continuation of time series data where required, whilst allowing for development of new questions where these better meet HMRC’s requirements, as specified at 2.34 and 4.21 to 4.27.

      - The tenderer’s approach to ensuring comparability to previous data where questions remain the same as previous waves of the survey.

      - The tenderer’s approach to cognitive testing, including recommended thoroughness, as specified at 4.20.

    - Fieldwork, analysis and reporting (12.5%)

      - The tenderer’s approach to fieldwork, analysis and reporting that will deliver in full the requirements, as specified in section 4 (and also specifically at 4.1, 4.7, 4.30, 4.32 and 4.36) in a timely manner.

      - The quality of the proposed methodological approach and how this will meet the needs of the project, as specified at 4.4, 4.5, 4.34, 4.48, 4.50 and 8.13.

      - How well the tenderer’s approach to developing research tools meets the requirements for robust findings.

      - The quality of the proposed analysis plans, including advanced analytical approaches with justification, and how well these will meet the needs of the project, as specified at 4.38.

      - The tenderer’s approach to weighting of data, as specified at 4.39.

      - How well the proposed outputs meet the requirements in full as set out in sections 8 including how well these meet the aims and objectives and provide concise, insightful information that HMRC can act upon, as specified at 4.41, 4.42, 8.22 and 8.35.

      - Consideration for working with other suppliers to create one narrative across HMRCs customer experience surveys, as specified at 4.45.

    - Qualitative research (5%)

      - The tenderer’s approach to qualitative research that will deliver the requirements in full as specified in section 4 and specifically at 4.52, 4.55, 4.58 and 8.13.

      - How well the tenderer’s approach to qualitative research meets the requirement for flexibility for the duration of the contract.

      - The tenderer’s proposed methodological approach with justification for how this will meet the needs of the project.

      - The quality of the proposed analysis plan and how this will meet the needs of the project.

    - Project plan (5%)

      - Whether the tenderer has satisfactorily demonstrated that their strategy will deliver each of the required activities as set out in section 5 and any additional activities as outlined by the tenderer in their approach, in full within the required timelines or sooner, as specified at 5.6.

      - Whether the tenderer has included a project plan and time schedule for the work that identifies the main tasks and key milestones that will be used to monitor progress, detailing clearly where HMRC is expected to contribute.

      - How well the key risks to the project have been identified in the risk register and how effective the proposed mitigation strategies are in minimising the impact and/or likelihood of these risks, with specific consideration of 7.2.

      - Whether the tenderer has considered the implications of a pause in fieldwork and have accounted for this in the timetable.

    - Team (7.5%)

      - How well the tenderer can demonstrate that their proposed team meets the required experience and expertise in full as outlined in section 9 (and specifically 9.3, 9.4 and 9.5). In addition to providing CVs, please include the staff grade of each member of the team and the number of days given to each key stage of the project per team member in this section (but do not include the costs), using the tables below.

Wave 1:

| Activity | Grade of staff | Number of days per staff grade |
| --- | --- | --- |
| Project Management (example) | Research Executive | X |
|  | Senior Research Executive | X |
|  | Research Director | X |
|  | Director | X |
|  | Statistician | X |
| Project Management |  |  |
| Survey design Review, develop and update methodology and sampling strategy |  |  |
| Questionnaire design Redevelop questionnaires, including cognitive testing of full questionnaire (including Welsh translation) |  |  |
| Advance Notification Letters |  |  |
| Fieldwork |  |  |
| Qualitative fieldwork Budget for at least 20 1:1 interviews, although we are open to using alternative qualitative research methods (Include Welsh translation) |  |  |
| Incentive administration |  |  |
| Analysis |  |  |
| Reporting |  |  |
| Results presentations x 3 |  |  |
| Total |  |  |

Wave 2:

| Activity | Grade of staff | Number of days per staff grade |
| --- | --- | --- |
| Project Management |  |  |
| Survey design Review, develop and update methodology and sampling strategy |  |  |
| Questionnaire design Redevelop questionnaires, including cognitive testing of full questionnaire (including Welsh translation) |  |  |
| Advance Notification Letters |  |  |
| Fieldwork |  |  |
| Qualitative fieldwork Budget for at least 20 1:1 interviews, although we are open to using alternative qualitative research methods (Include Welsh translation) |  |  |
| Incentive administration |  |  |
| Analysis |  |  |
| Reporting |  |  |
| Results presentations x 3 |  |  |
| Total |  |  |

Wave 3:

| Activity | Grade of staff | Number of days per staff grade |
| --- | --- | --- |
| Project Management |  |  |
| Survey design Review, develop and update methodology and sampling strategy |  |  |
| Questionnaire design Redevelop questionnaires, including cognitive testing of full questionnaire (including Welsh translation) |  |  |
| Advance Notification Letters |  |  |
| Fieldwork |  |  |
| Qualitative fieldwork Budget for at least 20 1:1 interviews, although we are open to using alternative qualitative research methods (Include Welsh translation) |  |  |
| Incentive administration |  |  |
| Analysis |  |  |
| Reporting |  |  |
| Results presentations x 3 |  |  |
| Total |  |  |

Project total:

| Activity | Grade of staff | Number of days per staff grade |
| --- | --- | --- |
| Wave 1 |  |  |
| Wave 2 |  |  |
| Wave 3 |  |  |
| Total |  |  |

      - How well the tenderer shows that their proposed team composition and team management approach will ensure that the team will be able to deliver the project in full, even during busy periods or in periods of absence and/or illness.

      - Whether parts (if any) of the project will be sub-contracted. If it is proposed to sub-contract any of the work, the same details as those provided by the Supplier should be given about the qualifications, experience and responsibilities of sub-contractor staff who will be involved.

    - Quality standards (5%)

      - Whether the tenderer has satisfactorily demonstrated they are able to meet the professional accreditation and/or quality standards as set out in section 7.

      - How well the quality control plan submitted by the tenderer satisfactorily demonstrates the proposed internal procedures will effectively assure quality control as set out in clause 7.1 of the ITT.

    - Social Value (10%)

      - Tenderers are required to provide a response to all questions included in Annex D Social Value. Responses to each question must not exceed 1000 words. Please refer to section 11 for further details.

    - Security (pass/fail)

      - Tenderers are required to provide a response to all questions included in Annex B Security plan which is assessed on a pass/fail basis. Where tenderers are unable to meet HMRC’s data security requirements, they will not be awarded the contract.

  - All tenderers will be evaluated on the quality criteria as detailed in section 17.5, accounting for 70% of the total marks and price (see section 19 below), accounting for 30% of the total marks.

  - Tenderers must set out their tender according to the quality criteria set out under clause 17.5 but can add additional sections such as an introduction and summary.

  - HMRC may request tenderers to clarify elements of their proposal in order to assess the quality score.

## Security

  - HMRC reserve the right to clarify security responses they deem unsatisfactory. HMRC reserve the right to exclude a tenderer if their security responses do not meet its requirements.

## Price and how we assess price

  - The total three-year budget available for this contract is up to the maximum of £500,000.

  - Due to budgetary constraints, HMRC will not consider for award a bid with a total cost exceeding £500,000.

  - For evaluation purposes, price forms 30% of the tenderer’s overall score.

  - Each cost proposal will be scored up to a maximum of 100. Using the lowest total price submitted as the benchmark, a calculation will be made to establish in percentage terms how much cheaper the lowest bid is relative to other bids and the percentage will then be used to provide a score, as in the following example:

    - Lowest price is £400 and is awarded a score 100.

The next lowest price is £425 therefore £400/£425 = 0.94 x 100 = Score of 94

The next lowest price is £522 therefore £400/£522 = 0.77 x 100 = Score of 77

  - Please refer to the Tendering Instructions for further details on price evaluation.

  - Tenderers must separately provide a completed Cost Model detailing their fixed cost offer (excluding VAT) for all 3 waves giving a breakdown of costs in person days to each task, as outlined in the Cost Model. This must be sent separately from the main tender as per 13.3 above.

  - For the avoidance of doubt, the unit costs/rate provided in the Cost Model must be the total cost of delivering that activity/service, inclusive of all third-party costs.

  - Tenders that do not include a fully completed Cost Model will not be accepted. Rows can be added to the Cost Model as necessary to allow for the inclusion of each staff member working on an activity.

  - Payments will be triggered through the satisfactory completion of 5 milestones. Unless agreed in writing by both HMRC and the Supplier, these milestones will be as follows:

    - The first milestone will be the full completion of all activities prior to commencing quantitative fieldwork, including the production of research materials. This would include ‘Scoping and development (including Welsh translation of research documents overhead)’ and ‘Sampling’ in the Cost Model, as well as one quarter of ‘Project Management including attendance at meetings.

    - The second milestone will be the full completion of all activities related to the quantitative fieldwork, including the delivery of interim findings. This would include ‘Quantitative fieldwork’ in the Cost Model, as well as one quarter of ‘Project Management including attendance at meetings.

    - The third milestone will be the full completion of all activities related to the qualitative fieldwork, including the production of research materials, sampling and recruitment, fieldwork, data cleansing and analysis, the delivery of interim findings, report of findings and methodological approach. This would include ‘Qualitative fieldwork’ in the Cost Model.

    - The fourth milestone will be the full completion of all activities related to analysis and presentation of quantitative data. This would include the ‘Analysis’ and ‘Headline/Full presentations of findings’ in the Cost Model, as well as one quarter of ‘Project Management including attendance at meetings.

    - The fifth milestone will be the full completion of all activities related to final report. This would include ‘Reporting’ in the Cost Model, as well as one quarter of ‘Project Management including attendance at meetings.

  - HMRC may require additional meetings and presentations to those as itemised in clause 10.3 above. In case HMRC requires additional meetings or presentations, these shall be costed on an hourly basis or pro-rata’d for half-hour meetings or presentations using the relevant wave’s Additional Services table included in the Cost Model.

  - Translation of research documents into Welsh must be itemised as outlined in clauses 8.13 and 8.14.

  - If HMRC decides not to continue with a project at any stage due to external or internal factors unrelated to the Supplier’s performance, and the Supplier has already incurred costs associated to that project with the agreement of HMRC, this should be communicated in writing to HMRC within 5 working days of the Supplier being notified of the discontinuation. All incurred costs must be clearly identified and a justification for these costs must be provided. Any incurred costs identified will be subject to negotiation and agreement with HMRC.

  - The total cost to deliver the first year will be fixed in line with the Supplier’s Cost Model submitted with their tender.

  - The total cost to deliver the second and third waves will be projections based on the assumption that HMRC’s requirements will be consistent from waves two to three. Should HMRC wish to proceed with the second and third waves under the scope of this contract and there are no amendments to HMRC’s requirements then the costs submitted during the tender will be fixed within the subsequent statement(s) of work. Any cost amendments required as a result of potential changes to HMRC’s requirements will be calculated using the rate card contained within the Supplier’s submitted Cost Model and incorporated into the contract using RM6126 DPS Joint Schedule 2: Variation Form v.1.0.

  - Tenderers must include a fully completed rate card as part of their cost submission. The rate card template is included in the Cost Model.

  - The rate card will not be evaluated as part of the tender but will be included within the final contract to calculate any amendments to the year 2 and 3 costs if necessary.

  - The unit costs/rates provided within the cost proposal should be the same as the unit costs/rates provided within the rate card. HMRC reserves the right to clarify or exclude a Tenderer if they submit a cost proposal that has been calculated with unit costs/rates different to those included within their rate card where HMRC is not satisfied that the cost difference is not reasonable.

  - Where HMRC chooses to proceed with the second and third waves the Supplier shall have the right to request a price review of the relevant Cost Model tab one month prior to the start of the relevant wave. Any resulting price review to the unit costs requested by the Supplier shall follow the process detailed in Paragraph 24 ‘Changing the contract’ of the RM6126 Core Terms (which can be found in the draft contract).

  - Any increases to the unit rates of the relevant Cost Model tab, which HMRC and the Supplier agrees to following the price review, shall not exceed the Consumer Price Index rate for the 12 months preceding the date of the review as published by the Office of National Statistics on their website, or shall be capped at 5%, whichever is the lower.

  - The Supplier must be able to provide to HMRC evidence of increases to their costs as part of the price review.

## Summary of Evaluation Criteria

  - The scores for quality and cost will be added to provide an overall score from 0 to 100, as summarised below.

Scoring Matrix:

| Evaluation criteria | Weighting |
| --- | --- |
| Quality – tenders | 70% |
| - Addressing aims & objectives - Sampling and recruitment - Questionnaire development - Fieldwork, analysis and reporting - Qualitative research - Project Plan - Team - Quality standards - Social Value | 7.5% 12.5% 5% 12.5% 5% 5% 7.5% 5% 10% |
| Security | Pass/Fail |
| Price | 30% |
| Total | 100% |

  - The tender with the highest overall mark will be selected by HMRC as the tendering organisation deemed to best meet the requirement and provide greatest value for money.

  - Clarifications with tenderers may be required at any point of the tendering process in order to clarify any aspects of their proposals.

## HMRC eTrading System

  - HMRC has a “Purchase Order Mandatory Policy” and with effect from 11th November 2019 will process all purchase orders and all invoices using its eTrading system, provided by SAP Ariba.

  - Successful Tenderers are required to register on the SAP Ariba Network in order to transact with HMRC via the eTrading system and to ensure that they will continue to be able to receive purchase orders from and issue invoices to HMRC.

  - Registration for HMRC’s eSourcing and eTrading portals is undertaken concurrently and instructions are set out here: SAP_Ariba_Supplier_Master_Guide.pdf (publishing.service.gov.uk) and included in Annex I. SAP Ariba will not charge suppliers to HMRC, VOA or RCDTS to register on the SAP Ariba Network and suppliers will not incur any fees when transacting with HMRC, VOA or RCDTS across HMRC’s eTrading system. However, fees may apply when transacting with suppliers’ other customers over the SAP Ariba Network.

  - Suppliers to HMRC, VOA and RCDTS are not required to invest in any additional products or services from SAP Ariba or from any other supplier in order to transact with HMRC, VOA or RCDTS using HMRC’s eTrading system.

  - Payment will be made by BACS within 30 days of receipt of a valid invoice. The invoice total should match the relevant stated milestone cost in the contract, unless a different cost is agreed in writing or via a contract variation.

## Data security and protection

  - Tenderers are required to submit a security plan within their Tender submission. This will detail your approach to safeguarding confidential information including your company policies for handling sensitive documents and computer files from unauthorised access. This will contain details of how the following will be administered:

    - How tenderers will hold data on sampled participants.

    - How long tenderers will keep data on sampled participants.

    - What details about participants will be passed to recruiters and/or interviewers; and

    - How tenderers will destroy data once they have been used.  This must include originally transferred data files, copies of data files held on all computers, and copies held on archived back-up systems.

  - If you intend to involve sub-contractors at any stage of the project, please include details of how you will ensure their compliance with all aspects of the Security Plan.

  - A Security Plan questionnaire is attached (please see Annex B) which is assessed on a pass/fail basis. Where tenderers are unable to meet HMRC’s data security requirements, they will not be awarded the contract.

  - Where the highest scoring tenderer is not awarded the contract due to failing to meet HMRC’s data security requirements as per 22.3, HMRC reserves the right to award the contract to the next highest scoring tenderer, subject to that tenderer meeting HMRC’s data security requirements.

## Other Ethical Issues

  - To preserve confidentiality and anonymity, details of individual participants in the research must not be included in the analysis and reports.

  - Published outputs of statistics will be consistent with statistical disclosure guidelines, as advised by HMRC.

## Procurement Transparency

  - HMRC is obliged to publish tender documents for all contracts with a whole life value of over £10,000. It is a condition of bidding for this work that tenderers agree to the subsequent publication of the contract once awarded.

  - If Tenderers believe that any of the information requested is commercially sensitive, they should provide such information in a separate letter marked as such.

  - HMRC ITTs are commercially sensitive documents; the contents of any HMRC ITT should not be divulged to those without a business need to know.

## Group Bids

  - In the event of a group of service providers, suppliers submitting an acceptable offer, the group will be required to nominate a lead partner with whom HMRC can contract. Alternatively, the group will need to form themselves into a single legal entity before the contract is awarded. An undertaking that the group will so form themselves, if required by HMRC, must be provided when the tender is submitted.

  - A fully completed compliance check form which provides the information necessary for HMRC to undertake the appropriate tax compliance checks, including the details of any proposed sub-contractors and all group participants in the event of a group bid must be submitted with the tender. The Supplier Compliance Check Form alongside the Subcontractors Revenue Compliance Check form (annex E) can be found in the ITT email.

## Access to Government Information

  - Under the Government Code of Practice on Access to Government Information, the HMRC must reserve the general right to disclose either information about your tender or the tender itself, including your price or range of prices, once a contract is awarded. However, you may request that certain information is not disclosed if to do so would prejudice your legitimate commercial interests. Requests for non-disclosure must accompany your tender and include clear and substantive justification together with a time limit when any confidential information could be disclosed – this is not normally expected to be more than 7 years. It would be helpful, if appropriate, if you could keep the areas that you consider should not be disclosed separate from other areas of your tender. The terms of any confidentiality agreement (not the items themselves – they would remain confidential) would, if necessary, be available for publication.

## Commissioning Conditions

  - By submitting a response to the tender exercise HMRC will deem the tenderer accepts HMRC’s Mandatory Terms which are included within DPS Order Schedule 23.

  - Additional contractual information relating to the Protection of Information is included in Annex A.

# Contract Award

## Acceptance of Offers

  - HMRC reserves the right not to accept the lowest cost, or any, tender.

  - Unless you make any formal statement to the contrary, HMRC reserves the right to accept any part of the tender without accepting the remainder.

  - Acceptance of a tender/ award of contract will be confirmed by written communication from HMRC.

## Financial Capacity

  - HMRC will act in accordance with the Public Contracts Regulations 2015 (and subsequent amendments to that bill) and Cabinet Office Procurement Policy Note 02/13 (Supplier Financial Risk Issues) when specifying any minimum financial standards and undertaking financial assessments.

  - Where considered appropriate, on the basis of a financial assessment, award of contract may be conditional on a successful Tenderer providing a Parent Company Guarantee. If the guarantor is a charity, HMRC would need to establish whether anything in the charity’s constitution prevents them from performing this role and, if so, whether an alternative guarantor may be required. Where tenderers are unable to satisfy HMRC’s minimum financial standards, they will not be awarded the contract.

## Accessibility Requirement

  - Any reports or online forms users need to consume or interact with must be fully accessible to WCAG 2.2 AA and work with commonly used assistive technologies.