## Front Cover
SCHEDULE OF WORKS
FOR THE
ALTERATIONS
TO
BRIDLINGTON AMD CLINIC
AT
BRIDLINGTON & DISTRICT HOSPITAL
BESSINGBY ROAD
BRIDLINGTON
YO16 4QP
York Teaching Hospital NHS Foundation Trust
Wiggington Road
York
YO31 8HE
Date: | 2015-05-21
Job Nr | 50069.211
Revision: | Version 1
Revision Date: | 21st May 2015
`

## QA
BRIDLINGTON AMD CLINIC
CONTENTS
| Document prepared by |  | Alan Bedford | `
:
Signed
| Date |  | 9th June 2015
For Sweett Group on behalf of York Teaching Hospital NHS Foundation Trust
| Checked and Verified by | :
Associate Director
Signed
Date
For Sweett Group on behalf of York Teaching Hospital NHS Foundation Trust
* Delete as applicable, if uncontrolled state reason

## Contents
BRIDLINGTON AMD CLINIC
CONTENTS
QA
Section One | Preliminaries
Section Two | Preambles/Materials and Workmanship
Section Three | Schedule of Works |  | `
Section Four | General Summary
Section Five | Form of Tender
Appendix A
Appendix B | Trust Guidelines for Contractors Working for the York Hospitals NHS Trust
Appendix C
Appendix D
Appendix E
Appendix F
Appendix G
Appendix H
* Delete as applicable, if uncontrolled state reason

## Sect 1 - Prelims
BRIDLINGTON AMD CLINIC
SECTION ONE
`
PRELIMINARIES
* Delete as applicable, if uncontrolled state reason

## Sect 2 - Preambles
BRIDLINGTON AMD CLINIC
SECTION TWO
PREAMBLES/MATERIALS & WORKMANSHIP
* Delete as applicable, if uncontrolled state reason

## Sect 2 - M&W
BRIDLINGTON AMD CLINIC
SECTION TWO
MATERIALS AND WORKMANSHIP
| C | Existing site/buildings/services
| C10 | Site survey
| C11 | Site investigation
| C20 | Demolition
| C41 | Repairing/ Renovating/ Conserving masonry
| F | Masonry
| F10 | Brick/ block walling
| F30 | Accessories/ sundry items for brick/ block/ stone
walling
| F31 | Precast concrete sills/ lintels/ copings/ features
| K10 | Plasterboard dry linings/ partitions/ ceilings
| K11 | Rigid sheet flooring/ sheathing/ decking/ sarking/
linings/ casings
| K30 | Panel partitions
| K40 | Demountable suspended ceilings
| L20 | Doors/ shutters/ hatches
| L40 | General glazing
| M | Surface finishes
| M10 | Cement based levelling/ wearing screeds
| M20 | Plastered/ Rendered/ Roughcast coatings
| M50 | Rubber/ plastics/ cork/ lino/ carpet tiling/ sheeting
| M60 | Painting/clear finishing
| N | Furniture/Equipment
| N10 | General fixtures/ furnishings/ equipment
| N14 | General signage systems
| N15 | Fire and safety signage systems
| P | Building fabric sundries
| P12 | Fire stopping systems
| P21 | Door/ window ironmongery
| P31 | Holes, chases, covers and supports for services
* Delete as applicable, if uncontrolled state reason

## Sect 3 - SoW
BRIDLINGTON AMD CLINIC
SECTION THREE
`
SCHEDULE OF WORKS
* Delete as applicable, if uncontrolled state reason

## SOW-Mgt
BRIDLINGTON AMD CLINIC
Please insert individual figures and amounts in to the Qty, Unit, Rate and Amount columns
Item | Description | Qty | Unit | Rate | Amount
0.0 | THE WORKS
0.0.1 | To carry out alteration works to the existing AMD Clinic within Bridlington Hospital as shown in more detail on the layout drawing including all associated works. |  | item
0.0.2 | The works are to be carried out in strict accordance with the Preliminaries, Preambles, Specifications and Drawings; |  | item
0.0.3 | The Contractor must programme all works to achieve completion within the designated Contract period; |  | item
0.0.4 | The Contractor is to allow for out of hours and/or Weekend working to achieve completion within the designated Contract period; |  | item
0.0.5 | The Employer will not accept any claim from the Contractor for working outside normal working hours unless formally agreed in advance; |  | item
0.0.6 | Where materials are specified by manufacturers name, a full set of manufacturers instructions are to be retained on site and it is the Contractors responsibility that they are strictly observed at all times; |  | item
0.0.7 | The Contractor is to bring to the attention of the Contract Administrator (CA) at Tender stage any discrepancies or variations between the drawings, specifications, instructions and manufacturers instructions; |  | item
0.0.8 | The Contractor must also bring to the attention of the manufacturer/materials supplier immediately, any discrepancy between the materials supplied, the manufacturers literature or site conditions; |  | item
0.0.9 | The Contractor shall indemnify the Employer against all third party claims emanating from the works; |  | item
0.0.10 | The Employer and the CA reserve the right to amend or omit any items of the works by instruction. No claims for loss, expense or delay shall be allowed in connection with such; |  | item
| Total carried forward to Section 3 summary sheet |  |  |  | 0
0.1 | MANAGEMENT
0.1.1 | Supervision Allow for maintaining the same full time working Foreman on site, for the Full duration of the works to effectively programme resources, receive instructions from the CA, in full accordance with the Preliminaries section; |  | item
0.1.2 | The Foreman is to remain the same throughout the duration of the works, be experienced in this type of work, be responsible for supervision and control of these works, and be able to programme resources accurately, be able to monitor and coordinate sub contractors and suppliers. |  | item
0.1.3 | Safety/CDM Regulations This project is not notifiable to the Health & Safety Executive (HSE) as the Contract period is not expected to exceed 30 working days or 500 man days; |  | item
0.1.4 | The Contractor is to allow for acting as Principal Contractor as defined by the CDM Regulations 2015, and must include for all specific requirements detailed in the Preliminary clauses of the specification and Pre Construction information, contained within the Preliminaries section. |  | item
0.1.5 | The Contractor is to provide suitable Health & Safety Plans, Method Statements, Risk Assessements etc for the approval of the client and Health & Safety Representative, prior to any works commencing on site; |  | item
0.1.6 | The Health & Safety Plans are to provide full details of how the Contractor is to manage Health & Safety risks on site, taking into account the Preliminaries section A34; |  | item
0.1.7 | Security/Access Emergency Access/Escape through the Fire Exits, adjacent rooms including staircases and external pathways/roads etc must be maintained at all times for emergency use by members of staff / building users etc during the course of the works. Where the route is changed the diversion must be adequately signed. Method statements will be required showing how this access will be maintained and managed. Works that affect the client's normal operation of the building should be undertaken out of hours; |  | item
0.1.8 | The contractor must allow for protecting all work areas around the perimeter of the building where staff, pedestrians, vehicles etc have access to and shall include barriers, warning signs etc. Alternative suitably signed and protected pedestrian walkways are to be provided by the contractor where works interrupt existing pedestrian routes for the duration of the works; |  | item
0.1.9 | In conjunction with the items mentioned above the Contractor must provide suitable protection for the delivery route used by Trust staff. This is to include suitable framing and timber plywood sheets to form protected corridor to comply with infection prevention guidelines. All costs associated with this element are to be identified here and must include for protecting staff from debris, materials, tools etc falling from above; |  | item
0.1.10 | The Contractor is to ensure that the site is left secure and safe at all times, and must not be left open, particularly at the end of the working day or over weekends. All ladders and access routes to scaffold shall be removed or secured to prevent unauthorised access being gained to scaffold and subsequently through ward windows; |  | item
0.1.11 | Allow for all temporary screening to the works to protect the adjacent areas of the building from dust and other nuisances; |  | item
0.1.12 | The Contractor is to leave no tools or materials unattended on site at any time; |  | item
0.1.13 | The client shall accept no liability with regards to the above; |  | item
0.1.14 | General A photographic schedule of condition should be prepared by the contractor recording specific defects in the area subject to the works, and the approved contractor access routes, particularly of the corridor floors, walls etc adjacent to the works. The full extent of this is to be agreed with the CA prior to starting works on site; |  | item
0.1.15 | Clean away all rubbish and surplus materials regularly as necessary or as directed by the Contract Administrator. Scrub or clean all floors, metalwork, fittings, etc, eradicate all stains and splashes and leave every part of the Works included in the Contract in a sound and satisfactory condition, free from all defects at completion to the entire satisfaction of the Contract Administrator. Lockable Skips are required; |  | item
0.1.16 | The contractor must allow for locating, identifying, marking and protecting all services, cables, ducts, conduits, pipes, drains etc that may be within the work areas and provide the contract administrator with a suitably marked up plan identifying the same along with method statements on how this will be managed; |  | item
0.1.17 | The adjacent areas of the hospital will remain occupied and in use throughout the period of the works. The building services and supplies to the hospital shall be maintained throughout the duration of the works. Any interruption to the hospital shall be with prior agreement and shall be for the minimum period possible. All preparation work shall be complete prior to interruption of the supply. A detailed method statement shall be approved prior to any works being carried out on the existing hospital services. No services shall be isolated without prior agreement; |  | item
0.1.18 | All personnel employed by the contractor will comply with York Hospitals Estates Department Policy on the Control of Contractors and all other relevant standards adopted by York Teaching Hospitals NHS Foundation Trust [see Appendix for list of documents which can be made available upon request]; |  | item
0.1.19 | The Contractor shall identify here all the costs associated with the hire, delivery, emptying etc of waste skips which are to be lockable units and sited in position to be agreed with Trust prior to works starting on site; |  | item
0.1.20 | Drawings/Specification & Dimensions All dimensions provided in the descriptions and drawings are approximate and the Contractor, his sub contractors and suppliers shall examine the existing site , to ascertain the full extent of the works and take all necessary dimensions before preparing the tender. The Contractor shall insert quantities within the schedule of works; |  | item
0.1.21 | The Contract drawings are to be read as a whole. Any areas of works shown or described on the drawings but omitted from the specification, and vice versa are to be included by the Contractor in his Tender; |  | item
0.1.22 | It is the Contractors responsibility to check that the tender documentation correlates with the contents list and inform the CA if there are any discrepancies or missing documentation, so that this can be rectified immediately; |  | item
0.1.23 | Where reference is made to British Standards and the British Standards Code of Practice, the latest version will apply. Where no particular standards are available, the materials shall be the best of their respective kinds and to the approval of the CA; |  | item
0.1.24 | Any Contractor Design element of the works is to be provided for the Trust to comment on prior to works being carried out on site. This is not client design and does not absolve the contractor or specialist sub contractor from their design obligations and responsibilities; |  | item
| Total carried forward to Section 3 summary sheet |  |  |  | 0

## SOW-GENERAL
BRIDLINGTON AMD CLINIC
Please insert individual figures and amounts in to the Qty, Unit, Rate and Amount columns
Item | Description | Qty | Unit | Rate | Amount
1 | DEMOLITION & STRIP OUT WORKS
1.1 | Asbestos
1.1.1 | The contractor is to be provided with a copy of the pre-refurbishment and demolition asbestos report prior to commencement of works. The contractor is to allow a Provisional Sum for the removal of any asbestos based materials. Allow for safe removal and disposal. Provisional Sum £1000.00 | 1 | prov sum | 1000 | 1000
1.2 | Demolition & Alteration (including all associated disposal costs)
1.2.1 | The contractor shall allow for carefully taking up existing floor finishes including any vinyl concealed by carpets, coved skirtings etc. Include for the removal of residual adhesive and clear debris from site. |  | m2
1.2.2 | Carefully take down and remove the existing internal walls in locations indicated on plan. The contractor is to include for the provision and installation of any temporary support as necessary prior to the removal of the walls. |  | item
1.2.3 | Where applicable, all existing surface mounted outlets/ sockets/ switches, power and data etc. to be carefully removed where affected by the proposed works. Existing cabling to be removed where no longer required or re-routed to suit new room layouts, all to contractors details and specification. All surfaces to be made good to accept decoration. |  | item
1.2.4 | Allow for constructing temporary hoardings in positions as necessary to segregate work area from staff areas, comprising stud partion with pre finish [wipeable surfaces] and sealed around all edges, sides, doors etc. Access door to be provided in location from main corridor side of room. |  | item
1.2.5 | Remove existing doors and frames as indicated on plan and dispose of off site. |  | item
1.2.6 | Carefully remove all loose furniture, fittings and equipment and store as necessary throughout the duration of the works. |  | item
1.2.7 | Carefully take down existing suspended ceiling tiles, grid, shadow battens and clear debris from site. Also include for the removal of the existing plasterboard ceilings if necessary depending on service runs and dispose of accordingly. |  | m2
| Total carried forward to Section 3 summary sheet |  |  |  | 0
2 | INTERNAL DOORS
2.1 | New Doors
2.1.2 | Supply and install new FD30S 51mm thick veneer (veneer to match adjacent existing doors) solid core timber doors and frame including all ironmongery into openings as indicated on drawing 50069.211 Rev.B. Also include for the supply and installation of the following; - 1½ Pairs of Butt Hinges BS EN 1935. 300mm x 30mm pull handles, kick plates to both sides of door, euro profile lock. Briton 2001 magnetic lock. - Combined intumescent heat, smoke and acoustic seals; 'Lorient LP1504DS' or similar approved 15 x 4mm combined seals rebated into door frame. - Door closer to comply with BS 8300, door closers must not require an opening force greater than 30N along the leading edge to operate in accordance with Approved Doc. M; - Ironmongery to be from 'Laidlaw Orbis' range, Laidlaw Ltd, Unit 1 Halifax Court, Halifax Road, Dunston, Gateshead, Tyne & Wear NE11 9JT. Tel. 0191 461 4100; - Signage "Fire Door Keep Shut" fixed to both sides of the door - Fire Resistance ID disk fitted both sides of door; |  | item
| Total carried forward to Section 3 summary sheet |  |  |  | 0
3.0 | FLOORING
3.1 | Flooring - Proposed New
3.1.1 | Supply and lay latex self-levelling screed if required to the existing floor in accordance with manufacturer's installation instructions as required to provide a suitable surface on to which to install new floor coverings. |  | m2
3.1.2 | Supply and install new vinyl floor covering. To be 'Tarkett-Marley IQ Optima' (colour blue 857) with continuous vinyl skirtings to match skirtings to be 100mm high complete with black pvc capping strip along the top edge of the vinyl skirting. Tarkett-Marley Floors Ltd Tel. 01622 854000. www.tarkett.com. |  | m2
3.1.3 | Contractor to seal all floor edges with door frames, architraves etc. using anti-fungal silicone sealant type soudal silirub clean room silicone sealant. |  | m
| Total carried forward to Section 3 summary sheet |  |  |  | 0
4.0 | Proposed Ceilings
4.1 | Allow for installing 50 x 25mm timber shadow battens to perimeter of rooms where suspended ceiling is to be fitted. |  | nr
4.2 | Supply and install new suspended ceiling to the areas affected by the works. To be 'Rockfon Medicare Standard' tiles with exposed 24 grid system. Modular size 600mm x 600mm. New ceiling to be installed at height of existing ceilings. Rockfon, 26-28 Hammersmith Grove, Hammersmith, London W6 7HA. Tel. 0208 222 7457. www.rockfon.co.uk |  | m2
4.3 | Suspension system to include for all hangers, fixings, main runners, cross members, primary channels, perimeter trims, splines, noggings, clips, bracing, bridging etc. |  | nr
| Total carried forward to Section 3 summary sheet |  |  |  | 0
5.0 | WALL FINISHES/ DECORATIONS
5.1 | Prepare all surfaces intended for decoration in accordance with the paint manufacturer's instructions. Infill fixing holes and undertake minor plaster repairs. Clean and prime surfaces. |  | m2
5.2 | Painted surfaces to existing joinery (doors, door frames, architraves, shadow battens, skirtings and the like) to be prepared and sanded to provide smooth and sound surface, filling any holes with a proprietary filler, prepare to BS800 followed by applying primer, 1 full coat Johnstones Professional undercoat, 2 full coats Johnstones Professional gloss trade paints or similar or equal approved; colour to be confirmed. |  | m2
5.3 | Prepare wall surfaces, and ceiling surfaces where applicable. Prepare and rub down surfaces, abrade to provide smooth sound surface, filling any holes with a proprietary filler, prepare to BS800 followed by applying 2 full coats of Johnstones Acrylic Eggshell trade paint, similar or equal approved. Colours to be confirmed. |  | m2
| Supply and install 'Altro Whiterock' semi-rigid pcvu cladding (colour: white) to full height walls to Disposal Room 22. Location: full height walls to Disposal Room 22. • Base: Skim plaster as clause. - Preparation: Surface sound and free from all contaminates. Dusty or friable surfaces to be stabilised using appropriate stabilising solution. • Fabricated underlay: Not required. • Flooring roll: - Manufacturer: Altro Walls, 48 Pinbush Road, South Lowestoft Industrial Estate, Lowestoft, Suffolk NR33 7NL - OR SIMILAR APPROVED. Tel: 01502 561364 Fax: 01502 588848 Email: walls@altro.com Web: www.altro.com. Product reference: Altro Whiterock semi rigid PVCu cladding. - BS EN 685 class: manufacturer to advise. - Width: 1220mm. - Thickness: 2.5mm. - Colour/ pattern: Standard White W103/W104. • Adhesive (and primer if recommended by manufacturer): Altrofix W139 two part urethane adhesive. • Accessories: Not applicable. |  | m2
| Total carried forward to Section 3 summary sheet |  |  |  | 0
6.0 | PARTITIONS
6.1 | Supply and install new partitions and infilling in locations indicated on drawing. Partitions to be 122mm thick 'Knauf' drywall or similar approved. To comprise of 70mm 'C' studs and 72mm 'U' channels and 2 x 12.5mm 'Knauf' standard wallboard with acoustic insulation inserted between studs. To extend to underside of structural soffit. Apply 'Knauf' sealant at all junctions between wall and adjoining structures. Knauf Tel. 01795 424499. |  | m2
6.2 | Manufacturer: Knauf Drywall, Kemsley, Fields Business Park, Sittingbourne, Kent, ME9 8SR Tel: 01795 424499. Fax: 01795 428 651. Email: technical@knauf.co.uk Performance: Fire resistance: 60/60 Integrity/insulation (Minutes), when tested to BS476: Parts 20&22: 1987 Sound Insulation: 52dB Rw, when tested to BS EN ISO140-3 BS2750: Part 3 1995 Impact Duty: Severe, in accordance with BS5234, Section 1.6: Severe Maximum Height: 4600mm at 600mm centres, 4900mm at 400mm centres, 5100mm at 300mm centres Limiting deflection: L/240 Maximum air pressure: 200pa Construction: Partition Width: Generally 122mm (excluding finishes). Where opening are to be infilled, thickness to match existing. Head condition: To underside of structural soffit Head deflection allowance: 20mm (tbc by structural engineer) Head track fillets: 2 x 15mm Knauf Fireshield Stud configuration: Knauf 70mm 0.55 gauge 'C' Studs at centres to suit maximum height* *Reduce stud centres to 400mm maximum for areas to receive a ceramic tiled finish. Head/Floor Channels: Knauf 72mm 'U' Channel (utilising deep flange 'U' channel if deflection allowance is specified). Plasterboard Linings: Boarding: 2 x 12.5mm Knauf Standard Wallboard. Outer layer 1 x 12.5mm Knauf Moistureshield to stud walls around Wet areas. Horizontal Board joints: Knauf Flat Fixing Plate required (please refer to design details) Fixings: Knauf Drywall Screws as clause 590 Sealant: Knauf Sealant as clause 515 Cavity Insulation: Thickness/type: Finishing: Tape and Joint: Taped and Jointed for a Seamless finish using Knauf Jointing Products as per clause 471 Primer: One coat of Knauf Wallboard Primer applied immediately after taping and Jointing. Skim Finish: Skimmed with Knauf Finishing Plaster as clause 680. General: To be installed in accordance with Knauf Drywall's recommendations Include for additional studs and support as necessary in locations where fittings are to be fixed to walls. Include for the application of acoustic sealant to perimeter junctions with walls, floors and ceilings and around openings where necessary. ACOUSTIC SEALANT • Manufacturer and reference: Knauf Sealant, by Knauf U.K. • Location: At junctions between wall(s) and adjoining structure, and at other airpaths. • Apply as a continuous bead to clean, dry, dust-free surfaces, leaving no gaps. • After application of sealant, bulk fill gaps in excess of 6mm between floor and underside of walls using Knauf joint compound. SEALING GAPS AND AIR PATHS • Location of sealant: To perimeter abutments and around openings. - Pressurized shafts and ducts: At board-to-board and board-to-metal frame junctions. • Application: To clean, dry and dust free surfaces as a continuous bead with no gaps. - Gaps greater than 6 mm between floor and underside of plasterboard: After sealing, fill with jointing compound. ACOUSTIC SEALANT • Sealant: Knauf Sealant. - Location: To perimeter junctions with walls, floors, and ceilings and around openings. - Before fixing boarding, apply as a continuous bead to clean, dry, dust-free surfaces, leaving no gaps. After application of sealant, fill gaps greater than about 6mm with Knauf Jointing Compound. SERVICE PENETRATIONS • The dry lining contractor must liase with other contractors to ensure that fire resistance and other specified performance requirements are not impaired by service penetrations. - In particular: Fire Dampers. - Form framed openings accurately for grouped services, ducts, etc. allowing for Knauf Fire Bats / Fire Stopping, Knauf Technical Lit. - Provide insulation backings to recessed electrical outlets and switches as recommended by Knauf U.K.
| Total carried forward to Section 3 summary sheet |  |  |  | 0
6.2 | IPS PANELS & WASHBASINS
6.2.1 | Supply and install new IPS panels in positions indicated on drawing no. 50069.211 Rev. B. All IPS must be HTM64 compliant. Core Material: 18mm thick V313 MR grade chipboard. Frame: Cladding and plinths to match. Edge treatment: Edged on non post-formed edges in 2mm PVC. Colour: IPS colour to be confirmed. IPS Units to extend up to ceiling level and be sealed if ceilings are of plasterboard construction. IPS units to extend above ceiling (trimmed proud) where practical and ceilings are of a suspended construction. |  | Item
6.2.2 | Supply and install new wash basins to IPS. Manufacturer: Armitage Shanks ‘HTM64 LB H Contour 21’ hospital pattern wash basin. - Web: www.idealstandard.com. - Email: info@thebluebook.co.uk. - Product reference: S2154 (LB-H M) Contour 21 back outlet washbasin in vitreous china 500 mm x 400 mm, no tapholes, no overflow, and no chainstay hole. • Wastes: S8746 Strainer for Contour basin outlet. • Traps: S8920 1¼" Resealing bottle trap, self-colour plastics, multipurpose outlet, 75 mm seal. • Accessories: S8750 1¼" Outlet adapter and S9161 Concealed hangers, toggle bolts and clips. All hot & cold water services to be HTM64 compliant. Taps to be 'Ideal Standard' A4553(AA) (TB H2A) Markwik 21 integral thermostat, single sequential lever bib mixer, single flow horizontal outlet, 2 x 1/2in inlets at 200mm centres fixed to IPS unit to be installed in accordance with manufacturer's recommendations. Tap connections not to be flexi-connection. N.B. New wash basins to be in locations indicated on drawing no. 50069.211 Rev.B |  | Item
| Total carried forward to Section 3 summary sheet |  |  |  | 0
6.3 | MISCELLANEOUS
6.3.1 | Signage - supply and fix new door and directional signs to newly formed rooms. To be yellow with contrasting lettering and to include tactile signage where appropriate. Wording of signage to be agreed. Allow a provisional sum of £1,000.00 for contractor to appoint a specialist signage sub-contractor to design, manufacture and install the signage. | 1 | prov sum | 1000 | 1000
6.3.2 | Windows - Privacy Film. Supply and fix privacy film to the windows to the newly formed consulting rooms. Client to confirm the following in relation to the blinds - Remove existing blinds. Supply and install new blinds, to be vertical clinical blinds to be supplied by 'Solo' or similar approved. |  | Item
| Total carried forward to Section 3 summary sheet |  |  |  | 0
7 | MECHANICAL & ELECTRICAL WORKS
7.1.1 | All mechanical and electrical works to be carried out in accordance with the drawings and specification as listed below) as provided by JH Partners. The contractor must submit an elemental M&E cost breakdown at tender stage.
7.1.2 | Mechanical Works (in accordance with drawings 0872-(59)-001 Rev.T1 Mechanical Services Heating and Mechanical Ventilation. Existing and Proposed Layout. 0872-(59)-002 Rev.T2 Mechanical Services Hot and Cold Water Services and FW Drainage. Existing and Proposed Layout. |  | item
7.1.3 | Electrical Works (in accordance with drawings 0872-(69)-001 Rev. T1 Electrical Services Fire Alarm and Lighting Layout. 0872-(69)-002 Rev. T1 Electrical Services Small power and containment layout. 0872/S/E Rev.T1 Electrical Services Specification. |  | item
8 | GENERAL
8.1 | Allow a contingency sum of £1,000.00 for unforseen works to be expended or deducted at the discretion of the Contract Administrator. | 1 | prov sum | 1000 | 1000
| Total carried forward to Section 3 summary sheet |  |  |  | 0

## Section 3 Summary
BRIDLINGTON AMD CLINIC
SECTION 4
COLLECTION
|  | Description | Qty | Unit | Rate | Amount
Schedule of Works Summary/Collection Page
BUILDING SCHEDULE OF WORKS
0.0 | THE WORKS | THE WORKS
0.1 |  | MANAGEMENT
1 | DEMOLITION & STRIP OUT WORKS | DEMOLITION & STRIP OUT WORKS
2 |  | INTERNAL DOORS
3.0 |  | FLOORING
4.0 |  | Proposed Ceilings
5.0 |  | WALL FINISHES/ DECORATIONS
6 |  | PARTITIONS
7 |  | MECHANICAL & ELECTRICAL
8 |  | GENERAL
|  |  |  | TOTAL CARRIED TO GENERAL SUMMARY | £

## Sect 4 - Gen Sum
BRIDLINGTON AMD CLINIC
SECTION FOUR
`
GENERAL SUMMARY
* Delete as applicable, if uncontrolled state reason

## Sect 4 - GENERAL SUMMARY
BRIDLINGTON AMD CLINIC
SECTION FOUR
GENERAL SUMMARY
Item | Description | Qty | Unit | Rate | Amount
Section One - Preliminaries
Section Two - Preambles
Section Three - Schedule of Works
|  |  | TOTAL CARRIED TO TENDER RETURN FORM | £

## Sect 5 - FORM OF TENDER
BRIDLINGTON AMD CLINIC
SECTION FIVE
`
FORM OF TENDER
* Delete as applicable, if uncontrolled state reason

## APPENDIX A
BRIDLINGTON AMD CLINIC
`
APPENDIX A | APPENDIX A
ASBESTOS INFORMATION
* Delete as applicable, if uncontrolled state reason

## APPENDIX B
BRIDLINGTON AMD CLINIC
`
APPENDIX B | APPENDIX A
Trust Guidelines for Contractors Working for the York Hospitals NHS Trust
Asbestos policy
Codes of Practice for Contractors
Contract award criteria
Fire Prevention
Maintaining confidentiality
Parking
Procedures for the Control of contractors
Race Equality Scheme
Working on electrical installations
For signature