Arts Council England Invitation to Tender

Title: Museum Development Impact Evaluation

Reference number: ART011-0086

Deadline for receipt of tender proposals: 12 noon, 26 January 2016

This Invitation to Tender consists of:

Section 1: 	Background

Section 2: 	Specification

Section 3: 	Instructions to bidders

Section 1: Background

Arts Council England champions, develops and invests in artistic and cultural experiences that enrich people's lives.  We support a range of activities across the arts, museums and libraries - from theatre to digital art, reading to dance, music to literature, and crafts to collections.

Great art and culture inspire us, bring us together and teach us about ourselves and the world around us. In short, they make life better. Between 2015 and 2018, we will invest £1.1 billion of public money from government and an estimated £700 million from the National Lottery to help create these experiences for as many people as possible across the country.

Arts Council England’s 10-year strategic framework and Goals 3 and 4

Arts Council England has recently published its refreshed strategic framework, Great Art and Culture for Everyone, which describes how the Arts Council’s vision for England will be achieved.  This refreshed strategy runs until 2020 and brings together previous strategies for the arts and for museums and libraries.

At the heart of this document are five inter-related strategic goals, which guide the Arts Council’s activity and investment:

- Excellence is thriving and celebrated in the arts, museums and libraries

- Everyone has the opportunity to experience and to be inspired by the arts, museums and libraries

- The arts, museums and libraries are resilient and environmentally sustainable

- The leadership and workforce in the arts, museums and libraries are diverse and appropriately skilled

- Every child and young person has the opportunity to experience the richness of the arts, museums and libraries

Great Art and Culture for Everyone describes Arts Council England’s aspirations for Goals 3 and 4, and in particular that ‘museums and libraries are resilient and environmentally sustainable’ and ‘The leadership and workforce in the arts, museums and libraries are diverse and appropriately skilled.’

Section 2: Specification

Introduction

Museums bring collections and the stories they hold to life, providing opportunities for enjoyment, learning and wellbeing. It is understood more than ever that their key role is to work alongside the communities they represent to collect, care for and share knowledge about material that reflects the rich history of the UK and the wider world.

The climate in which museums operate is changing on an unprecedented scale. The sector is experiencing long-term budget cuts and a culture change to reduce reliance on public funding, combined with a growing need to value and demonstrate the public impact of museums.

The pace and scale of this change must be appreciated by everyone working in the sector, so that museums can reassess their position, their role and their future. Armed with a fresh vision, museums need to invest in the people that make up their workforce so that they are flexible, adaptable and able to implement necessary change.

Museums Development Programme

From August 2012 to 31 March 2015 Arts Council’s aim was to ensure that there was suitable development support available to all accredited museums in England so that benefits to audiences and communities could be maximised. Arts Council did this by delivering a national network of museum development services that complemented other strands of Renaissance activity, and museum development services provided by other agencies.

The nine organisations successful in becoming Museum development providers, and the amounts they received over this three year period were:

- Bristol City Museum and Art Gallery and Archives; Plymouth City Museum and Art Gallery; Royal Albert Memorial Museum and Art Gallery; South West Federation of Museums and Galleries - £1,192,000

- Wolverhampton Museums, Galleries and Archives Service with the Marches Network.- £832,000

- Leicestershire County Council - £719,887

- Manchester Partnership (with Cumbria Museums Consortium) - £880,000

- Museum of London - £650,190

- Norfolk Museum and Archaeology Service - £1,141,000

- Royal Pavilion and Museums, Brighton and Hove; HCC Arts and Museums; Chatham Historic Dockyard Trust; Oxfordshire County Museums Service - £1,400,000

- Tyne and Wear Archive and Museums - £416,000

- York Museums Trust - £840,000

Museum Development is a £3 million per annum sector wide programme to drive development and deliver sustainability, resilience and innovation in England's regional museums. The programme is made up of investment from Arts Council with partnership funding from individual local authorities.

The total value of Museum Development grant investment by ACE was £9 million between 2012/15 in 9 grants.

Overarching Programme Aims

Through this funding Arts Council  aimed to see the high level national strategic goals, applied locally using local expertise to address local need, set within a joined up approach to cultural provision. In practice this was intended to take the form of:

- helping museums to deliver outcomes aligned to local need and local political agendas via, for example, strategic commissioning

- supporting forward planning, organisational health, sustainable business models, and appropriate governance and leadership

- supporting museums to genuinely connect their collections and mission to their communities and interest groups

- supporting museums to achieve increased user figures and greater levels of satisfaction

- supporting museums to develop their collections and engagement through specialist advice

- empowering museums to work together in self-sustaining networks to share skills and meet their own basic training needs

Museum Development programme funding formula

In the periods 2012-13, 2013-14 and 2014-15, £3 million of funding was available per annum. For the period of 2012-13 the length of the programme was eight months starting from August 2012. The total spend during this period was t £2 million in total.

Organisations were free to bid for any amount of money to provide museum development provision for any particular area. However, in making decisions on allocations, Arts Council England referred to the following table, which gave an indication of need, expressed as a percentage and based on a mix of factors:

 population

 number of Accredited museums

 geographical size of region

 museums needing museum mentor support (formerly curatorial advisors)

| Region | Funding allocation expressed as a percentage of the total funding available, derived from an equally weighted average of population/Accredited museums/ geographical area/ museums needing museum mentor support |
| --- | --- |
| East | 13.3 |
| East Midlands | 9.0 |
| London | 8.1 |
| North East | 5.2 |
| North West | 11.0 |
| South East | 17.5 |
| South West | 14.9 |
| West Midlands | 10.4 |
| Yorkshire | 10.5 |
| Total | 100.0* |

*Note: these figures are indicative only and rounded to one decimal place. The end total is therefore 99.9%.

Source data

Population is based on the mid-2009 figures from Office for National Statistics (ONS).

Accreditation data is based on the database October 2010.

Geographical data is based on 2007 standard area measurement derived from ONS.

Requirements and Proposed Methodology

Investing in this report at this time when the future form of museum’s development provision is being reviewed is important, the evaluation will provide us with enough scope to challenge the current operating models and enable us to make decisions regarding the business case for the programme.

Evaluation specification

Arts Council England’s aim is to evaluate Museum Development funding programme (2012/15) to identify the impact of the investment against the over-arching programme aims and provide effective museum development lessons and case studies that can be shared more widely.

We would like to look at the  programmes of development activities  undertaken between 2012/15 and to investigate the impacts produced by or attributed to these interventions  and how these led to the achievement of the desired goals, also to better understand what  best practice looks like and what conditions need to be in place in order to achieve maximum impact.

Arts Council England is seeking a service provider to analyse the current data sets collected across the regional programmes as part of this work. There are several providers that undertake annual benchmarking surveys.   From this work, the service provider will  identify a  core data set which could be used to support future investment and could potentially be linked into any providers funding agreements.

Evaluation Questions and Methodology

The Service Provider will aim to address the following questions:

An evaluation of the impact of the programme against programme aims

Did the programme produce the intended impacts in the short term? What are the prospects for the programme producing the intended impact in the longer term?

Nature of programme impacts and their distribution

Did these impacts reach the intended beneficiaries?

Are the impacts likely to be sustainable?

How does the programme work?

How did the programme contribute to the intended impacts?

What were the particular features of the programme that made a difference?

What has been the quality of implementation in different regions?

To what extent are differences in impact explained by variations in implementation?

Match of intended impacts with programme needs

To what extent did the impacts match the needs of intended beneficiaries?

What is the relationship if any between programme impacts and the funding from Arts Council per region as designated by the funding formula for this programme?

Value analysis

Did the investment lever in additional investment?

Are the additional investment sources gained likely to be sustainable and are they new sources of income to the organisation?

We anticipate the research methodology consisting of all or some of the following methods:

- Stakeholder interviews with programme staff (ACE and MD programme providers)

- Document review of existing programme documentation and a sample of grant application forms.

- Analysis of the current data sets collected across the regional programmes. There are several providers that undertake annual benchmarking surveys.   From this work, we would like to identify a  core data set which could be used to support future investment and could potentially be linked into any providers funding agreements. We would anticipate data sets being used to baseline and to track progress during the programme.

- Interviews with stakeholders who have contributed partnership funding. Depth interviews and case study research undertaken with a sample of museums participating in programme activities across the nine regions including identifying enablers and inhibitors. Where appropriate this research could be used to highlight stories of change, barriers, successful approaches and key lessons learnt through the programmes.

Research suppliers are asked to note the ideas for a research methodology suggested above and outline how they would implement a research strategy incorporating these ideas and suggestions with associated costs for each strand.

Suppliers are welcome to suggest fully costed alternative or additional research methods that meet the aims and objectives of the research and come within the budget. Suppliers should include in detail the phasing of different research approaches over the course of the contract. Suppliers should also provide information on how research participants will be engaged, conduct the research fieldwork and how they would ensure quality of data analysis and reporting outputs.

Expected outputs and deliverables

Objective

Evaluate the Museum Development funding programme to determine whether the aims and outcomes of the programme have been achieved. Refer to Tender documentation for further information.

Material produced (output)

Top line findings presentation and slides Final written report Full set of data tables with cross tabulations in a readily accessible format such as excel Minimum of nine case studies which highlight work of museum development providers or organisations supporting the MD programme e.g. Major partner Museums or across themes A set of research tools (for example, survey tool, topic guides, sampling framework) and methodology note.

Research suppliers are asked to note the proposed outputs expected and are welcome to suggest additional or alternative outputs they feel could be useful for Arts Council England

Procurement and Project Timetable

| Activity | Date |
| --- | --- |
| *Deadline for questions | 12 noon on 15 January 2016 |
| Tender deadline and initial evaluation of bids | 12 noon on 26 January 2016 |
| Bidder clarification meetings (if applicable) ** | 1 February 2016, London/ Manchester ACE offices tbc |
| Contract initiation meeting | 4 February 2016, Manchester or London ACE offices tbc |
| Presentation of initial work (including outline of proposed report contents) | End March 2016, Manchester or London ACE offices tbc |
| Draft of report + technical report/appendices | April 29 2016, Manchester or London ACE offices tbc |
| Final report | 16 May 2016 |

*Bidders should raise any queries they have about the requirements by sending an email to Eve.Macphee@artscouncil.org.uk quoting the reference number provided on the ITT.

**We reserve the right to carry out clarifications if necessary; these may be carried out via email or by inviting bidders to attend a clarification meeting. In order to ensure that both ACE’s and bidders’ resources are used appropriately, we will only invite up to three (the ultimate number will depend on the closeness of scores) highest scoring bidders to attend a clarification meeting. Scores will be moderated based on any clarifications provided during this meeting. You are responsible for all your expenses when attending such meetings. ACE reserves the right to vary all dates in this Invitation to tender, to terminate this procurement process and/or decide not to award a contract.

Research suppliers are asked to note the above delivery timescales (contract initiation meeting onwards) and include in their proposal how they would work towards these timescales.

Duration of Contract

Arts Council England will award the contract to the successful supplier for the period of February 2016 – May 2016. Exact dates will be confirmed at appointment and contract commencement.

Account Management

In performing the services required under this contract the supplier will report to Eve MacPhee and Kathy Fawcett, Relationship Manager Museums.

The Service Provider will maintain excellent communications with the Arts Council England at all times ensuring that it is well informed, aware of issues and central to decision making in relation to progress.  The successful bidder will:

- Identify a named contact acting as Contract Manager. The designated person will carry prime responsibility for the contract and will be the Accountable Officer

- Identify a named contact person as Service Manager. The designated person will carry prime responsibility for the delivery and implementation of services under this contract. The Service Manager and Contract Manager can be the same person, provided they have the relevant skills.

- The Contract Manager/Service Manager will liaise with and take instruction from the Arts Council England’s Contract Manager.

Include if appropriate to your contract details about:

    - Staff qualification and training requirements.

    - Staff supervision requirements

    - Possible staff transfer (TUPE) as part of the mobilisation plan.

We welcome consortium bids. Bidders should identify areas where it is considered that third parties (including sub-contractors) may be required to provide services. Bidders should identify all such third parties in their response along with details of their scope of involvement.

The Lead Bidder shall remain the point of contact for the Arts Council England and problem resolution. The Arts Council England shall enter into the contract with this Lead Bidder. The Lead Bidder will ensure that all terms and conditions of its agreement with the Arts Council England flow through to the third party. The Lead Bidder shall ensure continuity of service in the event that the third party fails to perform.

The supplier should provide weekly contract updates via email throughout the term of the contract. Additional meetings can be scheduled as and if required in discussion with the project managers at the Arts Council. These can be held at the Arts Council’s Manchester, Birmingham, London, Bristol, Brighton, Nottingham, Leeds or Newcastle offices, or via video conferencing between these as agreed by the parties.

Contract Value

The approximate value for the contract is in the range of £24,000 to £35,000 including VAT and expenses.  Bids in excess of £35,000 including VAT and expenses shall be excluded as unaffordable and will not be assessed against the evaluation criteria below.

You should provide an informed estimate of the cost of the project in a Table of

Charges

Payment Structure and billing requirements

Payment will be made on the achievement of agreed contract milestones. The payment profile will be agreed with the successful contractor and set out in the contract terms and conditions

Logo

The Arts Council England logo should be used alongside the supplier’s logo on all reporting outputs. Arts Council England will advise on house style guidelines at project set-up. The Arts Council England shall own all intellectual property created for it as part of the contract.

Section 3: Instructions to Bidders

Evaluation Criteria

You are required to respond to ALL of the criteria below.  To assist our evaluation of your tender submission, please ensure you clearly cross-refer your responses to the assigned numbers. Any relevant supporting tender documentation must also be clearly identifiable by a criteria number.

- Quality Criteria

65 marks will be allocated to your response to the Quality Questions (table 1 below). Each question will be scored using the methodology in the table 2 below.

Your overall score for each question will be calculated by multiplying the quality score you receive with the weighting for that question, set out below. This score will then be divided by the total maximum available score for the Quality Criteria (325) and multiplied by 65% to get your final score for that question.

Example: assume Bidder A scores 3 for Question 1: the formula is 3 x 10 = 30, 30 ÷ 325 x 65 = 6.00%

35% of the marks will be available for your Price Proposal. The methodology for scoring price is set out further below.

Your responses should be supported by evidence/previous successful implementation of proposed solution for meeting our requirements.

Please note – Though criteria are numbered, this does not relate to any order of importance

Table 1

| Quality Criteria | Weighting |
| --- | --- |
| A demonstrated understanding of the background to the research and the aims and objectives | 10 |
| Please detail your research methodology for meeting all of the requirements set out above. Please include a timetable for delivering the services. You should support your answer by reference to your previous relevant experience; setting out why your methodology is appropriate for this contract. You should also explain how you will ensure effective contract management and outline your proposals for communicating effectively with ACE and other stakeholders in delivering this contract. | 30 |
| 3. Please demonstrate your ability to deliver accurate, concise and well -structured written research by submitting two examples of published reports. Please include the reports as part of your bid or provide URLs. | 5 |
| 4. Skills and experience of the key personnel proposed for this contract in: delivering research in the arts and cultural sector ; and conducting analysis of equality and diversity and about workforce development | 20 |

Table 2

| Scoring Methodology |
| --- |
| 0 | Very Poor | No response or partial response and poor evidence provided in support of it. Does not give ACE confidence in the ability of the Bidder to deliver the Contract and/or our requirements are not met in most respects. |
| 1 | Weak | Response is supported by a weak standard of evidence in some areas giving rise to concern about the ability of the Bidder to deliver the Contract and/or our requirements are not met in some respects. |
| 2 | Satisfactory | Response is satisfactory and supported by a satisfactory standard of evidence. Gives ACE confidence in the ability of the bidder to deliver the contract, meets the requirements in most respects. |
| 3 | Good | Response is comprehensive and supported by good standard of evidence. Gives ACE a high level confidence in the ability of the Bidder to deliver the contract and meets ACEs requirements. |
| 4 | Very Good | Response is comprehensive and supported by a very good standard of evidence meeting ACE requirements and may exceed them in some respects. Gives ACE a very good level of confidence in the ability of the Bidder to deliver the contract. |
| 5 | Exceptional | Response is very comprehensive and supported by a high standard of evidence. Gives ACE a very high level of confidence in the ability of the Bidder to deliver the contract. May exceed ACE’s requirements in several respects. |

- Price criteria (35 marks)

35 marks will be awarded to the lowest priced bid and the remaining bidders will be allocated scores based on their deviation from this figure. Your total costs figure including VAT and expenses in the schedule of charges below will be used to score this question.

For example, if the lowest price is £100 and the second lowest price is £125 then the lowest priced bidder gets 35% (full marks) for price and the second placed bidder gets 26.2% and so on. (25/100 x 35 = 8.75 marks; 35 – 8.75 = 26.25 marks)

The bidder with the highest score when the quality and price marks are added up will be the preferred bidder.

Table of Charges

Bidders shall complete the table of charges below estimating the number of days and travel and subsistence costs associated with their bid. The total fixed price will be inclusive of VAT and inclusive of expenses and all costs to be incurred.

| Service | Quantity/Days | Unit costs/Day rate | Total |
| --- | --- | --- | --- |
| Pre contract set up meeting |  |  |  |
| Weekly email updates on progress |  |  |  |
| Rapid Evidence review |  |  |  |
| Primary data collection |  |  |  |
| Qualitative interviews |  |  |  |
| Analysis and reporting of primary research data |  |  |  |
| Development of full written research report and other reporting outputs |  |  |  |
| First draft of the research outputs |  |  |  |
| Final Report |  |  |  |
| Travel |  |  |  |
| Expenses |  |  |  |
| Sub-total |  |  |  |
| VAT at 20% |  |  |  |
| Total Price including VAT and expenses (this figure will be used to calculate your price score) Bids in excess of £36,000 including Vat and expenses shall be excluded from consideration as non compliant. |  |  |  |

Notes:

- Arts Council England reserves the right to reject abnormally low tenders.

- You should not submit additional assumptions with your pricing submission. If you submit assumptions you will be asked to withdraw them. Failure to withdraw them will lead to your exclusion from further participation in this competition.

# Instructions to Bidders continued

Please submit your tender offer in accordance with all of the instructions, requirements and specifications set out in the enclosed documentation.

You must treat these documents and any further information provided by Arts Council England as confidential at all times and only disclose them if necessary to prepare a compliant response to the tender.

Nothing in the enclosed documentation or appendixes, or any other communication made between Arts Council England and any other party, can be considered a contract or agreement at this stage.

## Compliance

Arts Council England reserves the right to disqualify any tenderers who do not fully comply with the requirements in the tender documentation, in particular the closing time and date.

## Contract Terms and Conditions

Arts Council England will award the contract to the successful tenderer for the period of February 2016 – May 2016. Exact dates will be confirmed on appointment and signing of a project contract.

The Arts Council’s standard terms and conditions for services will form part of the contract to be awarded. These can be downloaded and reviewed from our website:http://www.artscouncil.org.uk/media/uploads/pdf/Contract_for_Services_over_10K_v1_March_2012.pdf. The Preferred Supplier will not be permitted to enter into any negotiations on the terms of the Contract. Any attempt to negotiate amendments will breach the terms of this ITT and will result in the Preferred Supplier being excluded from the tender process. In such circumstances Arts Council England reserves the right to invite the next highest scoring Bidder to enter into the Contract.

Please note that Arts Council England are required to publish online the final awarded contract and any associated documentation. If you have any concerns about the future publication of sensitive information you should raise these within your tender proposal, highlighting which areas within your proposal you consider may be subject to exemption, and subsequent redaction, in line with the provisions of the Freedom of Information Act 2000 (FOIA). More information about FOIA can be found at www.ico.gov.uk.

## Validity of offer

You must offer your tender for acceptance for 60 days from the deadline for tender submission.

Please note that by submitting a tender response for consideration you are confirming that, as an officer for the company/organisation that you represent, you have read and understood the tender documents and that your offer to Arts Council England is open for acceptance for 60 days from the tender closing date.

## Tendering

If we need to amend any tender documents before the closing date, we will write to you with any changes. If we extend the deadline for tender responses, we will advise you.

Arts Council England reserves the right, in its absolute discretion, to cancel or suspend this tender process at any time and for any reason. If we need to do this we will notify you in writing as soon as reasonably practicably.

Arts Council England is not responsible, and will not pay for any expenses or losses you incur during, but not limited to, the tender preparation, site visits, post-tender negotiations or interviews.

Return of Tender

You must complete and submit your tender response/proposal electronically to procurement@artscouncil.org.uk  by the tender deadline of noon 26th January 2016

We will only accept responses submitted via the email address provided. We will not accept any responses submitted by any other method. Any tender delivered after the closing date and time for any reason will be discounted.

The Arts Council is not responsible if all or part of your tender is not received.

# Footnotes

Working Wonders: An Action Plan for the Museums workforce – Museums Association http://www.museumsassociation.org/download?id=969395

15-18 providers are the same as above apart from in the West Midlands which is now delivered by Major Partner Museum Ironbridge Gorge Museums