## Sheet1
Path Project
Date / company | Query | Response
20.12.22 | Extention to Tender | Extension. We are granting an extension to the deadline. Tender returns should be received by the Museum by 12 noon on Thursday 12th January.
20.12.22 |  | 2) Arising out of funding arrangements for the project the priority for the Horniman Museum and Gardens is to ensure that the finalised and agreed scope of works can be completed to a high standard by the 31st March 2023. Therefore depending on the returns received, the Museum may consider letting the work in the following manner:
20.12.22 |  | a. Entering into a single contract with a contractor able to demonstrate they have the resources to complete the scope by the 31st March. (In what is estimated to be a 9 week programme).
20.12.22 |  | b. Entering into contract with two or more contractors who have demonstrated competitive rates and an ability to undertake the work, but lack the resources to deliver the full package as a single contract. In this instance we would be looking to split the works into separate contracts, and whilst the scope of each would need to be agreed, they are likely to be as follows: Contract 1) Avenue, bandstand, general edging and resurfacing. Contract 2) Nature trail steps, ducting installations and water pipework installation.
20.12.22 |  | 3) Is a paper copy of the tender submission required? Yes, we require a paper copy of the tender submission to be received on 12 noon Friday 13th January 2023. This is to keep on file if successful.