## Sheet1
Highways England Confirmation of Task Order |  |  |  |  | Redacted under Section 40 and Section 43 of the FOI Act (2000)
Confidential and Commercially Sensitive Information which shall not be disclosed to third parties
Supplier: | Atkins
Project Title: | Examination in Public – Manston Airport Development Consent Order
Contract Ref. | 2589 | CPA No.: | 4094486 |  | BPA No.: | 4094933
PIN Description: | Development Planning 18-19 | Sub Pin: | 3 |  | PIN No.: | 564869
HE Reference: | SE 78 18/19ATK | HE Ordering Officer: |  |  | Redacted
Consultant Ref: | 5165058.428 | Consultant Contact: |  |  | Redacted
Start & End Date: | 18/03/2019 - 31/07/2019 | CTO Authorisation No.
Task Overview
For project background and history please refer task order brief. Highways England has requested technical support from Atkins to advise and provide support throughout the Examination process which is scheduled to finish late July 2019. Information available: The following information has been identified in the brief: • The Manston Airport DCO, available on PINS; • Historic correspondence on SHARE; • Highways England initial reviews of the first TA and TN1, provided by the applicant’s consultants; and • Draft Statement of Common Ground. Methodology The following tasks will be undertaken: • Mobilisation; reviewing background information and HE work to date on the Manston CTO to bring core team up to speed with scheme and technical requirements of the task; • Draft and advise HE officer responses to the Examining Authority’s questions, analyse and evaluate incoming Transport evidence and advise HE on adequacy/acceptability and provide draft responses accordingly; • Draft a consultation response on the DCO and collate a list of documentation available for evidence; • Provide critique of the applicant’s strategic transport model and associated outputs in relation to potential impacts on the SRN; • Review the technical adequacy of any highway proposals offered by way of mitigation; • Support on one iteration of redrafting Statement of Common Ground; • Support HE officer at relevant meetings outside of Examination Hearings (normal office hours); • Support HE officer at public meetings (out of office hours); • Respond to all requests within 48 hours unless otherwise agreed (for example review of strategic modelling work); and • Liaise, where instructed, with the consults representing the applicant to expedite any information requirements. Assumptions & Caveats This proposal is based on the following assumptions: • Task limited to transport consultancy advise reflecting items detailed in the draft SoCG; • All information and historic correspondence mentioned above will be provided to Atkins prior to work being undertaken; • The strategic model is a SATURN Model. If other modelling software is used, alternative resource will need to be sourced within Atkins; • A total of two days for two Atkins employees will be allocated for two Atkins relevant meetings outside of Examination Hearings (normal office hours); • A total of five days for two Atkins employees will be allocated for supporting HE officers at public meetings. Any additional time requirements will be added as a change; • All requests will be responded to within 48 hours, however, resourcing cannot be guaranteed immediately for additional tasks required.
Task Objectives and Milestones
Objectives • Assist HE with Examining Authority’s questions and provide draft responses accordingly; • Review of strategic traffic model and Transport Assessment written for proposal; and • Provide support to HE officer at all relevant meetings. Milestones • ASAP – receipt of all relevant information for Atkins to undertake review; • 18th March 2019 – Open Floor Hearing 3 and 4; • 17th May 2019 - Deadline 7 (including Final Statements of Common Ground submissions)
Task Outcomes
Highways England to protect the capability of the SRN from threats to its safety and capacity arising from the proposed re-opening of the Manston Airport within the Development Consent Order application.
Project Risk and Management
Risks • This fee is an estimation of review and support time provided by Atkins. All time and tasks are indicative and actual requirements are currently unknown. Accordingly, there is a risk that KPI’s will not be met on this task. Should any additional time likely be required, an early warning will be raised as soon as identified; • An indicative expense estimate has been identified to cover potential travel, accommodation and sustenance if required and may be revised depending on the actual length of the programme and meeting requirements; • Should evening attendance at Public Meetings be required, additional expenses would be required for overnight accommodation and sustenance; • Should there be any gaps identified or further data requests, there may be an impact on programme if a request is not met promptly; • There are also uncertainties around the following that could impact the programme and fee, which will only be resolved as the task is undertaken: o Number of meetings required; o The dates/programme for the Public Inquiry; and o The results of Atkins review of information. Management • Contract management – Chris Cary • Task coordinator – Alistair Bradley • Technical lead – Matt Croot • Modelling Technical reviewer– James Lindsay • Transport Assessment Technical reviewer – Colin Young
Project Title: | Examination in Public – Manston Airport Development Consent Order |  |  |  | HE Reference: | SE 78 18/19ATK
HE Project Sponsor | Sign: |  | Print Name: |  |  | Date:
Management Approver: | Sign: |  | Print Name: |  |  | Date:
Contractual Approval: |  |  | Print Name: |  |  | Date:
Fee Type: | Time Online
Notification of Non Conflict: | Redacted has signed the notification of non conflict or management of conflict for this task
Task History Record | Fee Estimate for the Task set out in this CTO | Invoiced Amount/Estimate this Financial Year |  | Date CTO Confirmed | Fee Amount Requested | HE Sponsor
SE 78 18/19ATK | 30196.36 | 0 |  |  | 30196.36 | Redacted
Fee Estimate / Fee Requested for the scope on this CTO |  |  |  |  | 30196.36
Carry over Amount from previous financial year |  |  |  |  | 0
Previously Invoiced Amount |  |  |  |  | 0
Cumulative Project Fee Estimate (this financial year) |  |  |  |  | 30196.36
Total Project Fee Estimate |  |  |  |  | 30196.36
Name | Grade | Hours |  | Hourly Rate | (£)
Redacted (Atkins Office) | Director | 8 | @ | Redacted | Redacted
Redacted (Atkins Office) | Principal Planner / Engineer | 16 | @ | Redacted | Redacted
Redacted (Atkins Office) | Senior Planner/Engineer | 168 | @ | Redacted | Redacted
Redacted (Atkins Office) | Assistant Planner/ Engineer | 242 | @ | Redacted | Redacted
Redacted (Atkins Office) | Principal Planner / Engineer | 70 | @ | Redacted | Redacted
Redacted (Atkins Office) | Associate Director | 32 | @ | Redacted | Redacted
Redacted (Atkins Office) | Director | 24 | @ | Redacted | Redacted
|  |  | @ |  | 0
|  |  | @ |  | 0
|  |  | @ |  | 0
|  |  | @ |  | 0
|  |  | @ |  | 0
|  |  | @ |  | 0
|  |  | @ |  | 0
|  |  | @ |  | 0
Date Produced: | 2019-03-15 |  | Works Total |  | 30196.36
Confidential and commercially sensitive information which shall not be disclosed to third parties
|  |  | Sub Total |  | 30196.36
|  |  | Expenses |  | 864
COMMERCIAL RESTRICTED / FINANCE FILE ONLY |  |  | Total |  | 31060.36