# How Heritage helps People and Places Thrive

Organisation	The National Lottery Heritage Fund

REFERENCE NHMF 249

Department	Business Innovation and Insight

Title of procurement	Evaluation of the impact of heritage helping people and places to thrive

Brief description of supply	Evaluation Service

Estimated value of tender	Up to £160,000 inc VAT and expenses.

Estimated duration	6 years

Name of the Fund Contact	Hilary Leavy
Evaluation Manager

Timetable	Response deadline: 9.00 am on 24th April 2019

Clarification questions deadline:  8th April 2019

Clarification & Negotiation meetings: W/c 29th April 2019

Confirmation of contract: W/c 6th May 2019

Completion of evaluation: April 2025

# 1.	Overview

  - The National Lottery Heritage Fund, formerly the Heritage Lottery Fund (HLF), was set up in 1994 under the National Lottery Act and distributes money raised by the National Lottery to support projects involving the national, regional and local heritage of the United Kingdom. We operate under the auspices of the National Heritage Memorial Fund (NHMF). In January 2019 we launched our current Strategic Framework: ‘Inspiring, leading and resourcing the UK’s heritage’. See the Fund's website for more details.

  - The Fund invests in the full breadth of the UK’s heritage and, through our funding, we aim to make a lasting difference for heritage and people. This is reflected in the outcomes for heritage, people and communities which underpin our grant-making.

  - The Fund intends to measure the impact of our next Strategic Funding Framework (SFF) by setting Key Performance Indicators (KPIs) that underpin our objectives. One of these objectives is:

We will demonstrate how heritage helps people and places to thrive

National Lottery players want to see us fund projects that produce a strong social benefit in local areas.

  - We want to demonstrate how our funding and our other activities lead to social benefit. We wish to commission an evaluation to help us measure the added value of our intervention in 13 Local Authorities we have identified as a special focus for the duration of our next funding framework. We hope to demonstrate this added value through comparison with a sample of other local authorities (i.e. control group) we have not identified as a special focus.

  - We have selected the 13 Local Authorities (LAs) we want to focus on by using historic measures of our funding spend combined with standard indices of deprivation. We selected using two parameters: 

• Areas that have received the lowest funding in the past – in the bottom 25% of all local authorities; 
• Areas that experience the highest deprivation – in the top 25% of all local authorities.

There are 391 LAs across the UK; 97 of which fall in the highest 25% most deprived as measured by standard indices of deprivation. Of this 97 LAs; 13 fall within the 25% historically least funded by The National Lottery Heritage Fund.

The 13 areas are: 
Brent (Greater London) 
Corby (Northamptonshire) 
Enfield (Greater London) 
Knowsley (Merseyside) 
Inverclyde (Scotland) 
Luton (Bedfordshire) 
Newham (Greater London) 
North East Lincolnshire 
North Lanarkshire (Scotland) 
Neath Port Talbot (Wales) 
Rhondda Cynon Taff (Wales) 
Tendring (Essex) 
Walsall (West Midlands)

  - Our local teams will work strategically with stakeholders, from within heritage and beyond, to identify the best way to support organisations to meet local needs. This will include, if appropriate, soliciting applications for priority heritage projects, and offering micro-grants as successfully trialled in Barrow-in-Furness in 2017. We wish to measure the added value of our intervention in the13 priority areas compared to other areas using a range of established indicators.

  - The evaluation should build on our Theory of Change which we will share with the successful bidder placing particular importance on evidencing:

- the value of our intervention
- what was achieved over the life of our Strategic Funding Framework
- what we can learn during the evaluation and what changes we may wish to make

  - The key overarching aim of the evaluation is to demonstrate how heritage helps people and places to thrive in specific areas, with additional support. The successful bidder will be required to work alongside each of our business delivery teams to shape the evaluation process and support them in identifying and capturing the social, economic or environmental change they wish to bring about.

Our objectives for the evaluation are:

- to understand the value our interventions have in helping people and places to thrive

- to demonstrate the improvements for the communities involved

- to learn from the experiences of each area to improve the support we provide

- to understand the value of a diverse cohort of beneficiaries

- to understand the value of ongoing support for organisations and learn about the best approaches for delivering this support

- to help The Fund tell the story of how we performed against our initial objective once the funding framework has ended.

  - The evaluation should be delivered in a collaborative relationship with the Fund, as well as with grantees and other stakeholders.
Key audiences for the evaluation include:
 - The Fund’s staff – particularly our business delivery teams
 - Other funders, heritage stakeholders and other interested parties

The evaluation will also be used to inform future policy development.  We will expect the consultants to identify learnings throughout the evaluation that we can act on to make any changes to our support.

# Method

We would like consultants to set out in the proposal a methodology to achieve the aim and objectives of the study.

  - We expect the evaluation to address the following questions

- How effective have the Fund’s activities been in achieving greater funding for the 13 identified areas?

- In what ways have the Fund’s work with the areas impacted on their awareness of our funding and their capacity to undertake heritage projects?

- How effective are the individual areas at demonstrating how heritage helps people and places to thrive?

- What can be learnt from the range of approaches undertaken?

  - We would like the evaluation to include:

- A framework which will enable the effective collection of data from communities locally to feed into the central evaluation

- a series of workshops and other skills development opportunities for our business delivery teams, enabling them to work to the requirements of the framework 
- recruitment of well-matched and representative participant and control populations (with clear rationale for sampling and selection)
- demographic analysis of beneficiaries with consideration of how typical they are of the Fund’s current beneficiaries
- baseline, annual and end of programme longitudinal data collection (with detailed mid-point and post-programme analysis)

# Outputs

  - The following outputs will be required:

- An evaluation framework;

- a draft midterm evaluation report in word;

- a final evaluation report in word;

- any other reports as set out here or agreed between the Fund and the contractor; and

- a set of research data, to be stored in a readily accessible electronic format such as Excel

# A project plan with specific deliverables* and timetable will be agreed with the successful consultant/ies. However, The Fund expects the following deliverables in accordance with the following timetable as a minimum:

| Deliverable/Key Milestones* | Due date |
| --- | --- |
| Inception Meeting to agree plans, including reporting structures, learning events and a communication and dissemination strategy | May 2019 |
| Development of an evaluation framework (including data collection requirements and monitoring processes) developed in collaboration with relevant business delivery teams | November 2019 |
| Short annual review report (maximum 15 pages) | April 2020, 2021, 2022 and 2024 |
| A midterm evaluation report, of 50 pages maximum, detailing learning to date and any recommendations to ensure outcomes are achieved | April 2023 |
| A final report, of 50 pages maximum, with structure agreed with the Fund | March 2025 |

# The above represents our minimum requirements.

# * The Fund reserves the right to amend this timetable where required.

  - All reports must adhere to the Fund’s accessibility and formatting guidance (appended).  We also expect reports to follow the layout advised in our evaluation guidance.

  - The initial findings will be confidential to the Fund. The Fund may prepare or commission summary reports and other materials for subsequent wider distribution, based on the results.

  - All reports to include appendices as agreed between the Fund and the contractor. The contents and structure of the report to be agreed in advance of writing. All reports to be supplied in electronic format and hard copy if requested.

  - The successful bidder must comply with all of the requirements of the Data Protection Act 2018 and shall ensure appropriate research consents from interviews or any data collection.

  - The successful bidder will be expected to discuss and present findings at appropriate times, to internal and external audiences, including our Board, our Senior Management Team, Grantees, policy makers and other external stakeholders.  The purpose of these presentations is to enable lessons to be learned and key policy and practice issues to be highlighted as the evaluation progresses.

  - We expect all projects we fund to adhere to the Social Research Association (SRA) ethical guidelines.  If your proposal raises particular ethical issues, you must indicate what they are and what your strategy for addressing them is.

# Contract management

  - We expect the research/evaluation to begin May 2019 and be completed by April 2025. The final report shall be submitted to the Fund by March 2025.

  - The anticipated budget is up to £160,000 to include all expenses and VAT. The contract will be let by the National Heritage Memorial Fund.

  - The payment schedule will be 30% of the value of the contract paid during year one; other payments will be agreed with the contractor based on completion of agreed milestones, with 10% to be paid after approval of the final report.

  - The contract will be based on the Fund’s standard terms and conditions.

  - The evaluation will be managed on a day to day basis for the Fund by Hilary Leavy, Evaluation Manager.

# Award Criteria

  - A proposal for undertaking the work should be a maximum of 15 pages and include:

- a detailed method for undertaking the study;

- details of staff allocated to the project, together with experience of the contractor and staff members in carrying out similar projects. The project manager / lead contact should be identified;

- the allocation of days between members of the team;

- the daily charging rate of individual staff involved;

- a timescale for carrying out the project;

- an overall cost for the work.

  - Your Bid will be scored out of 100%.

70% of the marks will be awarded to Quality

Each question will be scored using the methodology in the table below.

Tender responses submitted will be assessed by the Fund against the following Quality Questions:-

| - Demonstrated a clear understanding of the aims, objectives and main concerns of the evaluation. | Weighing 20% |
| --- | --- |
| - Demonstrated a record of producing high quality evaluation reports to support policy and practice development, and to do so concisely | Weighting 20% |
| - Demonstrated the bidder has the capacity and resources to carry out the evaluation within the timescale, or if working in partnership, each organisation has the capacity to fulfil its role and roles of each partner is clear. | Weighting 25% |
| - Demonstrated a clear and realistic project plan, showing phases of the evaluation, tasks for each phase and roles and responsibilities for each member of the team. | Weighting 15% |
| - Demonstrated well considered plans for feeding back learning and dissemination of evaluation findings. | Weighting 20% |

## Quality Questions scoring methodology

| Score | Word descriptor | Description |
| --- | --- | --- |
| 0 | Poor | No response or partial response and poor evidence provided in support of it. Does not give the Fund confidence in the ability of the Bidder to deliver the Contract. |
| 1 | Weak | Response is supported by a weak standard of evidence in several areas giving rise to concern about the ability of the Bidder to deliver the Contract. |
| 2 | Satisfactory | Response is supported by a satisfactory standard of evidence in most areas but a few areas lacking detail/evidence giving rise to some concerns about the ability of the Bidder to deliver the Contract. |
| 3 | Good | Response is comprehensive and supported by good standard of evidence. Gives the Fund confidence in the ability of the Bidder to deliver the contract. Meets the Fund’s requirements. |
| 4 | Very good | Response is comprehensive and supported by a high standard of evidence. Gives the Fund a high level of confidence in the ability of the Bidder to deliver the contract. May exceed the Fund’s requirements in some respects. |
| 5 | Excellent | Response is very comprehensive and supported by a very high standard of evidence. Gives the Fund a very high level of confidence the ability of the Bidder to deliver the contract. May exceed the Fund’s requirements in most respects. |

30% of marks will be awarded for Price.

The evaluation of price will be carried out on the Schedule of charges you provide in response to Table A

## Price Criterion at 30%

- 30 marks will be awarded to the lowest priced bid and the remaining bidders will be allocated scores based on their deviation from this figure. Your fixed and total costs figure in your schedule of charges table will be used to score this question.

- For example, if the lowest price is £100 and the second lowest price is £108 then the lowest priced bidder gets 30% (full marks) for price and the second placed bidder gets 27.6% and so on. (8/100 x 30 = 2.4 marks; 30-2.4 = 27.6 marks)

- The scores for quality and price will be added together to obtain the overall score for each Bidder.

## Table A - Schedule of Charges

Please show in your tender submission, the number of staff and the amount of time that will be scheduled to work on the contract with the daily charging rate.

Please complete the table below providing a detailed breakdown of costs against each capitalised description, detailing a total and full ‘Firm Fixed Cost’ for each element of the service provision for the total contract period. Bidders may extend the tables to detail additional elements/costs if required.

VAT is chargeable on the services to be provided and this will be taken into account in the overall cost of this contract.

As part of our wider approach to corporate social responsibility the National Heritage Memorial Fund/National Lottery Heritage Fund prefers our business partners to have similar values to our own. We pay all of our staff the living wage (in London and the rest of the UK) and we would like our suppliers and contractors to do likewise. Please highlight in you proposal/tender/bid whether you do pay your staff the living wage.

Bidders shall complete the schedule below, estimating the number of days, travel and subsistence costs associated with their tender submission.

TABLE A: (firm and fixed costs)

| Cost | Post 1 @cost per day (No of days) e.g. Project Manager/ Director @ £2 | Post 2 @cost per day (No of days) e.g. Senior Consultant/manager/researcher @£1.5 | Post 3 @cost per day (No of days) Junior Consultant/equivalent e.g. £1 | Total days | Total fees |
| --- | --- | --- | --- | --- | --- |
| Inception meeting to agree plans and finalise requirements with the Fund | Example 0.5 | 1 | 1.5 | 3 | £4 |
| [Add as necessary] |  |  |  |  |  |
| [Add as necessary] |  |  |  |  |  |
| [Add as necessary] |  |  |  |  |  |

| Cost Type | Value (£) |
| --- | --- |
| Sub - Total |  |
| VAT |  |
| Total* |  |

* (This must include all expenses as well as work costs; this figure will be used for the purposes of allocating your score for the price criterion and must cover the cost of meeting all our requirements set out in the ITT)

Notes: 	The Fund reserves the right to clarify quality and prices and to reject tenders that demonstrate an abnormally low quality response. The Fund also reserves the right to amend the timetable of work where required.

You should not submit additional assumptions with your pricing submission. If you submit assumptions you will be asked to withdraw them. Failure to withdraw them will lead to your exclusion from further participation in this competition.

# Procurement Process

  - THE FUND reserves the right to reject abnormally low scoring tenders. The Fund reserves the right not to appoint and to achieve the outcomes of the research/evaluation through other methods.

  - The procurement timetable will be:

- Deadline for clarification questions: 8th April

- Tender return deadline: 9am on 24th April

- Clarification meetings** may be held with shortlisted consultants and would take place on week commencing: 29th April

- The Fund will notify bidders of our procurement decision week commencing: 6th May

- *The Fund will upload response to clarification on Contracts Finder.  Please note that we will make the anonymised questions, and our responses to them, available to everyone on this website.

- **We reserve the right to carry out clarifications if necessary; these may be carried out via email or by inviting bidders to attend a clarification meeting.  In order to ensure that both the Fund’s and Bidder’s resources are used appropriately, we will only invite up to three (the ultimate number will depend on the closeness of the scores) highest scoring bidders to attend a clarification meeting.  Scores will be moderated based on any clarifications provided during this meeting.  You are responsible for all your expenses when attending such meetings.

  - Your tender proposals must be sent electronically via e-mail before the tender return deadline of 9am on 24th April to the following contact:

HILARY LEAVY

The National Lottery Heritage Fund

Holbein Place

London

SW1W 8NL

Hilary.Leavy@hlf.org.uk

  - Please visit the Fund's website for further information about the organisation.

# Appendix: Accessibility and formatting guidance

The National Lottery Heritage Fund is committed to providing a website that is accessible to the widest possible audience. Our site is annually tested by accessibility auditors and we must meet a AA compliance level. Our accessibility testing encompasses not just site functionality and design but all of our content, including downloadable documents.

Reports and other documents created for the Fund (including the tender submissions) need to be clear, straightforward to use and ready to circulate internally, externally and online, as well as suitable for use by screen reading software. Best practice in accessibility is summarised below:

## Readability

In the final report, and all other documents that may be published online including the tender application consultants should ensure that:

- The size of the font is at least 11pt;

- There is a strong contrast between the background colour and the colour of the text. Black text on a white background provides the best contrast. This also applies to any shading used in tables and/or diagrams;

- Italics are only used when quoting book titles for citations and items on the reference list should be arranged alphabetically by author

- Colour formatting and use of photos should be of a resolution size that is easily printable and does not compromise the printability of the document.

For further guidance on ensuring readability of printed materials, please refer to the RNIB Clear Print guidelines. These can be found on the RNIB website.

## Accessibility

Reports should adhere to the following guidelines:

## Formatting

Headings and content in your document should be clearly identified and consistently formatted to allow easy navigation for users. Heading Styles should be used to convey both the structure of the document and the relationship between sections and sub-sections of the content. Heading styles should follow on from each other i.e. Heading 1 then Heading 2.

## Spacing

Screen readers audibly represent spaces, tabs and paragraph breaks within copy, so it is best practice to avoid the repetitive use of manually inserted spaces. Instead, indenting and formatting should be used to create whitespace (e.g., use a page break to start a new page, as opposed to multiple paragraph breaks).

## Alternative text

Alt text is additional information for images and tables. This extra information is essential for both document accessibility (screen reading software reads the Alt text aloud) and for the web. Alt text should be concise and descriptive, and should not begin with ‘Image of’ or ‘Picture of’.

## Images

These should be formatted in-line with text, to support screen readers. Crediting pictures may be necessary, usually in response to a direct request from a third party.

## Tables

These should be for used for presenting data and not for layout or design. They should be simple and include a descriptive title. The header row should be identified and there shouldn’t be more than one title row in a table. There should be no merged or blank cells.

## Additional documents

Any additional information, separate to the report, for example proformas and transcripts which may be used as standalone documents must be fully referenced to the piece of work being submitting and therefore dated, formatted and numbered appropriately.

## Acknowledgement

All reports should acknowledge the Fund. Our logo can be found on the Fund's website.

## Further resources

Please refer to the WCAG 2.0 article on PDF techniques for further information.

Submitting your report to THE FUND

Please check the accessibility of your document using the Word accessibility checker before submitting: File – Info – Check for Issues – Check Accessibility.

Please submit your document as a Word file.

The Fund retains the right to amend documents in order to create accessible versions for publishing.