Order Schedule 20 (Order Specification)

This Schedule sets out the characteristics of the Deliverables that the Supplier will be required to make to the Buyers under this Order Contract

### Research Specification: Making Tax Digital for Income Tax Evaluation Research: Impacts on Taxpayers with a Total Annual Income Below £50,000

CCS Research & Insights DPS (RM6126)

Invitation to Tender

November 2025

Contents

1.	Introduction	3

2.	Context	3

3.	Research Audiences	4

4.	Methodology	5

5.	Timetable	6

6.	Length of Contract	7

7.	Outputs	7

8.	Quality and Risk Management	8

9.	Expertise and Capability	9

10.	Project Management and Contract Administration	10

11.	Research Cost Model: Research Scenarios and Rate cards	11

Annex A Statement of Work Form	14

## Introduction

  - HM Revenue & Customs (HMRC) invites Suppliers from the Research & Insights DPS (RM6126) to undertake a longitudinal study to evaluate the impact of Making Tax Digital (MTD) for Income Tax for sole traders and landlords with a total annual income under £50,000 from self-employment and property (before deducting expenses).

  - An evaluation is already underway to assess the impact of Making Tax Digital for Income Tax. This evaluation is focused on customers with qualifying self-employment or property income above £50,000. HMRC now require research to evaluate the impact of MTD for taxpayers with lower earnings. HMRC expects the evaluation to involve:

  - a longitudinal quantitative survey with five (5) annual survey waves; and

  - two (2) waves of qualitative interviews.

  - HMRC intends for this contract to be in place by January 2026 with the first survey wave expected in March 2026. This is HMRC’s preferred fieldwork period, Suppliers should deliver within this timeframe. Please see an indicative timeline in Section 4. The March 2026 delivery date enables participants to provide an accurate recall of their most recent Income Tax Self Assessment. The first survey will provide a baseline for sole traders and landlords earning between £30,000-£50,000; it is desirable that each subsequent survey is completed during the same calendar month each year to produce comparable results.

  - HMRC will maintain the overall management of the project.

## Context

  - Making Tax Digital (MTD) is a key part of HMRC’s transformation of the tax system to enhance customer experience, make it easier for taxpayers to get their tax right first time and reduce the scope for error. Mandated businesses and landlords will use MTD compatible software to keep digital records closer to the point of transaction and submit information to HMRC directly from those records. MTD is expected to reduce taxpayer errors and to generate net additional tax revenue for the Exchequer.

  - MTD for Income Tax is being introduced in phases. From April 2026, sole traders and landlords with income over £50,000 will be required to keep digital records and provide quarterly updates of their income and expenditure to HMRC through MTD-compatible software, as well as completing their annual tax return by 31 January. In April 2027 the threshold will lower to £30,000 and from April 2028 to £20,000.

  - HMRC requires a robust quantitative survey to evaluate the impact of this change for taxpayers with an income below £50,000. The research is designed to deliver baseline measurements of how customers in scope are managing their Income Tax Self Assessment obligations prior to implementation of MTD, with subsequent waves measuring the impact on customers as MTD is phased in.

  - HMRC commits to a baseline wave for the £30,000 - £50,000 cohort. The Supplier may then be required to conduct subsequent follow up waves so that HMRC can monitor changes with the same customers over time. The Supplier may also be required to evaluate the impact of MTD for Income Tax with taxpayers with a qualifying income of £20,000 to £30,000 who will need to use MTD for Income Tax from April 2028. If HMRC decides to proceed with subsequent waves of the research separate briefings will be provided to the research Supplier for each wave. All elements of any follow-on waves will be agreed as outlined in section 5.

## Research Audiences

  - HMRC is seeking a Supplier with expertise in evaluation and survey design to develop a longitudinal study to evaluate the impacts of Making Tax Digital on customers earning below £50,000.

  - This contract will comprise of a quantitative survey to establish a baseline with taxpayers with a qualifying income of £30,000 - £50,000, prior to them needing to start using MTD for Income Tax from April 2027.

  - HMRC anticipates an additional requirement to explore the early impacts of Making Tax Digital (MTD) following mandation, through qualitative interviews commencing in Autumn 2027. Suppliers should incorporate scope for this research within their proposed methodology.

  - HMRC expects to commission two post-mandation surveys, scheduled for March 2028 and March 2029, to assess the impact of MTD after customers have been mandated. Suppliers should factor these into their proposals as potential future phases of work.

  - Suppliers are encouraged to include research within their bids that evaluates the impact of MTD on customers with a qualifying income between £20,000 and £30,000. This research should closely align with the methods used to evaluate customers earning between £30,000 and £50,000.

  - HMRC reserves the right not to proceed with any additional research beyond the initial wave.

  - The contract will be awarded to the organisation that is deemed to have submitted the most economically advantageous tender (MEAT). Assessment will be based on the factors outlined in Section 11.

  - To ensure fairness all Suppliers are required to submit their tenders in accordance with these instructions and any further requirements contained in the invitation letter. Failure to comply could invalidate your tender.

## Methodology

  - The core objectives of this research are to:

  - assess the impact of MTD for Income Tax on customers’ practices and behaviour to evaluate the extent to which MTD is working as intended and any wider impacts on customers and their affairs over time.

  - collect robust longitudinal data on self-assessment customers in scope for MTD for Income Tax that can be linked anonymously to internal tax administration data to build a more comprehensive picture of the impact.

  - assess the impact of the policy on customer experience with regards to the implementation and ongoing use of MTD.

  - HMRC expects the research aims and objectives to be best met by the methodology as set out within this section.

  - HMRC requires a representative survey to support evaluation of MTD over five (5) years. The research must include a longitudinal random probability survey with a counterfactual element.

  - HMRC expects the survey to cover the following topics related to the affairs of taxpayers in MTD for Income Tax:

- Record-keeping: the ease and frequency of keeping business records and preparing and submitting a Self Assessment income tax return.

- Scope for error: customers’ confidence in the accuracy of their submissions and the support they receive or require when submitting their Self Assessment tax return.

- Administrative burdens: time spent on tax affairs and customers’ monetary costs in meeting their tax obligations.

- Wider costs and benefits: the use of financial and digital tools, confidence in these areas, and any emotional burden associated with self-assessment such as stress or anxiety.

- Perceptions of MTD: how easy or difficult customers anticipate their MTD submissions will be (baseline) and comparatively how they found their MTD submissions (post MTD mandation).

- Awareness tracking: how aware are Income Tax Self-Assessment (ITSA) customers of the MTD requirements and what preparations are they making ahead of mandation.

  - This first contract will include development of fieldwork materials, and a full baseline survey (wave 1) in early 2026 for the £30,000-£50,000 cohort, with subsequent waves of the survey annually. Subsequent waves will also be designed to evaluate the £20,000-£30,000 cohort. HMRC envisages the surveys to be conducted annually, as set out in Section 4.

  - A questionnaire is available from the evaluation of MTD for Income Tax for taxpayers with an income of £50,000 and above. HMRC intends to utilise the survey questions as a template for this evaluation (under £50,000). This survey will be provided to the appointed Supplier upon commencement of the project.

  - Whilst the core survey content is already developed, HMRC anticipates that amendments may be necessary to tailor the survey to the specification of this research. Suppliers should therefore include provisions for potential modifications within their proposed development costs for fieldwork materials.

  - HMRC expects there may be an additional requirement to explore early impacts of MTD post mandation through qualitative interviews. HMRC anticipate this would take place following the first quarterly returns - autumn 2027 for the £30,000-£50,000 cohort and autumn 2028 for the £20,000-£30,000 cohort. Tenders should include scope for this option within any proposed methodology.

  - HMRC expect Suppliers to make provision for interviews to be conducted in, or materials to be translated into Welsh where interviews are being conducted in Wales.

  - Suppliers must submit a methodology which aligns to all minimum requirements as set out within this section. Suppliers must ensure their approach to this methodology is fully justified and any risks fully explained.

  - Suppliers must complete the rate card included in the bid pack to provide costs for completing Wave 1 and indicative costs for the qualitative research described in Wave 3. Suppliers need to only complete costs in the rate card for the methods proposed within their tender – any methods not advised by the Supplier for this work do not need to be costed. The costs for wave 1 must be in line with those provided in the rate card.

  - Research Sample

    - The population of interest for the first survey wave (March 2026) is UK sole traders and landlords who complete a Self Assessment with a qualifying income from self-employment or property between £30,000 and £50,000 in a tax year.

    - The population of interest will change in line with the phased introduction of MTD. Taxpayers with a qualifying income between £20,000 and £30,000 will be required to join MTD in 2028, with the baseline survey for this cohort expected in February 2027.

    - The sample will be drawn from an internal HMRC database of businesses who complete a Self Assessment. Table 1 shows the population, split by the subgroups of interest to the study. There were approximately 1.1 million records with self-employment and/or property income between £30,000 and £50,000 in the 23/24 tax year in scope for the research.

Table 1: ITSA Population Subgroups Split (rounded)

| Subgroup | Number of SA customers with self-employment and/or property income |  |
| --- | --- | --- |
|  | £30k-£50k | £20k-£30k |
| Sole traders only | 800,000 | 640,000 |
| Landlords only | 180,000 | 260,000 |
| Sole trader and landlord | 100,000 | 80,000 |
| Total | 1,080,000 | 980,000 |

    - The sample will contain the business or individuals name, contact address, and telephone number as a minimum.

    - Whilst every effort will be made to ensure that the contact details passed to the Supplier will be accurate, there may be some missing or incorrect telephone numbers/email addresses. Suppliers must allow some time in their proposal for number matching.

    - HMRC expects Suppliers to incorporate a counterfactual design within the proposed methodology. This approach will enable the application of difference-in-differences analysis to robustly assess the impact of MTD.

    - The research Supplier will need to undertake some work to identify the best person to interview within those larger businesses, usually the person responsible for their business tax affairs.

  - Sample Size and Characteristics

    - Suppliers must outline how they will design a survey to provide findings within +/-2% margin of error at the 95% confidence interval for the overall population of interest. Suppliers must provide rationale as to how the survey will meet the margin of error and confidence interval criteria.

    - Suppliers must recruit a representative number of businesses and landlords based on the following subgroups:

- Size of business by income;

- Business type: self-employed, landlords, both self-employed and landlords; and

- Any comparison group (counterfactual).

    - Additional sub-groups of interest include UK nations, region, age of business, gender, agent representation, sector, and each of the groups being phased in at different times. Suppliers may suggest any additional sub-group analysis that may meet the research aims, providing sound justification and reasoning is provided.

    - HMRC acknowledge that some subgroups may be difficult to recruit. Therefore, Suppliers must apply appropriate weightings to the recruited sample and Suppliers must ensure reliability of further analysis that may be conducted.

    - Suppliers must outline how they will sample the population appropriately to build in a counterfactual element to the design. Suppliers must note that a control group will not be feasible for this study as all taxpayers in the population of interest (sole traders and landlords registered for Self Assessment) with an income over £20,000 will be mandated to join MTD at some point over the next 3 years. Suppliers should offer alternative counterfactual design options. HMRC recommends using a comparison group consisting of businesses whose income is close to, but just below, the threshold for mandation. Any options offered should be justified within the tender including how they arrived at size of the counterfactual group suggested and the effect that can be measured with a given level of confidence.

    - The sampling approach for each wave of this survey will also need to account for the longitudinal nature of this study. Suppliers shall outline how they will mitigate against attrition between waves whilst maintaining the confidence intervals required.

    - Suppliers must note the high level of churn within the population. The population will require screening year on year to check that the business status has not changed significantly between waves.

    - Suppliers must provide an estimate of the sample size necessary to achieve the required number of responses.

    - HMRC will not mandate the mode of recruitment or administration of the survey, yet justification for the mode(s) proposed must be provided. Please note that HMRC currently has limited coverage of accurate customer email addresses.

  - Where online methods are proposed with a telephone option, Suppliers must outline their approach to feasibility-testing the online element, and how Suppliers would minimise coverage and attitudinal biases of these online modes for the purposes of this research.

  - Where mixed-mode approaches are proposed, Suppliers must explain how they will mitigate mode effects and combine mixed-mode data following collection, clearly outlining any associated risks and mitigations.

  - Prior to fieldwork, the successful Supplier will issue potential respondents with an Advance Letter to inform and explain the purpose of the research. The Advance Letter should help to build trust and credibility. For any addresses in Wales this letter must be written in both English and Welsh. This process would be undertaken following the appointment of a successful contractor, so that Advance Letters can include information on who is conducting the research, enhancing trust and reassurance.

  - Suppliers can provide suggestions within their bid regarding ways to encourage participation with the research by the target population, but justification must be provided for the proposed method.

  - HMRC would like to encourage survey participants to grant permission for their survey responses to be linked to HMRC tax administration data, for research purposes only. HMRC will work with the successful Supplier to agree the best approach to this requirement. Suppliers should consider how best to meet this need within their proposal.

  - Suppliers must specify how they are going to analyse the data to answer the research questions of the study.

  - The analysis plan and instruments must be drafted and agreed with HMRC.

  - Suppliers must cost on the basis of undertaking one initial wave of the survey (baseline for £30-£50k cohort).

  - Previous studies

    - The evaluation approach and research undertaken to evaluate the impact of MTD for VAT is outlined in the report : Making Tax Digital for VAT final evaluation - GOV.UK

    - HMRC commissioned research to understand the ITSA customer base, and their preparedness for MTD requirements, which may provide useful insight into the population Income Tax Self Assessment: Readiness for Making Tax Digital - GOV.UK.

    - HMRC commissioned research to evaluate the impact of MTD for IT customers with self-employment or rental income above £50,000. This work is still ongoing.

  - Suppliers may propose alternative approaches to evaluate the impact of MTD for Income Tax, where they believe they may offer improved analytical value. Any such suggestions should be included in the annex of the submission. However, for the purposes of completing the pricing schedule within the Invitation to Tender (ITT), Suppliers must base their costings on the methodology outlined in Section 4.

  - Wave 1: Quantitative baseline survey

    - HMRC believes the best time to conduct fieldwork for a baseline of ITSA customers with incomes between £30,000 and £50,000 would be in March 2026. In the current system, ITSA customers must submit their annual tax returns on or before the 31 January. HMRC propose conducting fieldwork in March 2026 so that participants can accurately recall their most recent ITSA submission. HMRC believes that waiting until February and March 2027, immediately before mandation in April 2027, would lead to insurmountable contamination of the baseline, as many businesses will have already begun using the new software in preparation for the new rules.

    - Table 2 within Section 4 gives an overview of critical dates for wave 1, as well as future waves to complete the evaluation of the £30,000-£50,000 cohort and to evaluate the £20,000-£30,000 cohort.

## Annual survey waves

    - At the point of tender, HMRC only commits to requiring Wave 1 of this survey. It is highly probable that all subsequent waves of this longitudinal survey will be required. However, due to potential policy changes over the five (5) years to fulfil this requirement, the contract term will be structured as a one (1) year initial term with extension provisions in one (1) year aggregates, to be taken for the subsequent four (4) years.

    - The timeline in Section 5 sets out the expectations for wave 1.

    - HMRC will aim to notify the successful Supplier within 3 months of a contract extension to ensure the Supplier has not committed resource and does not incur opportunity costs.

    - Timeline changes for Waves 2,3, 4, and 5 will depend on changes to the scope of the research but the timelines are expected to be comparable to Wave 1.

    - HMRC expects that any future survey waves will be aligned to the specification for the initial wave as set out within this ITT. For the avoidance of doubt, HMRC anticipates that the requirement for any future wave(s) would be closely aligned to, if not identical to, the requirements set out in the following sections of this ITT:

a) Section 3 – Research Audiences

b) Section 4 – Methodology

c) Section 5 – Timetable

d) Section 7 – Outputs

e) Section 8 – Quality and Risk Management

f) Section 9 – Expertise and Capability

g) Section 10 – Project Management and Contract Administration

4.24.5 HMRC reserves the right to make some amendments to the anticipated specification for any future waves.

  - Wave 2

    - HMRC may require a survey in 2027 to provide a baseline those with income between £20,000 and £30,000, ahead of mandation in April 2028.

  - Wave 3

    - HMRC may also require a survey in 2028 to support the first post-mandation measure for those with income between £30,000 and £50,000.

  - Wave 4

    - HMRC may also require a survey in 2029 to provide the first post-mandation wave for customers with an income between £20,000 and £30,000.

    - The 2029 survey will also be the second post mandation wave for customers with an income between £30,000 and £50,000.

  - Wave 5

    - HMRC may require a survey in 2030 to provide the second post mandation wave for customers with an income between £20,000 and £30,000.

    - Qualitative Interviews:

    - Wave One

    - HMRC may require qualitative research in September 2027 to explore the early impacts of MTD on customers who earn between £30,000 and £50,000 in their first year of MTD mandation.

    - Wave Two

    - HMRC may require qualitative research in September 2028 to explore the early impacts of MTD on customers who earn between £20,000 and £30,000 in their first year of MTD mandation.

    - Research aims and objectives:

- Explore how customers perceive the costs and benefits of transitioning to MTD for ITSA since their mandation.

- How has this changed from before the introduction of MTD?

- How has MTD evolved customers’ record keeping practices?

- Are businesses experiencing any wider (non-tax) benefits?

- What are the barriers to change among businesses that have transitioned to MTD for ITSA?

    - For qualitative fieldwork, HMRC will require interview transcripts to allow internal quality assurance checks.

Table 2: Critical Dates

|  | January | March |  | April | September |
| --- | --- | --- | --- | --- | --- |
| 2026 | ITSA deadline | Wave 1 - £30k-£50k survey fieldwork (baseline) |  |  |  |
| 2027 | ITSA deadline | £20k-£30k survey fieldwork (baseline) |  | MTD Mandation £30k-£50k | £30k-£50k post mandation qualitative interviews |
| 2028 | ITSA deadline | £30k-£50k survey fieldwork (post mandation 1) |  | MTD Mandation £20k-£30k | £20k-£30k post mandation qualitative interviews |
| 2029 | ITSA deadline | £30k-£50k survey fieldwork (post mandation 2) | £20k-£30k survey fieldwork (post mandation 1) |  |  |
| 2030 | ITSA deadline | £20k-£30k survey fieldwork (post mandation 2) |  |  |  |

| Making Tax Digital: Evaluation Research - Indicative Timeline | £30-50k |  | £20-30k |  |
| --- | --- | --- | --- | --- |
| Year | Quantitative Research (March) | Qualitative Research (September) | Quantitative Research (March) | Qualitative Research (September) |
| 2026 | Baseline |  |  |  |
| 2027 |  | Interviews | Baseline |  |
| 2028 | Post Mandation 1 |  |  | Interviews |
| 2029 | Post Mandation 2 |  | Post Mandation 1 |  |
| 2030 |  |  | Post Mandation 2 |  |

Table 3: Indicative Timeline

4.29 Welsh Translation

4.29.1 To ensure HMRC meets its offer to Welsh customers, Welsh customers must be able to participate in Welsh, if they choose.

4.29.2 The Supplier must ensure where Computer-Assisted Telephone Interviewing (CATI) surveys are utilised, there is the option for telephone interviews to be conducted in Welsh. Likewise, if an online survey is utilised, participants must be able to toggle between English and Welsh versions of questions throughout the survey.

4.29.3 Similarly, the Supplier must ensure that all qualitative research can be completed in Welsh, if requested by a participant. HMRC anticipates that the Supplier may need to partner with specialists should this be requested by a participant. Any associated costs should be included within the Supplier’s completed Cost Model.

4.29.4 Communications, such as invitations to participate sent to potential respondents in Wales must also be in Welsh.

4.29.5 HMRC can support the Supplier with translation of communications and the survey, and will quality assure any Welsh translations provided by the Supplier.

4.30 Artificial Intelligence

4.30.1 Tenderers must not input raw, personal, official-sensitive, or un-published data into AI software during the project without prior consent from HMRC.

4.30.2 Tenderers must provide full details of any aspect of their proposal which has been produced with the assistance of generative AI.

4.30.3 Tenderers must inform HMRC if they are proposing to use AI technology for the delivery of this contract, detailing what and how they are proposing to use AI for and how this will benefit the delivery of this contract.

4.30.4 Tenderers must obtain permission from the Authority before the use of AI for the provision of any part of the service delivery

4.30.5 The Authority reserves the right to reject the use of AI in this contract and Tenderers must ensure that any proposal can be delivered without the use of AI if necessary.

## Timetable

  - The timeline provided below is indicative of the timelines expected by HMRC for a research project. Suppliers are required to demonstrate in their tenders that they will be able to complete the research within the below timelines or sooner, unless a revised timescale is agreed between the two parties during the project commissioning process. Timelines should be adjusted to account for multiple fieldwork waves as necessary.

| Activity | Indicative Date |
| --- | --- |
| Deadline for queries on ITT | December 2026 |
| Response to ITT queries | December 2026 |
| Deadline for response to ITT | December 2026 |
| Contract awarded | January 2026 |
| Set-up meeting | January 2026 |
| Opt-out period | March 2026 |
| Fieldwork | March 2026 |
| Analysis plan meeting | May 2026 |
| Presentation of findings | July 2026 |
| Final outputs signed off, project close | August 2026 |

  - The successful Supplier will be expected to attend a set-up meeting in the week commencing January 2026. The set-up meeting will be hosted via Microsoft Teams.

  - All stages of Wave 1 must be completed by Autumn 2026. Suppliers must demonstrate that they can meet this deadline.

  - Project timelines and milestones will be agreed for each wave commissioned under this contract. The Supplier shall deliver the milestone activity by the agreed timescales unless otherwise agreed by the two parties in writing.

  - Optional survey waves are outlined in Section 4. The successful contractor must be capable of delivering fieldwork the same time each year as outlined below. Suppliers must demonstrate that they can meet these deadlines.

## Length of Contract

  - The initial contract term will be one (1) year with extension provisions for up to four (4) years. The total potential contract term is five (5) years.

  - Following the first year of work HMRC reserves the right to not continue with future work. Subsequent years (Years two-five) will be subject to formal review. HMRC will notify the Supplier at least three (3) months ahead of any contract extension.

  - HMRC intends for this contract to be in place by January 2026, with baseline outputs delivered by Summer 2026.

  - HMRC reserves the right to pause or cancel a project at any point, in line with clause 9.8 of the Call-Off Contract. HMRC intends that the winning Supplier will deliver the requirement for the first wave as a minimum.

## Outputs

  - The Supplier must deliver the following outputs:

- Attendance at an initial project set-up meeting.

- Detailed project plan that outlines key dates and milestones and indicates any actions for HMRC, revisions to the project plan if substantial changes occur.

- Weekly progress updates, including survey response rates/interviews

- achieved.

- Agreed versions of all research instruments (survey, topic guides).

- Advance letters for recruitment of sole traders and landlords. For sole traders and landlords with addresses in Wales these letters must be written in both Welsh and English.

- Analysis plan agreed with HMRC.

- An anonymised data set in a format agreed with HMRC and any agreed appendices following data linking.

- Interview transcripts from any qualitative fieldwork.

- An interim and final findings headline note.

- Final presentation of findings at the end of all Wave 1 fieldwork to HMRC plus an electronic copy of the slide deck.

- A full report of findings to a standard publishable on GOV.UK and a technical appendix. Suppliers should allow for at least three drafts of the report before a final report is agreed. Two versions of the final written report are required (both in Microsoft Word):

- ‘Standard’ version of the report: this version of the report will be used for internal sign-off processes.

- ‘Markdown’ version of the report: Suppliers should reproduce the ‘standard’ version of the report using the markdown template included.

Reporting requirement

  - Final publishable report to be agreed by the HMRC Project Manager following a drafting and iteration process, prepared in Microsoft Word. Tenderers should plan for 3 drafts being required. This is not an upper limit depending on the amount of redrafting required. The report should be no longer than 30 pages (plus appendices), including an executive summary.

  - HMRC will require an additional version of the final report formatted in Govspeak markdown and prepared in Microsoft Word. This version should only be prepared following sign-off of the final publishable report agreed by the HMRC Project Manager. It should be identical to the signed-off Microsoft Word version, only with markdown coding included. No prior skills or experience are required by the contractor to produce this version – the HMRC Project Manager will provide guidance (example included at 7.8).

  - Draft copies of all key documents, such as survey scripts, presentation charts, topline and final reports provided to HMRC. These are to be submitted in sufficient time to the HMRC Project Manager for comments to be incorporated and for our approval to be given for the final version. Specific deadlines will be agreed with the HMRC team managing it.

  - All summaries, reports, data outputs (e.g., tables and graphs) should be provided in an electronic format, compatible with Microsoft Office applications.

  - All reports should be concise (no longer than 30 pages), written in plain English, follow the Gov.uk style guide, and follow HMRC’s accessibility guidance (the HMRC Project Manager will supply guidance prior to preparation of any report). HMRC expects all drafts to be complete, to have been proof-read before delivery and for data in the drafts to have been quality assured. HMRC may arrange for any final reports produced to be peer-reviewed, either in-house or externally.

Example Govspeak Markdown

  - Govspeak Markdown is a simple coding language used to publish content on Gov.uk. Developed by the Government Digital Service, it has been designed to be as easy-to-read and easy-to-write as possible, using simple punctuation instead of complicated tags and code.

  - The HMRC Project Manager will provide detailed guidance and examples of Govspeak Markdown during the reporting stage. An example of Govspeak Markdown is included below:

Final publishable report in Microsoft Word:

## 13.7 Qualitative research Figure 30 shows the profile of employers that took part in the qualitative follow-up interviews. - Figure 30: Profile of employers that took part in the follow-up qualitative interviews split by business size Business size; Number of interviews. Small (1 to 49 employees); 13. Medium (50 to 249 employees); 10. Large (250 or more employees); 7.

Formatted in Govspeak Markdown in Microsoft Word:

###13.7 Qualitative research Figure 30 shows the profile of employers that took part in the qualitative follow-up interviews. ####Figure 30: Profile of employers that took part in the follow-up qualitative interviews by business size Business size ¦ Number of interviews -¦- Small (1 to 49 employees) ¦ 13 Medium (50 to 249 employees) ¦ 10 Large (250 or more employees) ¦ 7

  - As with all outputs, contractors must include the cost of preparing the additional Govspeak Markdown version of the report into their cost proposal.

  - Delivery and format of the raw data set must be included in the Supplier’s proposal.

  - Delivery and format of presentations, including approximate number of slides, and whether this will take place online or face to face should be included the Supplier’s proposal.

  - There may be additional outputs required which will be agreed with the Supplier at the point of commissioning.

## Quality and Risk Management

  - Suppliers should look to demonstrate their evaluation expertise. Suppliers should have ISO9001 accreditation or be willing to achieve this.

  - Suppliers must include a quality control plan with their proposal, which must demonstrate their internal procedures to assure quality control. This must include an analysis plan showing the quality assurance processes undertaken at each stage of the project and a named member of the team who will conduct those tasks. This should include any proof reading or clearance by project directors.

  - Suppliers must include a project plan and time schedule for the work that identifies the main tasks and key milestones that will be used to monitor progress, indicating clearly where HMRC is expected to contribute.

  - Proposals must also include an assessment of the key risks to this project. This must identify the most significant risks to successful completion of the programme of work, assess the degree of risk (likelihood and impact), and set out strategies for minimising these risks and managing the consequences if problems occur. A risk register template is attached.

## Expertise and Capability

## HMRC acknowledges that considerable resources are required for the successful delivery of this project within the required timeframes and to sufficiently high standards. It is possible that Suppliers invited to tender have the skills and ability within their organisation to undertake all or part of this research but do not have sufficient resources required to successfully deliver the whole research requirement. HMRC therefore encourage Suppliers to collaborate with other Suppliers if required, and where relevant, to ensure that they are fully capable of undertaking this work.

## HMRC is seeking Suppliers who can demonstrate that their proposed research delivery team has:

- Experience of delivering robust policy evaluations within a broader strategic context which include a vigorous counterfactual element.

- Expertise in survey methodology and design including longitudinal and random probability surveys.

- Experience of developing and delivering qualitative research.

- The ability to utilise expertise and experience to apply industry best practice through all phases of the research.

- Experience of presenting to senior audiences including presenting technical and methodological issues in an accessible and engaging manner and drawing out strategic insights from complex research findings.

## Proposals must summarise the skills and expertise of their staff members relevant to this requirement. Suppliers must clearly identify the Project Manager and individual Project Managers and include their CVs as an annex. Each CV must not exceed two (2) pages.

## The proposal must specify details of which parts (if any) of the project will be sub-contracted, the name of the sub-contractor who will work on the project, their experience of related research, and their responsibilities within the project. If it is proposed to sub-contract any of the work, the same details as those provided by the Supplier should be given about the qualifications, experience and responsibilities of sub-contractor staff involved along with a description of their respective roles and the management arrangements put in place. Ultimately, the successful Supplier will be held to account for the performance of any sub-contractor and needs to demonstrate their confidence to successfully manage sub-contractors. This should also be considered for any joint submissions, as the second contractor will be treated as a sub-contractor.

## Project Management and Contract Administration

  - Robyn Kenwright is the HMRC Project Manager for this project. They will be responsible for the day-to-day management of the contract. Once the contract has been awarded, all contact with HMRC concerning the project should be made through them. The Supplier will be required to appoint a Contract Manager who will act as the principal point of contact for the department.

  - It is expected that the appointed Supplier will nominate Project Manager(s) to lead on the day-to-day management of the project. The Supplier’s Project Manager must work closely with the HMRC Project Manager, and with internal customers within HMRC throughout the duration of the project. The HMRC Project Manager must be kept informed of progress and be involved in key decisions. Proposed changes in project staffing (at all levels) or deviations from the agreed work programme must be discussed and agreed with the Project Manager in advance. Robyn Kenwright is responsible for all decisions that involve funding.

  - The award of this contract does not guarantee a minimum amount of work during the contract period. To maximise the value of the contract to HMRC and to the Supplier, regular review meetings will be held on a quarterly basis, or as required, between HMRC and the Supplier’s Project Manager. This ensures quality standards are met and contract management is effective for both HMRC and the appointed Supplier.

  - In costing the tender, the Supplier must allow for attendance at a minimum of four meetings annually. Most meetings are expected to take place at HMRC offices in Leeds or Manchester, or remotely, although some may take place at the Supplier’s premises. These might include the following:

- A project set-up meeting and implementation meetings.

- A briefing to discuss the initial findings / ensure robustness of the research / assess the feasibility of continuing to the next stage.

- Presentation of key findings and final analysis.

- A meeting to discuss requirements for the reporting stage of the research.

- 11. Research Cost Model: Research Scenarios and Rate cards

  - The contract value for Wave 1 will be £220,000 (excluding VAT). This includes development and baseline for those ITSA customers mandated to join MTD from 2027. Suppliers are asked to submit costings within this budget.

  - Price will be evaluated using a PQP methodology (Price per Quality Ratio), to assess the quality of the tenderer’s qualitative submission in relation to their price. The tender offering the lowest amount of price per quality point score will be determined as the most advantageous tender. The PQP score is calculated as follows:

  - Bidders must create a rate card for evaluation purposes. A scenario will be created using the rate card and the PQP methodology will be applied to achieve a score for each Supplier’s response.

  - HMRC reserves the right to not consider for award any tenders where the costings are in excess of £220,000 for Wave 1.

  - The Supplier must provide indicative costs for the qualitative research described in Wave 3.

  - The Supplier shall adhere to the costing assumptions outlined in the costing model.

  - Costs will be fixed throughout the duration of the contract.