Invitation to Tender to develop a high quality fuel poverty and health evaluation toolkit

Tender Reference Number: 1020/05/2015

Deadline for Tender Responses:  27 July 2015

Department of Energy and Climate Change

Date: 29 June 2015

The Department of Energy and Climate Change (“DECC”) wishes to commission via the DECC Evaluation Framework a project to develop a high quality fuel poverty and health evaluation toolkit

Enclosed are the following sections:

- Section 1 (page 3) 	Instructions on tendering procedures

- Section 2 (page 7) 	Specification of requirements

- Section 3 (page 18)	Further information on tendering procedure

- Section 4 (page 21)  	Declarations and information to be provided;

          - Statement of Non-Collusion

          - Form of Tender

          - Conflict of Interest

          - Questions for tenderers

          - Code of Practice for Research

- Annex A: Pricing schedule

- Annex B: Code of practice for research

Please register your interest in submitting a tender for this project by emailing William.boohan@decc.gsi.gov.uk. This will ensure you receive immediate notification of updates to the ITT process or answers to questions raised by potential bidders.

Please read the instructions on the tendering procedures carefully since failure to comply with them may invalidate your tender. Your tender must be returned by July 27 5pm clearly marked as “TENDER”.

I look forward to receiving your response.

Yours sincerely,

William Boohan

E:mail: William.boohan@decc.gsi.gov.uk

Section 1

Instructions and Information on Tendering Procedures

Invitation to Tender for expertise to develop high quality fuel poverty and health evaluation toolkit

Tender Reference Number: 1020/05/2015

Deadline for Tender Responses: 27 July2015

Contents

A.	Indicative Timetable	4

B.	Procedure for Submitting Tenders	4

C.	Conflict of Interest	5

D.	Evaluation of Responses	6

E.	Terms and conditions applying to this Invitation to Tender	6

F.	Further Instructions to Contractors	6

G.	Checklist of Documents to be Returned	6

# Indicative Timetable

The anticipated timetable for this tender exercise is as follows.  DECC reserves the right to vary this timetable. Any variations will be circulated to all organisations who have registered an interest in notifications.

| Tender Timeline | Date |
| --- | --- |
| Invitation to tender issued | 29 June |
| Deadline for questions relating to the tender | 13 July |
| Responses to questions published | 17 July |
| Deadline for receipt of tender | 27 July |
| Invite suppliers for bid clarification (if needed) | 28 July – 7 August |
| All suppliers alerted of outcome | 18 August |
| Contract award on signature by both parties | 25 August |
| Contract start date | 25 August |
| Kick off meeting | 2 or 3 September |

The contract is to be for a period of 13 – 15 weeks unless terminated or extended by the Department in accordance with the terms of the contract.

# Procedure for Submitting Tenders

The maximum page limit for tenders is 5 pages (excluding declarations).

Please email your proposal to William.boohan@decc.gsi.gov.uk  by 5pm on 27 July.

For questions regarding the procurement process please contact William Boohan.

Tenders will be received up to the time and date stated. Please ensure that your tender is delivered not later than the appointed time on the appointed date. The Department does not undertake to consider tenders received after that time. The Department requires tenders to remain valid for a period indicated in the specification of requirements.

DECC shall have the right to disqualify you from the procurement if you fail to fully complete your response, or do not return all of the fully completed documentation and declarations requested in this ITT.  DECC shall also have the right to disqualify you if it later becomes aware of any omission or misrepresentation in your response to any question within this invitation to tender. If you require further information concerning the tender process, or the nature of the proposed contract, email

William.Boohan@decc.gsi.gov.uk. All questions should be submitted by 5pm 13 July questions submitted after this date may not be answered. Should questions arise during the tendering period, which in our judgement are of material significance, we will publish these questions with our formal reply by the end of 17 July and circulate – unnamed - to all organisations in the framework. All contractors should then take that reply into consideration when preparing their own bids, and we will evaluate bids on the assumption that they have done so.

You will not be entitled to claim from the Department any costs or expenses that you may incur in preparing your tender whether or not your tender is successful.

# Conflict of Interest

The DECC standard terms and conditions of contract include reference to conflict of interest and require contractors to declare any potential conflict of interest to the Secretary of State.

For research and analysis, conflict of interest is defined the presence of an interest or involvement of the contractor, subcontractor (or consortium member) which could affect the actual or perceived impartiality of the research or analysis.

Where there may be a potential conflict of interest, it is suggested that the consortium or organisation designs a working arrangements such that the findings cannot be influenced (or perceived to be influenced) by the organisation which is the owner of a potential conflict of interest. For example, consideration should be given to the different roles which organisations play in the research or analysis, and how these can be structured to ensure an impartial approach to the project is maintained.

The process by which this is managed in the procurement process is as follows:

- During the bidding process, organisations may contact DECC to discuss whether or not their proposed arrangement is likely to yield a conflict of interest. Any responses given to individual organisations or consortia will be published on contract finder (in a form which does not reveal the questioner’s identity). Any organisation thinking of submitting a bid, should share their contact details with the staff member responsible for this procurement, to ensure they receive an update when any responses to questions are published.

- Contractors are asked to sign and return Declaration 3 (page 21) to indicate whether or not any conflict of interest may be, or be perceived to be, an issue. If this is the case, the contractor or consortium should give a full account of the actions or processes that it will use to ensure that conflict of interest is avoided. In any statement of mitigating actions, contractors are expected to outline how they propose to achieve a robust, impartial and credible approach to the research.

- When tenders are scored, this declaration will be subject to a pass/fail score, according to whether, on the basis of the information in the proposal and declaration, there remains a conflict of interest which may affect the impartiality of the research.

Failure to declare or avoid conflict of interest at this or a later stage may result in exclusion from the procurement competition, or in DECC exercising its right to terminate any contract awarded.

# Evaluation of Responses

The tender process will be conducted to ensure that bids are evaluated fairly and transparently, in accordance with agreed assessment criteria.  Further details are provided in the specification.

# Terms and conditions applying to this Invitation to Tender

This project is being commissioned via the DECC Evaluation Framework.  The DECC Standard Terms and Conditions of Contract will apply to this contract.

# Further Instructions to Contractors

The Department reserves the right to amend the enclosed tender documents at any time prior to the deadline for receipt of tenders. Any such amendment will be numbered, dated and issued by July 10. Where amendments are significant, the Department may at its discretion extend the deadline for receipt of tenders.

DECC reserves the right to withdraw this contract opportunity without notice and will not be liable for any costs incurred by contractors during any stage of the process. Contractors should also note that, in the event a tender is considered to be fundamentally unacceptable on a key issue, regardless of its other merits, that tender may be rejected. By issuing this invitation the Department is not bound in any way and does not have to accept the lowest or any tender and reserves the right to accept a portion of any tender unless the tenderer expressly stipulates otherwise in their tender.

# Checklist of Documents to be Returned

- Proposal (maximum 5  pages)

- Annex A – pricing schedule

- Declaration 1: Statement of non-collusion

- Declaration 2: Form of Tender

- Declaration 3: Conflict of Interest

- Declaration 5: Code of Practice (for R&D delete if not applicable)

Section 2

Specification of Requirements

Invitation to Tender for expertise to develop high quality fuel poverty and health evaluation toolkit

Tender Reference Number: 1020/05/2015

Deadline for Tender Responses: 27 July 2015

Contents

1.	Introduction and summary of requirements	8

2.	Background	8

3.	Aims and Objectives	9

4.	Outputs Required	9

5.	Ownership and Publication	9

6.	Quality Assurance	10

7.	Timetable	10

9.	Working Arrangements	10

10.	Required Skills	11

11.	Budget	11

12.	Evaluation of Tenders	12

# Introduction and summary of requirements

DECC is looking for an individual, small team  or consortium to develop a high quality evaluation toolkit that will enable local organisations delivering health-related fuel poverty schemes to improve the processes and assess the impacts of their interventions. The successful contractor will develop clear plans for what should be included in the toolkit and work closely with a range of stakeholders (including the policy team, wider DECC colleagues, and health and local delivery stakeholders) to ensure the toolkit developed is fit-for-purpose. This project is being commissioned via the DECC Evaluation Framework.

The work would consist of:

Phase 1: Assessment of evidence needs and development of Evaluation Toolkit

- Consulting delivery bodies & health sector funding decision-makers on their evaluation needs

- Researching the questions that bodies wish/need to answer (using Steering and wider Reference Group) and develop modular set of data requirements to answer these questions, as well as advice on how to gather and analyse that data, and on sources of further support and advice that may be available.

- Initial literature review and identification of existing, relevant evaluation resources.

- Gathering templates/model documents, which may need to be edited for relevance and applicability

- Presenting an assessment of strengths and limitations of different indicators, advice on implications of sample size, duration of follow up and consideration of confounders.

- Compiling the above resources into a modular toolkit, suitable for web-publication, covering the different aspects of evaluation of health and fuel poverty schemes

- Conducting a small-scale pilot or otherwise test the assumptions and the draft toolkit developed thus far. This would be expected to entail working with a local scheme in applying the draft guidance, and reporting on the lessons learnt for the final guidance.

- Producing finalised toolkit which has been adjusted for results of testing stage and which, for example, could include the following:

- How to identify a research question

- Choosing a process or an impact evaluation

- What methods are appropriate for what types of question

- What can realistically be achieved in different evaluation timeframes

- What can realistically be done in house versus what would need to be contracted out

- How to contract out

- Have you considered co-funding an evaluation with similar organisations

- How to report findings and individual advice on Transparency and publishing.

Phase 2: Implementation (to be costed separately with a break clause in contract to allow DECC to review)

- After launch of Toolkit, produce guidance on systematic and consistent implementation of Toolkit, to enable as much comparability between scheme evaluations as possible.

# Background

The links between health and fuel poverty are well-understood and many local schemes are delivering support to fuel poor people with physical and/or mental health problems that can be affected by cold homes.  The local schemes are run by a range of organisations including local authorities, housing associations, not-for-profit organisations and charities.  Typically, such schemes offer a broad range of support to low income households, living in homes with poor levels of energy efficiency.  This may for example include installation of energy efficiency measures (from draft proofing to replacement boilers and new central heating systems), advice on switching energy suppliers, benefits advice, fuel debt advice, and referral to a range of health, social care and housing-related services.  Delivery models vary enormously and there is limited evidence on which approaches (e.g. to targeting and referrals) are most effective or efficient.  In addition, there is a desire on the part of local delivery bodies to secure funding from the health sector, and Clinical Commissioning Groups approached for funding often desire evidence on health impacts / health and social care service impacts that is not currently gathered by the majority of local schemes.

There is a desire amongst local delivery bodies for a toolkit, tailored to health & fuel poverty, to support effective evaluation. This was evident from a workshop DECC held with local delivery organisations in December 2014 to explore evaluation, and subsequent engagement with stakeholders suggests there is increasing appetite to conduct evaluations that attempt to measure the health impacts of such schemes.

Limited resource in local delivery bodies makes it important to remove barriers to designing effective evaluations. Ideally a toolkit would provide standard advice in a modular format, from which delivery bodies can pick and choose the elements relevant to their scheme, their objectives and their capacity.  However, as the above suggests, there is unlikely to be a one-size-fits-all approach to evaluation and as such the guidance needs to be flexible where possible.

The toolkit should cover process evaluation (how to evaluate delivery effectiveness in a way which facilitates improvement) and impact evaluation (on fuel poverty, on health outcomes, and on health and social care services).

The developer of the toolkit will also need to show DECC that the draft toolkit has been rigorously tested and adjusted to overcome any problems identified.

# Aims and Objectives

DECC seeks hands on expertise to develop a high quality, fit for purpose, tested and proven evaluation toolkit, suitable for use by a range of local delivery organisations.  The toolkit should facilitate effective evaluation of a wide range of local health and fuel poverty schemes, enabling the organisations delivering those schemes to produce evidence about the effectiveness of their approach to delivery and/or their scheme’s impact.

# Outputs Required

The successful individual, small team  or consortium will be expected to work closely with DECC officials, a steering group and a wider reference group of stakeholders, including organisations representative of end users of the toolkit, over the length of the contract.

The following outputs will be required from the project at agreed milestones as set out on page 11.

Phase 1: Assessment of evidence needs and development of Evaluation Toolkit

- Consulting delivery bodies & health sector funding decision-makers on their evaluation needs

- Researching the questions that bodies wish/need to answer (using Steering and wider Reference Group) and develop modular set of data requirements to answer these questions, as well as advice on how to gather and analyse that data, and on sources of further support and advice that may be available.

- Initial literature review and identification of existing, relevant evaluation resources.

- Gathering templates/model documents, which may need to be edited for relevance and applicability

- Presenting an assessment of strengths and limitations of different indicators, advice on implications of sample size, duration of follow up and consideration of confounders.

- Compiling the above resources into a modular toolkit, suitable for web-publication, covering the different aspects of evaluation of health and fuel poverty schemes

- Conducting a small-scale pilot or otherwise test the assumptions and the draft toolkit developed thus far. This would be expected to entail working with a local scheme in applying the draft guidance, and reporting on the lessons learnt for the final guidance.

- Producing`-

- finalised toolkit adjusted for results of testing stage.

Phase 2: Implementation (to be costed separately with a break clause in contract to allow DECC to review)

- After launch of Toolkit, produce guidance on systematic and consistent implementation of Toolkit, to enable as much comparability between scheme evaluations as possible.

# Ownership and Publication

The products of the contract remain the property of DECC and will be published/further disseminated by DECC.

# Timetable

The following timetable has been developed so that the evaluation plan can be finalised in order to issue an ITT for the full evaluation work by the end of the year / start of 2015. We appreciate that the timetable is tight and there may be some scope for flexibility but please flag up any issues with this timetable.

| Action | Timing – completed by |
| --- | --- |
| Inception meeting | Week commencing 1 September 2015 |
| Toolkit delivered | 10 December 2015 |
| Guidance on implementation of toolkit | 1 April 2016 |

# Working Arrangements

The individual, small team  or consortium will be expected to work closely with DECC officials, a steering group and a wider reference group of stakeholders over the length of the contract and engagement will be expected to be continuous and on-going, this may include spending time working alongside DECC officials in DECC offices. If a small team is proposed, there should be one named lead for the work though which all enquiries can be channelled.

The bids should include details of who will sign off outputs and their role within the contractor’s organisation.

DECC will assist with setting up and administering the steering and reference groups, which we anticipate will consist of DECC representatives, colleagues from the Department of Health and Public Health England, representatives of local delivery organisations, including local authorities, amongst others, and representatives of health bodies (e.g. clinical commissioning groups). The steering and reference groups will be important for the development of a toolkit that is fit for purpose, providing the contractor with access to a range of expertise, including in the areas of delivery of local schemes, the needs of vulnerable individuals, knowledge of wider health policy and evidence on health and cold homes, and an understanding of the requirements of decision-makers in the health sector.

# Skills and experience

A range of different skills are required for this research. Contractors should clearly set out how the skills and expertise provided by each member of the proposed project team meet the requirements.

The following skills are considered particularly important for this work:

- Experience of designing evaluation of schemes delivering support to households, with qualitative / quantitative social research elements.

- Understanding of fuel poverty and energy efficiency

- Experience of health policy / the health sector,  including experience of health economics and of how to identify,  gather and use correct type of health data to inform decisions on health spending

- Expertise in drafting clear, accessible and impactful guidance.

- Experience of working with local organisations in different sectors.

- Ability to work consultatively and collaboratively: contractor will be required to consult with a diverse range of stakeholders and to make sound judgements about how to fulfil a range of end-user requirements based on those conversations.

- Organisational, writing and IT skills: the end product will need to be presented clearly, succinctly and in an easy to understand and easy to navigate format, which can be uploaded to the web.

- Strong analytical skills including ability to translate the evidence needs of end-users into a series of targeted analytical questions and ability to advise on most appropriate methodology.

# Budget

The budget for this project is £30,000 excluding VAT and is broken down as follows:

Phase1: £25,000

Phase 2: £5,000

Bidders should provide a full and detailed breakdown of costs (including options where appropriate). This should include staff (and day rate) allocated to specific tasks.

Value for money will be a criterion against which bids which will be assessed.

Payments will be linked to delivery of key milestones. The indicative milestones and phasing of payments is as follows:

- Consultation with end users and clear recommended outline for what the toolkit will look like – 25%

- Delivery of acceptable toolkit – 60%

- Delivery of implementation guidance (Phase 2 – optional) – 15%

In submitting full tenders, contractors confirm in writing that the price offered will be held for a minimum of 60 calendar days from the date of submission. Any payment conditions applicable to the prime contractor must also be replicated with sub-contractors.

The Department aims to pay all correctly submitted invoices as soon as possible with a target of 10 days from the date of receipt and within 30 days at the latest in line with standard terms and conditions of contract.

# Evaluation of Tenders

Contractors are invited to submit full tenders of no more than 5 pages, excluding declarations. Tenders will be evaluated by at least three DECC staff.

DECC will select the bidder that scores highest against the criteria and weighting listed below:

- Conflict of interest: pass/fail. See page 5 of the ITT for further information

EVALUATION CRITERIA AND SCORING

| #### Criterion | #### Description | #### Weighting |
| --- | --- | --- |
| 1 | Evidence of experience of designing effective evaluations of schemes with qualitative/quantitative social research methods. | 10% |
| 2 | Value for money | 20% |
| 3 | Clarity of proposal, deliverability and risk management | 20% |
| 4 | Understanding of the requirements and subject area | 20% |
| 5 | Communication skills and ability to work consultatively and collaboratively | 15% |
| 6 | Analytical and organisational skills | 15% |
|  |  | 100% |

Scoring Method

Tenders will be scored against each of the criteria above, according to the extent to which they meet the requirements of the tender. The meaning of each score is outlined in the table below.

The total score will be calculated by applying the weighting set against each criterion, outlined above; the maximum number of marks possible will be 100.  Should any contractor score 1 in any of the criteria, they will be excluded from the tender competition.

| Score | Description |
| --- | --- |
| 1 | Not Satisfactory: Proposal contains significant shortcomings and does not meet the required standard |
| 2 | Partially Satisfactory: Proposal partially meets the required standard, with one or more moderate weaknesses or gaps |
| 3 | Satisfactory: Proposal mostly meets the required standard, with one or more minor weaknesses or gaps. |
| 4 | Good: Proposal meets the required standard, with moderate levels of assurance |
| 5 | Excellent: Proposal fully meets the required standard with high levels of assurance |

Structure of Tenders

Contractors are strongly advised to structure their tender submissions to cover each of the criteria above. Complete the price schedule attached at Annex A, specifying the daily rates (ex-VAT) you will charge for each level of your staff.

Bid Clarification

DECC reserves the right to award the contract based on applicants’ written evaluation only if one candidate emerges from the evaluation stage as significantly stronger than the others.

DECC may invite all suppliers for bid clarification if they feel bid clarification should be carried out.

Feedback

Feedback will be given in the unsuccessful letters or emails.

Section 3

Further Information on Tender Procedure

Invitation to Tender for expertise to develop high quality fuel poverty and health evaluation toolkit

Tender Reference Number: 1020/05/2015

Deadline for Tender Responses: 27 July 2015

Contents:

A.	Definitions	15

B.	Data security	15

C.	Non-Collusion	16

# Definitions

Please note that references to the "Department" throughout these documents mean The Secretary of State for Energy and Climate Change acting through his/her representatives in the Department of Energy and Climate Change.

The Freedom of Information Act 2000 (“FOIA”) and the Environmental Information Regulations 2004 (“EIR”) apply to the Department.  You should be aware of the Department’s obligations and responsibilities under FOIA or EIR to disclose, on written request, recorded information held by the Department.  Information provided in connection with this procurement exercise, or with any contract that may be awarded as a result of this exercise, may therefore have to be disclosed by the Department in response to such a request, unless the Department decides that one of the statutory exemptions under the FOIA or the exceptions in the EIR applies.  If you wish to designate information supplied as part of this response as confidential, of if you believe that its disclosure would be prejudicial to any person’s commercial interests, you must provide clear and specific detail as to the precise information involved and explain (in broad terms) what harm may result from disclosure if a request is received, and the time period applicable to that sensitivity.  Such designation alone may not prevent disclosure if in the Department’s reasonable opinion publication is required by applicable legislation or Government policy or where disclosure is required by the Information Commissioner or the First-tier Tribunal (Information Rights).

Additionally, the Government’s transparency agenda requires that tender documents (including ITTs such as this) are published on a designated, publicly searchable web site.  The same applies to other tender documents issued by the Department (including the original advertisement and the pre-qualification questionnaire (if used)), and any contract entered into by the Department with its preferred supplier once the procurement is complete.  By submitting a tender you agree that your participation in this procurement may be made public.  The answers you give in this response will not be published on the transparency web site (but may fall to be disclosed under FOIA or EIR (see above)).  Where tender documents issued by the Department or contracts with its suppliers fall to be disclosed the Department will redact them as it thinks necessary, having regard (inter alia) to the exemptions/exceptions in the FOIA or EIR.

# Data security

The successful tenderer must comply with the Data Protection Act (DPA) 1998 and any information collected, processed and transferred on behalf of DECC, and in particular personal information, must be held and transferred securely. Contractors must provide assurances of compliance with the DPA and set out in their proposals details of the practices and systems they have in place for handling data securely including transmission between the field and head office and then to DECC. Contractors will have responsibility for ensuring that they and any subcontractor who processes or handles information on behalf of DECC is conducted securely. The sorts of issues which must be addressed satisfactorily and described in contractors’ submissions include:

- procedures for storing both physical and system data;

- data back-up procedures;

- procedures for the destruction of physical and system data;

- how data is protected;

- data encryption software used;

- use of laptops and electronic removable media;

- details of person/s responsible for data security;

- policies for unauthorised staff access or misuse of confidential/personal data;

- policies for staff awareness and training of DPA;

- physical security of premises.

- How research respondents will be made aware of all potential uses of their     data.

# Non-Collusion

No tender will be considered for acceptance if the contractor has indulged or attempted to indulge in any corrupt practice or canvassed the tender with an officer of DECC. Section 4 contains a "Statement of non-collusion" (declaration 1); any breach of the undertakings covered under items 1 - 3 inclusive will invalidate your tender.   If a contractor has indulged or attempted to indulge in such practices and the tender is accepted, then grounds shall exist for the termination of the contract and the claiming damages from the successful contractors. You must not:

- Tell anyone else what your tender price is or will be, before the time limit for delivery of tenders.

- Try to obtain any information about anyone else's tender or proposed tender before the time limit for delivery of tenders.

- Make any arrangements with another organisation about whether or not they should tender, or about their or your tender price.

Offering an inducement of any kind in relation to obtaining this or any other contract with the Department will disqualify your tender from being considered and may constitute a criminal offence.

Section 4

Declarations to be submitted by the Tenderer

Invitation to Tender for expertise to develop high quality fuel poverty and health evaluation toolkit

Tender Reference Number: 1020/05/2015

Deadline for Tender Responses: 27 July 2015

Contents

Declaration 1: Statement of non-collusion	18

Declaration 2: Form of Tender	19

Declaration 3: Conflict of Interest	20

Declaration 4: Questions for tenderers	22

# Declaration 1: Statement of non-collusion

To: The Department of Energy and Climate Change

1.  We recognise that the essence of competitive tendering is that the Department will receive a bona fide competitive tender from all persons tendering.  We therefore certify that this is a bona fide tender and that we have not fixed or adjusted the amount of the tender or our rates and prices included therein by or in accordance with any agreement or arrangement with any other person.

2. We also certify that we have not done and undertake not to do at any time before the hour and date specified for the return of this tender any of the following acts:

- communicate to any person other than the Department the amount or approximate amount of our proposed tender, except where the disclosure, in confidence, of the approximate amount is necessary to obtain any insurance premium quotation required for the preparation of the tender;

- enter into any agreement or arrangement with any other person that he shall refrain for submitting a tender or as to the amount included in the tender;

- offer or pay or give or agree to pay or give any sum of money, inducement or valuable consideration directly or indirectly to any person doing or having done or causing or having caused to be done, in relation to any other actual or proposed tender for the contract any act, omission or thing of the kind described above.

3. In this certificate, the word “person” shall include any person, body or association, corporate or unincorporated; and “any agreement or arrangement” includes any such information, formal or informal, whether legally binding or not.

……………………………………………………………………………….….

Signature (duly authorised on behalf of the tenderer)

……….………………………………………………………………………….

Print name

…………………………………………………………….…………………….

On behalf of (organisation name)

…………………………………………………………………….…………….

Date

# Declaration 2: Form of Tender

To: The Department of Energy and Climate Change

1. Having considered the invitation to tender and all accompanying documents

(including without limitation, the terms and conditions of contract and the Specification) we confirm that we are fully satisfied as to our experience and ability to deliver the goods/services in all respects in accordance with the requirements of this invitation to tender.

2. We hereby tender and undertake to provide and complete all the services required to be performed in accordance with the terms and conditions of contract and the Specification for the amount set out in the Pricing Schedule.

3. We agree that any insertion by us of any conditions qualifying this tender or any unauthorised alteration to any of the terms and conditions of contract made by us may result in the rejection of this tender.

4. We agree that this tender shall remain open to be accepted by the Department for 8 weeks from the date below.

5. We understand that if we are a subsidiary (within the meaning of section 1159 of (and schedule 6 to) the Companies Act 2006) if requested by the Department we may be required to secure a Deed of Guarantee in favour of the Department from our holding company or ultimate holding company, as determined by the Department in their discretion.

6. We understand that the Department is not bound to accept the lowest or any tender it may receive.

7. We certify that this is a bona fide tender.

…………………………………………………………………………........

Signature (duly authorised on behalf of the tenderer)

…………………………………………………………………………………

Print name

………………………………………………………………………….

On behalf of (organisation name)

………………………………………………………………………….

Date

# Declaration 3: Conflict of Interest

I have nothing to declare with respect to any current or potential interest or conflict in relation to this research (or any potential providers who may be subcontracted to deliver this work, their advisers or other related parties). By conflict of interest, I mean, anything which could be reasonably perceived to affect the impartiality of this research, or to indicate a professional or personal interest in the outcomes from this research.

Signed      …………………………………….

Name	…………………………………….

Position     …………………………………….

OR

I wish to declare the following with respect to personal or professional interests related to relevant organisations*;

- X

- X

Where a potential conflict of interest has been declared for an individual or organisation within a consortia, please clearly outline the role which this individual or organisation will play in the proposed project and how any conflict of interest has or will be mitigated.

- X

- X

Signed      …………………………………….

Name	…………………………………….

Position     …………………………………….

Please complete this form and return this with your ITT documentation - Nil returns are required.

* These may include (but are not restricted to);

- A professional or personal interest in the outcome of this research

- For evaluation projects, a close working, governance, or commercial involvement in the project under evaluation

- Current or past employment with relevant organisations

- Payment (cash or other) received or likely to be received from relevant organisations for goods or services provided (Including consulting or advisory fees)

- Gifts or entertainment received from relevant organisations

- Shareholdings (excluding those within unit trusts, pension funds etc) in relevant organisations

- Close personal relationship or friendships with individuals employed by or otherwise closely associated with relevant organisations

All of the above apply both to the individual signing this form and their close family / friends / partners etc.

If your situation changes during the project in terms of interests or conflicts, you must notify DECC straight away.

A DECLARATION OF INTEREST WILL NOT NECESSARILY MEAN THE INDIVIDUAL OR ORGANISATION CANNOT WORK ON THE PROJECT; BUT IT IS VITAL THAT ANY INTEREST OR CONFLICT IS DECLARED SO IT CAN BE CONSIDERED OPENLY.

# Declaration 4: Questions for tenderers

In some circumstances the Department is required by law to exclude you from participating further in a procurement.  If you cannot answer ‘no’ to every question in this section it is very unlikely that your application will be accepted, and you should contact us for advice before completing this form.

Please state ‘Yes’ or ‘No’ to each question.

| Has your organisation or any directors or partner or any other person who has powers of representation, decision or control been convicted of any of the following offences? | Answer |
| --- | --- |
| - conspiracy within the meaning of section 1 or 1A of the Criminal Law Act 1977 or article 9 or 9A of the Criminal Attempts and Conspiracy (Northern Ireland) Order 1983 where that conspiracy relates to participation in a criminal organisation as defined in Article 2 of Council Framework Decision 2008/841/JHA; |  |
| - corruption within the meaning of section 1(2) of the Public Bodies Corrupt Practices Act 1889 or section 1 of the Prevention of Corruption Act 1906; where the offence relates to active corruption; |  |
| - the offence of bribery, where the offence relates to active corruption; |  |
| - bribery within the meaning of section 1 or 6 of the Bribery Act 2010; |  |
| - fraud, where the offence relates to fraud affecting the European Communities’ financial interests as defined by Article 1 of the Convention on the protection of the financial interests of the European Communities, within the meaning of: |  |
| - the offence of cheating the Revenue; |  |
| - the offence of conspiracy to defraud; |  |
| - fraud or theft within the meaning of the Theft Act 1968, the Theft Act (Northern Ireland) 1969, the Theft Act 1978 or the Theft (Northern Ireland) Order 1978; |  |
| - fraudulent trading within the meaning of section 458 of the Companies Act 1985, article 451 of the Companies (Northern Ireland) Order 1986 or section 993 of the Companies Act 2006; |  |
| - fraudulent evasion within the meaning of section 170 of the Customs and Excise Management Act 1979 or section 72 of the Value Added Tax Act 1994; |  |
| - an offence in connection with taxation in the European Union within the meaning of section 71 of the Criminal Justice Act 1993; |  |
| - destroying, defacing or concealing of documents or procuring the execution of a valuable security within the meaning of section 20 of the Theft Act 1968 or section 19 of the Theft Act (Northern Ireland) 1969; |  |
| - fraud within the meaning of section 2, 3 or 4 of the Fraud Act 2006; or |  |
| - making, adapting, supplying or offering to supply articles for use in frauds within the meaning of section 7 of the Fraud Act 2006; |  |
| - money laundering within the meaning of section 340(11) of the Proceeds of Crime Act 2002; |  |
| - an offence in connection with the proceeds of criminal conduct within the meaning of section 93A, 93B or 93C of the Criminal Justice Act 1988 or article 45, 46 or 47 of the Proceeds of Crime (Northern Ireland) Order 1996; or |  |
| - an offence in connection with the proceeds of drug trafficking within the meaning of section 49, 50 or 51 of the Drug Trafficking Act 1994; or |  |
| - any other offence within the meaning of Article 45(1) of Directive 2004/18/EC as defined by the national law of any relevant State. |  |

# (For research and development projects only. Delete if not applicable)

# Declaration 5: Code of Practice

I confirm that I am aware of the requirements of the DECC Code of Practice for Research and, in the proposed project, I will use my best efforts to ensure that the procedures used conform to those requirements under the following headings:

Responsibilities

Competence

Project planning

Quality Control

Handling of samples and materials

Facilities and equipment

Documentation of procedures and methods

Research/work records

I understand that DECC has the right to inspect our procedures and practices against the requirements of the Code of Practice, and that I may be asked to provide documentary evidence of our working practices or provide access and assistance to auditors appointed by DECC.

(There is some flexibility in the application of the Code of Practice to specific research projects. Contractors are encouraged to discuss with DECC any aspects that cause them concern, in order to reach agreement on the interpretation of each requirement.)

Annex A: Pricing Schedule

Part A – Staff/project team charges

| Set up Costs – please specify |  |
| --- | --- |
| Expenses |  |

| *Grade/level of staff | Daily rate (ex VAT) | No. days offered over course of contract | Tasks to be undertaken on this project | Total price offered per staff member |
| --- | --- | --- | --- | --- |
|  | £ |  |  | £ |
|  | £ |  |  | £ |
|  | £ |  |  | £ |
|  | £ |  |  | £ |
|  | £ |  |  | £ |
| Sub-total |  |  |  | £ |

[*Suppliers should also include sub-contractors]

Part B – Non-staff/project team charges

| Item | No. of items | Price per item (ex VAT) | Total price per offered |
| --- | --- | --- | --- |
|  |  | £ | £ |
|  |  | £ | £ |
|  |  | £ | £ |
|  |  | £ | £ |
|  |  | £ | £ |
| Sub-total |  |  | £ |

Part C – Full price offered

| Sub-total (Part A + Part B) | £ |
| --- | --- |
| VAT | £ |
| TOTAL (Sub-total + VAT) | £ |

Annex B: Code of Practice for Research

(For research only. Delete if not applicable)

CODE OF PRACTICE FOR RESEARCH

Issued by the Department of Energy of Climate Change

DECC has developed this Code of Practice from the Joint Code of Practice issued by BBSRC; the Department for Environment, Food and Rural Affairs (Defra); the Food Standards Agency; and the Natural Environment Research Council (NERC) which lays out a framework for the proper conduct of research. It sets out the key aspects of the research process and the importance of making judgements on the appropriate precautions needed in every research activity.

The Code applies to all research funded by DECC. It is intended to apply to all types of research, but the overriding principle is fitness of purpose and that all research must be conducted diligently by competent researchers and therefore the individual provisions must be interpreted with that in mind.

PRINCIPLES BEHIND THE CODE OF PRACTICE

Contractors and consortia funded by DECC are expected to be committed to the quality of the research process in addition to quality of the evidence outputs

The Code of Practice has been created in order to assist contractors to conduct research of the highest quality and to encourage good conduct in research and help prevent misconduct,.

Set out over 8 responsibilities the code of practice provides general principles and standards for good practice in research.

Most contractors will already have in place many of the measures set out in the

Code and its adoption should not require great effort.

COMPLIANCE WITH THE CODE OF PRACTICE

All organisations contracting to DECC (including those sub-contracting as part of a consortium) will be expected to commit to upholding these responsibilities and will be expected to indicate acceptance of the Code when submitting proposals to the Department.

Contractors are encouraged to discuss with DECC any clauses in the Code that they consider inappropriate or unnecessary in the context of the proposed research project. The Code, and records of the discussions if held, will become part of the Terms and Conditions under which the research is funded.

Additionally, DECC may conduct (or request from the Contractor as appropriate) a formal risk assessment on the project to identify where additional controls may be needed.

MONITORING OF COMPLIANCE WITH THE CODE OF PRACTICE

Monitoring of compliance with the Code is necessary to ensure:

- Policies and managed processes exist to support compliance with the Code

- That these are being applied in practice.

In the short term, DECC can require contractors to conduct planned internal audits although DECC reserve the right to obtain evidence that a funded project is carried out to the required standard. DECC may also conduct an audit of a Contractor’s research system if deemed necessary.

In the longer term it is expected that most research organisations will assure the quality of their research processes by means of a formal system that is audited by an impartial and competent third party against an appropriate internationally recognised standard that is fit for purpose.

A recommended checklist for researchers can be found on the UK Research Integrity Office (UKRIO) website at http://www.ukrio.org/what-we-do/code-of-practice-for-research

SPECIFIC REQUIREMENTS IN THE CODE OF PRACTICE

1. Responsibilities

All organisations contracting to DECC (including those sub-contracting as part of a consortium will be responsible for the overall quality of research they conducted. Managers, group leaders and supervisors have a responsibility to ensure a climate of good practice in the research teams, including a commitment to the development of scientific and technical skills.

The Principal Investigator or Project Leader is responsible for all the work conducted in the project including that of any subcontractors. All staff and students must have defined responsibilities in relation to the project and be aware of these responsibilities.

2. Competence

All personnel associated with the project must be competent to perform the technical, scientific and support tasks required of them. Personnel undergoing training must be supervised at a level such that the quality of the results is not compromised by the inexperience of the researcher.

3. Project planning

An appropriate level of risk assessment must be conducted to demonstrate awareness of the key factors that will influence the success of the project and the ability to meet its objectives. There must be a written project plan showing that these factors (including research design, statistical methods and others) have been addressed. Projects must be ethical and project plans must be agreed in collaboration with DECC, taking account of the requirements of ethical committees or the terms of project licences, if relevant.

Significant amendments to the plan or milestones must be recorded and approved by DECC if applicable.

4. Quality Control

The organisation must have planned processes in place to assure the quality of the research undertaken by its staff Projects must be subjected to formal reviews of an appropriate frequency. Final and interim outputs must always be accompanied by a statement of what quality control has been undertaken.

The authorisation of outputs and publications shall be as agreed by DECC, and subject to senior approval in DECC, where appropriate. Errors identified after publication must be notified to DECC and agreed corrective action initiated.

5. Handling of samples and materials

All samples and other experimental materials must be labelled (clearly, accurately, uniquely and durably), and retained for a period to be agreed by DECC. The storage and handling of the samples, materials and data must be as specified in the project plan (or proposal), and must be appropriate to their nature. If the storage conditions are critical, they must be monitored and recorded.

6. Documentation of procedures and methods

All the procedures and methods used in a research project must be documented, at least in the personal records of the researcher. This includes analytical and statistical procedures and the generation of a clear audit trial linking secondary processed information to primary data.

There must be a procedure for validation of research methods as fit for purpose, and modifications must be trackable through each stage of development of the method.

7. Research/work records

All records must be of sufficient quality to present a complete picture of the work performed, enabling it to be repeated if necessary.

The project leader is accountable for the validity of the wok and responsible for ensuring that regular reviews of the records of each researcher are conducted

The location of all project records, including critical data, must be recorded. They must be retained in a form that ensures their integrity and security, and prevents unauthorised modification, for a period to be agreed by DECC

A recommended checklist for researchers can be found on the UK Research Integrity Office (UKRIO) website at http://www.ukrio.org/what-we-do/code-of-practice-for-research

Please note that this declaration applies to individuals, single organisations and consortia.

The Code of Practice is attached to this ITT as Annex C

Please delete as appropriate

Please note ethical approval does not remove the responsibility of the individual for ethical behaviour.

Please note that this also applies to projects being undertaken by consortia.