# Annex A

| Title of Project | Ocean Country Partnership Programme: Sri Lanka Technical advice and capacity building to support conservation and management of protected, endangered and threatened mobile marine species in Sri Lanka |
| --- | --- |
| Date and Time for Return of Bids | Monday 26 August 2024 17:00 (GMT) |
| Contract Reference Number | C24-0604-1918 |
| Address for Bid Submission | 1 electronic copy to be sent to TenderResponse@jncc.gov.uk PLEASE DO NOT SEND BIDS DIRECTLY TO HANNAH HOOD, JAMIE SMALL OR A MEMBER OF THE JNCC PROCUREMENT VIA THEIR WORK EMAIL ADDRESSES AS THIS WILL INVALIDATE YOUR BID. Bids must be less than 10 MB in size. On receipt of your bid, you will receive an automated e-mail to confirm receipt by the JNCC Support Co. If you do not receive this automated email, please contact the number below: (00 44 1733 866 988) |
| Contacts for Technical Information relating to this Project Specification | Procurement Team Joint Nature Conservation Committee Email: contractqueries@jncc.gov.uk Telephone: +441733 866987 |
| Contact for Queries Regarding the Procurement Procedure | Procurement Team Joint Nature Conservation Committee Email: contractqueries@jncc.gov.uk Telephone: +441733 866987 |
| Proposed Start Date | Monday 9 September 2024 |
| Proposed End Date | Monday 3 March 2025 |

Ocean Country Partnership Programme: Sri Lanka

Technical advice and capacity building to support conservation and management of protected, endangered and threatened mobile marine species in Sri Lanka.

Contents

1.	Joint Nature Conservation Committee	3

2.	Project Background	3

3.	Project Aims	4

4.	Project Objectives	5

5.	Contractor Requirements	8

6.	Potential Follow-On Work	8

7.	Product Specification	8

8.	Timescale	9

9.	Health and Safety	9

10.	Project Management	10

11.	Instructions for Bid Submission	10

12.	Evaluation Criteria	11

13.	Payment	12

14.	Additional Requirements	12

15.	Procurement Timetable (which may be subject to change)	13

## Joint Nature Conservation Committee

The Joint Nature Conservation Committee (JNCC) is the statutory adviser to the UK Government and devolved administrations on UK and international nature conservation.

Our role is to provide scientific evidence, information, and advice to inform decisions to protect the natural environment. Our specific role is to work on nature conservation issues that affect the UK as a whole and internationally, by:

advising Government on the development and implementation of policies for, or affecting, nature conservation in the UK and internationally;

providing advice and disseminating knowledge on nature conservation issues affecting the UK and internationally;

establishing common standards throughout the UK for nature conservation, including monitoring, research, and the analysis of results; and

commissioning or supporting research which it deems relevant to these functions.

Background to JNCC can be found on JNCC’s website at: https://jncc.gov.uk/about-jncc/

## Project Background

JNCC is a delivery partner for the Ocean Country Partnership Programme (OCPP), a UK government-led programme under the Blue Planet Programme. More information on the OCPP can be found here: https://www.gov.uk/government/publications/blue-planet-fund/ocean-country-partnership-programme-ocpp.

Through the OCPP we aim to support countries to strengthen marine science expertise, develop science-based policy and management tools and create educational resources for coastal communities. There are three main objectives for the OCPP:

- Marine Pollution: supporting countries to be equipped with the skills and expertise needed to tackle, reduce and mitigate marine pollution through the development of science led policy and improve our understanding of the impacts of pollution, as well as identifying and supporting effective responses, we will make sure that communities are better equipped to prevent and manage marine pollution. This will improve health and livelihoods.

- Sustainable Seafood: supporting the development of the skills and expertise needed to adopt sustainable seafood practices to reduce risks such as the spread of zoonotic diseases from unsustainable or unsafe activities and support trade in safe seafood. Assisting countries to crack down on illegal, unreported and unregulated fishing by supporting the development of better management, monitoring and enforcement capabilities.

- Marine Biodiversity: supporting countries to develop the skills and expertise needed to establish designated, well-managed and enforced marine protected areas to support healthy ecosystems with thriving biodiversity and fisheries that communities rely on for food and livelihoods. Achieving these objectives by strengthening marine science expertise, developing evidence-based policy and management tools, and creating educational resources for coastal communities.

Many protected, endangered and threatened (PET) species in Sri Lanka perform ecologically important roles within the marine environment (e.g. sharks, rays, marine mammals and marine turtles). As such, the presence and abundance of PET marine species are important indicators of marine ecosystem health. In addition to this, local coastal communities can benefit from the presence of PET species as important sources of income through sustainable ecotourism.

There is a need to increase awareness and address knowledge gaps related to the condition and distribution of these species in Sri Lanka, as well as to better understand the impact and nature of the threats to them. There are already multiple initiatives within the country to monitor and assess such species, but efforts to do this are not coordinated or widely known about/ accepted by key stakeholders and decision makers. By improving knowledge and understanding in these species, effective conservation and management measures may be developed, with benefits for the target species, local coastal communities and the wider marine environment. Building knowledge and capacity within communities, government agencies and non-governmental organisations on the need to protect PET mobile marine species will also build resilience to threats from pollution and climate change with strengthened governance, environmental knowledge, and management enforcement capacity.

## Project Aims

This contract focuses on increasing capacity within Sri Lanka to understand and therefore protect PET species in the marine environment. This may include, but is not limited to, species of sea turtles; marine mammals; sharks and rays; and seabirds. This work will contribute towards achieving and maintaining a healthy marine environment and build capacity of community-based management approaches for PET marine species.

This programme aims to:

- support and increase capacity on gathering reliable and robust evidence on the levels of PET marine species in Sri Lanka to inform baseline understanding of population health and extent.

- collate, co-ordinate and, where necessary, build upon existing PET marine species sightings, strandings and mortality data to strengthen the evidence base on the condition, distribution and threats to PET marine species in Sri Lankan waters. Support this data being used in condition assessments where relevant.

- increase key stakeholder (including government and local communities) awareness and understanding of the importance and value of maintaining healthy PET marine species populations to support their effective management.

- increase national monitoring, data collection and emergency response capacity through the establishment of a citizen science community network.

The aims of the programme will be met through the development and establishment of outputs listed in Section 4.

## Project Objectives

The project outputs will include:

Work Package 1 – Citizen science monitoring programme to collate and collect data on sightings, strandings and mortality of PET marine species.

  - Review existing citizen science monitoring data collection programmes for PET marine species in Sri Lanka and identify any overlaps or conflicts in data collection and gaps in species representation. Using existing monitoring protocols from the identified monitoring programmes, collate these with data requirements (e.g., key observations to be submitted for each programme – types of measurements, photographs etc.,) into consolidated PET marine species monitoring protocols. Where relevant, protocols should be split into ‘tiers’ e.g., some aimed at local communities who may have no prior knowledge of monitoring, some for specific purposes such as government departments.

  - Develop an action plan that outlines recommendations, key priorities and considerations for the creation of a citizen science data collection programme focused on the whale watching tourism industry. The contractor would be required to consider opportunities and approaches on how to raise awareness of the importance of Sri Lanka’s cetacean species amongst tourists, referencing existing management measures related to marine tourism, and encourage tourists and tour operators to contribute to data collection. Collaboration with the Sri Lanka Tourism Development Authority and tourism operators, particularly the whale watching industry, will be required to identify requirements for such a programme and the development of methodologies.

  - To compliment the consolidation and strengthening of this citizen science data collection, the contractor will also scope requirements for the development of a citizen science monitoring app that will encourage community engagement, increase awareness of marine PET species and build ownership of local marine assets that contribute to the livelihoods of coastal communities. Scoping will include user research to fully understand requirements for a citizen science app, including user stories to highlight preferences and points to avoid, to inform app development. This should be delivered as a scoping report. Note the app will not be developed under this contract.

Work package 2 – PET marine species awareness and education outreach programme.

  - Development, organisation and facilitation of local community workshops located in nine priority wildlife regions across Sri Lanka, to build capacity and raise awareness of PET marine species and provide training to enable local communities to input into the citizen science monitoring programme (work package 1). These workshops could be combined for ease of delivery if appropriate. Include estimated costs related to the delivery of workshops in your bid e.g., venue hire, travel and subsistence etc.

    - Workshops should focus on Sri Lanka’s seabirds, turtles and marine mammals. The contractor may subcontract experts to support the delivery of these. Please provide details and costs of potential subcontractors in your bid.

    - Workshop topics could include but are not limited to: species biology and ecology; related laws and regulations; threats; ongoing/ existing conservation and data collection methodologies (as appropriate); and strandings and mortality protocols.

    - Information to inform the scoping of a citizens science monitoring app (work package 1) could also be collected during these workshops.

    - Development of a report summarising the nine community workshops, key outputs, lessons learned, and monitoring, evaluation and learning (MEL) data to assess the impact of the workshops and feedback from attendees. The OCPP team will support the development of this MEL process.

  - Development and facilitation of PET marine species capacity building and identification workshops for key staff including Wildlife Rangers from the Department of Wildlife Conservation (DWC) and other relevant government organisations.

    - Workshop content should focus on identification skills for marine mammals, seabirds and turtles in Sri Lanka, basic data collection requirements for monitoring, strandings and mortality and provide an overview of the citizen science monitoring programme (work package 1 & 2) and national volunteer monitoring network (work package 3), raising awareness of ongoing relevant research and initiatives in PET marine species in Sri Lanka.

    - Training materials to be developed in Sinhala and Tamil and should include the development and delivery of a simple ID toolkit that could be used in the field.

    - Development of a report summarising the workshop, key outputs, lessons learned and MEL data to assess the impact of the workshop and feedback from attendees. The OCPP team will support the development of this MEL process.

  - Development and publication of a social media campaign targeting local communities, to raise awareness of PET mobile marine species in Sri Lanka; highlight existing educational materials and active projects undertaken by government and NGOs; and to promote citizen science monitoring opportunities, including short educational video’s on how to report sightings, strandings and mortalities.

Work package 3 – Development of a national volunteer monitoring network to support citizen science data collection for PET marine species and to provide support in the event of a marine related emergency response.

  - Work with Provincial Councils in nine wildlife priority regions to establish if and how Councils currently report sightings, strandings and mortality of mobile marine species. Information collected will inform work package 1.

  - Create regional voluntary Community Co-ordinator roles. The Community Co-ordinator would be responsible for co-ordinating volunteers in their region, including supporting training, health and safety, sharing of information and act as the point of contact between volunteers and government and non-governmental bodies, to respond to PET marine species-related emergencies including strandings or acute pollution events. The contractor will collaborate with the Provincial Councils and DWC to define the roles and responsibilities of the Community Co-ordinators.

    - Develop a road map to support the creation and longevity of the Community Co-ordinator network. The road map should outline agreed roles and responsibilities of all parties involved in the voluntary monitoring programme including how the Community Co-ordinator will integrate into existing structures; and recommendations to secure the future implementation of the network beyond the completion of this project.

  - Building upon the community workshops in work package 2, develop a volunteer programme that formally recognises trained individuals that have the knowledge and skills required to support the Community Co-ordinator and DWC in the monitoring and reporting of PET mobile marine species. The programme should:

  - Provide appropriate training to volunteers (work package 2).

  - Include volunteers from 9 wildlife priority regions as identified by DWC.

  - Provide appropriate documentation to outline volunteer requirements e.g., age, health and safety, responsibilities, key contact details, mandatory training etc.

  - Provide a formal certification to confirm individuals are trained and formally recognised as volunteers by DWC.

  - Include a volunteer register to record qualified volunteers and develop an appropriate communication method to maintain contact and share updates between the Community Co-ordinator, DWC and registered volunteers.

## Contractor Requirements

The successful contractor should:

- Have demonstrable expert knowledge of PET marine species (e.g., marine mammals, turtles, and sea birds) in Sri Lankan waters, including species ID and taxonomy.

- Be experienced in marine mobile species monitoring including monitoring design, data collection (both directly and via citizen science), analysis and quality assurance procedures.

- Be a confident communicator with experience of developing and delivering clear and accessible training and awareness programmes focused on the ecology and monitoring of marine wildlife to a variety of audiences both virtually (including use of social media) and in person.

- Have experience of successfully collaborating with Governments, NGOs, Universities and local communities, ideally in Sri Lanka.

- Have a good understanding, and ideally existing relationships, with stakeholder networks related to PET marine species in Sri Lanka and internationally.

- Be confident in translating written materials and verbal conversations between English, Tamil and Sinhala.

- Ideally, be based in Sri Lanka or have previous experience working there.

- Be willing to organise their own travel and subsistence related to the project (include estimated costs within your bid application).

## Potential Follow-On Work

Bidders should be aware that there is the potential for the successful bidder to be requested by JNCC to undertake additional work on this contract into the financial year 2025/26.

Please note however that the potential for additional work to be undertaken is subject to a continuing need, availability of funds and satisfactory contractor performance. For the avoidance of doubt, no guarantee can be given that you will be asked to undertake the potential additional work outlined within this Annex A document. Bidders are not asked to provide detailed project plans for these follow-on aspects at this stage.

## Product Specification

JNCC is committed to making its publicly available resources and documents accessible, in accordance with the Public Sector Bodies (Websites and Mobile Applications) (No. 2) Accessibility Regulations 2018.

Making material accessible means making sure it can be used by as many people as possible.  This includes those with:

- impaired vision

- motor difficulties

- cognitive impairments or learning disabilities

- deafness or impaired hearing

The outputs and material that JNCC publishes should be compliant with the Web Content Accessibility Guidelines version 2.1 AA standard.

## Timescale

Provisional dates for delivery of the contract outputs are set out below. Exact dates are to be agreed at the start-up meeting based on Contractor and JNCC staff availability.

| Output | Provisional Date |
| --- | --- |
| Start-up meeting (via video call) | 9th September 2024 |
| Proposed workplan provided by contractor | 16th September 2024 |
| Stakeholder start-up meetings (DWC, tourism industry, Provincial Councils) | 20th September 2024 |
| Finalised consolidated monitoring protocols (WP1) | 30th September 2024 |
| First draft of training workshop materials (WP2) | 18th October 2024 |
| First draft social media campaign strategy and content (WP2) | 4th November 2024 |
| Finalised training workshop materials (WP2) | 22nd November 2024 |
| First draft volunteer programme documentation (WP3) First draft Community Co-ordinator network road map (WP3) | 9th December 2024 |
| First draft whale watching citizen science action plan (WP1) | 16th December 2024 |
| Delivery of government and community workshops (WP2) Social media campaign (WP2) | 1st January - 14th February 2025 |
| First draft citizen science app scoping report (WP1) | 14th February 2025 |
| Delivery of final products | 3rd March 2025 |

## Health and Safety

The successful bidder is expected to follow appropriate Health and Safety Procedures including adhering to JNCC’ policy on safeguarding. For further information  https://jncc.gov.uk/about-jncc/corporate-information/safeguarding/ and to be able to undertake appropriate risk assessments, evidence of which should be supplied to JNCC.

Any incidents occurring within the contract period should be immediately reported to JNCC.

## Project Management

The successful Contractor shall nominate a project manager who shall be responsible for ensuring the project is completed satisfactorily and who shall be the main contact point for JNCC.

JNCC’s main contact points will be:

Name: Hannah Hood

Email: Hannah.hood@jncc.gov.uk

Telephone: +44 (0) 1224 083520

Name: Jamie Small

Email: Jamie.small@jncc.gov.uk

Telephone: +44 (0) 1733 259687

## Instructions for Bid Submission

The bid submission should include the following:

A brief summary of the bidder’s experience in relation to the requirements of this contract.

A proposed approach for achieving the objectives of the contract and delivering the detailed tasks identified within each objective.

A detailed project plan (including a Gantt chart) and an estimate of time required to achieve each objective.

Details of the Project Team including their roles and experience.

Overall quote for the contract (in GBP) should include:

  - Attending virtual start-up, interim and final meetings with JNCC project team.

  - Costs and time allocation should be clearly allocated to specific tasks under each work package within this contract/project, including all costs associated with workshop delivery (e.g., facility hire) and contractor’s travel and subsistence to undertake stakeholder workshops/stakeholder meetings. Note, if flights are required they should be economy or premium economy class only, with suitable justification for the use of premium economy.

  - Please refer to the contractors travel and subsistence rates document for all travel (these rates are analogous to the UK civil service rates).

  - If submitting a joint proposal bidders should clearly outline the lead contractor on their bid. Refer to PS4a Instructions to Tenderers email submission, 14. Group bids.

  - The contractor is to specify whether VAT at the prevailing rate would be applicable to this project and if so, provide their VAT registration number.

The following documentation:

  - If your company includes more than 5 employees, please provide copies of health and safety policy where available or a note regarding such items as lone working, emergency procedures and accident reporting;

  - Copies of current public and employer liability insurance certificates or equivalence which is the legal requirement in your jurisdiction;

  - Copies of any appropriate risk assessments; and

  - Copies of any environmental policies should you have them

In addition, note that the bid submission should provide sufficient information to allow assessment against the evaluation criteria outlined in Section 12.

JNCC has a responsibility to protect the people we work with, and who work for us, and we will continuously strive to prevent bullying, harassment, exploitation and abuse and child abuse from happening.

The OCPP takes a Gender Equality and Social Inclusion (GESI) approach across all elements of our programme to address unequal power relations and inequalities, reduce disparities and ensure equal rights, responsibilities, opportunities and respect for all individuals. The OCPP also takes all reasonable steps to safeguard the people we come into contact with (including staff and the communities in which programmes are delivered) from sexual exploitation, abuse and harassment (SEAH).  The OCPP team will work with the successful bidder to meet GESI and safeguarding expectations, including the collection of data to evaluate GESI under this project.

## Evaluation Criteria

JNCC is not bound to accept the lowest priced or any bid. Having the technical expertise and experience to complete the work to a high standard and being able to complete it within the timescale are of the essence for this contract.

The bid evaluation shall be undertaken by JNCC staff.

For information on how we handle personal data please see our Privacy Notice at https://jncc.gov.uk/about-jncc/corporate-information/privacy-statement/

Bids will be evaluated using the following criteria:

|  | EVALUATION CRITERIA | Maximum Score | Score |
| --- | --- | --- | --- |
| 1. Quality of Bid |  |  |  |
| 1 | Clarity and effectiveness of proposal, particularly training programme outline | 15 |  |
| 2 | Understanding of the requirements and adequacy of outputs | 15 |  |
| 3 | Identification and proposed solutions to potential risks/issues to the project which threaten success | 5 |  |
|  | Sub Total | 35 |  |
| 2. Details of Contractor |  |  |  |
| 4 | Relevant expertise and experience of species ID, taxonomy and undertaking monitoring of relevant PET mobile marine species in Sri Lanka | 20 |  |
| 5 | Experience developing and delivering accessible educational and awareness programmes related to PET mobile marine species for a range of stakeholders | 15 |  |
| 6 | Experience leading national-scale projects with multiple project partners, including community groups. Experience working with, and existing links with Sri Lankan stakeholders. | 10 |  |
|  | Sub Total | 45 |  |
| 3. Cost |  |  |  |
| 7 | Transparency and correctness of presentation | 10 |  |
| 8 | Fairness/reasonableness for the level of work and expertise required, including split of staff and allocated days of work | 10 |  |
|  | Sub Total | 20 |  |
| Total Score |  | 100 |  |

## Payment

PLEASE NOTE: All quotes and all payments must be based on British Pounds (£). If alternative currency payments are needed, please raise this at the earliest opportunity during the bid process so we can explore options.

Payment will be made on completion of the objectives following the submission of invoice(s) and based on the satisfactory undertaking of the contractual elements to the agreed standard of the JNCC Project Officer.

## Additional Requirements

All bidders are requested to carefully read the Terms and Conditions applying to this contract. Payment will only be made upon delivery of key outputs.

It is assumed that all costs associated with the production of figures, reproduction of photographs and the final report are accounted for within the rates/fees given.

The bidder is expected to supply all necessary equipment, software, licences, etc. to carry out the obligations required under the contract.

Any communications or social media statements to be released by the successful bidder on this work must be signed off by the OCPP team first. Reports, presentations and documents must use our branding and logo to be discussed with the project team.

## Procurement Timetable (which may be subject to change)

| Activity | Date |
| --- | --- |
| Publication of Contract Notice | 1 August 2024 |
| Last date for receipt of clarification questions | 19 August 2024 |
| Final submission date for bids | 26 August 2024 |
| Evaluation of bids | w/c 26 August 2024 |
| Post-tender negotiation/clarification and or presentation if required | w/e 30 August 2024 |
| Successful Bidder Notified & Contract award | w/c 2 September 2024 |
| Unsuccessful bidders notified | w/e 6 September 2024 |
| Start of project | 9 September 2024 |