## Sheet1
Trailing the Hidden Heritage Delivery Timetable
|  |  | 2017 | [8 empty] | 2018 | [11 empty] | 2019
|  |  | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May
Activity
S1 Events
12a Project Launch
12h Open Day
12i Heritage Open Day
12g Forest Discovery Day
12m Official Trail opening, celebration, and Project End
S2 Trail
Route Clearance
Trail Construction
Shelter Installation
Bench and Perch Installation
Interpretation Design
Interpretation Installation
Way Marking Installation
S3 Training workshops
Training in Archaeological skills
1a Caring for Earthwork Sites
1b Surveying Earthwork Sites
1c Downham Warren Lodge Site Investigations
1d Recording Site Results
1e Processing Finds
1f Monitoring Condition of Sites
Training in Historical Skills
2a Using Archival Resources
2b Using County HERs
2c Aerial Photographs and LIDAR
2d Reading a Historic Landscape
2e Discovering Warrening
Training in Natural Heritage Skills
3a Identifying Tree Species
3b Identifying Plants
3c Butterflies and Moths
3c Night Flying Moths and Bat workshop
3d Identifying Birds
3e Identifying Amphibians
3f Deer ID and Management Techniques
3g Tracking Skills
Training in Traditional Skills
4a Neolithic Flint Skills
4b Gun Flint Skills
4c Warrening Skills
4d Making a Warreners Smock
4e Living off the Land
Training in Visitor Management Skills
5a Leading Guided Walks
5b Organising Events for Heritage Projects
5c Meeting the Needs of Visitors with Additional Needs
5d Producing Interpretation
5e Giving Outreach Talks
5f Producing Learning Materials
S4 Activities
Archaeological Activities
6a Origins of Flint Mines
6b Bronze Age Burial Mounds
6c Downham Warren Lodge Site Investigation Report and Finds
6d Horseshoe Pit Survey
6e Old Track Survey
6f Discovering Flint Facing on Warren Banks
6g Plotting Estate Parkland features
6h 20th Century High Lodge
Natural Heritage Activities
7a Researching County Archives for Evidence of Species
7b Carry out Wildlife Surveys
7c Enhancing GC Newt Habitat
7d Enhancing SPA Habitat
Other Day schools
8a Climate Change and Forest Resilience
8b Photographing the Forest
8c Drawing and Painting in the Forest
S5 Learning Materials
Producing Formal Learning Materials
9a, 9b, 9c, 9d, Producing LM for Heritage features - Themed Days
9e Construction of Archaeological Investigation Pit
Producing Informal Learning Materials
9f, 9g, 9h, 9i Family and Children's Activities
S6 Interpretation Material
Producing Interpretation Material
10a, 10b, 10c, 10d, 10e Researching and Collation of Information for Interpretation
S7 Activities for Formal and Informal Learning
11a, 11b, 11c, 11d Formal Activities Schools and Adult Learners
11e, 11f, 11g, 11h, Informal Activities for Families and Children
S8 Events (other than those in S1)
12a, 12b, 12c, Presentation to Brandon TC, Thetford TC and AHM
12d General Outreach Presentations and Talks
12e Guided walks on Heritage Trail
12f Community Bus from Thetford and Brandon
12k Promotion Day for Regional Tourism Providers
S9 Project Administration
Recruitment
Appointment of Project Manager, Finance Manager and Civil Engineer
Meetings
Project Team Meetings
Reporting
Reports and Second Stage Payment
Monitoring and Evaluation
Final Monitoring and Evaluation inc. Final Claim
Access Audits
12l Access Audit of Site and Trail by Suffolk Coalition for the Disabled
Monitoring and Evaluation
Ongoing M&E for each Activity at Completion