## Sheet1
CLARIFICATION LOG
Tender: | 0036 Development of Health and Well-being Hub
Tender Reference: | 0036
Published Date:
Version number: | 6
Number | Clarification | Response | Reply date
1 | We are aware that the University has a framework in place, can you clarify that this opportunity is not being procured through the framework and if this is the case what is the reasoning for this being procured out with the framework? | The University does not have a suitable Framework in place and is therefore using this Open Procedure for the appointment of the necessary consultants to undertake the commission in question. | 2023-02-14
2 | The Scope of Services being tendered do not include for an NEC Project Manager, should we include for this service as part of our offering, or is there an incumbent organisation providing this service? | The role of Project Manager under NEC4, or its equivalent under other forms of Works Contract, is to be included within the Scope of Service for this commission. | 2023-02-16
3 | The pricing document makes allowance for the Tenderer to cost for Clerk of Works (CoW) services, but under the NEC FoC there is a named entity called the Supervisor who carries out much of the same services as the CoW - should we include for Supervisor services as part of our bid instead of CoW? | The role of Supervisor under NEC4, or its equivalent under other forms of Works Contract, is to be included within the Scope of Service for this commission. The employment of a Clerk of Works is in addition to the Supervisor role and the Price Schedule is to be completed accordingly. | 2023-02-16
4 | Regarding the requirement for the key parties to provide examples of similar project experience / technical ability can you clarify what you mean by Lead Consultant – is the organisation leading the bid / will be contracting with the client entity? | The Lead Consultant is the entity which the Client will enter into contract with. | 2023-02-16
5 | Also on the same subject, would it be possible for tenderers to provide details of experience / technical ability for projects that are virtually complete (i.e. PC within weeks), rather than post-Completion? | Projects which are not completed will not be assessed. For clarity, the date on the PC certifate, or equivalent, must be no later than the closing date for return of tenders for this commission | 2023-02-16
6 | We are bidding as a Lead Consultant and have Sub-Consultants (other organisations) to carry some of the other services. You state the other Sub-Consultants (other organisations) supporting us as Lead are required to complete the self-declaration in Part 1 and 2 of Volume 2. Are you asking for each organisation to also complete all sections contained with part 1 and 2 eg. Supplier information, grounds for mandatory exclusion and economic standing? | Yes. All organisations making up a Team must complete Parts 1 and 2. | 2023-02-17
7 | It is noted that within Appendix D of the tender ‘NEC4 Contract Conditions’ the Contract Data states Delay damages for completion of the whole of the service are set as £1,000 per day. Could the University of St Mark and St John clarify whether this is intended to be the case and if so how the Damages would be enforced? | The delay damages will be enforced in line with the terms of the contract | 2023-02-17
8 | The Price Schedule has lump sums against each activity stage. Do you require this as a whole team lump sum or would you like for us to add separate columns for other team disciplines which makes up the overall lump sum? | The only figures required are the total (lump sum) figures for each Stage. | 2023-02-17
9 | With respect to 3,500 character limit with spaces. Does this mean 3,500 character limit including spaces or spaces cane be on top? Also, are we able to increase the character limit please as the questions are very detailed for us to answer? | The limit is 3500 characters including spaces. Information provided beyond that limit will not be assessed | 2023-02-17
10 | With respect to 3,500 character limit with spaces. Are we permitted to include as many diagrams as we want to? Also, would you like separate CV’s as an appendix on top of the 3,500 character limit? | Diagrams are not permitted and if included, will not be assessed. Additional documents must not be sent and will not be assessed | 2023-02-17
11 | Access to view the Premises during the tender period | To minimise disruption to the tenants, bidders wishing to view the premises will be limited to 4 people, permitted a maximum of 1 hour inside the building and will not be permitted to enter occupied rooms | 2023-02-17
12 | The design deliverable identified in the Scope Of Service has been defined as follows: STAGE A - Initial Design and preparation of brief and concept design: STAGE B - Developed Outline Design, Detailed Design and tendering; STAGE C - Construction Contract; STAGE D - Commissioning and Handover | The end of Stage B aligns with the end of RIBA Stage 4. By completion of Stage B designs should be in a prescriptive format. Contractor design elements are to be kept to a minimum. | 2023-02-21
These deliverables do not align directly with the BSRIA BG6 deliverables for an MEP consultant, we are assuming that the MEP design at Stage B will be acceptable at RIBA 4i and the services contractor will be responsible for the RIBA 4iii & 5 stages duties.
13 | Please provide a copy of the Universities Net Carbon Zero and sustainability policy as we would like to understand the target defined as Zero Carbon. | Marjon Zero ¦ Plymouth Marjon University | 2023-02-21
14 | Your answer to your clarification 7 (clarification log v.05) for delay damages to the design team of £1000 per day will be enforced. Can you please clarify how this will be enforced without the availability of a detailed programme from yourselves and how delays will be evaluated? Also, what happens if the delays are caused by 3rd parties outside of our control and how will this be assessed? We have a number of team members pulling out of this tender because these damages are over and above any contract agreement seen before and insurers are not willing to accept this. | Any delays to the contract will be assessed in line with the terms of the contract, in particular clause 60.1, compensation events. A programme is to be provided by the appointed consultant, as per clause 31.1 | 2023-02-24
15 | Within your HWB consult tender schedule 1 Price FINAL, you state fees won’t be paid until satisfactory completion of the stated Activity at Stages A and B. This could potentially equate to 3/4 months per stage and fees will not be paid until the end of such time. This a large risk on the designers and under normal circumstances, fees are paid on a monthly basis against a %age completion of design/work. Can this please be considered for Stages A and B? | At the discretion of the University, interim payments may be made during Stages A and B. | 2023-02-24
16
Clarifications will be published against the Contract Notice on Find a Tender and Contracts Finder.
If interested in tendering for this project please ensure you add a "watch this notice" for alerts as from time to time additional information or clarifications may be published related to this tender.
It will be the responsibility of Bidders to ensure they are aware of all published clarifications and ensure that their bid has taken these into account.
In the event of any queries please contact: tenders@marjon.ac.uk