Change to Tender Submission Date

Following requests Cornwall Council has agreed to alter the return of tender information as detailed below. The change allows for Part B and Part C to be submitted at different dates. Please note that the clarifications period has been extended as well. Please also note that format for the submission of documents shall comply as Section 2.1 of the ITT as appropriate.

The extended date for tender return does not change any of the proposed contract dates.

Part B – Supplier Selection Criteria

Submit in accordance with the original ITT instructions by 3.00pm on 31st July 2015

Part C – Tender Return

The Commercial Offer and Quality Assessment are to be returned at the revised date in accordance with the ITT instructions by 3.00pm on Friday 14th August 2015.

2.2 Tender Timetable (changes highlighted)

It is the intention of the Council, that this procurement will follow a clear, structured and transparent process at all times and that all Tenderers will be treated equally.

The key dates for this procurement timetable are currently anticipated to be as follows:

| Timetable |  |
| --- | --- |
| Event | Date |
| Issue ITT | 23 June 2015 |
| Supplier event at King Edward Mine Please RSVP to Tamsin Daniel by Monday 6 July, 3pm: tamsin.daniel@cornwall.gov.uk | 9 July 2015, 14:00 |
| Deadline for receipt of clarifications (Part C only) | 24 July 2015 |
| Target date for responses to clarifications (Part C only) | 31 July 2015 |
| Deadline for return of Part B Supplier Selection Criteria | 31 July 2015 at 15:00 (3.00pm) |
| Deadline for return of Part C Tenders (Return Date) | 14 August 2015 at 15:00 (3.00pm) |
| Evaluation of Supplier Criteria (Part B) | 3 – 14 August 2015 |
| Evaluation of Tenders (Part C) | 17 – 28 August 2015 |
| Notification of Contract Award Decision | 28 August – 4 September 2015 |
| Confirm Contract Award | 4 September 2015 |
| Target Contract Commencement Date | 28 September 2015 |
| Issue Contract Award Notice | 30 September 2015 |

Tenderers should note that this is an indicative timetable only and may be subject to change. Any changes will be communicated to all Tenderers as soon as possible.