The SECCADS programme is a comprehensive business support programme tailored to meet the needs of the Creative, Cultural and Digital Sector.  The programme includes a number of different strands including:

- Engagement, initial diagnostics, on-going client management and signposting to support carried out by a network of local co-ordinators

- Specialist advice services provided by the University of Essex and by a range of business support organisations in different localities across the South East LEP area

- A business support grants programme

- A workshops and mentoring programme

Thurrock Council is seeking a provider who will deliver:

Summative Assessment to be undertaken between Nov 2019-July 2020 with a final approved report to be completed in September 2020 on behalf of SOUTH EAST CREATIVE CULTURAL AND DIGITAL SUPPORT (SECCADS), a project part funded by the European Regional Development Fund.

The summative assessment is required to provide insights into:

- project performance to enhance future implementation

- reliable evidence of the efficiency, effectiveness and value for money of the project

- insights into what and why interventions work (or not) and lessons for the future

It will also provide project level evidence which, when combined with national evidence of progress and impact, will result in stronger evidence of the overall impact and effectiveness of the ERDF operational programme across England. The evidence will also be particularly helpful for making the case for delivery approaches in the future or making the case for future funding.

The final outputs of this work will be a Summative Assessment that evaluates the SECCADS programme based on the outputs, outcomes and impacts laid out in the Summative Assessment Logic (see Appendix x) and meets the wider objectives, aims and approach outlined in the Summative Assessment Plan (see Appendix x). The successful contractor will be expected to work closely with the SECCADS project team to ensure that the data management, stakeholder contacts and approaches are agreed in an assessment methodology. A draft Summative Assessment plan must be prepared during August 2020 and a final approved version, in a format suitable for both online and print, available to the SECCADS project team no later than the 23rd September 2020. An executive summary, suitable for dissemination to a wide stakeholder base, must also be approved and available no later than the 23rd September. The contractor must ensure that the final invoice for this work is presented at the same time as the final approved documents are supplied.

There is no set approach to the methodology to be implemented. However, ERDF offer guidance and methods that should be considered to add value to national evidence. These can be found at

Summative Assessment Guidance   - April 2019:

https://assets.publishing.service.gov.uk/government/uploads/system/uploads/attachment_data/file/795499/ESIF-GN-1-033_ERDF_Summative_Assessment_Guidance_v3.pdf

Summative Assement Guidance, Appendices – April 2019:

https://assets.publishing.service.gov.uk/government/uploads/system/uploads/attachment_data/file/809976/ESIF-GN-1-034_ERDF_Summative_Assessment_Guidance_Appendices_v3__2_.pdf

The key performance indicators for this contract will be:

| Objective | Performance Measure | Target | Reporting Frequency |
| --- | --- | --- | --- |
| Methodology and project plan | Provide documentation to the Project Manager | 100% met | January 2020 |
| Approved Summative Assessment Exec Summary for publication | Provision of executive summary as a standalone document for publication to a wide range of public and private sector stakeholders. To be provided in a format that can be published online and printed (if required). Deadline for summary - latest 23.7.19 | 100% met | 23rd September 2020 latest |
| Final Summative Assessment report | Provide a final copy of the Summative Assessment Report, approved by the Thurrock project team, no later than the 23rd September 2020 | 100% met All documents provided | 23rd September 2020 latest |
| Final invoice must be sent to Thurrock Council no later than 23rd September 2020 | Invoice information correct ad presented on time | 100% met | 23rd September latest |

| TECHNICAL AND QUALITY QUESTIONS |  |  |  |
| --- | --- | --- | --- |
| Question | Bidder Response | Weighting (%) | Marks available |
| Using examples, provide your experience of ERDF project evaluation and summative assessment techniques Max 1000 words |  | 25 | 5 |
| Please outline your approach to the delivery of the summative assessment requirements outlined in the summative assessment plan, and how you will ensure you deliver on time. (Max 1000 words) |  | 20 | 5 |
| Please outline your knowledge of the CC&D sector and ERDF. State your approach to working with a wide range of CC&D stakeholders. (Max 500) words |  | 20 | 5 |
| Thurrock is committed to the implementation of the legislation introduced by the Public Services (Social Value) Act 2012. Please provide details of your proposal to deliver benefits to the communities you will be working in. (Max 150 words) |  | 5 | 5 |
| TOTAL |  | 70 | 20 |