## Schedule of Works
Project:
New Shotton Community Centre
Project 1442
Tender Schedule of Works
Date: | 2019-02-04
Revisions:
Notes:
To be read in conjunction with all other tender documents, drawings and schedules
All items to be priced against, do not use 'included elsewhere'
Item | Description | Unit | Total
Phase 1 - Construction of the New Community Centre
1 | Enabling Works
| Refer to drawing no. L(-1)102. | Note
1.1 | Erect & maintain 2no. advance warning footpath closure signs and temporary footpath diversion signs for the duration of the Works. | Item
1.2 | Carefully take down approx. 65m decorative metal railings (A) and set aside for client reuse. Tubular metal railings approx. 600mm high. | Item
1.3 | Remove approx. 20m metal railings around circular tarmac area (B) & dispose off site. | Item
1.4 | Carefully remove 2no. waste bins & set aside for client reuse. | Item
1.5 | Remove existing fencing around MUGA (C) and dispose off site. Grub up concrete foundations. | Item
1.6 | Excavate & remove tarmac area as hatched on drawing. | Item
1.7 | At the southern boundary, remove existing scrub shrubbery & all deleterious matter under boundary trees, including dilapidated former fence (D). | Item
1.8 | Remove & dispose of existing shrub planting (approx. 18m x 4.5m) adjacent existing car park (E). | Item
1.9 | Where tarmac removed, carefully remove kerbs and concrete bedding as well as gulleys. Existing redundant drains to be sealed. | Item
1.1 | Protection to existing trees as drawing L(-1)108. | Item
2 | Excavation & Reduced Levels
2.1 | Excavate to reduced levels & remove tarmac & hardcore from site. Set aside top soil for reuse prior to reseeding. | Item
2.2 | Excavate reduced levels for trenchfill foundations & new drainage. | Item
2.3 | Excavate trenches for incoming utilities as drawing no. L(-1)104. | Item
2.4 | Spray reduced formation under building with herbicide before construction of suspended ground floor. | Item
2.5 | Allow Provisional Sum for excavation & disposal of potentially combustible ashy made ground referred to in the Site Investigation. Allow for any testing required. | Item
3 | Foundations, Sub-Structures & Ground Floor Slab
3.1 | Foundations to be trenchfill 1800mm deep x 900mm wide for loadbearing walls and 1800mm x 600mm wide for internal walls. Concrete to be RC35 with minimum cement content 320kg/m3 with w/c ratio 0.5. | Item
3.2 | Blockwork dwarf walls on the trenchfill support block and beam floor, layout as drawing C/002 . Main Hall to be Hanson TJ1 with T008 beams, Remainder of building to be Hanson TJ3 with T008 beams. | Item
3.3 | Voids below block & beam floor to be ventilated with Rytons Periscope Underfloor Ventilators with Rytons Multifix Air Bricks, or similar approved. Colour to match brickwork, at maximum 2.000m centres to perimeter. Internal block dwarf walls to have regular voids to allow cross ventilation. | Item
3.4 | Allow for supplying & installing 5no uPVC ducts for utilities services into building. | Item
3.5 | Imported clean hardcore to make up levels. | Item
3.6 | Allow for 4no drain connections through block walls & top of trenchfill foundations connecting to MH01. | Item
3.7 | Construct 140mm high blockwork under timber frame wall plates, either 140mm or 90mm wide. | Item
4 | Drainage
4.1 | Existing foul and surface water drainage information is shown on Topographical Survey drawing & existing Site Plan. | Note
4.2 | New foul drainage to be 100mm dia uPVC pipework as shown on drawing L(-1)105, including manhole schedule. | Item
4.3 | Foul drainage under block & beam floor to be 100mm dia uPVC suspended hard under beams. Allow for sleeving or lintols over penetrations of external block walls on top of trenchfill. | Item
4.4 | New foul drainage connected to existing 150mm dia combined sewer in grassed area to south of existing car park with new manhole F02. Invert level to be checked to confirm drainage plan. | Item
4.5 | New surface water drainage from building to be 100dia uPVC as shown on drainage drawing L(-1)105. | Item
4.6 | Drainage to existing tarmac entrance road & parking areas as existing, with gullies & drain runs, cleaned out and cleared of tree roots cut as shown on CCTV survey. | Item
4.7 | New surface water drainage from building and new car park to be connected into existing 225mm dia drain at new manhole S09, with adjacent offline attenuation tank, 8m x 5m x 0.8m, all as drawings L(-1)105, 106 & 107. | Item
4.8 | New surface water drainage to new car park to be priced separately as part of Phase 2 works. | Note
5 | Timber Frame
5.1 | Design, manufacture & installation of timber frame including dual pitched roof & all bracing & structural calculations | Item
5.2 | Frame available from: Swift Timber Homes Ltd, Unit 2, Catkin Way, Greenfields Industrial Estate Bishop Auckland DL14 9TF tel. 01388 835222 or equal approved | Note
5.3 | Timber framing for external walls, gables & the internal Hall wall to be 140x38 C16 CLS timbers. Internal non-loadbearing walls to be 38x89 C16 CLS timbers. External wall to have 9mm OSB 3 board with reflective breather membrane. | Note
5.4 | Over Circulation allow for trimming rafters for 2no. Velux Rooflights, PK06, 940x1180mm. | Note
5.5 | Allow for 3no. CK02 Velux Rooflights in Hall roof fit between trusses, 550x780mm. | Note
5.6 | Allow for additional roof loading for approximately 16no. Solar PV panels, as drawing L(27)01. | Note
5.7 | For roof loadings allow for Marley Eternit Birkdale fibre cement tiles. | Note
5.8 | Roof construction is a combination of trussed rafters, and specialist trusses over the Hall (17). Lobby (01), Circulation areas (02) & (03) to be sw rafters on exposed purlins as shown on drawings. | Note
5.9 | Allow for trimming for 6no ceiling hatches, approx. 600mm x 550mm. | Note
5.1 | Supply & fit floor joists over rooms 13, 15 & 16 to be 150mm x 50mm @ 400mm centres, with 1800mm x 1800mm decking adjacent to hatch & fan to be 12mm plywood. | Item
6 | Roof Finish
6.1 | Marley Eternit Birkdale fibre cement slates, blue black, on 50x32 treated battens on breatheable membrane on 150x50 sw rafters at 600 centres or truss at 600 centres. | Item
6.2 | Marley dry ridge, valleys & verges. | Item
6.3 | Allow for trimming rafters & ceiling joists for rooflights & hatches. | Item
6.4 | Warm roof over Seating Area (03), Circulation (02) & Lobby (01) to have 100 Kingspan Insulation between 150x50 rafters, with 32.5mm insulated plasterboard to soffit & purlins exposed. | Note
6.5 | Hall 01, Office 07, Store 02 & IT Room 03 to have warm roof as item 5.3 from eaves up to horizontal tie beam. Above tie beam lay 300mm insulation quilt on 12mm plasterboard. Vertical sections of wall panels to be insulated to maintain warm roof. | Note
6.6 | Cold roofs in remaining trussed rafter areas to have 300mm quilt insulation & ventilated eaves. | Note
6.7 | Black uPVC Deep Flow gutters and downpipes on marine grade fascia & soffit, painted black. | Item
6.8 | Install 2no vent tiles over Kitchen for extracts. | Item
7 | External Walls
| Facing bricks to be Ibstock Smooth Buff and Ibstock Brunswick Tryfan Grey A0642A with light bucket handle joint in natural mortar. | Item
7.1 | External brickwork walls to be banded as shown on elevations. | Note
7.2 | Bricks laid stretcher bond and tied back to timber frame with Ancon Staifix STF6 ties, 127mm long fixed with 4x30mm stainless steel spax screws. | Item
7.3 | Timber Frame lintols over external windows & doors to be pre-galvanised mild steel, powder coated black, Catnic CTF5 or equal approved. | Item
7.4 | On the Hall 01 use I.C. 1.1 Overhanging Angled Sill bricks as soldier course between the brickwork & Coloured Render. Bricks 140mm high, 152mm deep (with 25mm overhang to front) and 65mm wide. Joints to be flush pointed. Also at external corners use IC5 Overhanging Angled Sill External Return. | Item
7.5 | At all door & window openings in external walls, fit 50mm Kingspan Thermabate Cavity Closers. | Item
7.6 | CBS cavity wall weep vents at 900 centres in wall at floor level & 450 centres over lintols (minimum 2 per lintol). | Item
7.7 | Allow for 2no. vertical movement joints in brickwork as shown on elevations. | Item
7.8 | Coloured render at high level in Hall external walls to be 5mm render in 2 coats over glass fibre mesh on 12mm carrier board on 80x35mm horizontal treated sw battens on 25x25 vertical treated sw battens with ventilation cavity, to be K Rend Scraped Texture or equal approved. | Item
7.9 | Form openings for 4no extract grills as detailed in Mechanical Services Builders Work Schedule. | Item
8 | Aluminium Windows & External Doors
8.1 | External doors as Drawing C(31)01 & Schedule S01. | Item
8.2 | Aluminium double glazed windows as Drawing C(31)02 & Schedule S02. | Item
8.3 | 3no. rooflights over Hall to be Velux CK02, 550x780mm, Integra electronically operated, with integral blinds. White polyurethane internal finish & standard laminated safety glass. | Item
8.4 | 2no. rooflights over Seated Area to be Velux PK06, 940x1180mm, Integra electronically operated. | Item
8.5 | Allow for insulated aluminium panels to match as shown. | Note
8.6 | Include for manifestations to low level glazing as shown. | Note
8.7 | Ironmongery to external doors to match internal. | Note
9 | Internal Door Sets & Ironmongery
9.1 | Internal doors as Drawing C(32)01 & Schedule S01 by Lloyd Worrall or equal approved, refer to Schedule LWTD2154.01. | Item
9.2 | Allow for fitting of door sets. | Item
9.3 | Include for manifestations to glazed screens as shown. | Note
10 | Floor Screed
10.1 | 65mm sand cement screed on separating layer on Kingspan Kooltherm K3 insulation board, with underfloor heating pipework laid in screed. | Item
10.2 | Screed thickness in individual rooms adjusted to take account of floor finishes to maintain FFL. | Note
10.3 | Include 25mm vertical insulation board at perimeter screed edge. | Item
10.4 | Include for movement joints in screed as required by BS8204.1:2000. | Item
10.5 | Self levelling screed as required under vinyl flooring. | Item
11 | Internal Walls
11.1 | Internal face of external timber frame to be 12.5mm Duplex foil backed plasterboard & skim unless stated otherwise. | Item
11.2 | Internal walls generally as 10.1, but moisture resistant 12.5mm board & skim to Kitchen (18), Male WC (10), Female WC (12) & Accessible WC (09), & Cleaner's Cupboard (11). | Item
11.3 | Double boarding one side of walls between Office (15) & Hall (17), Multipurpose Room (04) and between Office (08) & Toilets (09) & (10) with Acoustic Quilt (item 13.3). | Item
11.4 | Internal walls to Circulation (02), Seating Area (03), Multi Purpose Rooms (04) & (05), Hall (17) to be 15mm Duraline & skim. | Item
11.5 | 12.5mm painted plywood to Stores (07), (16) & (18a). | Item
11.6 | Internal stud walls to Plant Room (06) to be 15mm Fireline & skim. | Item
12 | Ceilings
12.1 | Ceilings to underside of trussed rafters to be 12.5mm Duplex Wallboard & skim to Circulation (02) (Part only), (03), Store (07), Office (08) & Reception (14). | Item
12.2 | Ceilings to underside of trussed rafters to be moisture resistant 12.5mm board & skim to Accessible WC (09), Male WC (10), Cleaners Cupboard (11), Female WC (12) & Kitchen (18). | Item
12.3 | 32.5mm insulated plasterboard & skim to underside of rafters in Circulation (02) (Part only), Seating Area (03) & sloping sides of Hall (17) roof. | Item
12.4 | 600x600mm tegular suspended ceilings in Lobby (01), Multi Purpose Rooms (04) & (05), to be Armstrong Perla OP, Class A acoustics or equal approved. | Item
12.5 | Ceiling to Plant Room (06) to be Fireline & skim. | Item
13 | Insulation
13.1 | Floor - 75mm Kingspan Kooltherm K3 Insulation boards, with 25mm insulation vertically at perimeter. | Item
13.2 | External Timber Frame - 100mm Kingspan K112 Framing Board, tightly fitted between studs. Same insulation fitted between studs above ceiling level where warm roofs are next to cold roofs. | Item
13.3 | Rockwool RW5 75mm acoustic quilt fitted between studs as item 10.3. | Item
13.4 | 300mm mineral fibre quilt laid above plasterboard ceilings, and on plasterboard to underside of trussed rafters. | Item
13.5 | The building envelope (external walls & roof) needs to be airtight as possible in order to achieve an acceptable air pressure test (item 17.3). All joints & junctions of materials not tightly fitted to be filled with expanding foam insulation. | Item
14 | Joinery, Fixtures & Fittings
14.1 | Window cill boards 25mm MDF rounded front edge. | Item
14.2 | Skirtings to be MDF, 144x18 Ogee section moulded & primed. | Item
14.3 | Architraves MDF, 69x18 Ogee, moulded & primed. | Item
14.4 | Door linings & stops primed from supplier ready for painting. | Item
14.5 | Boxing out of service pipes to be MDF on sw framing. | Item
14.6 | In Hall (17), Circulation (02), Seated Area (03), Multi Purpose Rooms (04) & (05), fit timber dado rail of 2no. 69x18 architrave sections, 830mm from FFL to top of dado. | Item
14.7 | Above dado rail allow for 6 sheets of 2440x1200x9.5 Sundeala K pinboard as notice boards, colour wheat. | Item
14.8 | Allow for 6no. ceiling hatches, 600x550 in Circulation (02), Store (07), Reception (14), Hall Store (16) & Hall (17), for cold roof access. | Item
14.9 | In Reception (14), construct 2no glazed hatches with 100mm x 100mm corner post, 1100mmhigh & 1200mm wide each, comprising sliding toughened glass screen on rollers with window lock. | Item
14.1 | In Office (08), supply & fit Commercial Anti Arson Post Box, size 320 x 650 x 200mm, available from Simply Postboxes (tel. 0800 0988777) | Item
14.11 | Supply & fit kitchen Units in Kitchen (18), to be Howdens Greenwich Ivory with Howdens Grey Oak Effect 38mm square edge worktop, including all upstands, plinths & end panels. Handles to be chrome effect square bar HKB. | Item
14.12 | Supply & fit 2no. steel roller shutters, manually operated with lock, RAL finished, approx. 900x1200mm, at hatches in Kitchen (18). | Item
14.13 | In Toilets (10) & (12) over vanity units fit bulkhead 500mm down from ceiling & 300mm deep, to be 50 x 50mm sw framing & plasterboard & skim finish. | Item
14.14 | In Male & Female Toilets (10 & (12) supply & fit vanity Units, Toilet Cubicles & IPS system, laminate finish, including all fittings & ironmongery, to detail on Drawing L(22)04 & 05. | Item
14.15 | In Toilets (10) & (12) supply & fit mirrors above vanity units approx 1300mm high x 1500mm wide. | Item
14.16 | In Cleaners (11) fit 2no shelves size 800x300 above Belfast sink, white melamine on strut uprights & brackets. | Item
14.17 | Supply & fit mirror 800x400 over whb in Accessible Toilet (09). | Item
14.18 | Supply & fit wall mounted baby change unit on wall in Accessible Toilet (09), BCU1 from Washware Essentials (tel. 01275 390603). | Item
14.19 | In roof space fit fire blanket at compartment wall between Hall (12) & Kitchen (18), Reception (14) & part IT Room (13). | Item
14.2 | Fit cupboards around 3no. manifold units in Store (07), Cleaners (11) & Store (16) with magnetic catches. | Item
14.21 | External signage, 300mm high upper case Helvetica medium or similar, individual Perspex letters, 6mm thick, secret fixed to render at high level on East elevation. | Item
14.22 | At Hall (17), form recess for bowls mat storage, approx. 4100mm wide x 800mm deep x 700mm high. 5no removable front panels approx. 800mm wide x 700mm high of 12mm MDF, sitting in channel 15mm deep flush with oak floor, and with magnetic catch at both sides at top. 2no small D handles to each panel to facilitate easy lifting out. Length of skirting fixed to each panel. | Item
15 | Sanitary Ware
15.1 | Include for all wastes, traps etc & connections to drainage. | Item
15.2 | In Cleaners (11), supply & fit Belfast sink, low level on legs with bib taps. | Item
15.3 | In Kitchen (18), supply & fit small s/s whb with taps. | Item
15.4 | In Male & Female Toilets (10) & (12), supply and fit vanity units each approx. 1600mm x 270mm deep with 4no. Semi counter top wash hand basins, Armitage Shanks Sandringham 21, 500mm, 2no. Tapholes, overflow & chainstay hole with Sandringham pillar taps or equal approved. Thermostats on hot water to all basins covered in Mechanical Specification. | Item
15.5 | In Male & Female Toilets (10) & (12), supply and fit 5no. Back to wall wc's, Armitage Shanks Concept Compact, with Conceala 2 cisterns, slow close seat & cover, colour bright blue, & dual flush plate. | Item
15.6 | In male Toilet (10), supply & fit 3no. Armitage Shanks Contour urinals, concealed in IPS system, with Conceala auto syphon and petcock. | Item
15.7 | In Accessible Toilet (09) supply & fit full Doc. M Pack including bright blue toilet seat & wall mounted grab rails. | Item
15.8 | Supply & fit full height IPS system behind WC's & urinals. | Item
15.9 | Fit isolation valves to all sanitary appliances. | Item
15.1 | Supply & fit cold water tap in Plant Room (06). | Item
16 | Finishes
16.1 | Location of finishes as Drawing L(-2)101. | Note
16.2 | Flooring: F1 - Howdens Prefinished 3 strip oak flooring, 14mm thick on 2mm matt suitable for underfloor heating. Include for metal cover strips at doorways. | Item
16.3 | F2 - Heckmondwike Battleship Barrier Matting, colour Pebble. | Item
16.4 | F3 - Altro Suprema II 2mm vinyl safety flooring with coved skirting, welded. | Item
16.5 | F4 - Carpet tiles, CFS Illusion. | Item
16.6 | F5 - Grey floor paint to screed. | Item
16.7 | Walls: W1 - 3 coats emulsion on plaster. | Item
16.8 | W2 - 200x100 glazed ceramic tiling, laid horizontally as splashbacks & behind kitchen units, H&R Johnson or equal approved. | Item
16.9 | Ceilings: C1 - 3 coats emulsion on plaster. | Item
16.1 | C2 - 600x600 Armstrong Perla OP, tegular, Class A acoustics, in white suspension system. | Item
16.11 | Woodwork - cills, skirtings, dado, door frames, architraves etc - pre-primed, 1 coat undercoat, 1 coat eggshell. Bare wood to have knotting & primer before undercoat & egg shell. | Item
16.12 | Plywood walls in Stores to have 2 coats emulsion. | Item
17 | External Works & Landscaping
17.1 | At existing turning area adjacent to tarmac parking bays, install new raised half battered kerbs and drop kerbs and relay tarmac to new levels. | Item
17.2 | Break out existing kerbs & lay new half battered kerbs & tarmac to new disabled parking bays; 300mm type 1 sub base, 60mm binder course and 30mm surface course. | Item
17.3 | White line marking to existing tarmac parking area, and also line marking to new disabled parking bays. | Item
17.4 | Construct speed bump where footpath crosses the tarmac road, all in Priora concrete blocks with brindle colour to the slopes and charcoal to the footpath. | Item
17.5 | New footpaths in front of building to be tarmac with concrete pin kerbs edging; 20mm wearing course on 40mm base course on 100mm compacted hardcore. | Item
17.6 | New tarmac footpath created with concrete pin kerb edging to north of building connecting to existing tarmac footpaths; 20mm wearing course on 40mm base course on 100mm compacted hardcore. | Item
17.7 | Security fence surround to garden area to west of building to be 2400mm high Euroguard Regular fencing, with 1200mm wide gate with push pad, detail to prevent opening from outside. | Item
17.8 | Security fence surround to Heat Pumps & Bin Store to be 2400mm high Euroguard Regular fencing, with 1200mm wide lockable gate. | Item
17.9 | Paving flags to external terrace, strip around building and service yard area to be Marshalls Buff 600x600mm paving slabs on sand/cement bed on 100mm compacted hardcore. | Item
17.1 | Refit 2no. waste bins, location to be agreed. | Item
17.11 | Supply & install 2no. Sheffield Cycle Hoops, colour black, 715mm wide & 800mm high, with 800mm between hoops. | Item
17.12 | Trees, shrubs, ground cover & climbers including preparation of topsoil beds, fertiliser, staking & aftercare as drawing L(92)01. | Item
17.13 | Grass seeding on new topsoil & prepared ground as L(92)01, as well as making good any damaged areas. | Item
18 | Mechanical Engineering Services
18.1 | Total carried forward from Mechanical Engineering Services Tender Summary Sheet. | Item
18.2 | Builders work associated with Mechanical Engineering Services. | Item
18.3 | Undertake airtightness testing in accordance with Part L of the Building regulations. | Item
19 | Electrical Engineering Services
19.1 | Total carried forward from Electrical Engineering Services Tender Summary Sheet. | Item
19.2 | Builders work associated with Electrical Engineering Services. | Item
19.3 | Excavate trench for power cables to lighting bollards and car park lighting columns, approx 600mm wide x 700mm deep x 110m long. Cover top & bottom with sand/pea gravel and backfill with graded material & reinstate. | Item
19.4 | Provide 4no concrete bases for bollard lighting, 300mm wide x 300mm long x 300mm deep, cast in base and flange plate to accept bollard. | Item
19.5 | Provide 3no concrete bases for car park lighting, 800mm wide x 800mm long x 1000mm deep, or as recommended by manufacturer | Item
19.6 | Supply & install 4.8kW integrated solar PV panel system, 2 rows of 8no panels, all black Viridian Clearline Fusion System by A.R. Power or equal approved. | Item
19.7 | Provisional Sum for Audio and Stage Lighting in the Hall. | SUM | 2000
20 | Utility Connections
20.1 | Electric, Water & Telecoms Connection Costs. | SUM | 10000
20.2 | Allow for liaison and coordination with the utility companies. | Item
20.3 | Provide a lay electricity cable and BT Openreach ducts in trench from junction with Bridge Road as drawing L(-1)104 including for draw pits, hand excavation around trees and all backfill & reinstatement). | Item
20.4 | Hand excavate to locate existing water supply, excavate, lay new water supply to the new community centre, backfill & reinstate as drawing L(-1)104. | Item
21 | Phase 2 - Asbestos Removal, Demolition & New Car Park
21.1 | Carry out pre-demolition asbestos survey of the existing community centre. | Item
21.2 | Isolate & disconnect existing services, liaising with the utility companies. | Item
21.3 | Following survey, obtain 3 quotes and arrange for the removal of any asbestos containing materials in the existing community centre. Provisional Sum. | SUM | 10000
21.4 | Demolish existing community centre including slab , sub base, walls & foundations, removing all off site. | Item
21.5 | Protect against damage to adjacent tarmac, paths & soft landscaping & make good on completion. | Item
21.6 | Drainage to east of building to be grubbed up & sealed at MH7. | Item
21.7 | Protect existing drainage to south of existing building. | Item
21.8 | Drainage under new car park to be perforated pipe as shown on drawing L(-1)105 with details on L(-1)106 & 107, connecting into S09 via a silt trap. | Item
21.9 | New car park to have half battered concrete kerbs, and to be Marshalls Priora Pencil Edge Permeable paving 200x100x80, colour brindle, with car parking lines in broken colour charcoal, laid on a 50mm laying course and 200mm sub base on MG15 Geogrid laid over sub grade. | Item
21.1 | Following demolition, infill matching pin kerbs to tarmac path to north of building. | Item
21.11 | Neatly cut existing tarmac path to front of original building, lay pin kerb and make good tarmac. | Item
21 | Preliminaries
21.1 | Phase 1 - Construction of new Community Centre. | Item
21.2 | Phase 2 - Asbestos removal, demolition & new car park. | Item
| TOTAL |  | 22000