## Cover
Appendix A2: ASC PMF Scoring Guidance
Asset Support Contract Performance Management Framework
Scoring Guidance
Version 1.1
May 2012

## Guidance
Goal Ref | HA Goal | Lever Ref | Lever | Old MAC Ref | NEW ASC Ref | Method of scoring | MST Area of Measure | Former API | CEM | Centrally scored? | AMOR Ref | Aspect | Aspect Evidence / Measures Scoring of performance should include consideration of the following typical evidence / measures | GREEN | AMBER | RED
1 | WE PROVIDE A SERVICE THAT OUR CUSTOMERS TRUST | 1.1 | CUSTOMERS ARE SATISFIED | - | 1.1a | CP | Service | API 03 |  | Y |  | Queries and complaints are resolved promptly and with due courtesy | Demonstrate - With respect to queries or complaints, the Provider provides a written reply within 10 working days of the relevant query or complaint being received Measure - % complaints queries or complaints replied to in writing within 10 working days | >=100% responded to within 10 days | >=95% responded to within 10 days | <95% responded to within 10 days
1 | WE PROVIDE A SERVICE THAT OUR CUSTOMERS TRUST | 1.2 | INFORMATION ON OCCUPANCIES IS AVAILABLE | 1.1.1a | 1.2a | CH | Service |  | CEM 02 | Y |  | Operate SRW System | Demonstrate - KPIs 1,2 and 3A, as reported in the monthly performance report, all have Green scores Evidence - SRW outputs (available from HA data) | KPI 1, 2 and 3A have all been scored Green for the month. | For KPI 1, 2 and 3A, at least one Amber score was achieved for the month | For KPI 1, 2 and 3A, at least one Red score was achieved for the month
1 | WE PROVIDE A SERVICE THAT OUR CUSTOMERS TRUST | 1.3 | MINIMISE ADVERSE IMPACT ON ROAD USERS | - | 1.3a | CP | Service |  |  | Y | Part 2 Outcome 3 | Occupancies are managed | Demonstrate - Occupancies are managed with no unacceptable additional delays Evidence - Provider records Per route - unacceptable additional delay M if >15 mins A if > 10 mins or If total delay > 30 mins | 0 Occupancies resulted in unacceptable additional delays | <=2 Occupancies resulted in unacceptable additional delays | >2 Occupancies resulted in unacceptable additional delays
1 | WE PROVIDE A SERVICE THAT OUR CUSTOMERS TRUST | 1.3 | MINIMISE ADVERSE IMPACT ON ROAD USERS | - | 1.3b | CP | Service |  |  | Y | Part 2 Deliverable 9 | Minimise the effect of Activities that adversely impact on road users | Demonstrate - Minimise the effect of Activities that adversely impact on road users so as not to to cause any unacceptable additional delays Evidence - Provider records Per route - unacceptable additional delay M if >15 mins A if > 10 mins or If total delay > 30 mins | 0 Activities resulted in unacceptable additional delays | <=2 Activities resulted in unacceptable additional delays | >2 Activities resulted in unacceptable additional delays
1 | WE PROVIDE A SERVICE THAT OUR CUSTOMERS TRUST | 1.4 | INCIDENTS ARE MANAGED TO MINIMISE DISRUPTION | 1.1.2a | 1.4a | O | Service | API 01 | CEM 01 | Y | Part 3 Table 3.1 | Incidents are cleared rapidly | Demonstrate - Incidents are cleared rapidly: 100% compliance with AMOR Table 3.1 Performance Metrics 1, 2 and 3 Evidence - Incident management records and/or Provider-initiated Operational Data | 100% compliance with AMOR Table 3.1 Performance Metrics 1, 2 and 3 since last PMF review | <100% and >= 90% compliance with AMOR Table 3.1 Performance Metrics 1, 2 and 3 since last PMF review | <90% compliance with AMOR Table 3.1 Performance Metrics 1, 2 or 3 since last PMF review
2 | WE SET THE STANDARD FOR DELIVERY | 2.1 | THE RIGHT PEOPLE, PROCESSES AND SYSTEMS ARE IN PLACE | 2.1.1a | 2.1a | CP | Right First Time |  | CEM 03 | Y |  | QMS performance | QMPs - Quality Management Points accrue for a range of QMS failures, whether arising from an audit by the Provider, the Service Manager or the relevant certification body Demonstrate - Level of performance for the Provider's QMS. Evidence - Quality Management Points (Contract Data Section 4.1) | Sum of Quality Management Points did not exceed 25 at any time in the last rolling three months | Sum of Quality Management Points exceeded 25 at any time in the last rolling three months and A quality warning notice was not issued or in effect at any time in the last rolling three months | A quality warning notice was issued or in effect at any time over the last rolling three months
2 | WE SET THE STANDARD FOR DELIVERY | 2.1 | THE RIGHT PEOPLE, PROCESSES AND SYSTEMS ARE IN PLACE | 2.1.1b | 2.1b | CP | Right First Time |  |  | Y |  | Non conformities are resolved | Demonstrate - Non conformities are identified, clear and achievable corrective action plans are in place, and successfully implemented - All non conformities recorded in a register / database - Appropriate corrective action plans produced for each non-conformity - Action Plans are successfully implemented Evidence - Non conformity register / database - Corrective Action Plans - Quality Management Points relating to non-conformities rows 3 to 7 (Contract Data Section 4.1) | In relation to rows 3 to 7 of the Contract Data Section 4.1: Sum of Quality Management Points did not exceed 15 at any time in the last rolling three months | In relation to rows 3 to 7 of the Contract Data Section 4.1: Sum of Quality Management Points did not exceed 25 at any time in the last rolling three months | In relation to rows 3 to 7 of the Contract Data Section 4.1: Sum of Quality Management Points exceeded 25 at any time in the last rolling three months
2 | WE SET THE STANDARD FOR DELIVERY | 2.1 | THE RIGHT PEOPLE, PROCESSES AND SYSTEMS ARE IN PLACE | 2.2.1b 2.2.1c | 2.1c | ES | Right First Time |  |  |  |  | Invoices provided on time and to the required accuracy | Demonstrate - Provider's invoices calculated and submitted in accordance with the requirements of the Contract - Invoices are a true and accurate record of services provided and substantiation is included, such that no corrections are required including those related to miscodings - Invoices submitted on or before the invoice date - Invoice separates Lump Sum and other activities Evidence - Invoices - Substantiation - Correspondence Note - Due to the timing of invoices, this Aspect will relate to invoices for the prior month. For example, when scoring April's performance by WD7 in May, performance against March's invoices will be assessed. | 100% of invoices submitted on time and 100% of invoices are valid and substantiated such that no corrections are required | At least 50% of invoices submitted on time and At least 50% of invoices are valid and substantiated such that no corrections are required | Less than 50% of invoices submitted on time or Less than 50% of invoices are valid and substantiated such that no corrections are required
2 | WE SET THE STANDARD FOR DELIVERY | 2.1 | THE RIGHT PEOPLE, PROCESSES AND SYSTEMS ARE IN PLACE | 2.2.1b 2.2.1c | 2.1d | ES | Right First Time |  |  |  |  | Cost Capture data provided on time and to the required accuracy | Demonstrate - Timely submission of Annex 5 PWC reports according to deadlines set - PWC report submitted on the last working day of the month - Costs reported one month after the month in which they are incurred - Adherence to PWC reporting template - Adherence to PWC reporting guidelines - Appropriate allocation of costs to relevent activities Evidence - Submission of PWC report by Service Provider by the last day of the month to the HA QS Commercial Team - Screenshots of emails sent - Correspondence from QS team re issues with quality/accuracy Note - This Aspect should be scored by agreement between the provider and the RCPT. The AMO reserves the right to moderate scores if centrally the QS Team informs them of non-compliance. | Annex 5 reports submitted on time and No issues with accuracy | Reports submitted up to two days late or Minor issues with accuracy | Reports submitted more than two days late or Major issues with accuracy
2 | WE SET THE STANDARD FOR DELIVERY | 2.1 | THE RIGHT PEOPLE, PROCESSES AND SYSTEMS ARE IN PLACE | 2.2.1b 2.2.1c | 2.1e | ES | Right First Time |  |  |  |  | Project Cost Control forms provided on time and to the required accuracy | Demonstrate - Project Cost Control forms provided on time and to the required accuracy Evidence - Submission of Project Cost Control forms | Forms submitted on time and No issues with accuracy | Forms submitted up to two days late or Minor issues with accuracy | Forms submitted more than two days late or Major issues with accuracy
2 | WE SET THE STANDARD FOR DELIVERY | 2.1 | THE RIGHT PEOPLE, PROCESSES AND SYSTEMS ARE IN PLACE | 2.2.1b 2.2.1c | 2.1f | ES | Right First Time |  |  |  |  | Scheme PCCR including ABS and final ‘CON forms’ provided on time and to the required accuracy | Demonstrate - The ASC Contract requires the Provider to submit to the Service Manager, within thirteen weeks after completion of a Scheme, a Post Completion Comparison Report (PCCR) (including Activity Benchmark Sheets (ABS) and final ‘CON forms’) between the Target Price and the Defined Cost plus Fee for each Scheme carried out by the Provider, together with an explanation for any differences. Evidence - Submission of Post Completion Comparison Report including Activity Benchmark Sheets (ABS) and final ‘CON forms’ | All data submitted, with sufficient explanations, within 13 weeks of Scheme completion | Date submitted after 13 weeks or Submitted incomplete or Submitted with insufficient explanations | Date submitted after 16 weeks
2 | WE SET THE STANDARD FOR DELIVERY | 2.1 | THE RIGHT PEOPLE, PROCESSES AND SYSTEMS ARE IN PLACE | 2.2.1d | 2.1g | ES | Right First Time |  | CEM 08 |  |  | Updating asset databases | Demonstrate - High quality asset data fit for its intended purpose entered in the relevant asset database in accordance with the timelines set out in the Asset Data Management Manual Measure - Compliance with the Asset Data Management Manual Provider Requirements and Annex 25 Evidence - Date of completion for all Schemes on site - As-Built records for all Schemes - Survey results prior to being loaded into the relevant asset database - Inspection records prior to being loaded into the relevant asset database - Evidence of changes in the relevant asset databases for all Schemes - Manage Asset Data Annex 24 Sub Process(s) in the Provider’s Quality Management Plan Note - It is anticipated that this Aspect will be scored through sample testing and/or SQRs | 100% of database updates since the last PMF review completed within required timeframe and accuracy. | <100% and >=90% of database updates since the last PMF review completed within required timeframe and accuracy. | <90% of database updates since the last PMF review completed within required timeframe and accuracy.
2 | WE SET THE STANDARD FOR DELIVERY | 2.1 | THE RIGHT PEOPLE, PROCESSES AND SYSTEMS ARE IN PLACE | 2.2.1d | 2.1h | ES | Right First Time |  |  |  |  | An asset database backlog does not exist | Demonstrate - An asset database backlog does not exist Evidence - Asset databases | No backlog of database updates exists | A backlog of database updates exists | The number of database updates in a backlog has increased since the last PMF review
2 | WE SET THE STANDARD FOR DELIVERY | 2.1 | THE RIGHT PEOPLE, PROCESSES AND SYSTEMS ARE IN PLACE | 2.2.1e | 2.1i | ES | Right First Time |  | CEM 07 |  |  | Quality management reporting delivered on time | Demonstrate - All Provider initiated reports produced as required and in accordance with Annex 19. Evidence - All Reports produced as required by Annex 19 since the last PMF review - Where appropriate, evidence of recommendations for further actions Note - Each report counts as one, regardless of differences in perceived importance to the HA. | 100% of reports required by Annex 19 since the last PMF review delivered on time and to the required quality | <100% and >=90% of reports required by Annex 19 since the last PMF review delivered on time and to the required quality | <90% of reports required by Annex 19 since the last PMF review delivered on time and to the required quality
2 | WE SET THE STANDARD FOR DELIVERY | 2.1 | THE RIGHT PEOPLE, PROCESSES AND SYSTEMS ARE IN PLACE | - | 2.1j | CH | Right First Time | API 08 |  | Y |  | Forecast and Actual Expenditure versus Budget | Demonstrate - Forecast Resource and Capital expenditure are close to budget - YTD Resource and Capital expenditure are close to YTD budget Evidence - SfM Forecast vs. Budget for each of Resource/Capital - SfM YTD Actual vs. YTD Budget for each of Resource/Capital | All SfM metrics are within a variance of ±5% | Not all SfM metrics are within a variance of ±5% and none exceed a variance of 10% | Any of the SfM metrics have a variance >10%
2 | WE SET THE STANDARD FOR DELIVERY | 2.2 | MANAGE CONTRACTS EFFICIENTLY | 2.2.1a | 2.2a | CP | Cost | API 14 |  | Y |  | Handling of Third Party Claims (Damage to Crown Property) | Demonstrate - Damage to Crown Property (DCP) claims (both over and under SP threshold) are managed effectively so as to promote the likelihood of cost recovery from culprits - Estimated costs of repairs are close to final costs Evidence - % complete and accurate TR430s issued to SM within 28 day deadline for above-threshold claims as per Annex 23.3.3 (DCP Metric 1) - % of above-threshold claims for which full evidence of costs has been supplied in accordance with HA requirements (DCP Metric 2) - % claims over threshold where full culprit details provided to HA (DCP Metric 3) - % claims over threshold where deviation between Estimated Cost of Repair vs. Final Cost is within 5% (DCP Metric 4) - % of claims where the Estimated Cost of Repair is above the threshold (and thus sent to HA) but the Final Cost is below the threshold (DCP Metric 5) - Rate of return (%) on under threshold claims is in line with that stated in the Annual Plan (DCP Metric 6) - Quantum of return (%) on under threshold claims is in line with contracted rate (DCP Metric 7) | DCP Metrics 1, 2, and 4 are each >= 95% and DCP Metrics 3, 6 and 7 are each >= 80% and DCP Metric 5 <= 5% | Not all DCP metrics are Green and none are Red | Any of DCP Metrics 1, 2 or 4 are < 90% or Any of DCP Metrics 3, 6 or 7 are <60% or DCP Metrics 5 > 15%
2 | WE SET THE STANDARD FOR DELIVERY | 2.2 | MANAGE CONTRACTS EFFICIENTLY | - | 2.2b | EC | Cost |  | CEM 04 |  |  | Number of Compensation Events raised by the Provider which are rejected by the Service Manager | Demonstrate - The Service Provider is seeking only valid compensation event claims as defined in Conditions of Contract Clause 60.1 (1-27) Evidence - Service Manager Compensation event records | No Provider initiated compensation events have resulted in the Service Manager notifying that the “Prices are not to be changed” since last PMF review as defined in Clause 61.4 | >0% and <=10% (by number) of Provider initiated compensation events have resulted in the Service Manager notifying that the “Prices are not to be changed” since last PMF review as defined in Clause 61.4 | >10% (by number) of Provider initiated compensation events have resulted in the Service Manager notifying that the “Prices are not to be changed” since last PMF review as defined in Clause 61.4
2 | WE SET THE STANDARD FOR DELIVERY | 2.2 | MANAGE CONTRACTS EFFICIENTLY | 2.1.1c | 2.2c | EC | Cost |  |  |  |  | HALMAT improvement target met | HALMAT - The HA Lean Metric & Assessment Tool (HALMAT) is used to assess service providers on how well they have incorporated Lean principles and tools into their processes. Timing of assessments is still to be confirmed for new ASCs. Demonstrate - That the HALMAT is being used and scores are increasing in line with agreed improvement plan. First assessment - Have HALMAT scores been moderated by the HA? Subsequent assessments - Is the ASC on track to meet its improvement target? How have total scores changed (across all questions)? MS = Milestone Score; CS = Current Score; PS = Previous Score Lean Improvement Score (LIM) = (CS-PS)/(MS-PS) Evidence - HALMAT scores Note - ASCs should score this N/A until first set of moderated scores has been received. | First assessment HALMAT moderated by HA deadline Subsequent assessments ASC is on track to ensure LIM >= 1 i.e. Have met or exceeded the milestone score as set in the improvement plan | First assessment HALMAT moderation deadline missed by less than a month Subsequent assessments ASC is on track to ensure 1 > LIM >= 0.8 i.e. Improvement in score is equal to or greater than 80% of that set in the improvement plan | First assessment HALMAT moderation deadline missed by more than a month Subsequent assessments ASC is on track to ensure LIM < 0.8 i.e. Improvement in score is less than 80% of that set in the improvement plan
2 | WE SET THE STANDARD FOR DELIVERY | 2.2 | MANAGE CONTRACTS EFFICIENTLY | - | 2.2d | EC | Cost |  | CEM 09 |  |  | Efficiency savings are generated as tendered | Demonstrate - Efficiency savings are generated as tendered. Evidence -Provider Tender Contract Data Part 2 Note - This metric will only be able to be scored once a year. That score should remain in place until the following year. | Lump sum annual discount >= percent tendered + 1% | Lump sum annual discount < percent tendered + 1% | N/A
2 | WE SET THE STANDARD FOR DELIVERY | 2.2 | MANAGE CONTRACTS EFFICIENTLY | - | 2.2e | ES | Product |  |  |  |  | Effective management of RTMC by ASC | Demonstrate - All relevant duties as per Annex 26 have been fulfilled Evidence - Records of correspondence, reviews, etc - Evidence of non-compliance including NCRs | All relevant duties as per Annex 26 have been fulfilled | Evidence exists that <=2 duties have not been fulfilled | Evidence exists that >2 duties have not been fulfilled
2 | WE SET THE STANDARD FOR DELIVERY | 2.2 | MANAGE CONTRACTS EFFICIENTLY | - | 2.2f | ES | Product |  |  |  |  | Effective management of contractors by ASC | Demonstrate - All relevant requirements as per Annex 9 have been fulfilled Evidence - Records of correspondence, reviews, etc - Evidence of non-compliance including NCRs | All relevant requirements as per Annex 9 have been fulfilled | Evidence exists that <=2 requirements have not been fulfilled | Evidence exists that >2 requirements have not been fulfilled
2 | WE SET THE STANDARD FOR DELIVERY | 2.2 | MANAGE CONTRACTS EFFICIENTLY | - | 2.2g | ES | Product |  |  |  |  | 360 degree feedback from RTMC and contractors is acted on | Demonstrate - Feedback from RTMC and contractors is logged and assessed - Actions are assigned to individuals and target dates set - Actions are on schedule to be completed by the target date - Status of feedback including update on actions is shared with RTMC/contractors Evidence - Feedback logs - Records of correspondence, reviews, etc | Feedback from RTMC and contractors is logged and assessed and Actions are assigned to individuals and target dates set and 100% of actions are on schedule to be completed by the target date and Status of feedback including update on actions is shared with RTMC/contractors | Feedback from RTMC and contractors is logged but not assessed or Actions are not assigned to individuals or target dates not set or >=90% of actions are on schedule to be completed by the target date | Feedback from RTMC and contractors is not logged or Actions are not documented or <90% of actions are on schedule to be completed by the target date or Status of feedback including update on actions is not shared with RTMC/contractors
2 | WE SET THE STANDARD FOR DELIVERY | 2.3 | ASSET RENEWAL AND IMPROVEMENT SCHEMES ARE DELIVERED TO PLAN | 2.2.2a | 2.3a | O | Time | API 06 | CEM 05 | Y |  | Deliver Schemes on time | For Capital Schemes with baseline cost >= £100K Demonstrate - Meeting the HA Strategic Goal of setting the standard for delivery in relation to target time and actual time for Schemes that are Live (i.e. from Actual Design Completion to 11 months after the month in which PCCR is reported). Evidence - Available supporting evidence at milestones 1, 2, 5 and 6. See PMM App E Annex 1. Measure - Total Percentage Time Variance: Net variance of actual time over all Live Schemes for both design and construction phases as a percentage of total planned construction duration | Net time of all Live Schemes is 5% or more below the predicted time | Net time of all Live Schemes is on or below predicted time by less than 5% | Net time of all Live Schemes is above predicted time
2 | WE SET THE STANDARD FOR DELIVERY | 2.3 | ASSET RENEWAL AND IMPROVEMENT SCHEMES ARE DELIVERED TO PLAN | 2.2.3a | 2.3b | O | Cost | API 07 | CEM 06 | Y |  | Deliver Schemes to budget | For Capital Schemes with baseline cost >= £100K Demonstrate - Meeting the HA Strategic Goal of setting the standard for delivery in relation to target cost and actual costs for Schemes that are Live (i.e. from Actual Design Completion to 11 months after the month in which PCCR is reported). Evidence - Available supporting evidence at milestones 1, 3 and 7. See PMM App E Annex 2. Measure - Total Percentage Cost Variance: Net variance of predicted/actual cost over all Live Schemes at either milestone 3 or milestone 7 versus predicted costs at milestone 1. | Net costs of all Live Schemes is 5% or more below the predicted costs | Net costs of all Live Schemes is on or below predicted costs by less than 5% | Net costs of all Live Schemes is above predicted costs
2 | WE SET THE STANDARD FOR DELIVERY | 2.3 | ASSET RENEWAL AND IMPROVEMENT SCHEMES ARE DELIVERED TO PLAN | 5.2.1b | 2.3c | ES | Cost |  |  |  |  | Changes to Programme are managed | Scope - This Aspect relates to Programme and Scheme data entered into SfM and provided to the AMO (either to the National Allocations Team or the AMO Performance Team via the Scheme Data Standard) Demonstrate - Full baseline Programme, monthly updates and SfM reporting on Schemes supplied to HA in accordance with monthly reporting cycle - All ICF/NDD Director approved new Schemes/changes to Programme (including Schemes dropped) are reported in month - For all new Schemes/changes to Programme in month (including Schemes dropped), relevant documentation has been provided to the Service Delivery Team/Asset Delivery Team within agreed timelines to ensure the region obtains ICF and/or NDD Director approval (as appropriate) - No changes to Schemes (new, changed, dropped) are being reported without ICF/NDD Director approval Evidence - Programme of Works - Monthly SfM and Scheme data standard reporting - Data provided to HA National Allocations Team - ICF Change Control/Approvals process | Full baseline Programme, monthly updates and SfM reporting on Schemes supplied to HA in accordance with monthly reporting cycle and All ICF/NDD Director approved new Schemes/changes to Programme (including Schemes dropped) are reported in month and For all new Schemes/changes to Programme in month (including Schemes dropped), relevant documentation has been provided to the Service Delivery Team/Asset Delivery Team within agreed timelines to ensure the region obtains ICF and/or NDD Director approval (as appropriate) and No changes to Schemes (new, changed, dropped) are being reported without ICF/NDD Director approval | For some new Schemes/changes to Programme in month (including Schemes dropped), relevant documentation has been provided to the Service Delivery Team/Asset Delivery Team within agreed timelines | Any of full baseline Programme, monthly updates or SfM reporting on Schemes not supplied to HA in accordance with monthly reporting cycle or Any ICF/NDD Director approved new Schemes/changes to Programme (including Schemes dropped) not reported in month or For all new Schemes/changes to Programme in month (including Schemes dropped), relevant documentation has not been provided to the Service Delivery Team/Asset Delivery Team within agreed timelines or Some changes to Schemes (new, changed, dropped) are being reported without ICF/NDD Director approval
3 | WE DELIVER SUSTAINABLE SOLUTIONS | 3.1 | THE IMPACT OF OUR NETWORK ON THE ENVIRONMENT IS MITIGATED | 3.1.1b | 3.1a | ES | Service |  |  |  | Part 0 | Effective use and application of design objectives/principles to prevent negative environmental impacts | To ensure - Design considerations are informed by Environmental Objectives (as per DMRB Vol10 and HA Environmental Strategy) at the earliest stage of a Scheme (note this is any Scheme, not just an Environment Scheme) - Design Principles of functionality, simplicity, unity, balance, sustainability and maintainability are applied - Negative environmental impacts are minimized and environmental enhancements are integrated into scheme design Demonstrate - An Environmental Coordinator has been appointed. - Environmental Objectives have been set against the Scheme and agreed with the Regional Environmental Advisor - The design team has been briefed on the Environmental Objectives by the Environmental Coordinator - Environmental impacts and enhancement options have been considered and the Regional Environmental Advisor and relevant competent authorities consulted Evidence - Environmental Impact Assessments - Records of Determination - Consultation Responses - Design Risk Assessments - Environmental Proposals Plans - Environmental scoping - Design reviews | Design team is comprised of appropriately qualified professionals covering the full range of technical disciplines required, and an Environmental Coordinator has been appointed. and Environmental Objectives have been set against the scheme and agreed with the area Regional Environmental Advisor. The design team has been briefed to understand the implementation of the Environmental Objectives. and Environmental impacts and enhancement options have been considered and appropriate documents have been prepared and consulted on with the area Regional Environmental Advisor and relevant competent authorities. | Design Team is incomplete (i.e. not all required specialists or no Environmental Coordinator) or Environmental Objectives set, but not agreed with the area Regional Environmental Advisor. No evidence of briefing on Environmental Objectives to the design team. or Some environmental impacts and enhancement options have been considered, but either these have not been furthered or Not all impacts / enhancement options have been considered. | No evidence of Design Team or Environmental Coordinator in place or No evidence of Environmental Objectives being set or No evidence that environmental impacts or options for enhancements have been considered
3 | WE DELIVER SUSTAINABLE SOLUTIONS | 3.2 | RESOURCES ARE USED EFFICIENTLY | 3.1.1c | 3.2a | ES | Service |  | CEM 14 |  | Part 0 | Site Waste Management Plans in place and operating | Demonstrate - Delivery of Site Waste Management Plans (SWMPs) in accordance with current legislation Evidence - Active Site Waste Management Plans - Quality system records | Compliance with all SWMP legislative requirements | Compliance with all but two SWMP legislative requirements | Failure to comply with three or more SWMP legislative requirements
3 | WE DELIVER SUSTAINABLE SOLUTIONS | 3.2 | RESOURCES ARE USED EFFICIENTLY | - | 3.2b | ES | Service |  |  |  | Part 0 | Implementation and promotion of the reuse and recycling of materials | Scope - In relation to non-hazardous construction and demolition waste (excluding material defined in category 17 05 04 in the list of waste) by weight for construction projects greater than £300,000 in value Demonstrate - An annual target is agreed with the regional team to increase % of waste reused or recycled and progress is reported each quarter - On track to hit this annual target - On track to reuse or recycle a minimum of 70% of waste by 2020 Evidence - Annual targets set and extrapolated towards the 2020 target. - Site Waste Management Plans - EnvIS submission data | An annual target is agreed with the regional team to increase % of waste reused or recycled and progress is reported each quarter and On track to hit this annual target and On track to hit the 2020 target | An annual target is agreed with the regional team but progress not reported last quarter or Not on track to hit the annual target but On track to hit the 2020 target | An annual target has not been agreed with the regional team or progress not reported for the last two quarters or Not on track to hit the 12/13 target and Not on track to hit the 2020 target
3 | WE DELIVER SUSTAINABLE SOLUTIONS | 3.2 | RESOURCES ARE USED EFFICIENTLY | - | 3.2c | ES | Service |  |  |  | Part 0 | Reduction in material consumption | Demonstrate - Development of a plan to reduce material consumption in schemes Evidence - Plan is informed by: DMRB Vol 2 Sec 3 (BA92/07) and Vol 7 part 2 (35/04); IAN 153/11; NDD Value Management Requirements (Dec 2011) Annex 2 (Road Renewals) - Project reports which demonstrate reduction in material consumption are being fed into development plan - Use of Lean tools and techniques to demonstrate where reduction in material consumption is feasable. - Innovative methods employed ( e.g through continuous improvement) will show reduction in material consumption - Use of the Managing Down Costs Toolkit: http://www.highways.gov.uk/partners/toolkits/tk_list_mdc.asp?alltips=1 | Development plan is in place which identifies where it is possible to achieve a reduction in material consumption | No plan is in place but is under development (scoping exercise completed as a minimum) | No plan for development is in place, and none being considered
3 | WE DELIVER SUSTAINABLE SOLUTIONS | 3.2 | RESOURCES ARE USED EFFICIENTLY | - | 3.2d | ES | Service |  |  |  | Part 0 | Implementation and promotion of energy saving procedures | Demonstrate - Forecasted annual energy savings (kWh) to 2015 are shown in the monthly return, and show a reduction in annual energy consumption against a 2009/10 baseline energy consumption figure Evidence - Monthly Network Energy Return | Forecasted annual energy savings to 2015 are shown in the monthly return, and show a reduction in annual energy consumption against a 2009/10 baseline energy consumption figure | Forecasted annual energy savings to 2015 are shown in the monthly return, but do not show a reduction in annual energy consumption against a 2009/10 baseline, but plans are in place to rectify this | Forecasted annual energy savings to 2015 are not shown in the monthly return
3 | WE DELIVER SUSTAINABLE SOLUTIONS | 3.3 | CARBON EMISSIONS ARE REDUCED | 3.1.1d | 3.3a | EC | Service |  |  |  | Part 0 | Implementation and promotion of a reduction in carbon emissions | Demonstrate - To agree and report on a forecasted reduction in carbon emissions (tCO2e) for 2012/13 against the 2011/12 reported baseline for total emissions (tCO2e) from previous MAC activities Note - Each ASC will agree its own annual forecasted reduction with Regional Teams Evidence - Quarterly Carbon Return - Carbon reduction projections (if applicable) | On target to reduce carbon emissions by the agreed target reduction | Expected to reduce carbon emissions by less than the forecasted figure | Expected to increase carbon emissions against 2011/12 baseline
3 | WE DELIVER SUSTAINABLE SOLUTIONS | 3.4 | NETWORK IMPROVEMENTS THAT SUPPORT SPATIAL, ECONOMIC AND ENVIRONMENTAL PRIORITIES ARE PROMOTED | 3.2.1b | 3.4a | ES | Product |  |  |  |  | Design and construction of non-Safety LNMS Schemes in accordance with the scheme accepted into the HA programme/agreed at VM | Demonstrate - Design assurance reviews undertaken and outcomes agreed prior to start of construction - All schemes completed in the month confirmed as being constructed in accordance with the design such that the benefits documented at VM stage are expected to be delivered -All H&S files complete and up to date > Relates to updates required by the end of the month, including those not carried out on time in previous months > Also applies to H&S files that are incomplete from a previous financial year Evidence - Design assurance reviews - Scheme completion dates - Scheme Completion Certificate - Completed/updated H&S files | All Schemes which started construction in the month had design assurance reviews undertaken and outcomes agreed prior to start of construction and All schemes completed in the month confirmed as being constructed in accordance with the design such that the benefits documented at VM stage are expected to be delivered and All H&S files complete and up to date | >=90% of Schemes which started construction in the month had design assurance reviews undertaken and outcomes agreed prior to start of construction and >=90% of schemes completed in the month confirmed as being constructed in accordance with the design such that the benefits documented at VM stage are expected to be delivered and >=90% of H&S files complete and up to date | <90% of Schemes which started construction in the month had design assurance reviews undertaken and outcomes agreed prior to start of construction or <90% of schemes completed in the month confirmedas being constructed in accordance with the design such that the benefits documented at VM stage are expected to be delivered or <90% of H&S files complete and up to date
3 | WE DELIVER SUSTAINABLE SOLUTIONS | 3.5 | THE IMPACT OF OUR NETWORK ON ADJACENT COMMUNITIES IS MITIGATED | - | 3.5a | ES | Service |  |  |  | Part 0 | Employment section of the Inclusion Action Plan developed and delivered | Demonstrate In relation to the workforce: - An assessment has been carried out to gauge current performance in relation to ensuring people with protected characteristics are not being discriminated against in employment policy/practice & opportunities to contribute to achieving equality related government initiatives are being taken including: • Information gathered and analysed on the outcomes of employment policies and practices - including but not limited to: > Recruitment and selection > Promotion > Exits • Consideration given to government initiatives and the extent to which suppliers can make a contribution including: > Apprenticeships > Use of SMEs > Use of supported businesses - Issues/Opportunities identified and action to deliver improvements included in the employment section of the Inclusion Action Plan - Actions and initatives in the plan are monitored and reviewed - All elements of the employment section of the Inclusion Action Plan required to be delivered are done so on time Evidence - Information on the current performance in of employment policies for people with protected characteristics - Employment section of Inclusion Action Plan - Progress reports on delivery of the Employment section of the Inclusion Action Plan - Independent assessments - Staff surveys Elements to include - See the Inclusion Action Plan guidance for details of what the Agency would, as a minimum, expect suppliers to have considered and included. | An assessment has been undertaken or is on track to be undertaken by the agreed target date and Improvements identified have been (or will be) added to the Employment section of the Inclusion Action Plan and 100% of the actions in the Employment section of the Inclusion Action Plan required to be delivered in the current year have been done so on time (or will be) | An assessment is planned but is not on track to be undertaken by the agreed target date or Improvements have been identified but not yet added to the Employment section of the Inclusion Action Plan or >=70% of the actions in the Employment section of the Inclusion Action Plan required to be delivered in the current year have been done so on time (or will be) | An assessment is not planned or Improvements have been identified but there are no plans to add to the Employment section of the Inclusion Action Plan or <70% of the actions in the Employment section of the Inclusion Action Plan required to be delivered in the current year have been done so on time (or will be)
3 | WE DELIVER SUSTAINABLE SOLUTIONS | 3.5 | THE IMPACT OF OUR NETWORK ON ADJACENT COMMUNITIES IS MITIGATED | - | 3.5b | ES | Service |  |  |  | Part 0 | Service Delivery section of the Inclusion Action Plan developed and delivered | Demonstrate - An assessment has been carried out to ensure that the particular needs of people with protected characteristics (both road users and local residents) are identified, understood and responded to in both the design and delivery of schemes to include how these needs will be met: > In communication before and during the scheme delivery > In consultation / engagement activity in relation to the scheme > In public relations activity /complaint handling during the scheme > Through training of the workforce - Actions to ensure needs are understood and responded to included in the Service Delivery section of the Inclusion Action Plan - Actions in the plan are monitored and reviewed - All elements of the Service Delivery section of the Inclusion Action Plan required to be delivered are done so on time Evidence - Assessments - Service Delivery section of the Inclusion Action Plan - Evidence of successful mitigations - Post-completion surveys | An assessment has been undertaken or is on track to be undertaken by the agreed target date and actions identified have been (or will be) added to the Service Delivery section of the Inclusion Action Plan and 100% of the actions in the Service Delivery section of the Inclusion Action Plan required to be delivered in the current year have been done so on time (or will be) and Evidence exists that actions have been effective | An assessment is planned but is not on track to be undertaken by the agreed target date or Actions have been identified but not yet added to the Service Delivery section of the Inclusion Action Plan or >=70% of the actions in the Service Delivery section of the Inclusion Action Plan required to be delivered in the current year have been done so on time (or will be) | An assessment is not planned or Improvements have been identified but there are no plans to add to the Service Delivery section of the Inclusion Action Plan or <70% of the actions in the Service Delivery section of the Inclusion Action Plan required to be delivered in the current year have been done so on time (or will be)
4 | OUR ROADS ARE THE SAFEST IN THE WORLD | 4.1 | A SAFE NETWORK IS MAINTAINED | - | 4.1a | CH | Product |  |  | Y |  | Geotechnical asset risk is managed effectively | Demonstrate - Potential defects with geotechnical assets are identified - Potential risks to road users are managed effectively Measure - The length of geotechnical assets in each of the Severe, High and Medium risk categories expressed as a % of the Area’s geotechnical asset length’ | % of network with Severe Risk Level is < 0.1 and % of network with High Risk Level < 0.4 and % of network with Medium Risk Level is < 8% | Any one of % of network with Severe Risk Level is >= 0.1 or % of network with High Risk Level >= 0.4 or % of network with Medium Risk Level is >= 8% | Two or more of % of network with Severe Risk Level is >= 0.1 or % of network with High Risk Level >= 0.4 or % of network with Medium Risk Level is >= 8%
4 | OUR ROADS ARE THE SAFEST IN THE WORLD | 4.1 | A SAFE NETWORK IS MAINTAINED | - | 4.1b | CP | Product |  |  | Y | Part 8 Deliverable 14 | Make safe defects: Lighting | Demonstrate - Sequential lamp failures are maintained to acceptable levels - Lighting asset failures across the inventory are acceptable - Lighting asset failures are rectified effectively Evidence - Lighting scouts - Lighting asset repair Measures - Max. number of sequential lamp failures (Lighting Metric 1) - Max. number of failures per length of lamps (Lighting Metric 2) - Rectification rate within 7 days (Lighting Metric 3) AMOR and lamp scouts - Lamp scouts should take place the last full week of April, August, October, November, December, January and February. Therefore we expect this Aspect to be scored for each of those months. Although 7 day rectifications may fall into the following month, the performance should be scored against the month that the lighting scout took place. Results should be available before the deadline to submit PMF scores to the AMO Performance Team. | Lighting Metric 1 <= 2 and Lighting Metric 3 <= 30% and Lighting Metric 2 = 100% | Lighting Metric 1 = 3 or Lighting Metric 3 <= 40% or Lighting Metric 2 >= 95% | Lighting Metric 1 > 3 or Lighting Metric 3 > 40% or Lighting Metric 2 < 95%
4 | OUR ROADS ARE THE SAFEST IN THE WORLD | 4.1 | A SAFE NETWORK IS MAINTAINED | - | 4.1c | O | Product |  |  | Y | Part 9 Deliverable 3 | Make safe defects: Paved Areas | Demonstrate - The following defects have been reduced to zero within 24 hours of verification: > Pothole > 150 mm diameter, or of > depth than that of the surface course thickness, or of > depth than 40 mm. > Local Surface Deformation > 40 mm > Ironwork - Difference in level around ironwork > 25 mm > Pothole > 25 mm depth or > 150 mm diameter > Local Surface Deformation > 25 mm > Trip Hazard - Any step change > 25 mm Evidence - Operational defect data | All defects made safe within the target time | <=2% of defects were not rectified within target time | >2% defects were not rectified within target time
4 | OUR ROADS ARE THE SAFEST IN THE WORLD | 4.1 | A SAFE NETWORK IS MAINTAINED | - | 4.1d | ES | Product |  |  |  | Part 13 Deliverables | Ensure the 14 soft estate deliverables of AMOR are satisfied | Demonstrate - All 14 soft estate deliverables of AMOR have been satisfied Note - Supplier to provide monthly evidence. Score can be overwritten if evidence exists that deliverables not met. Evidence - Proof of work completed provided by the Service Provider - Records of correspondence, reviews, etc - Evidence of non-compliance including NCRs | All 14 soft estate deliverables of AMOR have been satisfied | Service Provider can not provide evidence for <=2 deliverables or Evidence exists that <=2 deliverables have not been satisfied | Service Provider can not provide evidence for >2 deliverables or Evidence exists that >2 deliverables have not been satisfied
4 | OUR ROADS ARE THE SAFEST IN THE WORLD | 4.1 | A SAFE NETWORK IS MAINTAINED | - | 4.1e | CP | Product |  |  | Y | Part 15 Deliverables 5,6,7 | Sweeping and cleaning deliverables satisfied (Litter) | Demonstrate - 100% success rate in restoring the following areas to the grade specified and in the timescale specificied following notification > Carriageway, paved verges and paved central reservations of motorways and APTRs - B or C to A within 28 days (1 point) > Carriageway, paved verges and paved central reservations of motorways and APTRs - D to A within 7 days (1 point) > Motorway and APTR roundabouts and lay-bys, approach and slip roads - B or C to A within 14 days (1 point) > Motorway and APTR roundabouts and lay-bys, approach and slip roads - D to A within 7 days (1 point) > All other parts of the Area Network (non paved) - C to B within 28 days (1 point) > All other parts of the Area Network (non paved) - D to B within 7 days (1 point) If any element is N/A then score one point. Evidence - Proof of work completed provided by the Service Provider - Records of correspondence, reviews, etc - Evidence of non-compliance including NCRs | 6 points | 5 points | < 5 points
4 | OUR ROADS ARE THE SAFEST IN THE WORLD | 4.1 | A SAFE NETWORK IS MAINTAINED | - | 4.1f | ES | Product |  | CEM 10 |  | All parts | Number of AMOR performance targets meeting or exceeding threshold | Demonstrate - AMOR Performance Requirement Levels are being met. Evidence - Proof of work completed provided by the Service Provider - Service Provider inspection summaries - Records of correspondence, reviews, etc - Evidence of non-compliance including NCRs Note - If the Provider cannot demonstrate compliance with a Performance Requirement Level then the Level is assumed to be failed. | All AMOR Performance Requirement Levels are met since last PMF review | >=1 and <=6 AMOR Performance Requirement Levels failed since last PMF review | >6 AMOR Performance Requirement Levels failed since last PMF review
4 | OUR ROADS ARE THE SAFEST IN THE WORLD | 4.2 | A SAFE NETWORK IS PROVIDED | 4.2.1a | 4.2a | ES | Product |  |  |  |  | Design and construction of Safety LNMS Schemes in accordance with the scheme accepted into the HA programme/agreed at VM | Demonstrate - Design assurance reviews undertaken and outcomes agreed prior to start of construction - All schemes completed in the month confirmed as being constructed in accordance with the design such that the benefits documented at VM stage are expected to be delivered -All H&S files complete and up to date > Relates to updates required by the end of the month, including those not carried out on time in previous months > Also applies to H&S files that are incomplete from a previous financial year Evidence - Design assurance reviews - Scheme completion dates - Scheme Completion Certificate - Completed/updated H&S files | All Schemes which started construction in the month had design assurance reviews undertaken and outcomes agreed prior to start of construction and All schemes completed in the month confirmed as being constructed in accordance with the design such that the benefits documented at VM stage are expected to be delivered and All H&S files complete and up to date | >=90% of Schemes which started construction in the month had design assurance reviews undertaken and outcomes agreed prior to start of construction and >=90% of schemes completed in the month confirmed as being constructed in accordance with the design such that the benefits documented at VM stage are expected to be delivered and >=90% of H&S files complete and up to date | <90% of Schemes which started construction in the month had design assurance reviews undertaken and outcomes agreed prior to start of construction or <90% of schemes completed in the month confirmedas being constructed in accordance with the design such that the benefits documented at VM stage are expected to be delivered or <90% of H&S files complete and up to date
4 | OUR ROADS ARE THE SAFEST IN THE WORLD | 4.2 | A SAFE NETWORK IS PROVIDED | - | 4.2b | EC | Product |  |  |  |  | Delivery of Road Safety Audits and closing out actions | Demonstrate In relation to the RSAs due to be completed over the last 12 months: - RSAs were completed within required timeframe - Resulting actions were completed on time or are due to be completed on time Evidence - RSA programme - List of approved auditors - Audit reports - Actions closed out or departures/exceptions approved | In relation to the RSAs due to be completed over the last 12 months: 100% of RSAs were completed within required timeframe and 100% of resulting actions were completed on time or are due to be completed on time | In relation to the RSAs due to be completed over the last 12 months: >=90% of RSAs were completed within required timeframe and >=90% of resulting actions were completed on time or are due to be completed on time | In relation to the RSAs due to be completed over the last 12 months: <90% of RSAs were completed within required timeframe or <90% of resulting actions were completed on time or are due to be completed on time
4 | OUR ROADS ARE THE SAFEST IN THE WORLD | 4.3 | SAFETY INCIDENTS INVOLVING HA AND CONTRACTORS ARE REDUCED | 4.3.1b | 4.3a | CH | Safety | API 05 | CEM 13 | Y |  | Reduce accidents within the Provider's organisation (AFR) | Demonstrate - Accident Frequency Rate target set by HA Board met Measures - AFR in AIRSWeb | AFR <= Annual AFR target | AFR <= Annual AFR target + 0.05 | AFR > Annual AFR target + 0.05
4 | OUR ROADS ARE THE SAFEST IN THE WORLD | 4.3 | SAFETY INCIDENTS INVOLVING HA AND CONTRACTORS ARE REDUCED | 4.3.1a | 4.3b | ES | Safety |  |  |  |  | Compliance with the CDM Regulations 2007 | Demonstrate - Procedures in place to ensure compliance with the CDM 2007 Regulations and the ACoP (1 point) - Competent construction sector H&S advisor in post (1 point) - Workforce competency standards established and regularly reviewed (1 point) - Competent CDM Co-ordinator in post (1 point) - Workforce consulted and encouraged to report H&S concerns (1 point) - Established processes to engage and manage sub contractors (1 point) - Design outputs in accordance with CDM 2007 Reg. 11 and 18 [in addition Reg. 13, 19 and 22 for contractors and Reg. 20 for CDMC's]. (1 point) Evidence - H&S Policy - H&S Management system processes and procedures - Skills information and training records - Design review records - Scheme project delivery plans and risk regsiters | 7 points | N/A | < 7 points
5 | OUR NETWORK IS A DYNAMIC & RESILIENT ASSET | 5.1 | INFORMATION IS AVAILABLE TO SUPPORT EFFECTIVE DECISION-MAKING | 5.1.1a | 5.1a | ES | Product |  | CEM 15 |  |  | Inspection Management Programme delivered | Demonstrate - Inspection Management Programme documented and operating - All inspections in accordance with the Maintenance Requirements Plan - Opportunities to combine inspections at the same time as works are maximised to reduce network closures - Escalation of findings in accordance with AMOR Part 0. Evidence - Maintenance Requirements Plan - Inspection records | All inspections required by Maintenance Requirements Plan since last PMF review undertaken and recorded | <100% and >=95% of inspections required by Maintenance Requirements Plan since last PMF review undertaken and recorded | < 95% of inspections required by Maintenance Requirements Plan since last PMF review undertaken and recorded
5 | OUR NETWORK IS A DYNAMIC & RESILIENT ASSET | 5.1 | INFORMATION IS AVAILABLE TO SUPPORT EFFECTIVE DECISION-MAKING | 5.1.1b | 5.1b | ES | Product |  |  |  |  | Network is assessed | Demonstrate - Activities are being undertaken to provide performance intelligence across all maintenance and operational requirements relevant to the performance of the Area Network including: > Monitoring and data collection > Analysis > Decisions Evidence - Provider’s Quality Plan - Provider’s accepted Maintenance Requirements Plan (MRP) or equivalent - Provider’s accepted Watchman Plan - Analysis supporting proposed Schemes - Recommendations to the Employer for managing and optimising performance of the Area Network | The Watchman Plan has been implemented and has been reviewed within the last six months and Network data from all available sources identified in the MRP has been analysed and Network information used to make intelligence led decisions regarding maintenance and operational requirements | The Watchman Plan has been implemented but has not been reviewed within the last six months or Network data from only a limited number of sources (compared to the sources included in the MRP) has been analysed or Network information has not been used to make intelligence led decisions regarding maintenance and operational requirements | The Watchman Plan has not been implemented or has not been reviewed within the last 12 months or Network data has not been analysed
5 | OUR NETWORK IS A DYNAMIC & RESILIENT ASSET | 5.1 | INFORMATION IS AVAILABLE TO SUPPORT EFFECTIVE DECISION-MAKING | 5.1.1c | 5.1c | EC | Product |  |  |  | Part 1 Deliverable 6 | Appropriate schemes are identified and promoted | Demonstrate - No schemes have been submitted to value management without clear evidence that the Maintenance Requirements have been fulfilled. Evidence - SM appraisal of those Schemes that were submitted to them - This relates to NDD Value Management Requirements 3.7.3 bullet 4: The Service Manager...Confirms that the Provider has met its requirements under the watchman role before the project is developed further. Needs and issues which are regarded as part of the Provider's Lump Sum maintenance duties will be rejected. Note - This Aspect should be scored in relation to new schemes submitted to the SM in the month | 0 SM rejections | <=2 SM rejections | >2 SM rejections
5 | OUR NETWORK IS A DYNAMIC & RESILIENT ASSET | 5.2 | LONG TERM INTEGRITY OF THE ASSET IS SUSTAINED | - | 5.2a | CP | Product |  |  | Y |  | Maintenance Requirements Plan delivered | Demonstrate - All elements of the MRP have been delivered for the following asset types: > Drainage (1 point) > Fences, Screens and Environmental Barriers (1 point) > Geotechnical Assets (1 point) > Lighting (1 point) > Paved Areas (1 point) > Road Markings and Road Studs (1 point) > Road Restraint Systems (1 point) > Road Traffic Signs (1 point) > Soft Estate (1 point) > Structures (1 point) > Sweeping and Cleaning (1 point) > Tunnels (1 point) Note - Score 1 point if the asset type is N/A to your Area e.g. tunnels Evidence - MRP (including GAMP, LAMP, EMP) - Tracking of delivery against MRP | 12 points | >=10 points | < 10 points
5 | OUR NETWORK IS A DYNAMIC & RESILIENT ASSET | 5.2 | LONG TERM INTEGRITY OF THE ASSET IS SUSTAINED | 5.2.1a | 5.2b | ES | Product |  |  |  |  | Design and construction of Renewal Schemes in accordance with the scheme accepted into the HA programme/agreed at VM | Demonstrate - Design assurance reviews undertaken and outcomes agreed prior to start of construction - All schemes completed in the month confirmed as being constructed in accordance with the design such that the benefits documented at VM stage are expected to be delivered -All H&S files complete and up to date > Relates to updates required by the end of the month, including those not carried out on time in previous months > Also applies to H&S files that are incomplete from a previous financial year Evidence - Design assurance reviews - Scheme completion dates - Scheme Completion Certificate - Completed/updated H&S files | All Schemes which started construction in the month had design assurance reviews undertaken and outcomes agreed prior to start of construction and All schemes completed in the month confirmed as being constructed in accordance with the design such that the benefits documented at VM stage are expected to be delivered and All H&S files complete and up to date | >=90% of Schemes which started construction in the month had design assurance reviews undertaken and outcomes agreed prior to start of construction and >=90% of schemes completed in the month confirmed as being constructed in accordance with the design such that the benefits documented at VM stage are expected to be delivered and >=90% of H&S files complete and up to date | <90% of Schemes which started construction in the month had design assurance reviews undertaken and outcomes agreed prior to start of construction or <90% of schemes completed in the month confirmedas being constructed in accordance with the design such that the benefits documented at VM stage are expected to be delivered or <90% of H&S files complete and up to date
5 | OUR NETWORK IS A DYNAMIC & RESILIENT ASSET | 5.2 | LONG TERM INTEGRITY OF THE ASSET IS SUSTAINED | 5.2.1a | 5.2c | ES | Product |  | CEM 16 |  |  | Work which the Provider has undertaken is defect free throughout the contract period | Demonstrate - Work which the Provider has undertaken is defect free throughout the Contract period Evidence - Quality system records - Provider’s Routine and Planned Maintenance System - SRW - HAPMS | The number of unplanned defect repairs requiring traffic management in last rolling 3 months within Scheme areas constructed since Contract commencement = 0 | The number of unplanned defect repairs requiring traffic management in last rolling 3 months within Scheme areas constructed since Contract commencement >0 and <= 2 | The number of unplanned defect repairs requiring traffic management in last rolling 3 months within Scheme areas constructed since Contract commencement > 2
5 | OUR NETWORK IS A DYNAMIC & RESILIENT ASSET | 5.3 | THE NETWORK IS AVAILABLE DURING SEVERE WEATHER EVENTS | 4.1.2c | 5.3a | CH | Product |  | CEM 11 | Y |  | Salt Stock Capability Maintained | Demonstrate - Salts stocks are maintained in excess of minimum contracted limits Measure - Compliance with the minimum contracted salt stocks Evidence - Provider’s salt stock records - Mitigating Circumstances | Salt stocks remained in excess of minimum contracted quantity at all times since last PMF review | Salt stocks dropped below the contract minimum level at any time since last PMF review | Either - (a) Salt stock dropped below contract minimum level for more than 12 days or (b) salt stock dropped to less than 80% of the contract minimum level at any time.
5 | OUR NETWORK IS A DYNAMIC & RESILIENT ASSET | 5.3 | THE NETWORK IS AVAILABLE DURING SEVERE WEATHER EVENTS | 4.1.2a | 5.3b | CH | Product |  |  | Y | Part 4 Deliverable 2 | Appropriate precautionary salting provided | Demonstrate (if applicable) - Precautionary treatments delivered within the target treatment time for each route (excluding the turnaround time) as stated in the Severe Weather Plan - 100% of routes treated within the target treatment time Evidence - WRF 1 - Precautionary salting records (part of WRF1) - Percentage of route completions within contract time (data logging) Note - In the Winter Period 1 October – 30 April this Aspect should always be scored. Outside of the Winter period it should be scored N/A unless severe weather conditions were experienced in which case it should be scored as per the RAG guidance. | 100% of routes treated within the target treatment time | >=90% of routes treated within the target treatment time | <90% of routes treated within the target treatment time
5 | OUR NETWORK IS A DYNAMIC & RESILIENT ASSET | 5.3 | THE NETWORK IS AVAILABLE DURING SEVERE WEATHER EVENTS | 4.1.2b | 5.3c | CH | Product |  | CEM 12 | Y | Part 4 Deliverable 3 (Snow) | Lane availability maximised during severe weather conditions | Demonstrate - Lane availability is maximised during severe weather conditions Evidence - WRF 1 - Severe Weather Plan - Lane availability during severe weather conditions Note - In the Winter Period 1 October – 30 April this Aspect should always be scored. Outside of the Winter period it should be scored N/A unless severe weather conditions were experienced in which case it should be scored as per the RAG guidance. | 100% lane availability maintained in accordance with Severe Weather Plan since last PMF review | <100% and >=95% lane availability maintained in accordance with Severe Weather Plan since last PMF review | <95% lane availability maintained in accordance with Severe Weather Plan since last PMF review
5 | OUR NETWORK IS A DYNAMIC & RESILIENT ASSET | 5.3 | THE NETWORK IS AVAILABLE DURING SEVERE WEATHER EVENTS | - | 5.3d | O | Product |  |  | Y | Part 5 Outcome 1 | Flood events are minimised | Demonstrate - The drainage system is managed and maintained to minimise the risk of Flood Events on traffi cked surfaces and remove standing water from traffi cked surfaces. - Number of Flood Events on trafficked surfaces is zero. Evidence - HADDMS records - | Number of Flood Events on trafficked surfaces = 0 | Number of Flood Events on trafficked surfaces <=2 | Number of Flood Events on trafficked surfaces >2
5 | OUR NETWORK IS A DYNAMIC & RESILIENT ASSET | 5.3 | THE NETWORK IS AVAILABLE DURING SEVERE WEATHER EVENTS | - | 5.3e | O | Product |  |  | Y | Part 5 Deliverable 4 | Flood event details recorded | Demonstrate - All flood events set to 'Closed' status within 28 days of notification Evidence - Provider’s Routine and Planned Maintenance System - Operational defect data | All flood events set to 'Closed' status within 28 days of notification | 1 flood event not set to 'Closed' status within 28 days of notification | >1 flood event not set to 'Closed' status within 28 days of notification
5 | OUR NETWORK IS A DYNAMIC & RESILIENT ASSET | 5.3 | THE NETWORK IS AVAILABLE DURING SEVERE WEATHER EVENTS | - | 5.3f | ES | Product |  |  |  |  | Other severe weather events are mitigated effectively | Demonstrate - Responses to severe weather events were delivered in accordance with the Severe Weather Plan Evidence - Records of severe weather event - Severe Weather Plan | Responses to severe weather events were delivered in accordance with the Severe Weather Plan | Responses to severe weather events were delivered in accordance with the Severe Weather Plan but with minor issues experienced | Responses to severe weather events were not delivered in accordance with the Severe Weather Plan or with major issues experienced
| Count of Method of scoring | Method of scoring
| Goal Ref | CH | CP | O | ES | EC | Grand Total
| 1 | 1 | 3 | 1 |  |  | 5
| 2 | 1 | 3 | 2 | 11 | 3 | 20
| 3 |  |  |  | 8 | 1 | 9
| 4 | 2 | 2 | 1 | 4 | 1 | 10
| 5 | 3 | 1 | 2 | 5 | 1 | 12
| Grand Total | 7 | 9 | 6 | 28 | 6 | 56
[17 empty] | Strategic Goal | CH | CP | O | ES | EC | Total
[17 empty] | Trusted Service | 1 | 3 | 1 | 0 | 0 | 5
[17 empty] | Delivery | 1 | 3 | 2 | 11 | 3 | 20
[17 empty] | Sustainability | 0 | 0 | 0 | 8 | 1 | 9
[17 empty] | Safety | 2 | 2 | 1 | 4 | 1 | 10
[17 empty] | Asset | 3 | 1 | 2 | 5 | 1 | 12
[17 empty] | Total | 7 | 9 | 6 | 28 | 6 | 56

## Glossary
Glossary
Term | Meaning
AirsWEB | Accident and Incident Reporting System
AMO | Asset Management Office
AMOR | Asset Maintenance and Operational Requirements within ASC and MAC retrofit
API | Area Performance Indicator
ASC | Asset Support Contract
CDM | Construction (Design and Management) Regulations 2007
CDM-C | CDM Coordinator
DfT | Department for Transport
ECI | Early Contractor Involvement
EnvIS | Environmental Information System
EPA | Environmental Protection Act
FYB | Full Year Budget
FYP | Full Year Projection
H&S | Health & Safety
HA | The Highways Agency
HAIL | HA Information Line
HADDMS | HA Drainage Data Management System
HAGDMS | HA Geotechnical Data Management System
HAPMS | HA Pavement Management System
IAN | Interim Advice Note
KPI | Key Performance Indicator
LA | Local Authority
LNMS | Local Network Management Scheme
MST | Motivating Success Toolkit
NCR | Non-Conformity Report
NDD | Network Deivery & Development Directorate
NDDPG | NDD Performance Group
NMM | Network Management Manual
NOG | National Operations Group
PAF | Performance Audit Function
PMAG | Performance Management Advisory Group
PMF | Performance Management Framework
PWC | Providers Works Cost
QMP | Quality Management Point
QMS | Quality Management System
QS | Quantity Surveying
RAG | Red/Amber/Green scoring system
RSA | Road Safety Audit
RWSC | Routine & Winter Service Code
SMIS | Structures Management Information System
SP | Service Provider
SQR | Service Quality Review
SRW | Schedule of Roadworks (system)
TM | Traffic Management
VM | Value Management
WD | Working Day
WebDAS | Departures Approvals System
WRF | Winter Reporting Form

## DPCache
Goal Ref | HA Goal | Lever Ref | Lever | Old MAC Ref | NEW ASC Ref | Method of scoring
1 | WE PROVIDE A SERVICE THAT OUR CUSTOMERS TRUST | 1.1 | CUSTOMERS ARE SATISFIED | - | 1.1a | CP
1 | WE PROVIDE A SERVICE THAT OUR CUSTOMERS TRUST | 1.2 | INFORMATION ON OCCUPANCIES IS AVAILABLE | 1.1.1a | 1.2a | CH
1 | WE PROVIDE A SERVICE THAT OUR CUSTOMERS TRUST | 1.3 | MINIMISE ADVERSE IMPACT ON ROAD USERS | - | 1.3a | CP
1 | WE PROVIDE A SERVICE THAT OUR CUSTOMERS TRUST | 1.3 | MINIMISE ADVERSE IMPACT ON ROAD USERS | - | 1.3b | CP
1 | WE PROVIDE A SERVICE THAT OUR CUSTOMERS TRUST | 1.4 | INCIDENTS ARE MANAGED TO MINIMISE DISRUPTION | 1.1.2a | 1.4a | O
2 | WE SET THE STANDARD FOR DELIVERY | 2.1 | THE RIGHT PEOPLE, PROCESSES AND SYSTEMS ARE IN PLACE | 2.1.1a | 2.1a | CP
2 | WE SET THE STANDARD FOR DELIVERY | 2.1 | THE RIGHT PEOPLE, PROCESSES AND SYSTEMS ARE IN PLACE | 2.1.1b | 2.1b | CP
2 | WE SET THE STANDARD FOR DELIVERY | 2.1 | THE RIGHT PEOPLE, PROCESSES AND SYSTEMS ARE IN PLACE | 2.2.1b 2.2.1c | 2.1c | ES
2 | WE SET THE STANDARD FOR DELIVERY | 2.1 | THE RIGHT PEOPLE, PROCESSES AND SYSTEMS ARE IN PLACE | 2.2.1b 2.2.1c | 2.1d | ES
2 | WE SET THE STANDARD FOR DELIVERY | 2.1 | THE RIGHT PEOPLE, PROCESSES AND SYSTEMS ARE IN PLACE | 2.2.1b 2.2.1c | 2.1e | ES
2 | WE SET THE STANDARD FOR DELIVERY | 2.1 | THE RIGHT PEOPLE, PROCESSES AND SYSTEMS ARE IN PLACE | 2.2.1b 2.2.1c | 2.1f | ES
2 | WE SET THE STANDARD FOR DELIVERY | 2.1 | THE RIGHT PEOPLE, PROCESSES AND SYSTEMS ARE IN PLACE | 2.2.1d | 2.1g | ES
2 | WE SET THE STANDARD FOR DELIVERY | 2.1 | THE RIGHT PEOPLE, PROCESSES AND SYSTEMS ARE IN PLACE | 2.2.1d | 2.1h | ES
2 | WE SET THE STANDARD FOR DELIVERY | 2.1 | THE RIGHT PEOPLE, PROCESSES AND SYSTEMS ARE IN PLACE | 2.2.1e | 2.1i | ES
2 | WE SET THE STANDARD FOR DELIVERY | 2.1 | THE RIGHT PEOPLE, PROCESSES AND SYSTEMS ARE IN PLACE | - | 2.1j | CH
2 | WE SET THE STANDARD FOR DELIVERY | 2.2 | MANAGE CONTRACTS EFFICIENTLY | 2.2.1a | 2.2a | CP
2 | WE SET THE STANDARD FOR DELIVERY | 2.2 | MANAGE CONTRACTS EFFICIENTLY | - | 2.2b | EC
2 | WE SET THE STANDARD FOR DELIVERY | 2.2 | MANAGE CONTRACTS EFFICIENTLY | 2.1.1c | 2.2c | EC
2 | WE SET THE STANDARD FOR DELIVERY | 2.2 | MANAGE CONTRACTS EFFICIENTLY | - | 2.2d | EC
2 | WE SET THE STANDARD FOR DELIVERY | 2.2 | MANAGE CONTRACTS EFFICIENTLY | - | 2.2e | ES
2 | WE SET THE STANDARD FOR DELIVERY | 2.2 | MANAGE CONTRACTS EFFICIENTLY | - | 2.2f | ES
2 | WE SET THE STANDARD FOR DELIVERY | 2.2 | MANAGE CONTRACTS EFFICIENTLY | - | 2.2g | ES
2 | WE SET THE STANDARD FOR DELIVERY | 2.3 | ASSET RENEWAL AND IMPROVEMENT SCHEMES ARE DELIVERED TO PLAN | 2.2.2a | 2.3a | O
2 | WE SET THE STANDARD FOR DELIVERY | 2.3 | ASSET RENEWAL AND IMPROVEMENT SCHEMES ARE DELIVERED TO PLAN | 2.2.3a | 2.3b | O
2 | WE SET THE STANDARD FOR DELIVERY | 2.3 | ASSET RENEWAL AND IMPROVEMENT SCHEMES ARE DELIVERED TO PLAN | 5.2.1b | 2.3c | ES
3 | WE DELIVER SUSTAINABLE SOLUTIONS | 3.1 | THE IMPACT OF OUR NETWORK ON THE ENVIRONMENT IS MITIGATED | 3.1.1b | 3.1a | ES
3 | WE DELIVER SUSTAINABLE SOLUTIONS | 3.2 | RESOURCES ARE USED EFFICIENTLY | 3.1.1c | 3.2a | ES
3 | WE DELIVER SUSTAINABLE SOLUTIONS | 3.2 | RESOURCES ARE USED EFFICIENTLY | - | 3.2b | ES
3 | WE DELIVER SUSTAINABLE SOLUTIONS | 3.2 | RESOURCES ARE USED EFFICIENTLY | - | 3.2c | ES
3 | WE DELIVER SUSTAINABLE SOLUTIONS | 3.2 | RESOURCES ARE USED EFFICIENTLY | - | 3.2d | ES
3 | WE DELIVER SUSTAINABLE SOLUTIONS | 3.3 | CARBON EMISSIONS ARE REDUCED | 3.1.1d | 3.3a | EC
3 | WE DELIVER SUSTAINABLE SOLUTIONS | 3.4 | NETWORK IMPROVEMENTS THAT SUPPORT SPATIAL, ECONOMIC AND ENVIRONMENTAL PRIORITIES ARE PROMOTED | 3.2.1b | 3.4a | ES
3 | WE DELIVER SUSTAINABLE SOLUTIONS | 3.5 | THE IMPACT OF OUR NETWORK ON ADJACENT COMMUNITIES IS MITIGATED | - | 3.5a | ES
3 | WE DELIVER SUSTAINABLE SOLUTIONS | 3.5 | THE IMPACT OF OUR NETWORK ON ADJACENT COMMUNITIES IS MITIGATED | - | 3.5b | ES
4 | OUR ROADS ARE THE SAFEST IN THE WORLD | 4.1 | A SAFE NETWORK IS MAINTAINED | - | 4.1a | CH
4 | OUR ROADS ARE THE SAFEST IN THE WORLD | 4.1 | A SAFE NETWORK IS MAINTAINED | - | 4.1b | CP
4 | OUR ROADS ARE THE SAFEST IN THE WORLD | 4.1 | A SAFE NETWORK IS MAINTAINED | - | 4.1c | O
4 | OUR ROADS ARE THE SAFEST IN THE WORLD | 4.1 | A SAFE NETWORK IS MAINTAINED | - | 4.1d | ES
4 | OUR ROADS ARE THE SAFEST IN THE WORLD | 4.1 | A SAFE NETWORK IS MAINTAINED | - | 4.1e | CP
4 | OUR ROADS ARE THE SAFEST IN THE WORLD | 4.1 | A SAFE NETWORK IS MAINTAINED | - | 4.1f | ES
4 | OUR ROADS ARE THE SAFEST IN THE WORLD | 4.2 | A SAFE NETWORK IS PROVIDED | 4.2.1a | 4.2a | ES
4 | OUR ROADS ARE THE SAFEST IN THE WORLD | 4.2 | A SAFE NETWORK IS PROVIDED | - | 4.2b | EC
4 | OUR ROADS ARE THE SAFEST IN THE WORLD | 4.3 | SAFETY INCIDENTS INVOLVING HA AND CONTRACTORS ARE REDUCED | 4.3.1b | 4.3a | CH
4 | OUR ROADS ARE THE SAFEST IN THE WORLD | 4.3 | SAFETY INCIDENTS INVOLVING HA AND CONTRACTORS ARE REDUCED | 4.3.1a | 4.3b | ES
5 | OUR NETWORK IS A DYNAMIC & RESILIENT ASSET | 5.1 | INFORMATION IS AVAILABLE TO SUPPORT EFFECTIVE DECISION-MAKING | 5.1.1a | 5.1a | ES
5 | OUR NETWORK IS A DYNAMIC & RESILIENT ASSET | 5.1 | INFORMATION IS AVAILABLE TO SUPPORT EFFECTIVE DECISION-MAKING | 5.1.1b | 5.1b | ES
5 | OUR NETWORK IS A DYNAMIC & RESILIENT ASSET | 5.1 | INFORMATION IS AVAILABLE TO SUPPORT EFFECTIVE DECISION-MAKING | 5.1.1c | 5.1c | EC
5 | OUR NETWORK IS A DYNAMIC & RESILIENT ASSET | 5.2 | LONG TERM INTEGRITY OF THE ASSET IS SUSTAINED | - | 5.2a | CP
5 | OUR NETWORK IS A DYNAMIC & RESILIENT ASSET | 5.2 | LONG TERM INTEGRITY OF THE ASSET IS SUSTAINED | 5.2.1a | 5.2b | ES
5 | OUR NETWORK IS A DYNAMIC & RESILIENT ASSET | 5.2 | LONG TERM INTEGRITY OF THE ASSET IS SUSTAINED | 5.2.1a | 5.2c | ES
5 | OUR NETWORK IS A DYNAMIC & RESILIENT ASSET | 5.3 | THE NETWORK IS AVAILABLE DURING SEVERE WEATHER EVENTS | 4.1.2c | 5.3a | CH
5 | OUR NETWORK IS A DYNAMIC & RESILIENT ASSET | 5.3 | THE NETWORK IS AVAILABLE DURING SEVERE WEATHER EVENTS | 4.1.2a | 5.3b | CH
5 | OUR NETWORK IS A DYNAMIC & RESILIENT ASSET | 5.3 | THE NETWORK IS AVAILABLE DURING SEVERE WEATHER EVENTS | 4.1.2b | 5.3c | CH
5 | OUR NETWORK IS A DYNAMIC & RESILIENT ASSET | 5.3 | THE NETWORK IS AVAILABLE DURING SEVERE WEATHER EVENTS | - | 5.3d | O
5 | OUR NETWORK IS A DYNAMIC & RESILIENT ASSET | 5.3 | THE NETWORK IS AVAILABLE DURING SEVERE WEATHER EVENTS | - | 5.3e | O
5 | OUR NETWORK IS A DYNAMIC & RESILIENT ASSET | 5.3 | THE NETWORK IS AVAILABLE DURING SEVERE WEATHER EVENTS | - | 5.3f | ES