## Sheet1
Highways Agency Confirmation of Task Order
Confidential and Commercially Sensitive Information which shall not be disclosed to third parties
Supplier: | HALCROW | Sub Region: |  |  | North East
Project Title: | Tees Valley Aimsun model (2015 matrices)
Contract Ref. | 114/2/1391/3 | CPA No.: | 4078441 |  | BPA No.: | 4085566
PIN Description: | Spatial Planning | Sub Pin: | 2c |  | PIN No.: | 517414
HA Reference: | Y&NE 78 15/16HAL | HA Ordering Officer:
Consultant Ref: | V3BB006 (491064.BB.01.25) | Consultant Contact:
Start & End Date: | 15/06/2015 - 29/01/2016 | CTO Authorisation No. |  |  | 71415
Task Overview
This task involves the preparation of a calibrated and validated Aimsun model. The consultant will: • Collate and review the traffic survey data. • Sense check the traffic movements and journey times. • Liaise with survey company to understand the current rules in place to eliminate outlying results. • Highlight potential errors and collaborating with survey company for possible solutions. Once the consultant is satisfied that the survey data is accurate, they will: • Generate the trip matrices and distribute to Aimsun network. • Undertake the calibration and validation process and prepare the LMVR (local model validation report). The consultant will present the model and the LMVR to the project sponsor.
Task Objectives and Milestones
Produce a calibrated and validated Tees Valley Aimsun model.
Task Outcomes
A validated model to send to TAME for assessment and approval.
Project Risk and Management
Medium/Low: Delays in obtaining survey data.
Project Title: | Tees Valley Aimsun model (2015 matrices) |  |  |  | HA Reference: | Y&NE 78 15/16HAL
HA Project Sponsor | Sign: |  | Print Name: |  |  | Date: 12/6/2015
Management Approver: | Sign: |  | Print Name: |  |  | Date: 12/6/2015
Contractual Approval: |  |  | Print Name: |  |  | Date: 12/6/2015
Fee Type: | Target Cost |  | Sub Region: |  | North East
Notification of Non Conflict: | has signed the notification of non conflict or management of conflict for this task
Task History Record | Fee Estimate for the Task set out in this CTO | Invoiced Amount/Estimate this Financial Year |  | Date CTO Confirmed | Fee Amount Requested | HA Sponsor
Y&NE 78 15/16HAL | 39484.94 | 0 |  | 2015-06-15 | 39484.94
Fee Estimate / Fee Requested for the scope on this CTO |  |  |  |  | 39484.94
Carry over Amount from previous financial year |  |  |  |  | 0
Previously Invoiced Amount |  |  |  |  | 0
Cumulative Project Fee Estimate (this financial year) |  |  |  |  | 39484.94
Total Project Fee Estimate |  |  |  |  | 39484.94
Name | Grade | Hours |  | Hourly Rate | (£)
|  |  | @ |  | 0
|  |  | @ |  | 0
|  |  | @ |  | 0
|  |  | @ |  | 0
|  |  | @ |  | 0
|  |  | @ |  | 0
|  |  | @ |  | 0
|  |  | @ |  | 0
Date Produced: | 2015-06-15 |  | Works Total |  | 39484.94
Confidential and commercially sensitive information which shall not be disclosed to third parties
|  |  | Sub Total |  | 39484.94
|  |  | Expenses |  | 200
COMMERCIAL RESTRICTED / FINANCE FILE ONLY |  |  | Total |  | 39684.94