MEDICAL NON-EMERGENCY TRANSPORT SERVICES

Document 2- MOI-Selection Questionnaire states:

“2.1 Background and Context to the Procurement.

NHS Vale of York CCG are conducting this procurement on behalf of itself and NHS Scarborough and Ryedale CCG. There may potentially be other Contracting Authorities within the region that wish to join this procurement exercise in the future. This will be confirmed at ITT stage.

4.1 Procurement Timeline

The timeline ……. It should be noted that the dates are expected dates at the time of issuing this MOI and may be subject to change.”

The following CCG’s will now be included as part of this tender:

NHS Harrogate & Rural District CCG

NHS Hambleton Richmondshire & Whitby CCG

In order to allow the requirements of the additional 2 CCG’s to be included in the tender documentation and for the requisite notice to be served, a decision has been made to extend the timeline and the go live date is now 1 July 2018.

The original OJEU advert stated a total contract value for the 5 years plus optional extension of 2 years of circa £21million (£3m pa). This figure will now be circa £30million (£4.3m pa).

Below is the revised timetable for this procurement exercise:

| TIMETABLE |  |
| --- | --- |
| Activity | Date |
| Relaunch SQ | Mon 3 July 2017 |
| SQ Returned | No Later than Noon on Mon 24 July |
| Evaluation | Tues 25 July – Fri 4 Aug |
| Feedback letters issues and shortlisted bidders informed | w/c 7 August |
| ITT Live | Mon 18 September |
| ITT Return | Fri 27 October |
| Evaluation | Tues 31 October - Mon 4 December |
| Board Approvals | December 17 / January 18 |
| Alcatel Period | 5 January - 15 January 18 |
| Tender Award | 16th January 2018 |
| Mobilisation | 5 1/2 months |
| Contract Start Date | 1st July 2018 |

Based on the revisions to the original requirement, NHS Vale of York CCG is extending the SQ period to allow any additional organisations to express their interest and complete the SQ questionnaire.

Any existing organisations, who have already submitted a bid, DO NOT HAVE to resubmit their questionnaire.