## Budget
BILL OF QUANTITIES
DRAINAGE RENOVATION:
SANDY LANE FORMER CRICKET GROUND
AT
NORTH BADDESLEY RECREATION GROUND
[5 empty] | DATE: | 2024-02-06
ITEM | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT | Provisional
1 | PRELIMINARIES
1.1 | Allow for insurance of the works, materials, plant & equipment | Item |  | INCL. | INCLUDED
1.2 | Allow for site base establishment, storage & access arrangements | Item
1.3 | Transport of plant & equipment, return | Item
1.4 | Welfare provision overheads | Item
1.5 | Setting out of the works | Item
1.6 | Management & Supervision for the duration of the contract. | Item
1.7 | Other: (Material Testing) | Item
| Total Carried Forward to Summary |  |  |  | 0
ITEM | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
2 | PREPARATORY WORK
2.1 | Protect cricket square, allow for plywood boards to trenching zone and barrier tape/pegs | Item | 1
2.2 | Clearance, remove all debris, disused features | Item | 1
2.3 | De-silt outfall point, clear weeds and check headwall arrangement | lin.m | 1
2.4 | Topsoil strip & mound for spoil deposition banks around the site periphery | Item | 1
| Total Carried Forward to Summary |  |  |  | 0
ITEM | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
3 | PRIMARY DRAINAGE
3.1 | Drainage Pipe Installation
3.1.1 | Excavate for, supply & lay 150mm Ø main drain sealed pipe, backfilled with selected soil, incl. 100mm Rootzone to the surface | Lm | 115
3.1.2 | Excavate for, supply & lay 150mm Ø main drain, perforated pipe PROVISIONAL ITEM | Lm | 0 | EXCL. | EXCLUDED
3.1.3 | 1) Excavate for, supply & lay 80mm Ø lateral drains at 8m centres | Lm | 1394
| 2) 110mm main pipe | Lm | 0 |  |  | REMOVED
3.1.4 | Backfill perforated pipes | Lm | 1394
3.2 | Connect new main to a new headwall in at the outfall point in the existing woodland | Item | 1
3.3 | Install silt chambers | Nr | 2
3.4 | Treatment of existing silt chambers; | Nr | 2
3.5 | Allow for all lateral junctions. | Nr | 21
3.6 | Allow for all end caps. | Nr | 16
3.7 | Filter-wrapping of 80 & 110mm pipes - extra-over amount for filter-wrapping to all perforated pipes PROVISIONAL ITEM | Item | 0 |  |  | REMOVED
3.8 | Allow for topping up of drain runs POVISIONAL ITEM | Item | 1
3.9 | Install 225mm x 2m Twin Wall pipe in woodland path area and backfill with as dug arisings | Item | 1
NB: | All spoil to be spread on site in approved positions
| Carried Forward |  |  |  | 0
ITEM | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
4 | CULTIVATIONS & SEEDING
4.1 | Hand-pick and/or brush-up stones arising from the drainage trenching works and cart to tip. | Item | 1
4.2 | Vertidrain x1 passes | m² | 15100 |  |  | Singe Visit
4.3 | Surface re-levelling - working area less cricket square, using Koro Field Top Maker or similar | m² | 15100 |  |  | REMOVED
4.4 | Overseeding - overseed the whole pitch and outfield area using an approved sportsfield ryegrass mix | m² | 15100
4.5 | Liming - apply approved liming compound following soil testing recommendations | m² | 0 |  |  | REMOVED
4.6 | Fertilising - apply pre-seeding fertiliser | m² | 15100 |  |  | REMOVED
4.7 | Hydroseeding to lateral and sub-main drainlines PROVISIONAL ITEM | Lin.m | 0 |  |  | REMOVED
4.8 | Supply and spread topdressing sand to pitches 1 & 2 PROVISIONAL ITEM | m² | 8064
| Total Carried Forward to Summary |  |  |  | 0
ITEM | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
5 | RENOVATION & MAINTENANCE
5.1 | Tidy and renovate all other working areas | Item | 1
5.2 | Rolling, prior to the first cut | m² | 15100
5.3 | Mowing; first cut only | m² | 15100
5.4 | Allow for a decompaction operation to relieve compaction x 1 operations | m² | 15100 |  |  | REMOVED
5.5 | Allow for supplying and applying a broad-spectrum selective herbicide in accordance with the manufacturer’s instructions and all current legislation | m² | 0 |  |  | REMOVED
5.6 | Supply and evenly apply a granular fertilizer with an analysis of 16:6:6 or approved equivalent product at a rate of 350 kg/ha. | m² | 0 |  |  | REMOVED
5.7 | As 5.7, but apply a slow-release fertiliser | m² | 0 |  |  | REMOVED
5.8 | Install new cricket square water supply pipe and fittings | Item | 0 |  |  | REMOVED
5.9 | 1) Full maintenance up to the point of first cut mowing | Item | 0 | EXCL. | EXCLUDED
| 2) Provide 12 months full maintenance from the date of practical completion of the above works. PROVISIONAL ITEM | Item | 0 |  |  | REMOVED
| Total Carried Forward to Summary |  |  |  | 0
ITEM | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
6 | SECONDARY DRAINAGE
6.1 | Supply and install secondary drainage scheme comprising Top Drain Sand Slits installed using GKB Drainmaster. Sand Slits to comprise 40 mm wide x 200 mm deep exavated trenches @ 0.50 m centres backfilled with medium/fine sand to the surface. Remove drainage arisings to disposal on-site. | m² | 8064
ALTERNATIVE OPTION:
6.2 | Supply and install Sand Slit secondary drainage comprising 50 mm wide x 300 mm deep excavated trenches (AFT Wizz Wheel 75 + Agricultural tractor fitted with LGP tyres and GPS auto-steer) installed at 1.00 m centres and then backfilled with 2/6 mm washed gravel to within 150 of the surface and then washed medium/fine sand to the surface. Remove drainage arisings to disposal on-site. | m² | 8064
PROVISIONAL ITEM
We have priced for a Sand Slitting option as this secondary drainage will work more effectively with the 8m spacings on the primary laterals
| Total Carried Forward to Summary |  |  |  | 0
SUMMARY
1 | PRELIMINARIES |  |  |  | 0
2 | PREPARATORY WORK |  |  |  | 0
3 | PRIMARY DRAINAGE |  |  |  | 0
4 | CULTIVATIONS & SEEDING |  |  |  | 0
5 | RENOVATION & MAINTENANCE |  |  |  | 0
6 | SECONDARY DRAINAGE |  |  |  | 0
| GRAND TOTAL |  |  |  | 0
PLUS VAT
[CLIENT: ADD CONTINGENCY, VAT]