Schedule 8 (Implementation Plan and Testing)

Part A - Implementation

- definitions

  - In this Schedule, the following words shall have the following meanings and they shall supplement Schedule 1 (Definitions):

| “APHWS Supplier” | The supplier appointed to provide the web services described in Schedule 2 (Specification); |
| --- | --- |
| "Delay" | - a delay in the Achievement of a Milestone by its Milestone Date; or - a delay in the design, development, testing or implementation of a Deliverable by the relevant date set out in the Implementation Plan; |
| "Deliverable Item" | an item or feature in the supply of the Deliverables delivered or to be delivered by the Supplier at or before a Milestone Date listed in the Implementation Plan; |
| “Implementation Period" | has the meaning given to it in Paragraph 7.1; |
| “Users” | Has the meaning given to it in the Specification (Schedule 2). |

- Agreeing and following the Implementation Plan

  - A draft of the Implementation Plan is set out in the Annex to this Schedule.  The Supplier shall provide a further draft Implementation Plan Ten (10) Working Days after the Effective Date, which will set out the timescales for ensuring that the Supplier’s full Service obligations will formally be assumed on the Start Date.

  - The draft Implementation Plan:

    - must contain information at the level of detail necessary to manage the implementation stage effectively and as the Buyer may otherwise require; and

    - it shall take account of all dependencies known to, or which should reasonably be known to, the Supplier.

  - Following receipt of the draft Implementation Plan from the Supplier, the Parties shall use reasonable endeavours to agree the contents of the Implementation Plan. If the Parties are unable to agree the contents of the Implementation Plan within twenty (20) Working Days of its submission, then such Dispute shall be resolved in accordance with the Dispute Resolution Procedure.

  - The Supplier shall provide each of the Deliverable Items identified in the Implementation Plan by the date assigned to that Deliverable Item in the Implementation Plan so as to ensure that each Milestone identified in the Implementation Plan is Achieved on or before its Milestone Date.

  - The Supplier shall monitor its performance against the Implementation Plan and Milestones (if any) and report to the Buyer on such performance.

- Reviewing and changing the Implementation Plan

  - Subject to Paragraph 4.3, the Supplier shall keep the Implementation Plan under review in accordance with the Buyer’s instructions and ensure that it is updated on a regular basis.

  - The Buyer shall have the right to require the Supplier to include any reasonable changes or provisions in each version of the Implementation Plan.

  - Changes to any Milestones and Delay Payments shall only be made in accordance with the Variation Procedure.

  - Time in relation to compliance with the Implementation Plan shall be of the essence and failure of the Supplier to comply with the Implementation Plan shall be a material Default.

- Not Applicable

- What to do if there is a Delay

  - If the Supplier becomes aware that there is, or there is reasonably likely to be, a Delay under this Contract it shall:

    - notify the Buyer as soon as practically possible and no later than within two (2) Working Days from becoming aware of the Delay or anticipated Delay;

    - include in its notification an explanation of the actual or anticipated impact of the Delay;

    - comply with the Buyer’s instructions in order to address the impact of the Delay or anticipated Delay; and

    - use all reasonable endeavours to eliminate or mitigate the consequences of any Delay or anticipated Delay.

- Compensation for a Delay

  - If Delay Payments have been included in the Implementation Plan and a Milestone has not been achieved by the relevant Milestone Date, the Supplier shall pay to the Buyer such Delay Payments (calculated as set out by the Buyer in the Implementation Plan) and the following provisions shall apply:

    - the Supplier acknowledges and agrees that any Delay Payment is a price adjustment and not an estimate of the Loss that may be suffered by the Buyer as a result of the Supplier’s failure to Achieve the corresponding Milestone;

    - Delay Payments shall be the Buyer's exclusive financial remedy for the Supplier’s failure to Achieve a Milestone by its Milestone Date except where:

      - the Buyer is otherwise entitled to or does terminate this Contract pursuant to Clause 10.4 (When the Buyer can end this contract); or

      - the delay exceeds the number of days (the "Delay Period Limit") specified in the Implementation Plan commencing on the relevant Milestone Date;

    - the Delay Payments will accrue on a daily basis from the relevant Milestone Date until the date when the Milestone is Achieved;

    - no payment or other act or omission of the Buyer shall in any way affect the rights of the Buyer to recover the Delay Payments or be deemed to be a waiver of the right of the Buyer to recover any such damages; and

    - Delay Payments shall not be subject to or count towards any limitation on liability set out in Clause 11 (How much you can be held responsible for).

- Implementation Plan

  - The Implementation Period will be a two (2) Month period.

  - During the Implementation Period, the incumbent supplier shall retain full responsibility for all existing services until the Start Date or as otherwise formally agreed with the Buyer. The Supplier's full service obligations shall formally be assumed on the Start Date as set out in Award Form.

  - In accordance with the Implementation Plan, the Supplier shall:

    - work cooperatively and in partnership with the Buyer and incumbent supplier, where applicable, to understand the scope of Services to ensure a mutually beneficial transition of the Services to the Supplier;

    - work with the incumbent supplier, APHWS Supplier and Buyer to assess the scope of the Services and prepare a plan which demonstrates how they will onboard and transition the public sector Users of the Service from the incumbent to the Supplier;

    - enter into a licence with the APHWS Supplier to ensure that the APHWS Supplier may use the data to fulfil its contractual obligations;

    - liaise with the incumbent Supplier to enable the full completion of the Implementation Period activities; and

    - produce an Implementation Plan, to be agreed by the Buyer, for carrying out the requirements within the Implementation Period including, key Milestones and dependencies.

  - The Implementation Plan will include detail stating:

    - How the Supplier will set up and test its ordering system to enable Users to order data from the Start Data;

    - how the Supplier will work with the incumbent Supplier and the Buyer Authorised Representative to secure agreement, transfer and load up information about the Users of the current service;

    - how the Supplier will issue new licences to current Users, and on board any new Users wishing to use the Service;

    - how the Supplier will work with the APHWS Supplier to transfer details of Users who are eligible to access the web services of the APHWS Supplier in a GDPR compliant way including capturing and uploading information such as the details of Users;

    - how the Supplier will transfer the data both initially and for updates to the APHDS Supplier to enable both to upload data in order to provide each of the respective web services;

    - develop the support resources required for Users as described in the Specification (Schedule 2), and make these available for use;

    - a communications plan, to be produced and implemented by the Supplier, but to be agreed with the Buyer, including the frequency, responsibility for and nature of communication with the Buyer, organisations mentioned in 7.4.7 below and end Users of the Services; and

    - details of how the Supplier will link in with the Buyer’s other public sector contracted suppliers including, for example, Ordnance Survey and Royal Mail, and the APHWS Supplier.

  - In addition, the Supplier shall:

    - appoint a Supplier Authorised Representative who shall be responsible for the management of the Implementation Period, to ensure that the Implementation Period is planned and resourced adequately, and who will act as a point of contact for the Buyer;

    - mobilise all the Services specified in the Specification within the Contract;

    - manage and report progress against the Implementation Plan;

    - construct and maintain an Implementation risk and issue register in conjunction with the Buyer detailing how risks and issues will be effectively communicated to the Buyer in order to mitigate them;

    - attend progress meetings (frequency of such meetings shall be as set out in the Award Form) in accordance with the Buyer's requirements during the Implementation Period. Implementation meetings shall be chaired by the Buyer and all meeting minutes shall be kept and published by the Supplier; and

    - ensure that all risks associated with the Implementation Period are minimised to ensure a seamless change of control between incumbent provider and the Supplier.

Annex 1: Implementation Plan

The Implementation Plan is set out below and the Milestones to be Achieved are identified below:

| Milestone | Deliverable Items | Duration | Milestone Date | Buyer Responsibilities | N/A | Delay Payments |
| --- | --- | --- | --- | --- | --- | --- |
| [ ] | [ ] | [ ] | [ ] | [ ] |  | [ ] |
| The Milestones will be Achieved in accordance with this Schedule 8: (Implementation Plan and Testing) For the purposes of Paragraph 9.1.2 the Delay Period Limit shall be [insert number of days]. |  |  |  |  |  |  |

Part B - Testing

- Definitions

  - In this Schedule, the following words shall have the following meanings and they shall supplement Schedule 1 (Definitions):

| "Test Issue Management Log" | a log for the recording of Test Issues as described further in Paragraph 6.3 of this Schedule; |
| --- | --- |
| "Test Reports" | the reports to be produced by the Supplier setting out the results of Tests; |
| "Test Strategy" | a strategy for the conduct of Testing as described further in Paragraph 3.2 of this Schedule; |
| "Test Success Criteria" | in relation to a Test, the test success criteria for that Test as referred to in Paragraph 4 of this Schedule; |

- Continuous testing and monitoring

  - All Tests conducted by the Supplier shall be conducted in accordance with the Test Strategy and the Test Plan, and collectively form the basis of the Service monitoring regime that the Supplier has in place to ensure that each element of the Service is meeting the performance requirements.

  - The Supplier shall use reasonable endeavours to ensure that each of the web services monitoring regime is in place and operational before the date set out in the Implementation Plan for the commencement of each of the web services described in the Specification.

- Planning for testing

  - The Supplier shall develop the final Test Strategy as soon as practicable after the Start Date but in any case no later than twenty (20) Working Days after the Start Date.

  - The final Test Strategy shall include:

    - the process to be used to capture and record Test results and the categorisation of Test Issues;

    - the procedure to be followed should a web service fail a Test, or where the Testing of a Deliverable produces unexpected results, including a procedure for the resolution of Test Issues;

    - the process for the production and maintenance of Test Reports and a sample plan for the resolution of Test Issues;

    - the technical environments required to support the Tests; and

    - the procedure for managing the configuration of the Test environments.

- Preparing for Testing

  - The Supplier shall develop Test Plans for each of the web services described in the Specification and submit these for Approval as soon as practicable but in any case no later than twenty (20) Working Days prior to the start date for the relevant test as specified in the Implementation Plan.

  - Each Test Plan shall include as a minimum:

    - the relevant Test definition and the purpose of the Test, the requirements being Tested and, for each Test, the specific Test Success Criteria to be satisfied; and

  - The Buyer shall not unreasonably withhold or delay its approval of the Test Plan provided that the Supplier shall implement any reasonable requirements of the Buyer in the Test Plan.

- Passing Testing

  - The Test Success Criteria for all Tests shall be agreed between the Parties as part of the relevant Test Plan pursuant to Paragraph 4.

- Performing the tests

  - The Supplier shall manage the progress of Testing in accordance with the relevant Test Plan.

  - The Supplier will provide a Test Report to the Buyer where the Test Success Criteria has failed for more than a 30 minute period. The Test report will include:

    - an overview of the Testing conducted;

    - identification of the relevant Test Success Criteria that have not been satisfied together with the Supplier's explanation of why any criteria have not been met;

    - The steps that were taken in order to resolve the issue and for the Test Success Criteria to be successfully met.

  - The Supplier shall be responsible for maintaining the Test Issue Management Log and for ensuring that its contents accurately represent the current status of each Test Issue at all relevant times.  The Supplier shall make the Test Issue Management Log available to the Buyer upon request.