## Sheet1
CLARIFICATION LOG
Tender: | Design and Build Tender - Heart of Cornwall & Nature Gallery - Royal Institution of Cornwall
Tender Reference: | 01/2024 (02)
Published Date: | 2024-02-23
Version number: | 0.8
Number | Clarification | Response | Reply date
1 | Are there specific days the visits are organised for or can we come at anytime, and also how much time should we allow on site? | 8th February 2-4 and 21st February 1130 – 1330. You don't need to attend a formal site visit. However, staff will only be available to answer any queries on the dates and times specified. You are welcome to visit any time though to look at the spaces. An hour should be plenty. | 2024-01-31
2 | Can subcontracting be utilized for specific components of the project? If so, are there any restrictions or guidelines we should be aware of? | Yes. Subcontracting is allowable. See 4.16 - 4.24 in Tender Vol 1 instructions. Also Volume 2 (Part A) – Supplier Suitability. | 2024-01-31
3 | Our company has recently started trading, and our financial history is limited. How does the procurement process accommodate companies with a short financial trading history? | The tender process is not looking to assess selection based on financial criteria. The evaluations will require that the bidders are able to demonstrate their ability to fulfill the requirements as set out in the brief and they have the necessary skills and experience to achieve this in the quality responses. | 2024-01-31
4 | Could you please provide the estimated value of the contract? This information will help us assess our capacity and commitment appropriately. | The total overall maximum budget for the tender is £1,000,000m (including VAT) with the design element being £100k and £200k (including VAT) and the build aspects for the Works element being between £800k and £900k (including VAT). | 2024-01-31
5 | Who is the current supplier and how long have they been supplying the work? | There is not a current supplier in relation to these galleries. | 2024-01-31
6 | In the Volume 2 (Part A) - Supplier Suitability document, Section 7.4 Technical and professional ability (p.9) we assume that the term Lead Consultant refers to the principal contractor / exhibition builder and that Lead Designer refers to the exhibition designer. Is that correct? | Lead Consultant should read Lead Contractor and Lead Designer would indeed be the exhibition designer. Our apologies for any confusion caused on this point. | 2024-02-06
7 | For the sample projects (2x projects per consultant), we would like to submit a comparative permanent project that completed mid-year 2018 (6 years ago). We were then asked to design and build a second gallery albeit smaller adjacent to the main gallery that completed in 2020. With the Covid impact on the industry between now and then, could this project be accepted as one of the examples? | If this project evidences your experience of providing similar professional services at a scale, size and scope similar to the project under consideration through this tender process, in similar a setting, then yes. The response should include demonstrating successful engagement with clients, key external stakeholders and interest groups, understanding and application of sound project/programme management principles, and the logistical knowledge to deliver projects/programmes on time, to budget and to the expectations of the client and key stakeholders. | 2024-02-06
8 | Would the client accept Pre-Lims, Overhead and Profit and budget costs as a tender return? | Overall RIC is seeking clarity of the the costs included in the return in order to enable evaluations to be undertaken and, for the appointed supplier, clarity on costs to be charged under any resulting contract. Prelims and Overheads and profit can be included in the Price Schedule return under "Other costs". If these are included, please ensure these are clearly stated. | 2024-02-06
9 | What are your values? | Brave Using imagination, creativity and sideways thinking, we thrive on bringing people together for unexpected and unconventional experiences, conversations and interactions. We’re not afraid to stand up for what we believe in, for a better and fairer society for everyone. Welcoming Our spaces and team behaviours/ attitude are warm, safe, open and inclusive. We celebrate difference and work hard to listen and reflect what our diverse community needs – from calming corners to areas bustling with noise and energy – so everyone feels like they belong. Connected We’re in Cornwall and for Cornwall, but we also reach outwards – through stories, collaborations and exhibitions that are relevant in a much wider context, too. We use the expertise and insight from our collections and community to contribute to important conversations locally, nationally and internationally. Curious We’re always asking questions, exploring ideas and challenging ourselves to find new and better ways of doing things – never standing still or taking anything for granted. We’re a museum, but we’re continually re imagining what a museum can be – and the impact it can have. Committed We’re environmentally and socially responsible in everything we do, always looking for ways to reduce our environmental footprint and look after the community we serve. We’re not afraid to take a difficult path or change course if it brings us closer to achieving our purpose. | 2024-02-06
10 | On page 7 of the brief, under project summary it states that the project completion is end December ’24, however page 8 states that Phase 3 (including Heart of Cornwall Gallery / Nature Gallery) completion is March ’26. | Project completion is the end of December 2024. | 2024-02-07
11 | On the programme plan document it lists the following under core requirements: • Conservation Architect / Designer • Quantity Survey • Structural Engineer • Mechanical & Electrical Design • Contract administrator • Principal Designer (CDM Regs) Can you please confirm whether these are subject to a separate contract or whether they are to be provided under this D&B contract (assuming that the exhibition designer is not included in Conservation Architect / Designer)? | Royal institute of Cornwall would be seeking to have one contract with the Lead Contractor. Where the Lead Contractor deems it necessary to engage with others to provide the necessary services in order to undertake the the works, then they will be contract separately by the Lead Contractor as part of their supply chain. | 2024-02-14
12 | Is there a preference as to whether the Exhibition Designer or the Lead contractor take the lead in this tender (I.e. who the contract will be with)? | No preference | 2024-02-14
13 | In the contract document it states: The period for retention following completion or earlier termination is six years. Can you please clarify what this is referring to? Is it a financial retention? If so, can you please provide the percentage value? | Apologies - this should read 6 months at 5 percent. | 2024-02-14
14 | Are both the Lead Contractor and the Lead Designer required to hold the levels of insurance stated – in particular public liability at £10m. This is considerably higher than is normally required from the exhibition designer. | We would be seeking 10m from the Lead Contractor with whom we would be contracted with. | 2024-02-14
15 | Can you please confirm our understanding that the tender return is to be emailed to yourself and not uploaded onto a portal? | Please email to jackie@jackiegeorge.co.uk. If the files are large - then WeTransfer can be used | 2024-02-14
16 | Please confirm the expected extent of completion for December 2024? The wording talks of ‘substantiative completion of construction phase’. Is project completion December 2024, or do you envisage a period of time in 2025 for further works (like object installation?) | Project completion is the end of December 2024. | 2024-02-14
17 | Given there is no design, how are we to present construction costs in the price document? | Budget costs are set out in the ITT document. Ultimately we would expect bidders to provide a bid that sets out the design element - the bidders are then asked to work out (from experience) what remaining element of the budget can be set aside for the build element. | 2024-02-14
18 | Is the cost evaluation based on our fee proposal only, or is it the full quoted costs including fit-out elements (Ie the £1m) | The cost evaluation will be based on your fee proposal. - PLEASE SEE RESPONSE TO QUESTION 48 | 2024-02-23
19 | Are there full survey and drawing information available for the pipework and strip out elements of the proposed spaces for refurbishment? | No, no surveys exist. You should therefore cost for these within your proposal if deemed required. | 2024-02-14
20 | Is it anticipated / hoped we provide a new decoration scheme for the interior of the building including high level painting etc? | Yes | 2024-02-14
21 | Can we assume all engagement and audience work is by others? | Yes | 2024-02-14
22 | Who will provide content for the exhibition? This ranges from historical knowledge through to words, and images for graphics etc. | RCM will provide interpretation content and images, we expect the design company to design and produce the graphic panels, labels and other in gallery interpretation signage. | 2024-02-14
23 | Are there any floor plans we can look at? | Yes, building plans of the museaum are uploaded solely for information purposes : App_1 2012-0022-2 RCM Location codes Level 1 : App1_ 2012-0021-2 RCM Location codes Level 0 : App1_ 2012-0023-1 RCM Location codes Level 2 : App1_ 2012-0024-1 RCM Location codes Level 3 : App1_ 2012-0026-1 RCM Location codes Level 5 : App1_ 2012-0027-1 RCM Location codes Level 6 Along with Interpetation Strategy document and photo of front showing the area to be overhauled. | 2024-02-14
24 | Is the tender open for non UK based bidders? | Yes. | 2024-02-19
25 | Should we include a lighting designer as part of our team? | Yes. | 2024-02-19
26 | Should we include an AV/Digital designer as part of our team or are you looking to tender & contract AV separately? | Yes the AV/ Digital designer should be part of your team. | 2024-02-19
27 | Are the showcases within the Nature gallery controlled? Do the Nature collections require controlled showcase conditions? | We expect that some will require controlled showcase conditions. | 2024-02-19
28 | Would it be possible for you to confirm a Checklist for what is to be returned as part of the Tender? | Tender-Vol 2 - Part A - Sup Suitability_Final_(24.01.2024).docx Tender-Vol 2 - Part B - Sup Offer_Final_(24.01.2024).docx Schedule 1 - Price_Final_29.01.24.xlsx | 2024-02-19
29 | How developed are you expecting the sketch concept to be? | We are not expecting concept designs. We would like to see your approach to similar projects that will provide us with an idea of your design approach. If you do not have similar project experience, concept designs would be appreciated. | 2024-02-19
30 | Please clarify the word limit for: - relevant experience and contract examples for the Lead Consultant, Lead Designer and Cost Manager/QS - descriptions of two projects per consultant Do we need to include the above responses within the Word document supplied or can we create a separate document for this? If we use the Word doc, can we include images as part of the response? | Please look to include within the document provided. | 2024-02-19
31 | We note that section 2.3 within the Tender Volume document states that the core works is the complete redisplay of the ground floor permanent galleries; the Heart of Cornwall Gallery, the Nature Gallery. This work will include the detailed design from RIBA stage 1 for sign off by Royal Cornwall Museum to RIBA stage 6 to include delivery of contract administration, cost control and project management for the management of the construction works and delivery of the build element. Could you clarify the timescales for completion as there seems to be contradictory information within the documents. For example, the procurement timetable states the contract is to end by 31/12/2024, however these do not align with the timescales under section 5. Project Context in Appendix 1 which include completion of: Phase 1 by July 2024 Phase 2 by May 2024 Phase 3 by March 2026 Phase 4 by March 2027. If the completion date is 31/12/2024, can you confirm what needs to be completed by this point? | Project completion is the end of December 2024. | 2024-02-19
32 | We note that section 2.3 within the Tender Volume document states that the core works is the complete redisplay of the ground floor permanent galleries; the Heart of Cornwall Gallery, the Nature Gallery. This work will include the detailed design from RIBA stage 1 for sign off by Royal Cornwall Museum to RIBA stage 6 to include delivery of contract administration, cost control and project management for the management of the construction works and delivery of the build element. Could you clarify the timescales for completion as there seems to be contradictory information within the documents. For example, the procurement timetable states the contract is to end by 31/12/2024, however these do not align with the timescales under section 5. Project Context in Appendix 1 which include completion of: Phase 1 by July 2024; Phase 2 by May 2024; Phase 3 by March 2026; Phase 4 by March 2027. If the completion date is 31/12/2024, can you confirm what needs to be completed by this point? | Full design, build and installation by 31 December 2024. | 2024-02-19
33 | Were you intending to send the Mineral Gallery Interp strategy? Just wanted to know how this is relevant to this next tender (Atrium and Nature)? | We are developing the intepretation strategy. The central themes outlined in the Mineral Gellery strategy will remain the same throughout the museum. The detailed scheme for the nature gallery and Heart of Cornwall is in development. | 2024-02-23
34 | Do you know the core works that will need to be completed before completion date? | Full design, build and installation by 31 December 2024. | 2024-02-23
35 | Are you able to give indication on frequency of meetings for all phases of this project (from appointment to PC) for both Design and offsite Production. How many meetings would you request onsite and how many via Zoom/Teams? | We will be advised by you on this. Onsite meetings welcomed but a mixture is ideal. | 2024-02-23
36 | Do you wish to retain the current cases? | We would like to keep the cases in the Heart of Cornwall Gallery, but are willing to discuss options. | 2024-02-23
37 | What is the situation with the heating system? | Radiant panels are in place and are the only source of heating for the space. These are to be retained. | 2024-02-23
38 | Are the big items to stay? | Yes | 2024-02-23
39 | What are the thoughts about the collections? | The Nature Gallery collections are effective in telling contemporary stories. So the curation idea is to be kept but needs updating. It is currently very text heavy with lots of different fonts. Interactivity is to be retained. | 2024-02-23
40 | How would you like the spaces to be used? | Flexibly. Flexibility is a key word for these spaces. The displays must appeak to a wide audience. | 2024-02-23
41 | Should the cases be conditioned? | Some yes, some no. Details can be provided to the winning team. | 2024-02-23
42 | Do you have any links with academia? | Yes - but sporadic as we are such a small team. | 2024-02-23 | #
43 | Do you require seating? | Yes. Ideally a storage solution to be incorporated also. A variety is required for all ages and abilities. | 2024-02-23
44 | Do you have many school groups? | Yes - most days we have schools visiting. They are almost all primary schools and very much a priority for us. We are looking to increase audiences of all demographics. | 2024-02-23
45 | Do you require Cornish Language translation. | This will be very light touch - Cornish used in a way that is engaging and widens appeal. | 2024-02-23
46 | What is the situation with Branding. | Rebranding is currently underway and will be shared with the successful team. We anticipate that different spaces will have individual look and feel, but still retain a sense of unity with each other and our brand. | 2024-02-23
47 | Can you tell me more about the Main gallery collections. | The collections details are to be discussed further. We wish for audiences to be excited and connected to the Cornish identity. Lighting will need to be changed in the cabinets. More Powerpoints will be required. Wifi coverage is patchy. | 2024-02-23
48 | In question 18 you confirm that the evaluation will be based on the fee only. Can you confirm that within 'schedule 1- Price’ you only want to see a breakdown of fees and that build costs are not to be included? | Original response to Question 18 should be ignored. We have amended sections 3.37 and 3.49 of Volume 1 and uploaded a revised version of the document. We are seeking costs for the design fee element and the total design fee and construction costs. Reference should be made to the updated version of Volume 1 (see Tender-Vol 1-Instructions_Final_(23.02.24)), but in summary evaluations will be based on Quality / Social Value 75% and price 25% - (with Sub-Criteria – Design fee element 20% of 25% and Total bid costs (design and build) 80% of 25%). Please ensure that costs associated with the design element are split out separately from the build costs in the Price Schedule, see Columns “F” and “G”. The total cost should be within the budget as defined in section 2.6 of Tender-Vol 1-Instructions_Final_(23.02.24). | 2024-02-23
49 | In question 22 you confirm that RCM will provide content and images, can you expand on the make up of the RCM project team. ie identify roles such as Education and Learning / Community Engagement / Curatorial / Project Management. | We have a Collections & Engagement Manager, Engagement Manager, Learning Manager and Collections & Engagement Officer who will support with content development. A project support officer will your main contact and we have project manager who is an external Transformation Project Lead. | 2024-02-23
50 | In question 30 you confirm that Question 7.4 is to be answered within the word document. Is it OK to return Tender-Vol 2 - Part B - Sup Offer_Final_(24.01.2024) in our own format? | Yes as long as it is within the word limit. | 2024-02-23
51 | On Schedule 1 price final - it asks for a cost for a feasibility report and business plan? Are we correct to assume this is not required and if it is, what is your expectation? | Feasibility report and business plan are not required. | 2024-02-23
52 | Project commences only by work stage, next one confirmed at each one? | Design development will be an iterative process with the team at the Museum. Progress to the next stage will be confirmed by the museum team. Invoicing should reflect design stages. | 2024-02-23
53 | Can we add appendices for the project examples so that we can include photos? | Yes. | 2024-02-23
54 | You have asked for a ‘sketch concept’ as a creative response. However, in the recent clarifications you have said it is not essential if project examples demonstrate a design approach. Would you clarify this in the interest of a level playing field for all tenderers? Should we submit a sketch concept and what is your expectation? Could you provide a scope and length of this piece of work? Can this be submitted as a separate document as we cannot see where it would be submitted in the word documents? | A sketch is not required as part of the process. Some people may feel they want to include it to illustrate the questions. Your answers to the questions will be scored by the text you supply. A sketch is entirely your choice and not a requirement. This won't be included in the word counr and can be provided as a separate document. | 2024-02-23
Clarifications will be published against the Contract Notice on Contracts Finder.
If interested in tendering for this project please ensure you add a "watch this notice" for alerts as from time to time additional information or clarifications may be published related to this tender.
It will be the responsibility of Bidders to ensure they are aware of all published clarifications and ensure that their bid has taken these into account.
In the event of any queries please contact: