-

:

Joint Schedule 2 (Variation Form)

Crown Copyright 2018

# Joint Schedule 2 (Variation Form)

This form is to be used in order to change a contract in accordance with Clause 24 (Changing the Contract)

| Contract Details |  |  |
| --- | --- | --- |
| This variation is between: | Cabinet Office ("the Buyer") And Mott MacDonald ("the Supplier") |  |
| Contract name: | Routemap International Training ("the Contract") |  |
| Contract reference number: | CCCC21841 |  |
| Details of Proposed Variation |  |  |
| Variation initiated by: | Cabinet Office |  |
| Variation number: | 1 |  |
| Date variation is raised: | 22/03/2022 |  |
| Proposed variation | 12 Month time-only |  |
| Reason for the variation : | Time-only variation to deliver the capability development objectives that the initial contract (CCCC21841) seeks to meet. Two of the trainings that were to be delivered this month have needed to be postponed due to teams in India being badly affected by covid, subsequently reducing capacity and the ability to meet objectives within the original timeframe. |  |
| An Impact Assessment shall be provided within: | nla |  |
| Impact of Variation |  |  |
| Likely impact of the proposed variation: | n/a • |  |
| Outcome of Variation |  |  |
| Contract variation: | This Contract detailed above is varied as follows: - The Call-Off Contract with reference CCCC21 841 is extended for 12 months from 09/04/2022 until 09/04/2023 This extension period is time-only and therefore has no attendant cost, meaning that the original Call-Off Contract Value will not increase from the original awarded value of REDACTED TEXT under FOIA Section 43 Commercial Interests |  |
| Financial variation: | Original Contract Value: | REDACTED TEXT under FOIA Section 43 Commercial Interests |
|  | Additional cost due to variation: | REDACTED TEXT under FOIA Section 43 Commercial Interests |

I

Joint Schedule 2 (Variation Form) Crown Copyright 2018

J   New Contract value:	REDACTED TEXT under FOIA Section 43 Commercial Interests

- This Variation must be agreed and signed by both Parties to the Contract and shall only be effective from the date it is signed by Cabinet Office ["the Buyer"]

- Words and expressions in this Variation shall have the meanings given to them in the Contract.

- The Contract , including any previous Variations, shall remain effective and unaltered except as amended by this Variation.

Signed by an authorized signatory for and on behalf of the Cabinet Office ("the Buyer")

| REDACTED TEXT under FOIA Section 40, Personal Information | REDACTED TEXT under FOIA Section 40, Personal Information |
| --- | --- |
|  | REDACTED TEXT under FOIA Section 40, Personal Information |
|  | REDACTED TEXT under FOIA Section 40, Personal Information |
|  | REDACTED TEXT under FOIA Section 40, Personal Information |
|  | REDACTED TEXT under FOIA Section 40, Personal Information |

Signed by an authorised signatory to sign for and on behalf of the Supplier

CCZI20A11

REDACTED TEXT under FOIA Section 40, Personal Information

Framework Ref : RM6187 Model Version: v3.1