## Sheet1
CLARIFICATION LOG
Tender: | Falmouth Boardwalk Scheme, Swanvale
Tender Reference:
Clarification deadline:
Published Date: | 2021-03-02
Version number: | 2
Number | Clarification | Response | Reply date
1 | Please can you provided a detail drawing showing the composite framework make up? | No the design element of the frame to support the boardwalk is expected to be done by the supplier / installer in such a way that it fulfils the brief | 2021-02-24
2 | Can we offer a different product to Millboard that has been specified, the alternative would have a greater lifespan than Millboard? | The Council will consider an alternative product as long as it is recycled plastic. We would insist that in such situations you provide a quote for Millboard also though, in order to have a direct comparison with other tenderers. | 2021-02-24
3 | We have received a quotation from Millboard for supply only of the deck system that exceeds the projects maximum stated budget of £58,000 , with the costs of installation still to be added. Can you advise if there is more budget available for this project so we can decide how best to progress our quotation. | There is a little more money in our budget that allows for variation to the contract; please go ahead and submit your quote for using the specified product. Also as previously noted we are happy to accept a quote using an alternative solid recycled product as well. | 2021-03-02
In the event of queries please contact: