| CHANGE CONTROL NOTICE (CCN) |  |  |  |
| --- | --- | --- | --- |
| Contract Title: | Contract for the Provision of Government Project Delivery Hub (The Contract) |  |  |
| Contract Reference: | IPA 01 | Contract Change Number: | -1 |
| Date CCN issued: | 07th September 2022 | Date Change Effective from: | 01st September 2022 |
| Between: The Cabinet Office (The Customer) and Connect Internet Solutions Ltd (The Supplier) - The Contract is varied as follows: - An extension for nine months, taking the original end date of 31st August 2022 to 31st May 2023. - A further option to extend for one period of up to three months. - An uplift in value of £26,472.64. (excluding VAT) in total to original contract value of £77,943.40 (excluding VAT). This is £24,344.14 for the initial 9 months making the total Call-Off Contract value £102,287.54 ex VAT and the 3 months is £2,128.50 (excluding VAT). - Bringing the new Total Contract Value to £104,416.04 (Total Cost excluding VAT). - Words and expressions in this Change Control Notice shall have the meanings given to them in the Contract. - The Contract, including any previous Contract changes, authorised in writing by both Parties, shall remain effective and unaltered except as amended by this Change Control Notice. |  |  |  |
| Change authorised to proceed by: (Customer’s representative): 16/09/2022 16/09/2022 Redacted under Section 40, Personal Information Redacted under Section 40, Personal Information Signature Print Name and Job Title Date |  |  |  |
| Authorised for and on behalf of the Supplier: 16/09/2022 16/09/2022 Redacted under Section 40, Personal Information Redacted under Section 40, Personal Information Signature Print Name and Job Title Date |  |  |  |
| Authorised for and on behalf of the Customer: Redacted under Section 40, Personal Information Signature Print Name and Job Title Date 16/09/2022 16/09/2022 Redacted under Section 40, Personal Information |  |  |  |