## Sheet1
TITLE | PRICED RETURN - SCHEDULE OF WORKS
Client : | Environment Agency
Project: | Old Windsor Lock House - Void Refurbishment
Address: | Old Windsor Lock, Old Windsor, Windsor, SL4 2JZ
Contract: | JCT Minor Works
Issue Date: | 2022-08-11
Tender Return Date | Monday 12th September 2022 16:00
Contractor: | tbc
Contents list
Section
A | Preambles
A1 - Environment Agency Priorities
A2 - General
A3 - The Site/Particulars of the Work
A4 - Contract
B | Preliminaries
C | Schedule of Work
D | Pricing Summary Page
Appendicies | Appendix A SHEW CoP
Appendix B - Pre-Construction Information
Appendix C - Drawings
ITEM | DESCRIPTION OF WORKS |  | Unit | Item | Rate | Total
A | PREAMBLES
A1 | ENVIRONMENT AGENCY PRIORITIES
A1.1 | CARE OF THE ENVIRONMENT AND WILDLIFE: The Environment Agency is committed to the care and sustainability of the natural environment and its wildlife. It is essential that the greatest possible care be taken at all times to prevent any damage or pollution to the natural environment and its plant and animal wildlife. |  | - | Note | - | -
A1.2 | ENVIRONMENT AGENCY SITES: Most Environment Agency Sites are located near water with working lock gates and lock staff private facilities. All contractors must liaise with the lock keeper daily and at times when crossing lock gates is necessary and will be directed to work safely and within appropriate timescales |  | - | Note | - | -
A1.3 | PUBLIC ACCESS: Some lock sites have public footpaths across the lock gates and the island sites and the EA are committed to ensuring this access is retained safely throughout the works. It is the contractors responsibility to ensure that all works, including deliveries and transport of materials and equipment to and from site is undertaken in a safe and considerate way limiting risks to the their staff, the general public, EA staff and river users. |  | - | Note | - | -
A1.4 | ENVIRONMENT AGENCYS CORE HEALTH AND SAFETY VALUES ARE: All of us have the right to remain healthy and injury free at work. We are all vital to improving health and safety and we will: · work to prevent all injuries and occupational illnesses · all be responsible for health and safety · always check and learn from what we are doing · challenge and respond to challenge Remember health and safety is a way of life both at home and at work. “Constructing a better environment” applies to all works to residential properties. In all instances the principal contractor and contractor’s performance will be expected to meet or exceed the minimum standards required under the appropriate legislation. |  | - | Note | - | -
A1.5 | COMPETANCE AND TRAINING: TheEnvironment Agency has very specific competence and training requirements as detailed in “Safety is Paramount constructing a better environment”. The PC must ensure these are adhered to: · All operatives must hold a current CSCS card · All supervisors must hold a current SMSTS or SSSTS or CSCS Gold Card · Specific and relevant current qualifications must be held by those undertaking such tasks as erecting and checking scaffolding (CISRS) and scaffold towers (PASMA) or operating MEWP (IPAF) · Full access scaffolding must be erected by a NASC registered scaffolding company and must be tagged prior to use and regularly inspected |  | - | Note | - | -
A2 | GENERALLY
A2.1 | Where proprietary items are specified within this Works section and the preceding section, they must be installed in strict accordance with the manufacturer's recommendations and instructions. |  | - | Note | - | -
A2.2 | All proprietary items are to be installed by contractors approved by the supplier and the Contract Administrator. |  | - | Note | - | -
A2.3 | All provisional sums, provisional quantities and PC Sums are to be directed by the Contract Administrator. |  | - | Note | - | -
A2.4 | The siting of builders skips shall be agreed prior to commencement of works and the Contractor must obtain a licence for any skips deposited on the public highway and to conform to all conditions contained therein. Skips are to be removed from site promptly when full and replaced and provided with a secured cover at all times |  | - | Note | - | -
A2.5 | The siting of contractor's plant and stored materials within the boundaries of the premises are to be agreed with the Contract Administrator. |  | - | Note | - | -
A2.6 | Note: Before tendering, the contractor should examine the drawings and specification documents visible in Appendix to this schedule of works document, visit the site, check all measurements and dimensions and ascertain all local conditions and restrictions, accessibility, the full extent and nature of the work, the supply and conditions affecting labour and the execution of the contract generally. No claims arising from failure to do so will be considered. |  | - | Note | - | -
A3 | THE SITE/PARTICULARS OF THE WORK
A3.1 | DESCRIPTION OF THE WORK: The work comprises the internal redecoration and minor upgrades of the lock keepers house at Old Windsor Lock House. The works include the upgrading of the insulation in various locations, full redecoration throughout, the replacement of first floor carpets, replacement/overhauling of the bathroom and WC as detailed in the Scope of the Works |  | - | Note | - | -
A3.2 | LOCATION: Old Windsor Lock house is located on an island site accessed via a long narrow track which is open to the public and adjoins to the Thames Path. The main lock is located to the front of the property with access across the lock gates. The lock keeper on the site resides in the adjacent Lock Cottage. The house stands within its own privave garden enclosed by low timber fencing separating it from the river and additional land. The main river with weir runs to the rear of the property. The property is vacant for the duration of the contract |  | - | Note | - | -
A3.3 | TIMESCALE FOR COMPLETION OF THE WORKS: The works will be started on site Date to be arranged - Suggested 2 weeks after the acceptance of the tender and the Construction Phase Plan The works will be completed during a 6 week period |  | - | Note | - | -
A3.4 | EMPLOYER: The Environment Agency, Estates Department, Kings Meadow House, Kings Meadow Road, Reading, RG1 8DQ |  | - | Note | - | -
A3.5 | CONTRACT ADMINISTRATOR: (hereinafter referred abbreviated as CA): Mrs P J Salbany, Environment Agency based at Kings Meadow House Mob 07425 620502 (SECONDARY POINT OF CONTACT: Mrs Kathryn Forster, Environment Agency Mob 07795 883547 |  | - | Note | - | -
A3.6 | EA PERSONELLE RESPONSIBLE FOR THE LOCK SITE: Mr Martin Wilson Mob - to be provided once contract awarded |  | - | Note | - | -
A3.7 | EXISTING MAINS/SERVICES: Identify, protect, uphold and maintain any existing services, live drainage, ducts, water, electric, oil and other mains resources found during the carrying out of the Works. If any are damaged reinstate them before leaving site. Be liable for an indemnify The EA against any expense, liability or loss, claim or proceedings provided always that the damage is due to any negligence, omission or default of the Contractor's workpeople or sub-contractors |  | - | Note | - | -
A3.8 | A HEALTH & SAFETY FILE for the site is not available - however information will be passed to the contractor as part of this tender package including; EA SHEW CoP (Safety Health Environment & Wellbeing Code of Practice), Pre-Contruction Information including Asbestos Survey, Drawings including Site Plan, Existing Ground and First Floor Plans & Services Plan. |  | - | Note | - | -
A3.9 | RESTRICTION OF WORKING HOURS: Normal working hours will be 8am - 5.00pm, Monday to Friday - any working outside these hours must be agreed in advance with the CA Contractors are to report to the Lock Keeper daily upon arrival and departure |  | - | Note | - | -
A3.10 | ACCESS TO THE SITE FOR THE WORKS: The access road is adjacent to a bridge with limited visibility. The track is narrow with limited passing places with the river on one side and there is limited parking. The contractor is responsible for ensuring suitable delivery vehicles are provided when bringing materials and equipment to site. Access roads are not to be blocked at any time as access for emergency vehicles is required 24/7 |  | - | Note | - | -
A3.11 | PARKING: Contractors and Employees vehicles - there is limited space for parking vehicles and limited turning space. Parking for a maximum of 1no. Contractor Vans is permitted any additional vehicles or deliveries to be managed with the lock keeper and agreed arrangements with the CA prior to commencement Space to be maintained for emergency vehicles 24/7 |  | - | Note | - | -
A3.12 | SITE FACILITIES/SITE ACCOMMODATION - The house with its services and facilities are available for use througout the contract period. If at any time the WC is out of action due to the works there is an additional facility available for contractor use in the Lock Keepers mess room - this space must be kept clean and tidy and will be used by other EA staff working on site. The kitchen within the house can be used as a contractors mess area during the works |  | - | Note | - | -
A3.13 | SECURITY: Hording, Fences and Gates: There is no public footpath across this island site and the garden is private - however there is access to other areas of the island by members of the public who are making use of mooring facilities. Public access is also permitted within the lock area for boat users and other small craft. It is the Contractors responsibility to keep the works secure and separate from members of the public and other personelle on site. |  | - | Note | - | -
A3.13 | SMOKING/VAPING: Not permitted on site |  | - | Note | - | -
A3.14 | NOISE: The use of radios or other audio equipment is not permitted |  | - | Note | - | -
A3.15 | SITE WASTE MANAGEMENT: The contractor is to separate out construction waste where possible and ensure that all opportunities to reuse and recycle site waste. Making use of a licenced waste carrier that carries out recycling of waste material is essential to this project to manage finite resources and prevent waste and a Waste Transfer Note will be required for all waste removed from site. Burning of waste materials is not permitted on site at any time The contractor must take all reasonable precautions to prevent pollution The use of pesticides and/or biocides is not permitted The site is on a septic tank and as such no waste material is to be flushed down sinks, WCs or drains especially with regards to painting, all brushes are to be cleaned in contractors buckets and any cleaners and thinners are to be taken off site and not discarded down the drains or anywhere else on site |  | - | Note | - | -
A3.16 | DEFECTS IN EXISTING CONSTRUCTION: Report to the CA without delay with possible solutions and prices for rectification where possible |  | - | Note | - | -
A3.17 | HOT WORKS: Hot works are not permitted without the prior approval of the CA and the issue of a Hot Works Permit which the contractor is to self manage |  | - | Note | - | -
A3.18 | NAME BOARDS/ADVERTISMENTS: Contractors name boards or advertisments will not be permitted except with the prior approval of the CA |  | - | Note | - | -
A4 | CONTRACT: JCT MINOR WORKS AGREEMENT
A4.1 | The contract to be used is the JCT Minor Works Contract |  | - | Note | - | -
A4.2 | DATE OF COMMENCEMENT OF THE WORKS: To be agreed |  | - | Note | - | -
A4.3 | LIQUIDATED DAMAGES: £250/week |  | - | Note | - | -
A4.4 | RECTIFICATION PERIOD: 12 months |  | - | Note | - | -
A4.5 | PERCENTAGE OF THE VALUE OF THE WORKS: 95% |  | - | Note | - | -
A4.6 | SUPPLY OF DOCUMENTATION: 3 months |  | - | Note | - | -
A4.7 | CONTRACTORS INSURANCE: Public Liability of £5,000,000.00 The contractor is to arrange Developers Contingency Insurance (Clause 21.2.1) in joint names Before starting works on site the Contractor is to submit documentary evidence of the insurances required by the contract |  | - | Note | - | -
B | PRELIMINARIES
B1.1 | Allow for all necessary preliminaries, plant, machinery, scaffolding where required and attendance, in order to comply with the proceeding and foregoing sections. | £ | 1 | Item
B1.2 | CDM REGULATIONS: Allow for acting as Principle Contractor under CDM regulations, including Health and Safety in line with attached EA SHEW CoP. Include for all H&S Signage, fencing, fire extinguishers, notifications, safety plans and provide information for safety files. The contractor will need to provide details of their proposed working methods at the time of tender to ensure that they have fully considered these requirements. These will be assessed by the project team including the Client, Contract Administrator and Principal Designer/CDM Coordinator as part of the overall selection procedure. | £ | 1 | Item
B1.3 | PROJECT MANAGER - The contractor is to provide a suitably qualified and experience Project Manager and/or Site Foreman as necessary to manage the works throughout the project - With the minimum qualification of Gold CSCS Card, CITB Site Supervision Safety Training Scheme (SSSTS) Certificate or Equivalent (evidence to be provided) | £ | 1 | Item
B1.4 | REPORTING: The Contactor is to allow for regular weekly reporting of progress including any issues to the CA in the form of face to face or virtual meetings. The contractor must inform the CA of any issue as they arrise to ensure they can be dealt with quickly and not cause delay to the works. Should there be any time when the CA cannot be contacted the contractor must manage the works so that progress can be maintained in alternative locations of the site | £ | 1 | Item
B1.5 | WORKING AT HEIGHT: The contractor is to provide safe and suitable means of working at height where required and in accordance with CDM best practice. | £ | 1 | Item
B1.6 | SITE ACCESS: The contractor is to provide safe and suitable access for site operatives and materials. This will include a Site Traffic Managment Plan which must include details on deliveries and storage of materials. Safe passage across the lock gates to the island site must also be included - this could be by hand or by boat but it will be the contractor who must arrange and manage this alongside the direction of the lock keeper. Life jackets will be necessary when working close to water - this includes deliveries to and from the site across the lock gates and within 2m of the waters edge | £ | 1 | Item
B1.7 | SECURITY OF THE BUILDING: The contractor is responsible for ensuring the building is kept secure, wind and watertight at all times. Any damage caused to the building as a result of insufficient security, wind and weatherproofing measures during these works must be immediately remedied at the contractors cost. | £ | 1 | Item
|  | £ | 1 | Item
B1.8 | SEPARATION OF THE WORKS: The Contractor is to include for the provision of warning barriers around the works, including areas used for storage of materials during the course of the contract, inclusive of warning notices and safety tape/bollards etc. | £ | 1 | Item
B1.9 | COORDINATION OF THE WORKS: Allow to arrange, coordinate and monitor a programme with each subcontractor, supplier, local authority and statutory undertaker, and obtain and supply information as necessary for coordination of the work on site. | £ | 1 | Item
B1.10 | The contractor must provide product guarentees and site H&S plan at end of works, including opperating and maintenance manuals for any newly installed products and materials | £ | 1 | Item
B1.11 | The contractor is to provide progress photos of insulation upgrades to the pitched ceilings and floor insulation for future EPC survey and inspection | £ | 1 | Item
B1.12 | CLEANING: The site is to be kept tidy througout the building process and waste must be regularly cleared from site and not permitted to build up to excessive levels. | £ | 1 | Item
B1.13 | FINAL CLEAN: Prior to handover the contractor must allow for a Complete Builders Clean including all internal surfaces and internal glazing. | £ | 1 | Item
CARRY FORWARD TO SECTION D (Summary Page)
C | SCHEDULE OF WORKS
C0.1 | Please note that existing plan drawings have been included in Appendix C of this tender document. Proposed Drawings in relation to the removal of the Bathroom. Drawings are to scale when printed at A3 however it is the Contractors responsibility to ensure dimentions are checked on site prior to the submission of any prices |  | - | Note | - | -
C0.2 | The Contractor must, when pricing this Schedule of Works, take into consideration the requirements within all sections of this specifiation and the attached Appendicies of this tender document. Failure to do so will be at the risk of the Contractor. |  | - | Note | - | -
C0.3 | Not withstanding the conditions set out in the ‘National Building Specification’ guidelines and the ‘Standard Method of Measurement’ 7th Edition. The Contractor’s general cost items are to be priced in accordance with the ‘RICS New Rules of Measurement’ volume 2, 1st edition, (RICS:NRM-2 v1). |  | - | Note | - | -
C1 | DEMOLITION AND STRIP OUT WORKS
C1.0 | The Contractor is to review the asbestos refurbishment survey which is included within the PCI Document and can be found in Appendix B of this tender document. Please note Asbestos was removed from the kitchen during the previous refurbishment and no further asbestos has been identified - however should the contractor identify anything that he considers suspected to include Asbestos work must stop in the location and the EA must be contacted immediately. |  | - | Note | - | -
C1.1 | Allow to carefully lift all ground floor carpets to living room, dining room, kitchen and entrance hall and set aside for re-fitting. (this is to allow for the repair of the floor to the entrance of the dining room and the installation of insulation between the ground floor floor joists) | £ | 1 | Item
C1.2 | Strip out the worn carpet to the stairs and landing and 3 bedrooms and clear from site. | £ | 1 | Item
C1.3 | Provide the necessary protection to the kitchen fittings during any stripping out works including the cooker. The existing timber shed can be used to store materials during the works - the contractor is responsible for providing a suitable padlock to maintain security of this storage facility | £ | 1 | Item
C1.4 | Allow to remove all wallpaper from walls, skeiling and ceilings and clear from site. (historic leak to ceiling of bedroom 3 where water tank leaked - now repaired and drained down) | £ | 1 | Item
C1.5 | Allow to wash down all walls, skeilings and ceilings with sugar soap and/or dilute bleach solution or alternative anti-fungal wash to remove adhesive residue and any black mould growth. | £ | 1 | Item
C1.6 | Check in roof space and report back on thickness of insulation - allow to increase to 350mm glass fibre insulation and provide a 2m sq safe standing area around the roof access hatch on loft legs above new insulation to allow for safe future inspections | £ | 1 | Item
C1.7 | Remove bath and clear from site, remove shower (previously disconnected by EA electrician) and clear from site Carefully remove wash hand basin and taps from bathroom and and set aside for refitting. Remove towel rails from site and set aside for re-fitting Carefully remove WC pan and WHB from WC set aside for inspection by CA and possible re-use Remove tiled finish from walls of bathroom and WC and clear from site | £ | 1 | Item
C1.8 | Remove all tiled floor fininsh from Bathroom, WC and rear hallway and clear from site | £ | 1 | Item
C1.9 | Remove polystyrene tiles from ceiling of WC and clear from site | £ | 1 | Item
C1.10 | Remove all redundant water and waste pipes from bathroom and WC and clear from site | £ | 1 | Item
C1.11 | Carefully disconnect waste and water supply to kitchen sink and carefully remove section of work top with sink up to cooker and set aside for refitting | £ | 1 | Item
C1.12 | Carefully remove sink base unit, plinth and all fittings and set aside for refitting | £ | 1 | Item
C1.13 | Allow to hack-off areas of blown plaster to landing area, under sink (behind base unit) and in recess where washing machine and dishwasher were located. Remove all debris from site. Identify any further areas of blown plaster and bring to the attention of the CA and allow for inspection of additional areas by CA to agree any further scope | £ | 1 | Item
C1.14 | Identify source of water/damp behind sink to external wall - (likely to have been leaking for some time as wall saturated with moss and plant growth evident externally) | £ | 1 | Item
C1.15 | Inspect area to side of back door - damp (possible that back steps bridges damp course? Or volume of water from kitchen leak? Inspect find location of damp and damp course and bring to the attention of CA for site inspection | £ | 1 | Item
C1.16 | Check kitchen sink drainage connections and waste pipes and reseal all joints. Check water pipes in the location and reseal any leaking joints as necessary. | £ | 1 | Item
C1.17 | Allow to remove fitted wardrobe to Bedroom 1 and clear from site | £ | 1 | Item
C1.18 | Allow to remove shelves to bedroom 2 and clear from site | £ | 1 | Item
C1.19 | Creat new opening between kitchen and small lounge to create access for dining area off kitchen in position of small hatch - provide necessary concrete lintol to support head of new doorway with sufficient 100mm bearing on each side of new opening - provide new door lining and rehang salvaged door from other side of kitchen - refix salvaged architrave to either side of new doorway and prepare ready for decoration | £ | 1 | Item
C1.20 | Remove existing door and architrave between large living area and kitchen and set aside for use in new opening off kitchen in position of existing hatch | £ | 1 | Item
C2 | PREPARATION AND REPAIR
C2.1 | Allow to make good external wall behind sink base unit and in recess for washing machine and to sides of back door using lime plaster (possibly extend into area behind oven) - Hack off existing damp and blown plaster and clear from site allow to dry fully prior to replastering and ensure new plaster is dry prior to refitting kitchen units. Provide a plaster finish in strict accordance with manufacturers recommendations using 9mm of lime hemp plaster applied in 2 layers while still wet with strenghthening mesh fixed between coats as detailed in manufacturers recommendations and leave to dry and brush to provide key When fully dry apply 1 no. 3mm finishing coat using Superfine fininsh coat as detailed in manufacturers recommendations and fininsh smooth with trowel or sponge ready to receive Clay paint finish. Blend in with existing surrounding gypsom plaster to either side. | £ | 1 | Item
C2.3 | Allow to fill all areas of minor cracking to plastered walls and ceiling prior to decoration. Rake out cracks to 3mm minimum or sound base and remove all loose material. Fill as required with suitable fine finishing filler and allow to dry and prepare to smooth finish ready to receive painted finish | £ | 1 | Item
C2.4 | Allow to make good all areas where blown plaster removed to landing and any other areas not suffering from damp with 1 no. base coat and 1 no. skim coat of gypsum plaster finished flush ready to receive painted finish. | £ | 1 | Item
C2.5 | Allow to scrape off all areas of flaking paint to walls and ceilings and prepare prior to redecoration | £ | 1 | Item
C2.6 | Allow to make good loose floor boards in entrance to dining room where creaking and moving when walked upon | £ | 1 | Item
C2.7 | Roof Void/Cupboard off landing Allow to carefully lift all boards to the floor area within this roof void - Supply and fit 100mm rockwool insulation between ceiling joists to ensure insulation is provided throughout this void at floor level - ensure ventillation is retained at eaves. Refix floor boards to reinstate the floor to this roof void/cupboard to provide storage to tenant. | £ | 1 | Item
C2.8 | Supply and fit 75mm Cellotex GA4075 PIR board insulation between vertical joists to landing and bedrooms to the extent of the cupboard/roof void accessed off landing. Ensure Cellotex is cut to fit snuggly between joists and pushed in so that face of board lines with outer face of timber uprights (carefully ensuring insulation is not pushed too far into the reveal which would damage the lath and plaster finish) Provide silver taping over joints and over timbers to this vertical studwork | £ | 1 | Item
C2.9 | Supply and fix 75mm cellotex to the rear face of this door to the landing roof void/cupboard to ensure the door is also insulated | £ | 1 | Item
C2.10 | Following removal of all wallpaper and all loose material to the pitched ceilings allow to supply and fix wood fibre insulation to all areas of pitched ceilings using Schneider Room 140 T&G 40mm wood fibre board in strict accordance with manufacturers recommendations. Measure and cut boards to fit all areas of pitched ceilings including angled cuts to fit flush against adjacent vertical walls and horizontal ceilings. Dampen surface of ceiling and apply Iso-vit E-cork adhesive mortar using a 10mm notched trowel to ensure even coat Push room 140 wood fibre boards into the Iso-Vit adhesive mortar - drill and fix 2 anchors with large plastic washers into the middle of each board to hold in position - work from base up with staggered joints Allow to dry for 1 day prior to plastering Fix additional screws with engineered washers to each corner and 2 additional fixings to long sides and 1 to short sides (minimum) Provide a plaster finish in strict accordance with manufacturers recommendations using 9mm of lime hemp plaster applied in 2 layers while still wet with strenghthening mesh fixed between coats as detailed in manufacturers recommendations and leave to dry and brush to provide key When fully dry apply 1 no. 3mm finishing coat using Superfine fininsh coat as detailed in manufacturers recommendations and fininsh smooth with trowel or sponge ready to receive Clay paint finish. See Ty-Mawr Data Sheet for installation - https://drive.google.com/file/d/1-xlHLEyM1lO7Sgl5i-zDXutQb_-r2F7d/view Ensure photographs are taken throughout the process of each room to show level of insulation being installed to provide evidence of upgrade for EPC inspector - photographs to be forwarded to CA at end of contract as photographic evidence annotated to show what was done. | £ | 1 | Item
C2.11 | Allow to lift floor boards to suspended ground floors and fit 100mm Cellotex GA4100 or equivalent insulation between the joists. Provide treated timber battens fixed to the underside of the floor joists to support the PIR Insulation. Ensure the insulation is cut to fit snuggly between the joists - ensure the top of the joists and joints are taped with silver tape prior to refixing the existing floor boards and ensure barrier is provided up behind skirtings to prevent drafts. Refix existing floor boards | £ | 1 | Item
C2.12 | Allow to refit existing floor finishes - carpets to living room and dining room, and vinyl to kitchen and front entrance halls | £ | 1 | Item
C2.13 | Allow to prepare all new areas of gypsom plaster with 2no. mist coats and 1no. full coats of emulsion paint | £ | 1 | Item
C2.14 | Allow to prepare all areas of new lime plaster with suitable breathable waterbased paint finish such as Earthborne clay paint or similar alternative (not standard emulsion) | £ | 1 | Item
C2.15 | Allow to rub down and prepare all areas of previously painted timber prior to full redecoration - remove all flaking paint, and prepare surface to ensure smooth finish ready to receive full redecoration including staircase (including central area where previously unpainted) | £ | 1 | Item
C2.16 | Overhaul existing door handles and latches to internal doors and leave in full working order | £ | 1 | Item
C2.17 | Overhaul existing front and rear external door including locks, hinges and linings which are sticking to the front door - ensure the locking mechanisms work effectively as these currently stick on both doors | £ | 1 | Item
C2.18 | Overhaul the existing secondary glazing and Upvc windows and doors to ensure they all function adequately. Replace cracked glazing to left hand casement to living room front elevation window | £ | 1 | Item
C2.19 | Allow to inspect the loft areas above the bedrooms and upgrade the insulation to 350mm depth - provide an area of 2 sqm boarding on loft legs above the level of the insulation to provide a safe platform for future inspection | £ | 1 | Item
C2.20 | Block up opening between kitchen and large living area using 100x50mm treated timber studs with 100mm rockwool insulation batts packed between studs to provide some sound insulation. Fix 12.5mm Gyproc fire line board to both sides of studwork and provide plaster skim fininsh and prepare with mist coat ready to receive full decoration | £ | 1 | Item
C2.21 | Repair the loose and sagging floor board in the entrance to the small lounge/dinng room at the entrance with the front hall. The floorboard is loose and dropping in and requires additional support - allow CA to inspect prior to covering up and ensure no rotten timbers are left in situ (or take photographs) | £ | 1 | Item
C2.22 | Allow to take photographs of all works progressing especially those which upgrade the existing insulation to ensure that this is recorded - including evidence of the depth of insulation installed (by means of a measuring tape in the photograph) This will be required for the EPC inspection to ensure that all thermal improvements can be included. Photographs to be shared with CA during progress of contract and included in the H&S File at the end of the project | £ | 1 | Item
C3 | KITCHEN
C3.1 | Allow to overhaul all drawers and cupboards to existing kitchen to ensure they open and close adequately. Leave kitchen in good functioning condition | £ | 1 | Item
C3.2 | Supply and fix silver metal edging to the edge of the existing work top in the doorway to the living room and where the current fridge freezer is located. Trim the work top and provide metal edging to each side of the oven | £ | 1 | Item
C3.3 | Remove all flaking paint from wall behind hallway adjacent to staircase and prepare ready to receive new painted finish | £ | 1 | Item
C3.4 | Once fully dry fix back the base units and sink with new water connections and waste pipes for sink, washing machine and dishwasher | £ | 1 | Item
C3.5 | Re-seal gap between worktop and existing tiles | £ | 1 | Item
C4 | BATHROOM
C4.1 | Supply and fit new bath and refix existing wash hand basin as per existing layout in bathroom. Refit WC pan and WHB to WC | £ | 1 | Item
C4.2 | Supply and fix all necessary copper pipework to provide hot and cold water supply to all newly installed Bath and WHBsand cold supply to shower and WC as required | £ | 1 | Item
C4.3 | Supply and fix new electric shower - Mira Event XS or equivalent (suitable for lower pressure areas and not affected by other water use in the property) (to be connected by EA Framework Electrical Contractor) | £ | 1 | Item
C4.4 | Supply and fix all necessary waste pipes, traps and plugs to all fittings and connect up to existing soil pipe | £ | 1 | Item
C4.5 | Install taps as required to bath and shower and plug wastes | £ | 1 | Item
C4.6 | Allow to decorate bathroom throughout Using Dulux bathroom paint to ceiling and walls | £ | 1 | Item
C4.7 | Supply and fix 40mm Marmox Multiboard to external walls of bathroom and WC prior and 10mm Marmox Multiboard to all other internal walls prior to fixing waterproof covering (tiling or shower boarding) - Allow to fix in strict accordance with manufacturers recommendations https://www.marmox.co.uk/uploads/catalogue_gallery/47/datasheets/Marmoxbrochure.pdf Measure the Multiboard and cut to size. It is very easy to cut with a saw or knife. Offer the Multiboard up to the wall and use Marmox washers and screws. Screws should generally be at least 20mm longer than the thickness of the board. Be aware of any electrical wires or pipe work that may be in the wall. Short boards – 3 rows of 3 fixings (1 inch from the edges) Long boards – 3 rows of 5 fixings (1 inch from the edges) Joints - Tape all the joints with Marmox Reinforcing Tape also tape all of the corners, joints and screw holes with Marmox Self Adhesive Waterproof tape. Supply and fix new approved tiles or shower board up to ceilings within bath/shower and up to dado level behind WC and WHBs All wall covering boards or tiles to be agreed with CA prior to ordering | £ | 1 | Item
C4.8 | Allow to provide a new Upvc cover to the sill and surrounds and seal edges prior to fixing insulation board to ensure a good seal around the timber window surround - ensure all joints and junctions are sealed with waterproof sealant | £ | 1 | Item
C4.9 | Allow to supply and fit new shower screen to existing bath to prevent future damage to window surround | £ | 1 | Item
C4.10 | Allow to provide new tiled floor fininsh to WC, Bathroom and rear entrance hall | £ | 1 | Item
C4.11 | Allow to reinstall radiator/towel rail within bathroom and supply and WC | £ | 1 | Item
C5 | EXTERNAL
C5.1 | Externally repair guttering to front right hand corner where it has come unattached | £ | 1 | Item
C5.2 | Replace broken bracket to Soil Pipe just above ground level | £ | 1 | Item
C5.3 | Repair decayed timber to corner of porch canopy prior to redecoration | £ | 1 | Item
C5.4 | Cut back vegetation surrounding house including elder tree growing adjacent front elevation under living room window and vegetation leading up to the front door, clear steps down to concrete hardstanding area adjacent to shed. | £ | 1 | Item
C5.5 | Allow PC £200 to make good steps where necessary | £ | 1 | Item
C5.6 | Allow to break out hardstanding area between sheds and provide compacted base ready to receive new paved or gravelled area with no trip hazards (clear any debris from site) | £ | 1 | Item
C5.7 | Allow to rake out cracks in path around property and fill with cement to provide level path around all sides especially to rear and ensure no trip hazards are left | £ | 1 | Item
C5.8 | Provide new timber gate to front garden entrance to match existing - re-use all existing ironmongery | £ | 1 | Item
C5.9 | Rub down and prepare timber to existing porch canopy | £ | 1 | Item
C5.10 | Re-decorate porch canopy with 2 no. undercoats and 1 no. full coat of Dulux Weathersheild in brilliant white - supporting brackets to be stained in dark brown to match existing | £ | 1 | Item
C5.11 | External repairs to hardstanding around outside of house…. Paths and steps going down to patio area - patio area very uneven - needs relaying with new slabs? | £ | 1 | Item
C5.12 | Supply and lay new golden gravelled area between sheds with weed barrier underneath to provide non trip outside space | £ | 1 | Item
C5.13 | Allow to undertake areas of re-pointing to external brickwork to match existing lime based mortar with sharp sand agregate - sample panel to be provided for approval by CA prior to undertaking larger areas. Allow for an initial 10 Sqm Colour and texture to match existing as closely as possible | £ | 1 | Item
C6 | DECORATION - DECORATE THROUGHOUT
C6.1 | The contractors internal redecoration costs are to include removal of isolated redundant fixings, making good any cracks, fixing holes and areas of damage prior to redecoration. | £ | 1 | Item
C6.2 | Prior to decorating, allow to protect surfaces, floor finishes and all fixtures and fittings, allow to loosen light fittings, switches sockets and the like prior to decoration | £ | 1 | Item
C6.3 | Allow to prepare all walls and ceilings where mould growth has been washed off and redecorate with Dulux Trade Mouldshield Fungicidal Matt paint in line with the manufacturers guidelines - colour to be brilliant white | £ | 1 | Item
C6.4 | Allow all areas of newly finished plaster to be allowed to dry out completely prior to redecoration. | £ | 1 | Item
C6.5 | Allow to decorate all new lime plaster to pitched ceilings with suitable breathable clay paint such as Earthborne paint or suitable alternative - apply in strict accordance with manufacturers recommendations - colour to be brilliant white and continue application onto main ceilings to obtain uniform finish to ceiling areas | £ | 1 | Item
C6.6 | Allow to decorate all previously painted walls and ground floor ceilings with 2 full coats of Dulux Trade Matt Emulsion paint fininsh in brilliant white | £ | 1 | Item
C6.7 | Allow to decorate all previously painted timber with 1no. undercoat and 2 no. full coats of Dulux satin wood pure brilliant white paint fininsh applied in strict accordance with manufacturers recommendations including hand rail and balustrading to staircase | £ | 1 | Item
C7 | ELECTRICS: To be undertaken by EA Term Contractor Prior to construction works commencing
Disconnect Shower - to be carried out by EA electrician, disconnect light from bathroom and WC and all cabling prior to replacing lights and shower in bathroom (once bathroom has been refurbished allow to refix lighting and new electric shower to be Mira Event XS or equivalent (suitable for lower pressure areas and not affected by other water use in the property) Remove light fitting from living room and clear from site - replace with single pendant fitting Remove redundant smoke detector from bedroom 1 and clear from site, install new mains opperated smoke detection system with 1 smoke detector to hall, 1 smoke detector to landing, 1 heat detector to kitchen and 1 combined heat and CO detector to living room (where log burner located) Disconnect electric heater from WC and all electrical cabling and connections and clear from site Provide 2no. additional double sockets to each of the larger 2 bedrooms and 1 no double socket to landing...... positions to be agreed Install 2 no. extractor fan to bathroom and WC - QF100HTX5CON Manrose Quiet Fan X5 Conceal with Humidistat sensor to be installed over shower in bathroom and in WC - ensure this vents externally either via an existing soffit or by core drilling the external wall and providing a vent with cover flaps externally to prevent incomming draughts Replace light bulbs to ensure LED bulbs/fittings are provided througout property External light to rear patio/path area needs checking as this has not worked or flickers Carry out an electrical condition report and make good any C1 or C2 faults
C8 | HEATING
C8.1 | Extend heating sytem to provide additional radiator to landing area (currently no heating in this area) New double panel radiator to be provided to left of cupboard door | £ | 1 | Item
C8.2 | Extend heating system to provide additional radiator to WC | £ | 1 | Item
| Sub-Total | £
| CARRY FORWARD TO SECTION D (Summary Page) | £
D | Summary Page
B -Preliminaries
C - Schedule of Works
C1 - Demolition and Stripping out Works
C2 - Preparation and Repair
C3 - Kitchen
C4 - Bathroom
C5 - External
C6 - Decoration
C8 - Heating
SUB-TOTAL
CONTINGENCY SUM 10%
GRAND TOTAL