## Sheet1
NEDF Move Management Programme v1.8
Updated: | 2022-09-30
|  | Week | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | Comments
| Duration (Days) |  | 2023-06-05 | 2023-06-12 | 2023-06-19 | 2023-06-26 | 2023-07-03 | 2023-07-10 | 2023-07-17 | 2023-07-24 | 2023-07-31 | 2023-08-07 | 2023-08-14 | 2023-08-21 | 2023-08-28 | 2023-09-04 | 2023-09-11
Activity
General - Last Teaching Week | 2023-05-21
General - End of Assessment Period | 2023-06-05
SoADA (metals and wood) Teaching ends |  |  | 2023-06-19: 2023-06-20
SoADA Workshop Access Ends |  |  | 2023-07-17: 2023-07-21; 2023-07-31: 2023-08-01 | Definitive cut off for postgrad.
NEDF Early Access and Handover | 1 |  | 2023-06-12: 2023-06-12; 2023-07-03: BAM Clean; 2023-07-24: Completion | Early Access TBC
Decommission existing equipment SECAM | 2023-05-18 |  | 2023-07-03: BAM Clean | BAM open to allowing installation of large items 3 weeks prior to handover. Precision lab potentially 18/05/23 SoECAM could commence decomissioning earlier than SoADA
Decommission existing equipment SoADA | TBC |  | 2023-07-03: BAM Clean | SoADA unlikely to be able to commence large scale decommissioning much earlier although Simon Standing has undertaken to look at SoADA. Less pressure for SoADA if mostly newly procured items
Existing equipment compliance upgrades | TBC | [16 empty] | Zero impact for SoADA if new items procured SoADA tender should be out to market within the next 2 weeks 15th September deadline.
Delivery of group 2 and 3 items | TBC |  | 2023-07-03: BAM Clean
Equipment moves by specialist movers | TBC |  | 2023-07-03: BAM Clean | Allowance appears realistic (SoADA PIN Intel) Awaiting first 3 SECAM procurement bundles to confirm
Residual equipment moves by McMullen | 6 weeks |  | 2023-07-03: BAM Clean | Mcmulllin confirms realistic allowance
Service connections (TBC) | SoADA 10-15 SECAM TBC |  | 2023-07-03: BAM Clean | 2- 3 weeks for SoADA if (Drews/Totus). XX weeks for SoECAM
Testing and commissioning | SoADA 5-10 SECAM TBC |  | 2023-07-03: BAM Clean | Risk assessment and Insurer inspections SoADA 1no week
In Use | 1 |  | 2023-07-03: BAM Clean; 2023-09-11: IN USE 18/09/2023
Lead in activities
Procurement of group 2 and 3 items
Delivery of group 2 and 3 items
Activities to follow
Disposal of group 4 items not required
Non essential equipment moved in S2