# Annex A

| Title of project: | Review of the evidence supporting the provision and resilience of ecosystem services of select marine habitats and species. |
| --- | --- |
| Date and time for return of tenders: | Tuesday 28 January 2020 at 16:00 hours |
| Contract Reference No: | C19-0370-1409 |
| Address for tender submission: | 1 electronic copy to be sent to TenderResponse@jncc.gov.uk PLEASE DO NOT SEND TENDERS DIRECTLY TO PAUL IVORY OR DORA IANTOSCA VIA THEIR PERSONAL EMAIL ADDRESSES, AS THIS WILL INVALIDATE YOUR TENDER Tender responses must be less than 10 MB in size. On receipt of your tender, you will receive an automated e-mail to confirm receipt by JNCC Support Co. If you do not receive this automated email, please contact, in the following order: Sue Wenlock (00 44 1733 866880) Chris Downes (00 44 1733 866877) |
| Contacts for technical information relating to this project specification: | Paul Ivory Marine Natural Capital Joint Nature Conservation Committee Email: paul.ivory@jncc.gov.uk Tel: +44 (0)1733 866 975 |
| Contact for any queries regarding the tendering procedure: | Dora Iantosca Finance Team Joint Nature Conservation Committee Email: Dora.Iantosca@jncc.gov.uk Tel: 01733 866894 |
| Proposed start-date: | As soon as possible upon awarding contract |
| Proposed end-date: | March 2020 |

Review of the evidence supporting the provision and resilience of ecosystem services of select marine habitats and species

- Contents

Review of the evidence supporting the provision and resilience of ecosystem services of select marine habitats and species…………………………………………………………………2

1.	Joint Nature Conservation Committee	3

2.	Project Aims	3

3.	Project Background	3

4.	Terminology	4

5.	Project Objectives	5

5.1 Primary Objectives: Marine Ecology.	5

5.2 Secondary Objectives: Marine Ecology.	5

6.	Project Objectives: Detailed tasks	5

6.1 Objectives: Marine Ecology	6

6.1.1 General information	6

6.1.2 Primary Objective 1………………………………………………………………….....10

6.1.3 Primary Objective 2………………………………………………………………….....11

6.1.4 Primary Objective 3………………………………………………………………...…..12

6.2 Secondary Objectives: Marine Ecology………………………………………………...…13

6.2.1 Secondary Objective 1………………………………………………………………....13

6.2.2	Secondary Objective 2:).	14

7.	Outputs	15

8.	Dissemination	16

9.	Timescale	16

10.	Health and safety	16

11.	Product specification	16

12.	Project management	16

13.	Instructions for tender submission	17

14.	Evaluation Criteria	18

15.	Payment	19

16.	Additional Contractor requirements	19

17.	References	19

## Joint Nature Conservation Committee

The Joint Nature Conservation Committee (JNCC) is the statutory adviser to the UK Government and devolved administrations on UK and international nature conservation. Its work contributes to maintaining and enriching biological diversity, conserving geological features and sustaining natural systems.

Our role is to provide evidence, information and advice so that decisions are made that protect natural resources and systems. Our specific role is to work on nature conservation issues that affect the UK as a whole and internationally:

advising Government on the development and implementation of policies for, or affecting, nature conservation in the UK and internationally;

providing advice and disseminate knowledge on nature conservation issues affecting the UK and internationally;

establishing common standards throughout the UK for nature conservation, including monitoring, research, and the analysis of results; and

commissioning or supporting research which it deems relevant to these functions.

Background to JNCC can be found on the JNCC website: http://jncc.defra.gov.uk/page-1729

## Project Aims

The purpose of this project is to determine qualitative scores for the provision of ecosystem services by marine habitats and species in the UK. These scores will be incorporated into existing JNCC Evidence Products which are used to underpin Ecosystem Services and Natural Capital tools for use in management and decision making.

## Project Background

Growing interest in marine natural capital has highlighted the need to better understand the provision and flow of marine ecosystem services from marine habitats and species. Knowledge of which habitats exist, which organisms inhabit these and, the processes performed by those organisms, can be of economic, ecological and cultural value.

In recent years there has been an increased focus within both UK policy and science on the concept of Natural Capital and the services and benefits that flow from this. JNCC is working to develop the evidence base within the marine environment where significant evidence gaps exist.

A Natural Capital approach requires different users and sectors to have access to evidence and evidence products such as Natural Capital accounts, asset and risk registers. They will need robust, flexible and usable evidence with known confidence and propriety to make informed decisions.  To gather and manipulate data anew for each project would be wasteful and risk multiplying error.

The Natural Capital Committee defines Natural Capital as “The elements of nature that directly or indirectly produce value to people, including ecosystems, species, freshwater, land, minerals, the air and oceans, as well as natural processes and functions.” (Natural Capital Committee, 2014). Sustainable use of natural resources can yield significant benefits to society and so appropriate management of these assets and consideration in decision making are essential for these to be realised. The Committee was established to advise UK Government on matters relating to Natural Capital which has been done through a series of reports and recommendations which have fed into the development of the Defra 25 Year Environment Plan (Defra, 2018). The Committee advises that natural capital assets need to be identified to provide a baseline from which to monitor changes in natural capital assets and their potential to provide services and benefits to inform decision making.

The benefits derived from assets in this context are those benefits provided to society which may be are affected by the quantity, quality or location of the underpinning asset. Developing an understanding of these assets will expand the information resource available for assessments based on natural capital and to inform sustainable management decisions that in turn will help support the improvement and restoration marine ecosystems. Availability and use of such tools will be foundational to achieving the goals of the 25 Year Environment Plan.

JNCC is developing a practical framework of standardised, multi-purpose Evidence Products to meet this need, which together will provide a reliable foundation for Marine Natural Capital (mNC) assessment work at different scales and for different uses.   These cover ecosystem service provision, asset status and metadata among others.

These Evidence Products are foundational and will be developed iteratively, refined and improved over time, leading to the production of tools to assist marine managers and business incorporate Natural Capital into their decision making.

This project builds on previous work to improve confidence in the relationships to improve understanding and confidence in estimating the relationships between marine features and ecosystem services provision, in the features associated with the current project.

## Terminology

Certain terms are already established in this workstream. The most important ones for this contract are defined below.

FESP - (Features-Ecosystem Services Provision)

FESS - (Feature x Ecosystem Services Sensitivity)

## Project Objectives

This tender is split into primary and secondary objectives.  Primary objectives are our priority which must be met by any tenderer. Applicants are asked to set out clearly how the costs would be split amongst the objectives.

### 5.1 Primary Objectives: Marine Ecology.

To undertake a thorough literature review to:

- Consolidate and summarise evidence of ecosystem services (Table 2) that are provided by the marine features listed as Primary in Table 1.

- Consolidate and summarise evidence of how ecosystem service provision (as identified in Primary Objective 1) is influenced when the marine feature is exposed to anthropogenic pressures (Table 3).

- Consolidate and summarise evidence of ecosystem functions/services supporting and provided by Nephrops norvegicus and Ammodytes spp.

### 5.2 Secondary Objectives: Marine Ecology.

To undertake a thorough literature review to:

- Consolidate and summarise evidence of ecosystem services (Table 2) that are provided by the marine features listed as Secondary in Table 1.

- Consolidate and summarise evidence of how ecosystem service provision (as identified in Secondary Objective 1) is influenced when the marine feature is exposed to anthropogenic pressures (Table 3).

## Project Objectives: Detailed tasks

The specific tasks and description of outputs required to fulfil each objective are outlined below. The tender submissions must provide a description of how the objective outputs will be delivered and propose any additional aspects which may be necessary to meet the objectives. This must also include the approach/es the contractor intends to use for the literature review. Guidance on Knowledge Synthesis Methods is availble from the Eklipse project (Dicks et al., 2016).

Sufficient time and resources (including financial) should be allowed for requesting and collating relevant information from suitable organisations; tenderers should specify which information they intend to consider and where they intend to source such information from.

## 6.1 Objectives: Marine Ecology

### 6.1.1 General information

Tables 1 – 3 below contain subsets of habitats, Ecosystem Services and anthropogenic pressures that limit the scope of this review. The list of Ecosystem Services and anthropogenic pressures should be considered draft and will be finalised when the contract is awarded, however the number will not change significantly.

Table 1: Translation of EUNIS Codes to JNCC codes for Deep Sea biotopes

Table 2: List of relevant Ecosystem Services with showing code and source

| Code | Name of Ecosystem Service | Source |
| --- | --- | --- |
|  | Primary production | Potts et al. (2013) |
|  | Nutrient cycling | Potts et al. (2013) |
|  | Formation of species habitat | Potts et al. (2013) |
|  | Formation of Physical Barriers | Potts et al. (2013) |
|  | Natural Hazard Regulation | Potts et al. (2013) |
|  | Carbon Sequestration | Potts et al. (2013) |
| C1.1.5.1 | Wild plants used for nutrition (including algae and fungi) | CICES 5.1 |
| C1.1.5.2 | Wild plant - fibres and other materials | CICES 5.1 |
| C1.1.6.1 | Wild animals used for nutritional purposes | CICES 5.1 |
| C1.1.6.2 | Wild animals: - fibres and other materials | CICES 5.1 |
| C1.2.1.1 | Plant materials collected for maintaining or establishing a population | CICES 5.1 |
| C1.2.1.2 | Plants collected to breed new varieties | CICES 5.1 |
| C1.2.1.3 | Plant gene extracted to construct new biological entities | CICES 5.1 |
| C2.1.1.1 | Bio-remediation by micro-organisms, algae, plants and animals | CICES 5.1 |
| C2.1.1.2 | Filtration/sequestration/storage/accumulation by micro-organisms, algae, plants and animals | CICES 5.1 |
| C2.2.1.1 | Control of erosion rates | CICES 5.1 |
| C2.2.1.3 | Hydrological cycle and water flow regulation | CICES 5.1 |
| C2.2.2.1 | Gamete dispersal | CICES 5.1 |
| C2.2.2.3 | Maintaining nursery populations and habitats | CICES 5.1 |
| C2.2.6.1 | Regulation of chemical composition of atmosphere and oceans | CICES 5.1 |

Table 3: List of relevant pressures associated with species, habitats and biotopes

| Pressure Code | Pressure |
| --- | --- |
| B3 | Introduction or spread of invasive non-indigenous species (INIS) |
| B5 | Removal of target species |
| B6 | Removal of non-target species |
| D1 | Habitat structure changes - removal of substratum (extraction) |
| D2 | Penetration and/or disturbance of the substrate below the surface of the seabed, including abrasion |
| D4 | Smothering and siltation rate changes (Heavy) |
| D5 | Smothering and siltation rate changes (Light) |
| D6 | Abrasion/disturbance of the substrate on the surface of the seabed |
| H1d | Temperature decrease |
| H1i | Temperature increase |
| H2d | Salinity Decrease |
| H2i | Salinity Increase |
| L2sb | Physical change (to another seabed type) |
| L2sed | Physical change (to another sediment type) |
| P2 | Hydrocarbon & PAH contamination. Includes those priority substances listed in Annex II of Directive 2008/105/EC. |
| P7 | Organic enrichment |
| P8 | Deoxygenation |

For objectives 1 – 3, JNCC will provide the following:

  - a list of marine features (biotopes and species) for which the contractor should review the available literature for relational information. We expect the contractor to consider all/any sources of evidence and justify their use.

  - A list of Ecosystem Services to be considered, thereby limiting the scope of the review. However, we expect the contractor to take a flexible approach and record any significant evidence related to other Ecosystem Services that is discovered during the review of the targeted services.

  - A list of anthropogenic pressures to be considered, thereby limiting the scope of the review. However, we expect the contractor to take a flexible approach and record any significant evidence related to other anthropogenic pressures that is discovered during the review of the targeted pressures.

  - JNCC mNC Evidence Product templates for recording final determinations of provision, sensitivity of service and confidence.

For objectives 1-3, we would expect the contractor to use the following sources, though we would like the contractor to discuss any alternatives they consider would be valuable with JNCC:

  - Thorough literature search building on any relevant evidence identified in existing marine Ecosystem Service provision matrices (Potts et al., 2013, Tempera et al., 2016, Burden et al., 2017).

  - Objective 2 requires the review of evidence of how specific Ecosystem Services maybe be influenced when a habitat is exposed to a pressure, rather than damage to the habitat. However, MarLIN Marine Evidence based Sensitivity Assessment (MarESA) and associated reports such as Tillin and Tyler-Walters (2014a and b) should be considered as the starting point for this objective.

  - Confidence estimations - Appendix C from Defra report no. ME5218;

  - Common International Classification of Ecosystem Services (CICES)

  - Pressure definitions developed by the OSPAR Intercessional Correspondence Group on Cumulative Effects (ICG-C) – Amended 25th March 2011 (OSPAR, 2011)

- The review is expected to encompass peer-reviewed scientific literature as well as government research reports.

- The full reference details of the evidence must be provided, and the interactions discussed in each piece of literature summarised in the Literature Review Log Table (LRLT)

- Relevant habitat(s) should be recorded in the LRLT for each piece of literature as well as whether the evidence only relates to specific contained biotopes, the parent habitat or is being used as a proxy.

- Copies of the literature reviewed must be retained by the contractor and provided to JNCC as part of this contract.

6.1.2 	Primary Objective 1: Undertake literature review to consolidate and summarise evidence of ecosystem services (Table 2) that are provided by the marine feature listed as Primary in Table 1.

The contractor will review a wide range of literature on the provision of Ecosystem Services by marine features and develop summary provision scores:

  - Gather evidence of the listed biotope complex or habitat’s provision of intermediate and final Ecosystem Service(s)

    - Consider the listed biotope complex or habitat in a U.K. context.

    - Record in the LRLT if the evidence is only applicable to specific biotopes or biotope complexes that are constituents of the listed feature

    - Record in the LRLT if the evidence is for another habitat used as a proxy

    - Record in the LRLT which biological zone(s) the evidence is relevant to for the listed Deep-Sea habitats (Parry et al., 2015)

  - For each combination of listed feature and service considered in the review, summarise the evidence of service provision in a summary table.

  - A determination of provision and where possible a qualitative indication (negligible, low, mod., high) of the magnitude of service provision should be recorded in the summary table. These should be determined based on the strength of the evidence identified in the literature review along with expert judgement.

  - A narrative for any expert judgement applied should be recorded in the summary table.

  - A determination of the confidence in service provision

  - Estimates of the confidence or reliability of the evidence must be attempted using guidelines in Appendix C from Defra report no. ME5218.

6.1.3 	Primary Objective 2: Undertake literature review to consolidate and summarise evidence of how ecosystem service provision (as identified in Primary Objective 1) is influenced when the marine feature is exposed to anthropogenic pressures (table 3).

The contractor will review a wide range of literature on the functions and processes that underpin the Ecosystem Service provisions and on how exposure to anthropogenic pressures may impede or enhance these provisions.

  - For each marine feature and ecosystem service provision combination in Primary Objective 1 gather evidence of how the provision may be influenced by exposure to each of the anthropogenic pressures in Table 3.

    - Consider how the functions of the marine feature are influenced by exposure to the pressure and the relevance of the function to the service provision. Consider how the pressure may influence the service provision directly.

    - When determining the condition of a marine asset and strength of service flow using the existing feature sensitivity score, the assessment assumes all services provided by the marine feature are influenced negatively and equally by exposure to a pressure. The evidence developed by this objective will be used to more accurately portray vulnerability of service provision.

    - Record in the LRLT if the evidence is only applicable to specific biotopes or biotope complexes that are constituents of the listed feature

    - Record in the LRLT if the evidence is for another habitat used as a proxy

    - Record in the LRLT which biological zone(s) the evidence is relevant to for the listed Deep-Sea habitats (Parry et al 2015)

  - For each combination considered in the review, summarise the evidence of service sensitivity in a summary table.

  - A determination of influence (positive, negative) and where possible a qualitative indication (e.g. negligible, low, mod., high) of the sensitivity of service provision should be recorded in the summary table. These should be determined based on the strength of the evidence identified in the literature review along with expert judgement.

  - A narrative for any expert judgement applied should be recorded in the summary table.

  - A determination of the confidence of service sensitivity to pressure.

  - Estimates of the confidence or reliability of the evidence must be attempted using guidelines in Appendix C from Defra report no. ME5218 for the confidence estimation.

6.1.4 	Primary Objective 3: Undertake literature review to and summarise evidence of ecosystem functions/services supporting and provided by Nephrops norvegicus and Ammodytes spp.

The contractor will review a wide range of literature on the ecology of the marine species to develop summary Ecosystem Service provision scores and identify functions/services provided to the marine species by benthic and pelagic habitats.

  - Gather evidence of the marine species provision of intermediate and final Ecosystem Service(s) in a U.K. context

  - Gather evidence of the functions/services provided by benthic and pelagic habitats that support the marine species

  - For each combination of marine species and service considered in the review, summarise the evidence of service provision, supporting habitats and functions/services in a summary table.

  - A determination of provision and where possible a qualitative indication (negligible, low, mod., high) of the magnitude of service provision by the marine species should be recorded in the summary table. These should be determined based on the strength of the evidence identified in the literature review along with expert judgement.

    - Where necessary record the relevant life stage of the marine species

  - A determination supporting benthic habitats and biotopes and the relevant functions/services they provide to the marine species should be recorded in the summary table. These should be determined based on the strength of the evidence identified in the literature review along with expert judgement.

    - Where necessary record the relevant life stage of the marine species

  - A narrative for any expert judgement applied should be recorded in the summary table.

  - A determination of the confidence in service provision

  - Estimates of the confidence or reliability of the evidence must be attempted using guidelines in Appendix C from Defra report no. ME5218.

  - Secondary Objectives: marine ecology

    - Secondary Objective 1: Undertake literature review to consolidate and summarise evidence of ecosystem services (Table 2) that are provided by the marine feature listed as Secondary in Table 1.

The contractor will review a wide range of literature on the provision of Ecosystem Services by marine features and develop summary provision scores:

  - Gather evidence of the listed biotope complex or habitat’s provision of intermediate and final Ecosystem Service(s)

    - Consider the listed biotope complex or habitat in a U.K. context.

    - Record in the LRLT if the evidence is only applicable to specific biotopes or biotope complexes that are constituents of the listed feature

    - Record in the LRLT if the evidence is for another habitat used as a proxy

    - Record in the LRLT which biological zone(s) the evidence is relevant to for the listed Deep-Sea habitats (Parry et al., 2015)

  - For each combination of listed feature and service considered in the review, summarise the evidence of service provision in a summary table.

  - A determination of provision and where possible a qualitative indication (negligible, low, mod., high) of the magnitude of service provision should be recorded in the summary table. These should be determined based on the strength of the evidence identified in the literature review along with expert judgement.

  - A narrative for any expert judgement applied should be recorded in the summary table.

  - A determination of the confidence in service provision

  - Estimates of the confidence or reliability of the evidence must be attempted using guidelines in Appendix C from Defra report no. ME5218.

### Secondary Objective 2: Undertake a literature review to consolidate and summarise evidence of how ecosystem service provision (as identified in Secondary Objective 1) is influenced when the marine feature is exposed to anthropogenic pressures (table 3).

The contractor will review a wide range of literature on the functions and processes that underpin the Ecosystem Service provisions and on how exposure to anthropogenic pressures may impede or enhance these provisions.

  - For each marine feature and ecosystem service provision combination in Secondary Objective 1, gather evidence of how the provision may be influenced by exposure to each of the anthropogenic pressures in Table 3.

    - Consider how the functions of the marine feature are influenced by exposure to the pressure and the relevance of the function to the service provision. Consider how the pressure may influence the service provision directly.

    - When determining the condition of a marine asset and strength of service flow using the existing feature sensitivity score, the assessment assumes all services provided by the marine feature are influenced negatively and equally by exposure to a pressure. The evidence developed by this objective will be used to more accurately portray vulnerability of service provision.

    - Record in the LRLT if the evidence is only applicable to specific biotopes or biotope complexes that are constituents of the listed feature

    - Record in the LRLT if the evidence is for another habitat used as a proxy

    - Record in the LRLT which biological zone(s) the evidence is relevant to for the listed Deep-Sea habitats (Parry et al., 2015)

  - For each combination considered in the review, summarise the evidence of service sensitivity in a summary table.

  - A determination of influence (positive, negative) and where possible a qualitative indication (e.g. negligible, low, mod., high) of the sensitivity of service provision should be recorded in the summary table. These should be determined based on the strength of the evidence identified in the literature review along with expert judgement.

  - A narrative for any expert judgement applied should be recorded in the summary table.

  - A determination of the confidence of service sensitivity to pressure.

  - Estimates of the confidence or reliability of the evidence must be attempted using guidelines in Appendix C from Defra report no. ME5218 for the confidence estimation.

## Outputs

The following outputs are expected from this contract:

| Primary objectives | Output |
| --- | --- |
| 1 | - Literature Review Log Table (LRLT) – record of the literature identified as evidence of Ecosystem Service provision by the listed marine feature, detailing relevance to biotope, biogeographic zone and service class. - Summary Table of evidence, provision scores, expert judgment narrative and confidence scores for each feature and service combination. - Log of literature review search terms and sources. |
| 2 | - Literature Review Log Table (LRLT) – record of the literature identified as evidence of how Ecosystem Service provision by the listed marine feature is influenced when exposed to anthropogenic pressures, detailing relevance to biotope, biogeographic zone and service class. - Summary table of evidence, service sensitivity score, expert judgement narrative and confidence score for each feature x service x pressure combination. - Log of literature review search terms and sources. |
| 3 | - Literature Review Log Table (LRLT) – record of the literature identified as evidence of ecosystem functions/services supporting, and provided by, Nephrops norvegicus and Ammodytes spp. - Summary Table of evidence, provision scores, supporting habitat/biotope and service, expert judgment narrative and confidence scores for each marine species and service combination. - Log of literature review search terms and sources. |
| Secondary objectives | Output |
| 1 | - Literature Review Log Table (LRLT) – record of the literature identified as evidence of Ecosystem Service provision by the listed marine feature, detailing relevance to biotope, biogeographic zone and service class. - Summary Table of evidence, provision scores, expert judgment narrative and confidence scores for each feature and service combination. - Log of literature review search terms and sources. |
| 2 | - Literature Review Log Table (LRLT) – record of the literature identified as evidence of how Ecosystem Service provision by the listed marine feature is influenced when exposed to anthropogenic pressures, detailing relevance to biotope, biogeographic zone and service class. - Summary table of evidence, service sensitivity score, expert judgement narrative and confidence score for each feature x service x pressure combination. - Log of literature review search terms and sources. |

## Dissemination

All products produced by this contract will be JNCC products and shall not be published or disseminated without the written permission of JNCC. They may at some point in the future be published on the JNCC website and all material supplied as part of this contract shall remain copyright of JNCC. However, unless specified, the direct findings from this contract are intended for internal use within JNCC only.

## Timescale

Provisional dates for delivery of the contact outputs are set out below. Exact dates are to be agreed at start-up meeting based on Contractor and JNCC staff availability. We recognise that this will need tight project management and JNCC will ensure that our own resource will not delay progress.

We expect that only the start-up meeting and final meeting will need to occur in person.

| Milestones | Provisional dates |
| --- | --- |
| Start-up meeting (UK) | End January 2020 |
| Interim progress meetings upon completion of each objective: | February 2020 March 2020 |
| Final delivery | Mid-end March 2020 |

## Health and safety

The Contractor is expected to follow appropriate Health & Safety procedures and undertake appropriate risk assessments, evidence of which should be supplied to JNCC. (NB under no circumstances should any work or service commence prior to the receipt of written approval of the risk assessment by JNCC H&S advisor)

Any incidents occurring within the contract should be immediately reported to JNCC.

## Product specification

Any documentation produced by this contract must adhere to the JNCC report template, house style guidance http://cms/JNCCIntranet63/pdf/NewDesign_JNCC_DesignIDv1.4LowRes.pdfand 	and JNCC evidence quality expectations unless stated otherwise. All products should be provided electronically via email as Microsoft Excel spreadsheets or Microsoft Word documents (where necessary).

Copies of documentation associated with the case studies should be provided in electronic format with an associated reference catalogue.

## Project management

The Contractor shall nominate a project manager, who shall be responsible for ensuring the project is completed satisfactorily and who shall be the main contact point for JNCC.

JNCC’s main contact point will be:

Paul Ivory

Senior Marine Natural Capital Adviser

Biodiversity & Ecosystems Services Team

Joint Nature Conservation Committee

Monkstone House

City Road

Peterborough

PE1 1JY

Email: paul.ivory@jncc.gov.uk

Tel: +44 (0)1733 866 975

## Instructions for tender submission

The tender submission should include the following:

A brief summary of the potential Contractor’s experience in relation to the requirements of this contract;

A proposed approach for achieving the objectives of the contract (and delivering the detailed tasks identified within each objective). This should be sufficiently detailed allow assessment against the evaluation criteria (Section 14). This must include the Contractors proposed approach to carrying out the reviews of literature (see Dicks et al., 2016 for guidance);

A detailed project plan (including Gantt chart), including the proposed work programme and an estimate of time required to achieve each objective;

Details of Quality Control procedures to be followed

Details of the Contractor’s own internal Quality Management System;

Details of the Project Team, including their roles and experience, an estimate of their time input into each task, and CVs of all personnel involved in the contract;

Overall quote for the contract, to include:

  - Daily rates for all members of the Project Team;

  - Costs and time allocation should be clearly allocated to specific tasks within this contract, including each objective; and

  - VAT if applicable. The contractor is to specify whether VAT at the prevailing rate would be applicable to this project and to provide their company’s VAT registration number.

The following documentation:

  - Copies of health and safety policy statements where available or a note regarding such items as lone working, emergency procedures and accident reporting;

  - Copies of current public and employer liability insurance certificates; and

  - Copies of any appropriate risk assessments.

  - Copies of any environmental policies should you have them

In addition, note that the tender submission should provide sufficient information to allow assessment against the criteria outlined in Section 14.

For information on how we handle personal data please see our Privacy Notice at http://jncc.defra.gov.uk/privacypolicy

## Evaluation Criteria

JNCC are not bound to accept the lowest priced or any tender.  Having the technical expertise and experience to complete the work to a high standard, and being able to complete it within the timescale, are of the essence for this contract.

Tenders will be evaluated using the following criteria:

|  | EVALUATION CRITERIA | Max Score | Score |
| --- | --- | --- | --- |
| 1. Quality of proposal, (50% of the total for the three assessment categories) |  |  |  |
|  | Clarity of proposal (particularly work plan and deliverables) | 10 |  |
|  | Understanding of, and relevance to, the requirements (in particular the adequacy of outputs and understanding of marine ecosystem function, services and the effects of anthropogenic pressures on marine ecosystem functions and services) | 10 |  |
|  | Soundness and logicality of methods and literature review approach/es | 7 |  |
|  | Realism and measurability of milestones | 6 |  |
|  | Identification and proposed solutions to potential problems/risks | 6 |  |
|  | Serious weaknesses which threaten success | 6 |  |
|  | Probability of success | 5 |  |
|  | Sub Totals | 50 |  |
| 2. Details of Contractor (25 % of the three assessment categories) |  |  |  |
|  | Expertise, experience and balance of team | 9 |  |
|  | Risks if important team members drop out | 7 |  |
|  | Adequacy of subcontractors (if any) | 9 |  |
|  | Sub Totals | 25 |  |
| 3. Cost (25% of the total for the three assessment categories) |  |  |  |
|  | Transparency and correctness of presentation | 6 |  |
|  | Fairness/reasonableness for the level of work and expertise required | 6 |  |
|  | Appropriateness of ratio of senior to junior staff time | 6 |  |
|  | Clarity of each team member’s contribution and value added | 7 |  |
|  | Sub Totals | 25 |  |
| Total score |  | 100 |  |

## Payment

Payment will be made on completion of the objectives, following the submission of an invoice(s); and based on satisfactory undertaking of the contractual elements to the agreed standard of the JNCC Project Officer.

## Additional Contractor requirements

All tenderers are requested to carefully read the Terms and Conditions applying to this contract. Payment will only be made upon delivery of key milestones.

It is assumed that all costs associated with the production of figures, reproduction of photographs and the final report are accounted for within the rates and fees given.

The Contractor is expected to supply all necessary equipment, software, licences etc. to carry out the obligations required under the contract.

## References

Burdon, Daryl & Potts, Tavis & Barbone, Carol & Lucas, Mander. (2017). The matrix revisited: A bird's-eye view of marine ecosystem service provision. Marine Policy. 77. 78-89. 10.1016/j.marpol.2016.12.015.

Dicks, L.V., Haddaway, N., Hernández-Morcillo, M., Mattsson, B., Randall, N., Failler, P., Ferretti, J., Livoreil, B., Saarikoski, H., Santamaria, L., Rodela, R., Velizarova, E. and Wittmer, H. 2017. Knowledge synthesis for environmental decisions: an evaluation of existing methods, and guidance for their selection, use and development – a report from the EKLIPSE project.

Parry, M.E.V., Howell, K.L., Narayanaswamy, B.E., Bett, B.J., Jones, D.O.B., Hughes, D.J., Piechaud, N., Nickell, T.D., Ellwood, H., Askew, N., Jenkins, C. & Manca, E. 2015. A Deepsea Section for the Marine Habitat Classification of Britain and Ireland. JNCC report No. 530 Joint Nature Conservation Committee, Peterborough

Potts, T., Burdon, D., Jackson, E., Atkins, J., Saunders, J., Hastings, E. Langmead, O. 2014. Do marine protected areas deliver flows of ecosystem services to support human welfare? Marine Policy 44, 139-148.

Tillin, H.M. & Tyler-Walters, H. 2014. Assessing the sensitivity of subtidal sedimentary habitats to pressures associated with marine activities: Phase 2 Report – Literature review and sensitivity assessments for ecological groups for circalittoral and offshore Level 5 biotopes. JNCC Report 512B

Tempera F., C. Liquete & A.C. Cardoso (2016). Spatial distribution of marine ecosystem service capacity in the European seas. EUR 27843. Luxembourg (Luxembourg): Publications Office of the European Union. doi:10.2788/753996

Scottish Natural Capital Asset Index 2015 version

Knowledge synthesis for environmental decisions, URL: http://www.eklipse-mechanism.eu/apps/Eklipse_data/website/EKLIPSE_D3-1-Report_FINAL_WithCovers_V6.pdf

MarESA, URL: https://www.marlin.ac.uk/sensitivity/sensitivity_rationale

Tillin and Tyler-Walters (2014a), URL: http://jncc.defra.gov.uk/page-6790

Tillin and Tyler-Walters (2014b), URL: http://jncc.defra.gov.uk/page-7247

Defra ME5218, URL: http://randd.defra.gov.uk/Default.aspx?Menu=Menu&Module=More&Location=None&Completed=0&ProjectID=19471

CICES, URL: https://cices.eu/

Defra ME5218, URL: http://randd.defra.gov.uk/Default.aspx?Menu=Menu&Module=More&Location=None&Completed=0&ProjectID=19471

Defra ME5218, URL: http://randd.defra.gov.uk/Default.aspx?Menu=Menu&Module=More&Location=None&Completed=0&ProjectID=19471

Defra ME5218, URL: http://randd.defra.gov.uk/Default.aspx?Menu=Menu&Module=More&Location=None&Completed=0&ProjectID=19471

Defra ME5218, URL: http://randd.defra.gov.uk/Default.aspx?Menu=Menu&Module=More&Location=None&Completed=0&ProjectID=19471

Defra ME5218, URL: http://randd.defra.gov.uk/Default.aspx?Menu=Menu&Module=More&Location=None&Completed=0&ProjectID=19471