## 14.11.23-Neighbourhoods
Objectives (from Co-op contract) | Metric/Milestone (a build on what is in Co-op contract) |  |  | Main Project Outcomes (from Partners contract) | Desired Impacts | Hypotheses
We aim to…. | …through…... |  | …...by….... | ….in order to... | …which means that/what you will see is… | What we will test through the evaluation process is….
| i.e. the activity | i.e. the number | i.e. the date
OBJECTIVE 1 To provide training and development opportunities to 400 community leaders utilising the peer-to-peer support network. | To develop a project platform that is accessible to all. | One Sharepoint system established | 2023-10-01 | OUTCOME 1 1.Building community capacity: working with Voluntary, Community and Social Enterprise (VCSE) organisations, building the capacity of diverse communities. | A lively, creative, relevant and useful shared space is highly valued and well used by community partners. | We will check via survey Qs: that the ways that using the Nature Neighbourhoods partners' Sharepoint site was easy, fun and effective - adding value to all. We will check via online metrics.
| To develop training packages that meet the needs/requirements of the VCSE organisations over the course of the project. | The number to be determined by need. | Collaboration kick off Oct 23 |  | Nature Neighbourhoods partners enjoy and benefit from training in areas they have identified as important to them and have increased confidence, capacity and capability in these areas* Funding, fundraising and leveraging further support; Governance for smaller organisations; Social enterprise business models; Community co-design; Asset-based community development practices; Place making; Systems change understanding and planning; Knowledge and understanding of environmental policy; Comms; Local community orgs as 'change agents' *these areas have been identified at project launch; others will emerge during the project VCSE organisations feel more able to catalyse long term change in local neighbourhoods | We will check via the monthly sessions that the resources developed/co-created/collated are meeting the needs of the participating orgs. Specific check and challenge will be made to see if the VCSE orgs believe that the training and resources is adding to their abilities to catalyse long term change in their local neighbourhoods.
| To engage x400 community leaders; ensure that all partners commit to DE&I principles so that the cohort is representative and inclusive; train and support the leaders throughout the lifetime of the project. | At least 400 community leaders trained; commitments made by all partners to DE&I | By Sep 25 |  | Partners are proud that the local networks they create are representative of their local community. A number of communities have engaged younger volunteers throughout the project. Co-op and the charities challenge themselves to adapt to the needs of new and different participants - and share the learning in the organisations as we go. | We will use the monthly meetings opportunity to check-in with partners re: any additional support they may need to ensure that their Plan is being developed in ways that are inclusive of all interested groups in the community - and offer any assistance from the charities and/or Co-op where this could help. We will check via survey Qs and case studies that the participants' experience was posiitve, welcoming and relevant to them.
OBJECTIVE 2 To establish, grow, and connect a diverse network of 16+ community groups who are taking nature-positive action at a local and regional scale. | To sign up x18 VCSE partner organisations | 18 Local VCSE Organisations participating in the project | By Jan 24 | OUTCOME 2 Neighbourhood action for nature: VCSE anchor organisations will support local communities to take more climate and nature positive actions. | Co-op member pioneers, partners and assets are engaged in x18 communities, assisting, mobilising people and sharing skills and connections. The charity partners' are similarly connected into the communities where they are co-located. | We will use the monthly meetings as an opportunity to check-in.
OBJECTIVE 3 .Internal and External Learning: Identify and support community champions, to recognise and platform the contribution of communities in creating a nature positive UK. | To develop at least x24 peer to peer networking meetings for the VCSE organisations; and capture learnings and stories from these activities. | At least 24 networking meetings for the VCSE organisations; | 2025-09-01 | OUTCOME 3 Successful communities: Training will be provided to local ‘system actors’ who sit within organisations such as local authorities, landowners, businesses, and funders. | Nature Neighbourhoods partners are connected to each other (and where appropriate NLCF Climate Action Fund funded projects)and this accelerates their progress in developing their plans. | We will test this on in an ongoing way as well as through surveys at the end of year 1 and at project end.
| To curate best-in-class resources for VCSEs and community leaders and from this develop at least x15 resource toolkits for the VCSE partners during the course of the project; accessible to all project participants on the Sharepoint site and published on the Nature Neighbourhoods website/digital space for use by any community organisation in future. | At least 15 resource toolkits created for VCSE and other partners and shared on Sharepoint | Apr 24-Sep 25 |  | Training provided is engaging, accessible, relevant and adds real value - as reported by those involved. Nature Neighbourhoods partners enjoy the process of helping to both commission and in some cases deliver training to their peers. Partners have increased confidence, capacity and capability in areas they have identified (see also resources above):- Funding and fundraising; Governance for smaller organisations; Social enterprise business models; Community co-design; Asset-based community development; Systems change understanding; Local community orgs as 'change agents' *Training topics will be determined throughout the project - similarly resources (as above) | We will check via regular feedback post-training sessions that participants find the training meets their needs, is accessible, fun and worthwhile.
| To ensure ease of access of resources for all by the creation of a free-to-use external platform/website by Sept 2025 | One external platform with free to use resources | 2025-09-01 | OUTCOME 4 Organisational learning and generous leadership: Building the capability of project partners to support community action for climate and nature. | Organisations taking part in Nature Neighbourhoods, and others that have not, use and value new resources - saying they make a difference to their ambitions for the Plan they are creating. | We will use adaptive management - i.e. we will learn as we go and this will improve the resources during tghe course of the project. We will check via surveys of the participating organisations and a number of non-participating organisations in the movement.
| To develop resources for different local system actors (e.g. Local Authorities, Businesses) | The number to be determined by need. | Jun 24 - Jun 25 |  | Local system actors like Local Authorities self report that they are becoming better equipped to understand and support the role of community-led organisations in improving outcomes for nature locally and feel clear and positive about the value brought to their community's Plan by the charities and by Co-op. | We will test this via surveys and some individual case studies.
| To create, and promote, the stories of x40 community members (project participants including Co-op Member Pioneers); to include their reasons for taking nature and climate action. To be told regularly over the course of the project. | x40 stories | Apr 24 - Jun 25 |  | A co-created and creative brief leading to engaging and inspiring content which features on Co-op community channels and the partners' channels. | We will check via surveys and social listening that participants are proud and actively share and promote their stories, using them to create further engagement.
| To create and share an Interim Report of the first year impacts and learnings in September 2024 (using the content in the project update reports) which will feed into the final project impact report. NEW OBJECTIVE THAT WAS NOT IN CONTRACT | One interim report | 2024-09-01 |  | Everyone involved is proud of their contribution to an engaging and shareable report; and confident that it represents their experience and learnings in year 1. The report has a value to organisations outside of the project - orgs in the nature movement, and other community orgs in the CAF funding cohort. | We will check via surveys. We will have a specific session with National Lottery Community Fund about the learnings from year 1 and capture their feedback as well as sharing the results.
| To develop and deliver x1 online end-of-project conference and x1 final impact report for September 2025 (to include but not limited to Exec Summary, Presentation on Final Findings for Steering Group and Project Board - plus similar for the project conference). | One conference and one final report | 2025-09-01 |  | All participants co-create and are proud of the project report and conference. Both the report and conference contribute to additional future action by the participating organisations:- Co-op Member Pioneers report increased enthusiasm, confidence and skills in supporting local nature, environment and climate projects. Co-op staff and partners report increased understanding of their role in supporting local systems change, and are proud of helping make a difference. Co-op corporately have an enhanced story to tell to customers, suppliers and partners about living their commitment to nature and sustainability. NT, WWF and RSPB teams champion the role of community organisations in achieving local systems change for nature which ladders up directly to national systems change. National Lottery Community Fund value and disseminate the learnings from Nature Neighbourhoods and would look positively on a further application. | Via survey Qs we will test whether NN has helped organisations to leverage more funding; more influence/engagement from local system actors; new and more diverse participants; and contributed to other positive stakeholder relationships. We will test how and to what extent the PPfN-informed community-led plans for local system change are shaping the work of the x3 charities and their approach to power and knowledge sharing. This will be tested thgrough Qs to key teams and individuals; and also the x3 organisations' reports on their progress re: their reponses to the PPfN.