# Skills for the Future evaluation

Organisation	Heritage Lottery Fund

Department	Strategy & Business Development

Title of procurement		Skills for the Future evaluation: focus on workforce diversity

Brief description of supply	Evaluation services

Estimated value of tender	Up to £17,500, including expenses and VAT

Estimated duration	December 2017 to March 2018

Name of HLF Contact	Emma Stagg

Strategy & Business Development

02920 234 151

emma.stagg@hlf.org.uk

Timetable	Response deadline:

10am on 28 November 2017

Clarification questions deadline:

14 November 2017

Clarification & Negotiation meetings if required:

4&5 December 2017

Confirmation of contract:

Week commencing 11 December 2017

Completion of research:

23 March 2018

# 1.	Overview

  - The Heritage Lottery Fund (HLF) was set up in 1994 under the National Lottery Act and distributes money raised by the National Lottery to support projects involving the national, regional and local heritage of the United Kingdom. We operate under the auspices of the National Heritage Memorial Fund (NHMF). Since April 2013 we have been operating under our current Strategic Framework: ‘A lasting difference for heritage and people’. See the HLF website for more details.

  - HLF invests in the full breadth of the UK’s heritage and, through our funding, we aim to make a lasting difference for heritage and people. This is reflected in the outcomes for heritage, people and communities which underpin our grant-making.

  - HLF has invested in three rounds of Skills for the Future funding since 2009. A total of 111 projects have received funding (54 in 2009 – Cohort 1, 39 in 2012 – Cohort 2 and 18 in 2016 – Cohort 3) and 66 projects have completed. The grant programme was a strategic response to the impact of the recession, designed to put the heritage sector in a stronger position for recovery. It recognised the need for targeted employer-led interventions to deliver key heritage skills, sometimes what are niche skills needed by relatively small numbers of people in the heritage economy. The Skills for the Future programme built on the successful delivery of our smaller-scale Training Bursaries programme and both have sought to ensure the future sustainability of heritage through the supply of a skilled and more diverse workforce. The majority of the budget in a Skills for the Future project is dedicated to bursaries for trainees and direct training costs.

  - The aims of the Skills for the Future programme are to:

- fund high quality work based training opportunities to equip people with the skills to pursue a career in heritage;

- meet identified skills shortages and gaps in the heritage sector;

- enhance the capacity of the heritage sector to deliver sustainable training and share good practice; and

- increase the diversity of the heritage workforce.

  - For HLF, the lack of diversity in the current heritage workforce is a major concern. To reflect this, the outcome ‘more people and a wider range of people will have engaged with heritage’ was weighted in assessment of the applications to the Skills for the Future programme in 2016. Priority was given to projects which set ambitious and credible targets for the recruitment and support of trainees who will broaden the workforce profile of individual organisations and the heritage sector in the longer-term.

  - Interim evaluation with Cohort 2 Project Managers has shown that “the Skills for the Future programme has gone some way towards encouraging organisations to focus their efforts on attracting non-traditional candidates into the heritage sector. There are clear examples of success in attracting diverse groups.” Nevertheless, challenges remain.

  - A review of project evaluation reports (produced by grantees before completing projects), which we commissioned in 2016, noted that “evidence on progress towards the ‘workforce diversity’ strand of the programme is insufficient to draw clear conclusions on whether this aim has been achieved. Data on this aspect of the programme is very limited in the evaluation reports, and there is insufficient consistency in the way evaluations report the stated objectives, the quantitative targets and the projects’ actual achievements with regard to diversity. In particular, there is only limited and anecdotal evidence of increased workforce diversity in terms of ethnicity – whereas projects with an aim to recruit younger trainees or disabled people seem to have fared better.” The majority of the evaluation reports under review were focused on projects funded in the first cohort of Skills for the Future in 2009; we anticipate future evaluation reports might demonstrate improved data collection and diversity outcomes.

  - Wider monitoring and evaluation of the programme has indicated that projects focusing on an age imbalance within the heritage workforce have been reasonably successful. We know that 51% of trainees responding to our trainee starter survey were aged 18-25. As a result, we wish to focus this current research on projects that have addressed diversity in terms of:

- Disability;

- Gender;

- Race; and

- Lower-Socio-Economic Status.

  - In order to better support our grantees to diversify the workforce – whatever the grant programme they apply to in the future – we want to understand more about the success, or not, of Skills for the Future projects in recruiting a more diverse workforce and the experience of people who have benefited from this training.

1.10	The primary audiences for the report are HLF’s Board of Trustees, senior heritage sector leaders, and those practitioners responsible for heritage workforce development. The report will be circulated amongst all participating grantees.

# Methodology

  - A method for the work is open for consultants to propose. However, we anticipate that it will most usefully include the following:

  - A desk review of the application forms and training plans of 39 Skills for the Future projects (our Cohort 2 round of projects awarded funding in 2014) to:

- Identify the baseline data and gaps in the data used to establish the demographics of the workforce relating to the following sectors:

    - Museums, Libraries and Archives

    - Land and Biodiversity

    - Industrial, Maritime and Transport

    - Historic Built Environment.

- Identify the targets and plans proposed by individual grantees in relation to diversifying the workforce and judge the extent to which these targets and plans were specific, measurable attainable and appropriate.

- Identify a sub-sector of projects that included a focus on the following protected characteristics as part of their diversity focus:

  - Disability

  - Gender

  - Race

and/or sought to target trainees with

  - Lower-Socio-Economic Status.

  - A desk review of the success of individual projects (identified in c. above) in achieving their diversity targets and outcomes to identify best practice and lessons learnt using:

- Trainee starter and exit surveys;

- Grantee self-evaluation reports (15 completed to date) or progress reports where these are not yet available;

- An existing data set based on interviews with Project Managers;

- Interviews with former trainees.

  - A topic guide for interviews with a sample of former trainees with a protected characteristic or Lower-Economic Status.

  - Best practice guidelines for identifying and measuring progress against workforce diversity outcomes.

  - Ten case studies which highlight approaches to inclusive recruitment and retention that have applicability across the wider heritage sector.

# Outputs

  - The following outputs will be required:

- a draft final report in Word;

- a final report in Word;

- any other reports as set out here or agreed between HLF and the contractor;

- a set of presentation data such as a slide deck of infographic; and

- a set of research data, to be stored in a readily accessible electronic format such as Excel.

  - All reports must adhere to HLF’s accessibility and formatting guidance (appended).

  - The initial findings will be confidential to HLF. HLF may prepare or commission summary reports and other materials for subsequent wider distribution, based on the results.

  - All reports to include appendices as agreed between HLF and the contractor. The contents and structure of the report to be agreed in advance of writing. All reports to be supplied in electronic format and hard copy if requested.

  - All bidders are required to adhere to all appropriate regulations and guidelines on the collection, storage, transmission and destruction of personal data (MRS/SRA, Data Protection Act 1998: Guidelines for Social Research, April 2013).

# Contract management

  - We expect the research/evaluation to begin December 2017 and be completed by 23 March 2018. The final report shall be submitted to HLF by 2 March 2018.

  - The anticipated budget is up to £17,500 to include all expenses and VAT. The contract will be let by the National Heritage Memorial Fund.

  - The payment schedule will be 40% following the inception meeting and 60% on sign off the final reports.

  - The contract will be based on the HLF standard terms and conditions.

  - The research will be managed on a day to day basis for HLF by Emma Stagg.

# Award Criteria

  - A proposal for undertaking the work should include:

- a detailed method for undertaking the study;

- details of staff allocated to the project, together with experience of the contractor and staff members in carrying out similar projects. The project manager/lead contact should be identified;

- the allocation of days between members of the team;

- the daily charging rate of individual staff involved;

- a timescale for carrying out the project;

- an overall cost for the work.

  - Your Bid will be scored out of 100%.

70% of the marks will be allocated to your response to the Quality Questions below. Each question will be scored using the methodology in the table below.

Tender responses submitted will be assessed by HLF against the following Quality Questions:

| Quality Question | Weighting |
| --- | --- |
| - To what extent does the tender response demonstrate an understanding of the issues related to this research brief? | 40% |
| - To what extent is the method appropriate to the research requirements set out in this brief? | 30% |
| - What is the extent of the experience of similar heritage and social research? | 15% |
| - How well has the tenderer structured a research team in order to successfully manage the contract and deliver the required work to the budget and timetable required by HLF? | 15% |

## Quality Questions scoring methodology

| Score | Word descriptor | Description |
| --- | --- | --- |
| 0 | Poor | No response or partial response and poor evidence provided in support of it. Does not give the HLF confidence in the ability of the Bidder to deliver the Contract. |
| 1 | Weak | Response is supported by a weak standard of evidence in several areas giving rise to concern about the ability of the Bidder to deliver the Contract. |
| 2 | Satisfactory | Response is supported by a satisfactory standard of evidence in most areas but a few areas lacking detail/evidence giving rise to some concerns about the ability of the Bidder to deliver the Contract. |
| 3 | Good | Response is comprehensive and supported by good standard of evidence. Gives the HLF confidence in the ability of the Bidder to deliver the contract. Meets the HLF’s requirements. |
| 4 | Very good | Response is comprehensive and supported by a high standard of evidence. Gives the HLF a high level of confidence in the ability of the Bidder to deliver the contract. May exceed the HLF’s requirements in some respects. |
| 5 | Excellent | Response is very comprehensive and supported by a very high standard of evidence. Gives the HLF a very high level of confidence the ability of the Bidder to deliver the contract. May exceed the HLF’s requirements in most respects. |

30% of marks will be awarded for Price.

The evaluation of price will be carried out on the Schedule of charges you provide in response to Table A

## Price Criterion at 30%

- 30 marks will be awarded to the lowest priced bid and the remaining bidders will be allocated scores based on their deviation from this figure. Your fixed and total costs figure in your schedule of charges table will be used to score this question.

- For example, if the lowest price is £100 and the second lowest price is £108 then the lowest priced bidder gets 30% (full marks) for price and the second placed bidder gets 27.6% and so on. (8/100 x 30 = 2.4 marks; 30-2.4 = 27.6 marks)

- The scores for quality and price will be added together to obtain the overall score for each Bidder.

## Table A - Schedule of Charges

Please show in your tender submission, the number of staff and the amount of time that will be scheduled to work on the contract with the daily charging rate.

Please complete the table below providing a detailed breakdown of costs against each capitalised description, detailing a total and full ‘Firm Fixed Cost’ for each element of the service provision for the total contract period. Bidders may extend the tables to detail additional elements/costs if required.

VAT is chargeable on the services to be provided and this will be taken into account in the overall cost of this contract.

As part of our wider approach to corporate social responsibility the National Heritage Memorial Fund/Heritage Lottery Fund prefers our business partners to have similar values to our own. We pay all of our staff the living wage (in London and the rest of the UK) and we would like our suppliers and contractors to do likewise. Please highlight in you proposal/tender/bid whether you do pay your staff the living wage.

Bidders shall complete the schedule below, estimating the number of days, travel and subsistence costs associated with their tender submission.

TABLE A: (firm and fixed costs)

| Cost | Post 1 @cost per day (No of days) e.g. Project Manager/ Director @ £2 | Post 2 @cost per day (No of days) e.g. Senior Consultant/manager/researcher @£1.5 | Post 3 @cost per day (No of days) Junior Consultant/equivalent e.g. £1 | Total days | Total fees |
| --- | --- | --- | --- | --- | --- |
| Inception meeting to agree plans and finalise requirements with the Fund | Example 0.5 | 1 | 1.5 | 3 | £4 |
| [Add as necessary] |  |  |  |  |  |
| [Add as necessary] |  |  |  |  |  |
| [Add as necessary] |  |  |  |  |  |

| Cost Type | Value (£) |
| --- | --- |
| Sub - Total |  |
| VAT |  |
| Total* |  |

* (This must include all expenses as well as work costs; this figure will be used for the purposes of allocating your score for the price criterion and must cover the cost of meeting all our requirements set out in the ITT)

Notes: HLF reserves the right to clarify quality and prices and to reject tenders that demonstrate an abnormally low quality response. HLF also reserves the right to amend the timetable of work where required.

You should not submit additional assumptions with your pricing submission. If you submit assumptions you will be asked to withdraw them. Failure to withdraw them will lead to your exclusion from further participation in this competition.

# Procurement Process

  - HLF reserves the right to reject abnormally low scoring tenders. HLF reserves the right not to appoint and to achieve the outcomes of the research/evaluation through other methods.

  - The procurement timetable will be:

Deadline for clarification questions*: 14 November 2017

Tender return deadline: completed proposal to be returned to HLF by 10.00 am on 28 November 2017.

Clarification meetings** may be held with shortlisted consultants and would take place on week commencing 4 December 2017

HLF will notify bidders of our procurement decision week commencing: 11 December 2017.

*HLF will upload responses to clarification on our website, here.  Please note that we will make the anonymised questions, and our responses to them, available to everyone on the HLF website.

**We reserve the right to carry out clarifications if necessary; these may be carried out via email or by inviting bidders to attend a clarification meeting.  In order to ensure that both HLF’s and Bidder’s resources are used appropriately, we will only invite up to three (the ultimate number will depend on the closeness of the scores) highest scoring bidders to attend a clarification meeting.  Scores will be moderated based on any clarifications provided during this meeting.  You are responsible for all your expenses when attending such meetings.

  - Your tender proposals must be sent electronically via e-mail before the tender return deadline of 10am on 28 November to the following contact:

Diane La Rosa

Heritage Lottery Fund

Holbein Place

London

SW1W 8NL

Diane.La.Rosa@hlf.org.uk

  - Please visit the HLF website for further information about the organisation.

# Appendix: Accessibility and formatting guidance

HLF is committed to providing a website that is accessible to the widest possible audience. Our site is annually tested by accessibility auditors and we must meet a AA compliance level. Our accessibility testing encompasses not just site functionality and design but all of our content, including downloadable documents.

Reports and other documents created for HLF (including the tender submissions) need to be clear, straightforward to use and ready to circulate internally, externally and online, as well as suitable for use by screen reading software. Best practice in accessibility is summarised below:

## Readability

In the final report, and all other documents that may be published online including the tender application consultants should ensure that:

- The size of the font is at least 11pt;

- There is a strong contrast between the background colour and the colour of the text. Black text on a white background provides the best contrast. This also applies to any shading used in tables and/or diagrams;

- Italics are only used when quoting book titles for citations and items on the reference list should be arranged alphabetically by author

- Colour formatting and use of photos should be of a resolution size that is easily printable and does not compromise the printability of the document.

For further guidance on ensuring readability of printed materials, please refer to the RNIB Clear Print guidelines. These can be found on the RNIB website.

## Accessibility

Reports should adhere to the following guidelines:

## Formatting

Headings and content in your document should be clearly identified and consistently formatted to allow easy navigation for users. Heading Styles should be used to convey both the structure of the document and the relationship between sections and sub-sections of the content. Heading styles should follow on from each other i.e. Heading 1 then Heading 2.

## Spacing

Screen readers audibly represent spaces, tabs and paragraph breaks within copy, so it is best practice to avoid the repetitive use of manually inserted spaces. Instead, indenting and formatting should be used to create whitespace (e.g., use a page break to start a new page, as opposed to multiple paragraph breaks).

## Alternative text

Alt text is additional information for images and tables. This extra information is essential for both document accessibility (screen reading software reads the Alt text aloud) and for the web. Alt text should be concise and descriptive, and should not begin with ‘Image of’ or ‘Picture of’.

## Images

These should be formatted in-line with text, to support screen readers. Crediting pictures may be necessary, usually in response to a direct request from a third party.

## Tables

These should be for used for presenting data and not for layout or design. They should be simple and include a descriptive title. The header row should be identified and there shouldn’t be more than one title row in a table. There should be no merged or blank cells.

## Additional documents

Any additional information, separate to the report, for example proformas and transcripts which may be used as standalone documents must be fully referenced to the piece of work being submitting and therefore dated, formatted and numbered appropriately.

## Acknowledgement

All reports should acknowledge HLF. Our logo can be found on the HLF website.

## Further resources

Please refer to the WCAG 2.0 article on PDF techniques for further information.

Submitting your report to HLF

Please check the accessibility of your document using the Word accessibility checker before submitting: File – Info – Check for Issues – Check Accessibility.

Please submit your document as a Word file.

HLF retains the right to amend documents in order to create accessible versions for publishing.