Due Diligence Consultancy for Transfer of Estates Function to HMCTS

Statement of Requirements - Annex B

# PURPOSE

  - The purpose of this requirement is to undertake a due diligence exercise on the Estates Services and resources that will pass from the Ministry of Justice (MoJ) to the newly created Property Directorate in Her Majesty’s Courts and Tribunals Service (HMCTS) to confirm the scope of services that will transfer, the management information that currently exists to support those services and the obligation within the services and to whom these need to be provided. This work will ensure the smooth transfer of these services between MoJ and HMCTS.

  - The presentation of options for how it should take forward the management of the services into a future operating model.

  - The objective of this due diligence work is to provide HMCTS with a clear understanding of the services and requirements that are proposed to transfer from the MoJ to HMCTS, how that transfer should be managed and suggestions on the future operating model for the Estate function.  An assessment of short and medium terms risks should be provided.

# BACKGROUND TO THE CONTRACTING aUTHORITY

Her Majesty’s Courts & Tribunals Service (HMCTS) is responsible for the administration of the Court system across England and Wales and for the administration of the majority of the Tribunals system across the UK. It is run as a partnership between government and the judiciary, ensuring that justice can be done, and the rule of law supported. The function of HMCTS affects the lives of millions of people across the UK every year, whether directly or indirectly.

HMCTS is a large government agency, employing around 18,000 staff, and operating from just under 500 locations with a gross annual budget of around £1.8bn.

HMCTS is an executive agency sponsored by the Ministry of Justice (MoJ).

# Background to requirement/OVERVIEW of requirement

  - Like any service provider, the success of HMCTS depends on the quality of the service we provide and how we are meeting user expectations in the modern age. We know the level of service currently received at a court or tribunal is at best inconsistent and, at worse frustrating, despite the great efforts of our staff. Our model for service provision is clearly outdated - accessing our service often involves filling in paper forms, travelling to one of our buildings to complete a simple process or arranging face-to-face meetings to get basic guidance and advice. This leads to unnecessary complexity, confusion and delay for our users – as well as high levels of cost.

  - Even where we have tried to introduce more digital ways of working, we often rely on digitised versions of paper based business processes, layered on top of legacy IT systems, some of which are over 30 years old. They were not designed with a digital service in mind, being built to replicate paper forms and processes rather than taking advantage of opportunities to pre-populate or respond to users’ selections. We have outdated back-end systems that prevent effective data sharing with our partner agencies, adding to delay, inefficiency and failure in the system. Our services have often been designed in silos, rather than developing a consistent approach to our user experience across our service.  It follows that our user experience is inconsistent and unnecessarily confusing, particularly to our vulnerable users.

  - HMCTS is committed to creating a modern, effective and user-friendly Courts & Tribunals Services that delivers better justice at lower cost. HMCTS has secured a package of investment worth up to £780m over 5 years to embark on an ambitious programme of change and innovation to deliver a system that is fit for the 21st century.  Backed by the Lord Chief Justice, the Senior President of Tribunals and HM Treasury, this programme will deliver radical change and leave a sustainable legacy for this crucial public service that individuals, communities and businesses rely on across the UK. We are calling this transformation “The Reform Programme”.

3.4	In early 2015 the HMCTS Reform Programme (the programme) commenced work to develop a coherent, future-proofed and user-centric vision and strategy for the transformation of HMCTS, and as of April 2016 the Programme moves into delivery.

# scope of requirement

4.1	The seven areas of activity shall be considered against the following:

4.1.1	Current Organisation and Operating Model

HMCTS wishes to understand at a high level:

•	the organisation of the current function, spans of control, authority and delegation etc,

•	the service obligations of the current function

•	The schedule of standard operating procedures and processes

•	A description of the function's internal control and governance procedures

•	The current expected levels of service and the arrangements that exist for monitoring and ensuring compliance, including reporting

•	IT and Management systems

4.1.2	Finance

The transfer of the services to HMCTS will mean that HMCTS has direct financial responsibility. HMCTS wishes to understand the extent of these financial responsibilities in the following areas:

•	Total annual outgoings

•	Service Charges

•	Rates

•	Other Occupation Costs

•	Utility Costs

•	Facilities Management

•	Capital

•	Function Operating costs

By benchmarking against other industry sectors whether the budget allocated for the management of the running of the organisation is sufficient to meet the needs and the options for improving the way that the services are delivered.

HMCTS would like to understand the underlying financial control and budgeting process in place and their relative effectiveness

41.3	Commercial and contractual relationships

An appropriate view of the current contractual landscape, and any commercial/legal risks/issues arising from the transition.

4.1.4	Management and Performance Information

HMCTS wishes to understand the current management and performance information for Estates that is measured and reported including the current high level indicators of success. This could include information that is directly generated internally within HMCTS and MoJ and/or is provided by external suppliers. The use that is made of this information and how far the information influences decisions at a strategic level and feeds into the current high level indicators of success.

HMCTS will be seeking to ensure that the future indicators of success are aligned to the broader objectives of HMCTS. To achieve this alignment, HMCTS needs to know whether the current information is complete or whether there are any significant areas of information that are missing that should be obtained. If there are any significant gaps, the benefits of collecting the information and options as to how this information could be cost effectively provided.

4.1.5	Building a future Target Operating Model

HMCTS wishes to establish whether the current operating model, as will transfer from MoJ, is appropriate to meet the future needs and challenges of HMCTS. We require proposals on the options about the types of operating models that currently exist for a similar size estate taking into consideration the unique nature and usage of the HMCTS estate. The steps that would be required to achieve these options, the risks that exist and how they could be mitigated and the opportunities and benefits that they offer.

4.1.6	People and Process transfer

The transfer of the Estate function may involve upwards of 50 staff transferring from MoJ to HMCTS. (HMCTS want to know the most effective way that staff could be transferred across).

4.1.7	Risk, mitigation and opportunities

This should consider the risks that currently exist within the Services to be transferred across to HMCTS and how they are currently managed and mitigated.

The challenges and risks that will arise during the transition of the services from MoJ and HMCTS and how they could be managed and mitigated. HMCTS would be willing to consider a phased approach to the transfer of services rather than a big bang approach, if the challenges and risks were considered too great.

The opportunities there may be during the transition of the services from MoJ and HMCTS to deliver immediate improvements to the delivery of services and the key steps in taking forward those opportunities.

The risks that will exist following the transfer of the Services to be transferred across to HMCTS and how they should be managed and mitigated. It is recognised that the risks may be the same as exist prior to the transfer to HMCTS but we are keen to identify any new risks, changes in the levels of risks or different ways that the risks could be managed and mitigated.

# The requirement

5.1	Process and Suppliers Approach

HMCTS will assist in gathering key information which the supplier will require. There will also be a need to engage with a range of people to gather and understand the information including senior management, members of the HMCTS Estates team, members of the MoJ Estates team, members of the Commercial and Contract Management Directorate (CCMD) and other staff throughout the organisation. HMCTS will facilitate the meetings.  There may be some sensitivity about engaging with staff and we will assist in this.

HMCTS are looking for proposals detailing the approach that would be undertaken to gather information, the initial and subsequent engagement with staff to build effective relationships and to ensure that information is obtained.

HMCTS envisage that this work will take place over a six week period.  HMTCTS requires a combination of Partner/Director, senior managers and managers/business analysts. With regard to the Partner/Director, they should have a specific role not a quality assurance role within the assignment.

See also Section 6. Key Milestones.

5.2	Format of Output

HMCTS are seeking a strategic focused report that shows the required due diligence on the seven areas of activity that will transfer and reflects the Scope. It should provide a clear understanding about the transfer of Estates function to HMCTS, a health check on the Estate function, the roles and responsibilities that HMCTS will be assuming with the transfer, the options available for improvements and future operating model and the risks and opportunities that exist.

The report should be written in non-technical language which is capable of easily being transferred to other environments so that key issues and information can be understood within the broader HMCTS.

In preparing the report HMCTS will expect that comparisons of practice and benchmarking will be undertaken with other appropriate sectors, whilst recognising the unique nature of the HMCTS estate, to identify options and approaches that could be adopted by HMCTS to deliver a high performing Estate function.

5.3	An indicative timetable for the process and approach is set out below in 6.1

# key milestones

## 6.1	The Potential Provider should note the following project milestones that the Authority will measure the quality of delivery against:

| ### Milestone | ### Description | ### Timeframe |
| --- | --- | --- |
| ### 1 | ### Mobilisation and initial fact gathering and engagement meetings | ### Within week 1 of Contract Award |
| ### 2 | ### Information gathering and staff engagement leading to production of an initial report and presentation to senior stakeholders. | ### Within weeks 2 - 3 of Contract Award |
| ### 3 | ### Using feedback about the initial report to determine further information gathering and staff engagement: ### Production of the final report and presentation to senior stakeholders. | ### Within weeks 4-6 of Contract Award |

# authority’s responsibilities

## See 6.1 detailing how HMCTS will assist with the supplier.

# PRICE

## Prices are to be submitted via the BRAVO Solutions e-portal excluding VAT using Annex E.

# STAFF AND CUSTOMER SERVICE

## The Authority requires the Potential Provider to provide a sufficient level of resource throughout the duration of the Contract in order to consistently deliver a quality service to all Parties.

## Potential Provider’s staff assigned to the Contract shall have the relevant qualifications and experience to deliver the Contract.

## The Potential Provider shall ensure that staff understand the Authority’s vision and objectives and will provide excellent customer service to the Authority throughout the duration of the Contract.

# Security requirements

- 10.1 	Within one (1) Month of the Commencement Date, the Provider shall provide for Approval a draft Security Plan setting out its proposals for ensuring compliance with the Authority IT Security Policy.  Within such reasonable timescales as is notified by the Authority the Provider shall update and implement the Approved Security Plan taking into the account the Authority’s comments and recommendations.

- The Security Plan will set out the security measures to be implemented and maintained by the Service Provider in relation to all aspects of the Services and all processes associated with the delivery of the Services and shall at all times comply with and specify security measures and procedures which are sufficient to ensure the Services comply with:

    - the Client IT Security Policy;

    - any further requirements set out in the Requirements relating to security; and

    - the Data Protection Legislation and the obligations imposed on the Service Provider under Clause.

- The Provider shall comply, and shall procure the compliance of its Sub contractors and the Provider Personnel with the IT Security Policy and the Security Plan and the Provider shall ensure that the Security Plan fully complies at all times with the Client IT Security Policy.

- The Plan will be reviewed and updated by the Service Provider annually to ensure it continues to meet with the Requirements and any other requirements and of the Authority.

Any changes to the Security Plan shall be made in accordance with the Change Control Procedure.

# payment

### The Customer shall pay all sums properly due and payable to the Supplier in respect of the Contract Services in cleared funds by no later than thirty (30) calendar days after the date of a validly issued invoice for such sums.

### The Supplier shall ensure that each invoice (whether submitted electronically or in a paper form) contains all appropriate references and a detailed breakdown of the Contract Services provided and any disbursements and that it is supported by such other documentation as may reasonably be required by the Customer to substantiate the invoice.

### The Supplier shall ensure that all invoices submitted to the Customer for Contract Services are exclusive of the Management Charge payable to the Authority in respect of the Contract Services. The Supplier shall not be entitled to increase the Contract Charges by an amount equal to such Management Charge or to recover such Management Charge as a surcharge or disbursement.

### The Supplier shall make any payments due to the Customer without any deduction whether by way of set-off, counterclaim, discount, abatement or otherwise unless the Supplier has a valid court order requiring an amount equal to such deduction to be paid by the Customer to the Supplier.

### All payments due shall be made in cleared funds to such bank or building society account as the recipient Party may from time to time direct in writing.

### 11.2	Staged Payment

### Payment shall be paid in two stages. The first stage will be paid on completion of milestones 1 and 2 (and outlined in 6.1).  This first stage will be on a time and materials (T&M) basis and capped at 50% of the overall bid price. The second stage payment will be paid on production of a final signed off report and successful presentation to senior stakeholders (milestone 3). The second staged payment will 50% of the overall bid price.  The overall price will be capped at the bid price and payment shall not exceed this amount.

## Recovery of Sums Due

## Wherever under the Contract any sum of money is recoverable from or payable by the Supplier (including any sum which the Supplier is liable to pay to the Customer in respect of any breach of the Contract), the Customer may unilaterally deduct that sum from any sum then due, or which at any later time may become due to the Supplier under the Contract

### Any overpayment by either Party, whether of the Contract Charges or of VAT or otherwise, shall be a sum of money recoverable by the Party who made the overpayment from the Party in receipt of the overpayment.

# Location

## The location of the Services will be carried out at Ministry of Justice, 102 Petty France, London. This site will be deemed the ‘home office’ for travel and subsistence purposes.