# Call-Off Schedule 20 (Call-Off Specification)

This Schedule sets out the characteristics of the Deliverables that the Supplier will be required to make to the Buyers under this Call-Off Contract

Bid Pack

Attachment 3 – Statement of Requirements

Contract Reference: CCCC25A08

Procurement / Contract Title: Provision of Social Care Discovery

CONTENTS

1.	PURPOSE AND OVERVIEW OF THE REQUIREMENT	3

2.	BACKGROUND TO CCS	3

3.	BACKGROUND TO THE REQUIREMENT	3

4.	DEFINITIONS	4

5.	SCOPE OF THE REQUIREMENT	4

6.	MANDATORY DELIVERABLES (SUPPLIER RESPONSIBILITIES)	5

7.	POTENTIAL, ACTUAL OR EXPECTED DELIVERY VOLUMES (IF APPLICABLE)	8

8.	LOCATION	8

9.	CCS RESPONSIBILITIES	8

10.	KEY MILESTONES AND DELIVERABLES	9

11.	SUSTAINABILITY AND CARBON NET ZERO	9

12.	SOCIAL VALUE	10

13.	STAFF AND CUSTOMER SERVICE	10

14.	CONTINUOUS IMPROVEMENT	10

15.	SECURITY AND CONFIDENTIALITY REQUIREMENTS	10

16.	PRICING MECHANISM	11

17.	PAYMENT AND INVOICING	11

18.	CONTRACT MANAGEMENT AND KEY PERFORMANCE INDICATORS	12

# PURPOSE AND OVERVIEW OF THE REQUIREMENT

Project Overview:

  - CCS is launching a first-phase Discovery Project into Social Care to scope and map options and opportunities for CCS’ future direction and participation in the Social Care market, focusing on the Adult Social Care sector.

  - CCS is interested in how it and other organisations can deliver the best value for its customers, public sector and citizens through involvement in the Social Care sector. This Discovery Project will start the journey for CCS to enable discussions and strategy development on its involvement in this sector. This would include how CCS can support customers from a commercial perspective, including the determination of future work scope and continuation into future phases of work. This may involve a decision not to participate further or to offer a phased approach to implementing new Frameworks or other support services.

  - This work is expected to be completed in 2025 with a maximum duration of up to 20 weeks. The Project will conclude with a recommendations report that will enable an informed decision on CCS' future plans in this sector. CCS works in partnership with other organisations including Public Buying Organisations, Government Departments and Local Authorities. CCS anticipates that the final report will be shared with these organisations.

# BACKGROUND TO CCS

  - CCS is a procurement organisation that is here to help the UK public sector get better value for money from its procurement of goods and services. We support government departments as well as public and third sector organisations and, by working together, contribute to the delivery of world-class public services for UK citizens.

  - Customers and their individual needs are at the heart of everything we do. We help 20,000 of them across the length and breadth of the country, advising and assisting in the purchase of everything from locum doctors and laptops to police cars and electricity. We have the opportunity to indirectly build stronger communities in all parts of the UK and support the public sector on its sustainability journey to help power up Britain.

# BACKGROUND TO THE REQUIREMENT

Adult Social Care Sector:

  - CCS works closely with customers and stakeholders in Central and Local Government and recognises the challenges in the sector and the potential for CCS to help define its role in supporting buyers across the landscape.

  - It is recognised that there are significant challenges in this market and that there are increasing pressures in this sector. CCS has not provided solutions that are all-encompassing or that focus in particular on the delivery of products and services that are solely dedicated to Adult Social Care delivery and support.

  - This Discovery Project is aimed at demonstrating what value CCS can add to this market to enable better outcomes for local authorities and how it can extend coverage. It is key for this discovery to collaborate closely and listen to our customers to inform future phases of work in this area and to be supported by comprehensive market analysis and understanding.

  - The report should consider how CCS can make the case for delivering commercial value to this market area on a national scale, or where it can make targeted impacts over the coming financial years.

  - This will be a new contract for CCS, and we do not have any existing live contracts in place relative to this sector specific discovery.

  - There will be no need to collaborate or integrate with other Suppliers, as this project is independent.

# DEFINITIONS

| Expression or Acronym | Definition |
| --- | --- |
| CCS | Means; Crown Commercial Service |
| MHCLG | Means; Ministry of Housing, Communities and Local Government |
| LGA | Means; Local Government Association |
| ADASS | Means; Association of Directors of Adult Social Services |
| ADCS | Means; Association of Directors of Children's Services |
| SOLACE | Means; Society of Local Authority Chief Executives |
| NHS | Means; National Health Service |

# SCOPE OF THE REQUIREMENT

  - This is a first-phase project that will help support how CCS can support its key partners and define a possible future role in providing buying solutions or other support mechanisms in the Adult Social Care market.

  - This project considers that all elements of Adult Social Care will be in the scope of the first phase of this project. This would include a non-exclusive list of Adult Social Care and community-based commissioned services.

  - This project aims to build upon engagement and work completed to form a comprehensive view of the market and opportunities for CCS.

  - It is expected that the Discovery Partner will deliver and enable the following inputs to the report:

    - A proposal of an effective plan of delivery of the Discovery Project with weekly updates provided, including:

      - Ensuring engagement with a selected group of stakeholders to inform the progress of the Discovery project and to inform eventual outcomes.

      - Providing existing knowledge of capability, capacity, and health of the Adult Social Care market.

  - As a result of this project, the following is expected to be considered and collated into a final report:

    - A comprehensive market analysis of the sector, setting out the market appetite for national value-adding activity through a qualitative and evidence-based assessment.

    - A consolidated view of public sector organisations, in particular local authorities, interest in CCS’ role in this market and how we could achieve better commercial value in this market with a summarised view of customer and stakeholder interests and views.

    - To understand the capability and capacity for CCS to deliver national value-adding informed by the perspectives of buyers and suppliers.

    - Options analysis and appraisal for opportunities in this sector for CCS, including commercial interventions and solutions.

    - A categorised view of the supplier market supporting the Adult Social Care sector.

  - The report should be structured into three main categories:

    - Market Analysis;

    - Customer Engagement; and

    - Options appraisal and analysis.

  - The Discovery Project would be expected to be up to 12 weeks in duration, with the overall project not exceeding 20 weeks.

# MANDATORY DELIVERABLES (SUPPLIER RESPONSIBILITIES)

Report Requirements:

  - The priority for the Discovery and final report is to set out a direction for CCS to consider options for future involvement in this market area. It is expected that this report will potentially provide recommendations on how CCS can be involved, for example:

    - Provision of products such as Commercial Frameworks, including Dynamic Purchasing System.

    - How it can best provide commercial advisory services and market support to customers.

    - How CCS could potentially partner with organisations to deliver commercial solutions.

    - Piloting solutions in focused market areas in the sector or with a specific defined focus area.

    - Enabling or achieving innovation or new solutions in this market area.

    - Accessing existing CCS services and how to maximise these services within the sector.

    - Providing other value-add products or services.

  - This report may also consider where CCS should pause activity to focus on other priority areas such as further exploring the market, awaiting future direction or developing further networks in this sector as examples. This report may conclude not to further activity.

  - Key Documentation:

  - It is expected that the Discovery Partner will provide the following documentation:

    - A detailed market assessment included in a report, with the provision of any key data and information supporting conclusions.

    - Consolidation of customer and stakeholder viewpoints and inputs into a written report.

    - Conclusions and recommendations, with a focus throughout the market assessment and customer and stakeholder reports on the options appraisal and future recommendations for CCS’ involvement in the market.

    - A detailed assessment of options, including a comprehensive options analysis outlined within the final report.

    - Presentation material, including a short presentation with an overview of the Discovery (5 slides max.) and a summary of the outputs of the Report (20 slides max.).

  - Market and Suppliers:

  - Consideration and analysis of the following factors:

    - Market capability and capacity for any national value-adding activity;

    - A qualitative and evidence-based assessment of the interests of suppliers in the market;

    - Local and national market areas and supply chains;

    - Market Health;

    - Cost drivers for services;

    - The role of private financing in the sector;

    - Understanding profitability in the sector supplier drivers and the buyer's bargaining power nationally;

    - National, regional, local, and hyper-local markets;

    - Frameworks and Contracts that are in place today across PBOs and other local arrangements with an analysis of their effectiveness;

    - Benefits of a national commercial solution to help drive economies of scale, access to the market, suppliers, and providers, and to facilitate effective buying routes;

    - Key future drivers and potential developments in the market that may impact the sector and commercial arrangements;

    - Delivery of key government and local authority procurement priorities including local supply chains, social value, carbon net zero, and tackling modern slavery; and

    - A concise overview of high-performing international government-led adult social care sectors, encompassing the promotion of innovation.

  - Health Care, Local Authorities, Buyers, Commissioners & Users

  - Consideration of the following factors:

    - Detailing key stakeholders and lobbyists, including details of interest level, role, and potential engagement requirements of CCS.

    - Detailing the role of Central Government departments and their requirements for the future.

    - Potential for public sector organisations, particularly local authorities, to achieve better commercial value in the Adults Social Care Services Market.

    - Reviewing current work and progress to date in forming commercial arrangements, including assessment of existing commercial routes to market.

    - Engagement and insight from key public sector stakeholders such as MHCLG, the LGA, ADASS, ADCS, SOLACE and NHS England.

    - Engagement with key customers in the market to capture priorities and gauge the interest in and appetite for national commercial solutions, including the preferred scope and scale of services covered.

    - The potential change of government and likely policy shifts which may arise and have an impact on the market.

  - Options Appraisal and Recommendations:

    - The identification of any opportunities for CCS to add value for the public sector through an increased national role in this market.

    - Identification of any opportunities for strategic and operational efficiencies which could be delivered through a national commercial solution.

    - If it is determined that national procurement solutions would not provide benefit, outlined improvements that can be made to existing services to increase efficiency and effectiveness in the sector.

    - Why the move to provide national social care procurement solutions would or would not provide benefits to CCS and the sector.

    - Understand the reputational and resource inputs and potential risks for CCS associated with a national procurement provider in these sectors.

    - An analysis of the existing products and services that could be tailored to provide additional benefit or value to customers.

    - Detail the capacity, skills, and specific resource requirements CCS will need to build a commercial/customer and technical team for Social Care.

    - Ensuring that any proposed solutions are aligned with any regulatory requirements.

  - The Supplier should be capable of supplying CCS with examples of previous work in the pertinent sector, along with the associated outcomes.

  - The Supplier must ensure that the resources allocated to the project possess adequate expertise and experience in the sector to meet the outline report requirements.

# POTENTIAL, ACTUAL OR EXPECTED DELIVERY VOLUMES (IF APPLICABLE)

  - It is anticipated that this will constitute a standalone discovery requirement; however, depending on the initial findings, CCS may necessitate further discovery in the future.

  - Volume of requirements cannot be guaranteed.

# LOCATION

  - All work will be actioned remotely. In the event that face-to-face meetings are required, these will be located at either a UK CCS site or UK Supplier site.

# CCS RESPONSIBILITIES

  - CCS will provide all the necessary upfront criteria, to enable the Supplier to gather and present against the report requirements.

  - CCS will arrange any necessary security access in the event that CCS onsite meetings are required.

  - CCS will ensure that sufficient resource and points of contacts are put in place to support Supplier enquiries.

  - CCS will schedule weekly progress calls to be held virtually with the Supplier.

# KEY MILESTONES AND DELIVERABLES

  - The Supplier must ensure that the Social Care Discovery project does not exceed 20 weeks from initiation to close, with the final report and presentation to CCS by week 16.

  - The following Contract milestones/deliverables shall apply:

| Milestone / Deliverable | Description | Timeframe or Delivery Date |
| --- | --- | --- |
| 1 | Project team assigned; CCS contact initiated | By week 1 from Contract Award |
| 2 | Suppliers outline plan and approach to CCS | 10 days from contract Start |
| 3 | Market Discovery and Analysis | By no later than week 7 from Contract Award |
| 4 | Finalising Report | By no later than week 10-12 from Contract Award |
| 5 | Present Final Report | By Week 12-16 |
| 6 | Revisions IF required | By week 18 |
| 7 | CCS Approval and acceptance of the final report | By week 20 |

# SUSTAINABILITY AND CARBON NET ZERO

  - The Supplier is required to provide training for their team on sustainability practices relevant to the project, ensuring that all personnel are knowledgeable about their environmental responsibilities.

  - All materials, where possible, used in project delivery must be sourced sustainably, including preference for recycled, reclaimed, or sustainably-sourced products.

  - The Supplier is required to employ sustainable work practices, such as minimising waste, using energy-efficient methods, and sustainable travel policies

  - The Supplier will be committed to delivering services in a manner that considers environmental impacts and social responsibility, ultimately contributing to a more sustainable project outcome.

# SOCIAL VALUE

  - The Supplier is required to work towards initiatives that demonstrate their contribution to:

    - Workforce Diversity & Inclusion – Creating opportunities for underrepresented groups, including training and employment initiatives.

    - Skills Development & Employment – Providing upskilling programs, or career development support.

  - The Supplier is required to collaborate with CCS to enhance project management competencies and the skills associated with discovery research within CCS, thereby supporting workplace skill development.

# STAFF AND CUSTOMER SERVICE

  - The Supplier shall provide a sufficient level of resource throughout the duration of the Contract in order to consistently deliver a quality service within the outline timescales.

  - The Supplier’s staff assigned to the Contract shall have the relevant qualifications and experience to deliver the Contract to the required standard.

  - The Supplier shall ensure that staff understand CCS vision and objectives and will provide excellent customer service to CCS throughout the duration of the Contract.

# CONTINUOUS IMPROVEMENT

  - Changes to the way in which the Services are to be delivered must be brought to CCS attention and agreed prior to any changes being implemented.

# SECURITY AND CONFIDENTIALITY REQUIREMENTS

  - Please refer to Call-Off Schedule 9 (Security).

  - The Supplier must treat all information as commercially sensitive, including but not limited to publishing any reference to the contract and its contents on external media sites.

  - Any external communications must be referred to CCS before publication.

  - The Supplier must make CCS aware of any conflict of interest that may occur in them undertaking this project. This should be notified to CCS ahead of project commencement.

  - Any conflict of interest that arises during project execution should be detailed and escalated immediately to the CCS.

  - CCS is the data controller and the Supplier, or any subcontractors, will be a data processor.

# PRICING MECHANISM

  - Please refer to Call-Off Schedule 5 (Pricing).

  - All prices are excluding VAT and are inclusive of expenses, such as travel and subsistence.

# PAYMENT AND INVOICING

  - Payment milestone as follows:

| Milestone / Deliverable | Description | Timeframe or Delivery Date | Payment |
| --- | --- | --- | --- |
| 1 | Project team assigned; CCS contact initiated | By week 1 from Contract Award | Week 8 - 20% of the total cost will be paid on CCS acceptance of the delivered services against the outlined requirements and deliverable milestones. |
| 2 | Suppliers outline plan and approach to CCS | 10 days from contract Start |  |
| 3 | Market Discovery and Analysis | By no later than week 7 from Contract Award |  |
| 4 | Finalising Report | By no later than week 10-12 from Contract Award | Week 16 - 30% of the total cost will be paid on CCS acceptance of the delivered services against the outlined requirements and deliverable milestones. |
| 5 | Present Final Report | By Week 12-16 |  |
| 6 | Revisions if required | By week 18 | Week 20 - 50 % of total cost will be paid on CCS acceptance of the final report delivered against the outline requirements and deliverable milestones. |
| 7 | CCS Approval and acceptance of the final report | By week 20 |  |

  - Payment will only be made following satisfactory delivery of the agreed deliverables at each stage, accepted and signed off by the CCS.

  - CCS will establish a team to review the outputs, including the final report and approve acceptance.

  - Before payment can be considered, invoice/s must include a detailed elemental breakdown of work completed and the associated costs.

  - Electronic Invoices should be submitted to the following email address for request for payment: supplierinvoices@crowncommercial.gov.uk.

  - Hard copy invoices should be submitted to: Crown Commercial Service, 8th Floor, The Capital, Old Hall Street, Liverpool, L3 9PP.

# CONTRACT MANAGEMENT AND KEY PERFORMANCE INDICATORS

  - Please refer to Call Off Schedule 15 (Call-Off Contract Management).

  - Within 10 Working Days of the contract Start Date, the Supplier shall provide CCS with details of how they intend to proceed with the Social Care Discovery activity. This must be communicated and agreed by both CCS and the Supplier.

  - The Supplier shall attend weekly progress meetings held virtually with CCS, providing updates in alignment with the outlined proposal. Update reports should be provided in word/excel/PowerPoint format, as preferred by the Supplier.

  - CCS will facilitate the weekly calls.

  - The Supplier may be required to participate in more frequent progress meetings if necessary.

  - As part of the weekly calls, the Supplier is expected to provide details of progress, such as, but not exhausted:

    - Project Status Updates: Regularly provide comprehensive updates on the overall status of the project, including key developments

    - Progress Reports: Discuss comprehensive progress reports, including the consultant's grade and the time taken to complete the work undertaken. Outline completed tasks, milestones achieved, and any deviations from the initial plan.

    - Timescale Reviews: Assessment of the project timeline, highlighting any necessary adjustments and the rationale behind such changes.

    - Concerns and Resolutions: Address any emerging concerns promptly, ensuring that potential issues are identified and resolved efficiently to maintain project momentum.

  - CCS will measure the quality of the Supplier’s delivery by:

| KPI/SLA | Service Area | KPI/SLA description | Target |
| --- | --- | --- | --- |
| 1.1 | Supplier Engagement and Responsiveness | The Supplier's appointed Project Manager must respond to all communications from CCS within 24 hours, ensuring a smooth flow of information and timely decision-making | 95% adherence |
| 1.2 | Supplier Engagement and Responsiveness | Meetings and workshop attendance, represented by the relevant resources | 100% attendance |
| 1.3 | Supplier Engagement and Responsiveness | Supplier must notify CCS prior to any delegation of responsibilities by the Supplier’s Contract Manager | achieve 100% compliance |
| 2 | Issue Management | Supplier will work to resolve identified issues within three working days | achieving a target of 95% |
| 3 | Risk | Identify and report 100% of potential risks, ensuring that all findings are communicated to CCS promptly | within 3 working days of recognition |
| 4.1 | Operational | On -time delivery rate | 95% on time to deliver |
| 4.2 | Operational | Resource utilisation | 95% effectiveness of allocated resources |
| 4.3 | Operational | Adherence to budget | 100% compliance |
| 4.4 | Operational | Report Accuracy | Less than 5% revisions |

  - CCS reserves the right to terminate and exit the contract in accordance with Call-Off Schedule 10 (Exit Management).