## Summary Sheet
M621 J1 to J7
Traffic Management Bill of Quantities
ITEM | Description | Cost
A | Traffic Management for Site Compounds | N/A
B | Traffic Management - Mobilisation | 0
C | Traffic Management | 0
D | Temporary Vehicle Restraint System | 0
E | Maintenance (Plant & Labour Only) | 0
F | Temporary Automatic Speed Camera at Roadwork's (TASCAR) | 0
G | Journey Time Reliability Signs & ANPR Cameras | 0
H | Vehicle Recovery | 0
I | Temporary CCTV | 0
J | Additional items | 0
K | TM Staff Resource | 0
| Total Cost | 0

## B - TM Mobilisation
B) M621 J1 to J7 - Traffic Management Package - TM Mobilisation
Item | Description | Quantity | Unit | Rate | Total | Notes
B1 | Mobilisation of Main Works
B1.1 | Mobilisation at start of project (Prepare equipment, load at source etc.) | 1 | Item |  | 0
B1.2 | Install maintain, hire and remove Work Start Here Advanced signs (Allow 10no) | 10 | Item |  | 0 | Price based on 200xht
B1.3 | Install maintain, hire and remove Strategic Satellite signs (Allow 20no) | 20 | Item |  | 0
B1.4 | Provision of Driver information signs (Allow 60 no black and yellow 200xht signs) | 60 | Item |  | 0 | E.G as per Ch8 D4.13.10
B1.5 | Provision of Overhead Hazard signs (Allow 30 no) | 30 | Item |  | 0 | 1050x750
B1.6 | Provision of coloured cones for W/A - Overhead - No waiting zones etc (Allow 1000no) | 1000 | Item |  | 0
B1.7 | Provision of Site Speed Limit signs (Allow 30no) | 30 | Item |  | 0 | 1050 x 750
B1.8 | Provision of Overbridge and Underbridge location ID sign (Allow 20no) | 20 | No |  | 0 | 1050 x 750 black and yellow
B1.9 | Provision of Signal Not In Use signs (Allow 10no) | 10 | No |  | 0 | 200xht WBM
0

## C - Traffic Management
C) M621 J1 to J7 - Traffic Management Package - Construction Phase TM
Description |  |  | Quantity |  | Rate | Total | Start Date | End Date | No of nights allowed | Notes
C1.1 | Install - Phase 1 - Narrow lanes system on B Track (Westbound) drawing number HE551464_VIR_TTM_XX_DR_ZZ_0097_S5_P02 to HE551464_VIR_TTM_XX_DR_ZZ_0106_S5_P02
C1.1.1 | Layout equipment prior to installation narrow lanes system |  | 2 | Item |  | 0 |  |  | 1 | allow for 1 IPV crew to layout
C1.1.2 | Install full carriageway closure from M621 Junction 7 to Junction 3, including entry slips at Junctions 7, 6 and 4 | [7 empty] | 1
| A | Traffic Management resource | 1 | Item |  | 0 |  |  |  | 2 x IPV Dual crews to install mainline & secondary closure, & 3 no 2 man transit crews to act as gatement & Marshalls
| B | Temporary Road Markings | 1 | Item |  | 0
| C | Fabrication of Diversion Route to facilitate Closure of M621 B Track (Westbound) | 1 | Item |  | 0
| D | Fabrication of Diversion Route to facilitate Closure of Junctions 6 and 4 Entry slip roads | 1 | Item |  | 0
C1.1.3 | Install full carriageway closure from M621 Junction 7 to Junction 3, including entry slips at Junctions 7, 6 and 4 to facilitate installation of VRS |  | 2 | Night |  | 0 |  |  | 2 | 2 x IPV Dual crews to install mainline & secondary closure, & 3 no 2 man transit crews to act as gatement & Marshalls
C1.1.4 | Daily Hire of TM equipment for TM Phase 1 on B Track |  | 115 | Days |  | 0 | 2022-06-07 | 2022-09-30
C1.2 | Install - Phase 2 - Narrow lanes system on A Track (Eastbound) drawing number HE551464_VIR_TTM_XX_DR_ZZ_0107_S5_P02 to HE551464_VIR_TTM_XX_DR_ZZ_0118_S5_P02
C1.2.1 | Layout equipment prior to installation narrow lanes system |  | 1 | Item |  | 0 |  |  | 1 | allow for 1 IPV crew to layout
C1.2.2 | Install full carriageway closure from M621 Junction 1 to Junction 3, including entry slips at Junctions 1, 2 and 2A | [7 empty] | 1
| A | Traffic Management resource | 1 | Item |  | 0 |  |  |  | 2 x IPV Dual crews to install mainline & secondary closure, & 3 no 2 man transit crews to act as gatement & Marshalls
| B | Temporary Road Markings | 1 | Item |  | 0
| C | Fabrication of Diversion Route to facilitate Closure of M621 A Track (Eastbound) | 1 | Item |  | 0
| D | Fabrication of Diversion Route to facilitate Closure of Junctions 2 and 2A Entry slip roads | 1 | Item |  | 0
C1.2.3 | Install full carriageway closure from M621 Junction 1 to Junction 3, including entry slips at Junctions 1, 2 and 2A to facilitate installation of VRS |  | 1 | Night |  | 0 |  |  | 1 | 2 x IPV Dual crews to install mainline & secondary closure, & 3 no 2 man transit crews to act as gatement & Marshalls
C1.2.4 | Daily Hire of TM equipment for TM Phase 2 on A Track |  | 133 | Days |  | 0 | 2022-09-30 | 2023-02-10
C1.3 | Install - Phase 2 - Narrow lanes system on B Track (Westbound) drawing number HE551464_VIR_TTM_XX_DR_ZZ_0107_S5_P02 to HE551464_VIR_TTM_XX_DR_ZZ_0118_S5_P02
C1.3.1 | Layout equipment prior to installation narrow lanes system |  | 1 | Item |  | 0 |  |  | 1 | allow for 1 IPV crew to layout
C1.3.2 | Install full carriageway closure from M621 Junction 4 to Junction 1, including entry slips at Junctions 3 and 2 | [7 empty] | 1
| A | Traffic Management resource | 1 | Item |  | 0 |  |  |  | 2 x IPV Dual crews to install mainline & secondary closure, & 2 no 2 man transit crews to act as gatement & Marshalls
| B | Temporary Road Markings | 1 | Item |  | 0
| C | Fabrication of Diversion Route to facilitate Closure of M621 B Track (Westbound) | 1 | Item |  | 0
| D | Fabrication of Diversion Route to facilitate Closure of Junctions 3 and 2 Entry slip roads | 1 | Item |  | 0
C1.3.3 | Install full carriageway closure from M621 Junction 4 to Junction 1, including entry slips at Junctions 3 and 2 to facilitate installation of VRS |  | 2 | Night |  | 0 |  |  | 2 | 2 x IPV Dual crews to install mainline & secondary closure, & 3 no 2 man transit crews to act as gatement & Marshalls
C1.3.4 | Install full carriageway closure from M621 Junction 4 to Junction 1, including entry slips at Junctions 3 and 2 to facilitate removal of VRS in centre Res |  | 1 | Night |  | 0 |  |  | 1 | 2 x IPV Dual crews to install mainline & secondary closure, & 3 no 2 man transit crews to act as gatement & Marshalls
C1.3.4 | Daily Hire of TM equipment for TM Phase 2 on B Track |  | 133 | Days |  | 0 | 2022-09-30 | 2023-02-10
C1.4 | Install - Phase 3 - Switch Narrow lanes system on A Track (Eastbound) drawing number HE551464_VIR_TTM_XX_DR_ZZ_0119_S5_P02 to HE551464_VIR_TTM_XX_DR_ZZ_0131_S5_P02
C1.4.1 | Layout equipment prior to installation narrow lanes system |  | 1 | Item |  | 0 |  |  | 1 | allow for 1 IPV crew to layout
C1.4.2 | Install full carriageway closure from M621 Junction 1 to Junction 3, including entry slips at Junctions 1, 2 and 2A | [7 empty] | 1
| A | Traffic Management resource | 1 | Item |  | 0 |  |  |  | 2 x IPV Dual crews to install mainline & secondary closure, & 3 no 2 man transit crews to act as gatement & Marshalls
| B | Temporary Road Markings | 1 | Item |  | 0
| C | Fabrication of Diversion Route to facilitate Closure of M621 A Track (Eastbound) | 1 | Item |  | 0
| D | Fabrication of Diversion Route to facilitate Closure of Junctions 2 and 2A Entry slip roads | 1 | Item |  | 0
C1.4.3 | Install full carriageway closure from M621 Junction 1 to Junction 3, including entry slips at Junctions 1, 2 and 2A to facilitate installation of VRS |  | 1 | Night |  | 0 |  |  | 1 | 2 x IPV Dual crews to install mainline & secondary closure, & 3 no 2 man transit crews to act as gatement & Marshalls
C1.4.4 | Daily Hire of TM equipment for TM Phase 3 on A Track |  | 110 | Days |  | 0 | 2023-02-11 | 2023-06-01
C1.5 | Install - Phase 3 - Switch Narrow lanes system on B Track (Westbound) drawing number HE551464_VIR_TTM_XX_DR_ZZ_0119_S5_P02 to HE551464_VIR_TTM_XX_DR_ZZ_0131_S5_P02
C1.5.1 | Layout equipment prior to installation narrow lanes system |  | 1 | Item |  | 0 |  |  | 1 | allow for 1 IPV crew to layout
C1.5.2 | Install full carriageway closure from M621 Junction 4 to Junction 1, including entry slips at Junctions 3 and 2 | [7 empty] | 1
| A | Traffic Management resource | 1 | Item |  | 0 |  |  |  | 2 x IPV Dual crews to install mainline & secondary closure, & 2 no 2 man transit crews to act as gatement & Marshalls
| B | Temporary Road Markings | 1 | Item |  | 0
| C | Fabrication of Diversion Route to facilitate Closure of M621 B Track (Westbound) | 1 | Item |  | 0
| D | Fabrication of Diversion Route to facilitate Closure of Junctions 2 and 2A Entry slip roads | 1 | Item |  | 0
C1.5.3 | Install full carriageway closure from M621 Junction 4 to Junction 1, including entry slips at Junctions 3 and 2 to facilitate installation of VRS |  | 1 | Night |  | 0 |  |  | 1 | 2 x IPV Dual crews to install mainline & secondary closure, & 2 no 2 man transit crews to act as gatement & Marshalls
C1.5.4 | Daily Hire of TM equipment for TM Phase 3 on B Track |  | 110 | Days |  | 0 | 2023-02-11 | 2023-06-01
C1.6 | Install - Phase 4 - Extend Narrow lanes system on A Track (Eastbound) drawing number HE551464_VIR_TTM_XX_DR_ZZ_0132_S5_P02 to HE551464_VIR_TTM_XX_DR_ZZ_0141_S5_P02
C1.6.1 | Layout equipment prior to installation narrow lanes system |  | 1 | Item |  | 0 |  |  | 1 | allow for 1 IPV crew to layout
C1.6.2 | Install full carriageway closure from M62 Junction 27 to M621 Junction 3, including entry slips at Junctions 1, 2 and 2A | [7 empty] | 1
| A | Traffic Management resource | 1 | Item |  | 0 |  |  |  | 2 x IPV Dual crews to install mainline & secondary closure, & 3 no 2 man transit crews to act as gatement & Marshalls
| B | Temporary Road Markings | 1 | Item |  | 0
| C | Fabrication of Diversion Route to facilitate Closure of M621 A Track (Eastbound) | 1 | Item |  | 0
| D | Fabrication of Diversion Route to facilitate Closure of Junctions 2 and 2A Entry slip roads | 1 | Item |  | 0
C1.6.3 | Install full carriageway closure from M621 Junction 1 to Junction 3, including entry slips at Junctions 1, 2 and 2A to facilitate installation of VRS |  | 1 | Night |  | 0 |  |  | 1 | 2 x IPV Dual crews to install mainline & secondary closure, & 3 no 2 man transit crews to act as gatement & Marshalls
C1.6.4 | Daily Hire of TM equipment for TM Phase 4 on A Track |  | 393 | Days |  | 0 | 2023-06-01 | 2024-06-28
C1.7 | Install - Phase 4 - Reduce Narrow lanes system on B Track (Westbound) drawing number HE551464_VIR_TTM_XX_DR_ZZ_0132_S5_P02 to HE551464_VIR_TTM_XX_DR_ZZ_0141_S5_P02
C1.7.1 | Layout equipment prior to installation narrow lanes system |  | 2 | Item |  | 0 |  |  | 1 | allow for 1 IPV crew to layout
C1.7.2 | Install full carriageway closure from M521 Junction 7 to Junction 3, including entry slips at Junctions 7, 6 and 4 | [7 empty] | 1
| A | Traffic Management resource | 1 | Item |  | 0 |  |  |  | 2 x IPV Dual crews to install mainline & secondary closure, & 3 no 2 man transit crews to act as gatement & Marshalls
| B | Temporary Road Markings | 1 | Item |  | 0
| C | Fabrication of Diversion Route to facilitate Closure of M621 B Track (Westbound) | 1 | Item |  | 0
| D | Fabrication of Diversion Route to facilitate Closure of Junctions 6 and 4 Entry slip roads | 1 | Item |  | 0
C1.7.3 | Install full carriageway closure from M621 Junction 7 to Junction 3, including entry slips at Junctions 7, 6 and 4 to facilitate Removal of VRS |  | 2 | Night |  | 0 |  |  | 2 | 2 x IPV Dual crews to install mainline & secondary closure, & 3 no 2 man transit crews to act as gatement & Marshalls
C1.7.4 | Daily Hire of TM equipment for TM Phase 4 on B Track |  | 393 | Days |  | 0 | 2023-06-01 | 2024-06-28
C1.8 | Remove - Phase 4 - Narrow lanes system on A Track (Eastbound) drawing number HE551464_VIR_TTM_XX_DR_ZZ_0132_S5_P02 to HE551464_VIR_TTM_XX_DR_ZZ_0141_S5_P02
C1.8.1
C1.8.2 | Install full carriageway closure from M62 Junction 27 to M621 Junction 3, including entry slips at Junctions M62 J27 & M621 J1, J2 and J2A | [7 empty] | 1
| A | Traffic Management resource | 1 | Item |  | 0 |  |  |  | 2 x IPV Dual crews to install mainline & secondary closure, & 3 no 2 man transit crews to act as gatement & Marshalls
| B | Temporary Road Markings | 1 | Item |  | 0
| C | Fabrication of Diversion Route to facilitate Closure of M621 A Track (Eastbound) | 1 | Item |  | 0
| D | Fabrication of Diversion Route to facilitate Closure of Junctions 2 and 2A Entry slip roads | 1 | Item |  | 0
C1.8.3 | Install full carriageway closure from M621 Junction 1 to Junction 3, including entry slips at Junctions 1, 2 and 2A to facilitate Removal of VRS |  | 2 | Night |  | 0 |  |  | 2 | 2 x IPV Dual crews to install mainline & secondary closure, & 3 no 2 man transit crews to act as gatement & Marshalls
C1.9 | Removal - Phase 4 - Narrow lanes system on B Track (Westbound) drawing number HE551464_VIR_TTM_XX_DR_ZZ_0132_S5_P02 to HE551464_VIR_TTM_XX_DR_ZZ_0141_S5_P02
C1.9.1
C1.9.2 | Install full carriageway closure from M621 Junction 4 to Junction 1, including entry slips at Junctions 3 and 2 | [7 empty] | 1
| A | Traffic Management resource | 1 | Item |  | 0 |  |  |  | 2 x IPV Dual crews to install mainline & secondary closure, & 2 no 2 man transit crews to act as gatement & Marshalls
| B | Temporary Road Markings | 1 | Item |  | 0
| C | Fabrication of Diversion Route to facilitate Closure of M621 B Track (Westbound) | 1 | Item |  | 0
| D | Fabrication of Diversion Route to facilitate Closure of Junctions 3 and 2 Entry slip roads | 1 | Item |  | 0
C1.9.3 | Install full carriageway closure from M621 Junction 4 to Junction 1, including entry slips at Junctions 3 and 2 to facilitate Removal of VRS |  | 2 | Night |  | 0 |  |  | 2 | 2 x IPV Dual crews to install mainline & secondary closure, & 3 no 2 man transit crews to act as gatement & Marshalls
C2.0 | Install - M621 Junction 2 - Phase 1 & 1B - Overnight lane closures - drawing number CN270-VIR-TTM-M2-CW-000001 & 000001B | [8 empty] | Programme and design TBC
C2.0.1
C2.0.2 | Install lane closures on M621 Junction 2 including gyratory and A643 | [7 empty] | 1 | 2 x IPV crews & 1 no 2 man transit crew to install overnight lane closures.
| A | Traffic Management resource | 1 | Item |  | 0
C2.0.3 | Daily Hire of TM equipment for M621 Junction 2 - Phase 1 & 1B |  | 128 | Days |  | 0 | 2022-10-04 | 2023-02-09
C2.1 | Install - M621 Junction 2 - Phase 2 - Narrow Lanes to Verge - drawing number CN270-VIR-TTM-M2-CW-000002
C2.1.1 | Layout equipment prior to installation narrow lanes system |  | 2 | Item |  | 0 |  |  | 1 | allow for 1 IPV crew to layout
C2.1.2 | Install full carriageway closure of M621 Junction 2 including exit & entry slips | [7 empty] | 1
| A | Traffic Management resource | 1 | Item |  | 0 |  |  |  | 2 x IPV Dual crews to install mainline & secondary closure, & 3 no 2 man transit crews to act as gatement & Marshalls
| B | Temporary Road Markings | 1 | Item |  | 0
| C | Fabrication of Diversion Route to facilitate Closure of M621 J2 | 1 | Item |  | 0
C2.1.3 | Install full carriageway closure from M621 Junction 2 including exit & entry slips to facilitate installation of VRS |  | 2 | Night |  | 0 |  |  | 2 | 2 x IPV Dual crews to install mainline & secondary closure, & 3 no 2 man transit crews to act as gatement & Marshalls
C2.1.4 | Daily Hire of TM equipment for M621 Junction 2 - Phase 2 |  | 115 | Days |  | 0 | 2022-06-07 | 2022-09-30
C2.2 | Install - M621 Junction 2 - Phase 3 - Narrow Lanes to Verge - drawing number CN270-VIR-TTM-M2-CW-000003
C2.2.1 | Layout equipment prior to installation narrow lanes system |  | 2 | Item |  | 0 |  |  | 1 | allow for 1 IPV crew to layout
C2.2.2 | Install full carriageway closure of M621 Junction 2 including exit & entry slips | [7 empty] | 1
| A | Traffic Management resource | 1 | Item |  | 0 |  |  |  | 2 x IPV Dual crews to install mainline & secondary closure, & 3 no 2 man transit crews to act as gatement & Marshalls
| B | Temporary Road Markings | 1 | Item |  | 0
| C | Fabrication of Diversion Route to facilitate Closure of M621 J2 | 1 | Item |  | 0
C2.2.3 | Install full carriageway closure from M621 Junction 2 including exit & entry slips to facilitate installation of VRS |  | 2 | Night |  | 0 |  |  | 2 | 2 x IPV Dual crews to install mainline & secondary closure, & 3 no 2 man transit crews to act as gatement & Marshalls
C2.2.4 | Daily Hire of TM equipment for M621 Junction 2 - Phase 3 |  | 96 | Days |  | 0 | 2023-05-11 | 2023-08-15
C2.3 | Install - M621 Junction 2 - Phase 4 - Switch traffic onto new widened areas - drawing number CN270-VIR-TTM-M2-CW-000004
C2.3.1 | Layout equipment prior to installation narrow lanes system |  | 2 | Item |  | 0 |  |  | 1 | allow for 1 IPV crew to layout
C2.3.2 | Install full carriageway closure of M621 Junction 2 including exit & entry slips | [7 empty] | 1
| A | Traffic Management resource | 1 | Item |  | 0 |  |  |  | 2 x IPV Dual crews to install mainline & secondary closure, & 3 no 2 man transit crews to act as gatement & Marshalls
| B | Temporary Road Markings | 1 | Item |  | 0
| C | Fabrication of Diversion Route to facilitate Closure of M621 J2 | 1 | Item |  | 0
C2.3.3 | Install full carriageway closure from M621 Junction 2 including exit & entry slips to facilitate installation of VRS |  | 2 | Night |  | 0 |  |  | 2 | 2 x IPV Dual crews to install mainline & secondary closure, & 3 no 2 man transit crews to act as gatement & Marshalls
C2.3.4 | Daily Hire of TM equipment for M621 Junction 2 - Phase 4 |  | 15 | Days |  | 0 | 2023-08-16 | 2023-08-31
C2.3 | Install - M621 Junction 2 - Phase 5 - drawing number CN270-VIR-TTM-M2-CW-XXXXXX Details to TBC
C2.3.1 | Layout equipment prior to installation narrow lanes system |  | 2 | Item |  | 0 |  |  | 1 | allow for 1 IPV crew to layout
C2.3.2 | Install full carriageway closure of M621 Junction 2 including exit & entry slips | [7 empty] | 1
| A | Traffic Management resource | 1 | Item |  | 0 |  |  |  | 2 x IPV Dual crews to install mainline & secondary closure, & 3 no 2 man transit crews to act as gatement & Marshalls
| B | Temporary Road Markings | 1 | Item |  | 0 |  |  |  | Road makings not priced due to incomplete final design
| C | Fabrication of Diversion Route to facilitate Closure of M621 J2 | 1 | Item |  | 0
C2.3.3 | Install full carriageway closure from M621 Junction 2 including exit & entry slips to facilitate Removal of VRS |  | 2 | Night |  | 0 |  |  | 2 | 2 x IPV Dual crews to install mainline & secondary closure, & 3 no 2 man transit crews to act as gatement & Marshalls
C2.3.4 | Daily Hire of TM equipment for M621 Junction 2 - Phase 5 |  | 15 | Days |  | 0 | 2023-08-16 | 2023-08-31
C2.3 | Remove - M621 Junction 2 - Phase 5 - Surfacing works - drawing number CN270-VIR-TTM-M2-CW-XXXXX Details TBC
C2.3.1 | Layout equipment prior to installation narrow lanes system |  | 2 | Item |  | 0 |  |  | 1 | allow for 1 IPV crew to layout
C2.3.2 | Install full carriageway closure of M621 Junction 2 including exit & entry slips | [7 empty] | 1
| A | Traffic Management resource | 1 | Item |  | 0 |  |  |  | 2 x IPV Dual crews to install mainline & secondary closure, & 3 no 2 man transit crews to act as gatement & Marshalls
| B | Temporary Road Markings | 1 | Item |  | 0 |  |  |  | Road makings not priced due to incomplete final design
| C | Fabrication of Diversion Route to facilitate Closure of M621 J2 | 1 | Item |  | 0
C2.3.3 | Install full carriageway closure from M621 Junction 2 including exit & entry slips to facilitate surfacing works |  | 4 | Night |  | 0 |  |  | 4 | 2 x IPV Dual crews to install mainline & secondary closure, & 3 no 2 man transit crews to act as gatement & Marshalls
C2.4 | Install - Ellend Road - One way system - drawing number HE551464-VIR-TTM-XX-DR-ZZ-0005
C2.4.1 | Layout equipment prior to installation one way system |  | 1 | Item |  | 0 |  |  | 1 | Allow for 1 no 7.5t crew to layout
C2.4.2 | Install one way system on Ellend Road from the junction of Ellend Road and Cemetery Road to Baron Close | [7 empty] | 1
| A | Traffic Management resource | 1 | Item |  | 0 |  |  |  | 2 no 2 man transit crews
| B | Fabrication of Diversion Route | 1 | Item |  | 0
C2.4.3 | Install full carriageway closure of Ellend Road from the junction of Ellend Road and Cemetery Road to Baron Close |  | 1 | Night |  | 0 |  |  | 1 | 1 x 7.5t Dual crew to install mainline & secondary closure, & 3 no 2 man transit crews to act as gatement & Marshalls
C2.4.4 | Daily Hire of TM equipment for Ellend Road one way system |  | 242 | Days |  | 0 | 2022-09-01 | 2023-05-01
C2.4 | Install - Ellend Road - Two way traffic signals on Cemerty Road - drawing number HE551464-VIR-TTM-XX-DR-ZZ-0007
C2.4.1
C2.4.2 | Install two way system on Cemetery Road at the junction with Ellend Road | [7 empty] | 1
| A | Traffic Management resource | 1 | Item |  | 0 |  |  |  | 2 man transit crew
C2.4.3 | Daily Hire of TM equipment for Ellend Road traffic signals system |  | 61 | Days |  | 0 | 2023-03-01 | 2023-05-01
0

## D - Temporary VRS
D) M621 J1 to J7 - Traffic Management Package - Temporary Barrier
Description |  | Quantity | Unit | Rate | Total | Start Date | End Date | No of nights allowed | Notes
D1.1 | Install - Phase 1 - Narrow Lanes system on B Track (Westbound)
D1.1.1 | Install 1030m temporary VRS (N2 / W1) in 4 sections between Chainages 10530 - 10215, 10050 - 9625, 9470 - 9370, 8850 - 8650 | 1030 | m |  | 0 |  |  | 2 | Completed under carriageway closure
D1.1.2 | Install 4 no Crash Cushion | 4 | no |  | 0
D1.1.3 | Daily Hire of 1030m N2 W1 | 725 | Days |  | 0 | 2022-06-07 | 2024-06-01
D1.1.4 | Daily hire of 4 No Crash cushion | 725 | Days |  | 0 | 2022-06-07 | 2024-06-01
D1.1.5 | Lift 1030m temporary VRS (N2 / W1) in 4 sections between Chainages 10530 - 10215, 10050 - 9625, 9470 - 9370, 8850 - 8650 | 1030 | m |  | 0 |  |  | 2 | Completed under carriageway closure
D1.1.6 | lift 4 no Crash Cushion | 4 | no |  | 0
D1.3 | Install - Phase 2 - Narrow Lanes system on B Track (Westbound)
D1.3.1 | Install 905m temporary VRS (N2 / W1) in 4 sections between Chainages 7750 - 7350, 6700 - 6540, 6475 - 6360, 6230 - 6000 | 905 | m |  | 0 |  |  | 2 | Completed under carriageway closure
D1.3.2 | Install 4 no Crash Cushion | 4 | no |  | 0
D1.3.3 | Daily Hire of 905m N2 W1 | 637 | Days |  | 0 | 2022-09-30 | 2024-06-28
D1.3.4 | Daily hire of 4 No Crash cushion | 637 | Days |  | 0 | 2022-09-30 | 2024-06-28
D1.3.5 | Lift 905m temporary VRS (N2 / W1) in 4 sections between Chainages 7750 - 7350, 6700 - 6540, 6475 - 6360, 6230 - 6000 | 905 | m |  | 0 |  |  | 2 | Completed under carriageway closure
D1.3.6 | lift 4 no Crash Cushion | 4 | no |  | 0
D1.4 | Install - Phase 2 - Narrow Lanes system on A Track (Westbound)
D1.4.1 | Install 400m temporary VRS (N2 / W1) between Chainages 7300 - 7700 | 400 | m |  | 0 |  |  | 1 | Completed under carriageway closure
D1.4.2 | Install 1 no Crash Cushion | 1 | no |  | 0
D1.4.3 | Daily Hire of 400m N2 W1 | 134 | Days |  | 0 | 2022-09-30 | 2023-02-11
D1.4.4 | Daily hire of 1No Crash cushion | 134 | Days |  | 0 | 2022-09-30 | 2023-02-11
D1.4.5 | Lift 400m temporary VRS (N2 / W1) between Chainages 7300 - 7700 | 400 | m |  | 0 |  |  | 1 | Completed under carriageway closure
D1.4.6 | lift 1 no Crash Cushion | 1 | no |  | 0
D1.5 | Install - Phase 3 - Switch Narrow Lanes system on B Track (Westbound)
D1.5.1 | Lift 400m temporary VRS (N2 / W1) between Chainages 7750 - 7350 (for C/Res works) | 400 | m |  | 0 | 2023-02-09 | 2023-02-10 | 1 | Completed under carriageway closure
D1.5.2 | lift 1 no Crash Cushion (for C/Res works) | 1 | no |  | 0
D1.5.3 | Install 450m temporary VRS (N2 / W1) between Chainages 7200 - 6920 (for verge works) | 450 | m |  | 0 | 2023-02-11 | 2023-02-12 | 1 | Completed under carriageway closure
D1.5.4 | Install VRS splitter detail at Junction 2A exit slip | 1 | no |  | 0
D1.5.5 | Daily hire VRS splitter detail at Junction 2A exit slip | 503 | no |  | 0 | 2023-02-11 | 2024-06-28
D1.5.6 | Daily Hire of 400m N2 W1 | 503 | Days |  | 0 | 2023-02-11 | 2024-06-28
D1.5.4 | Remove VRS splitter detail at Junction 2A exit slip | 1 | no |  | 0 |  |  | 1 | Completed under carriageway closure
D1.5.5 | Remove 450m temporary VRS (N2 / W1) between Chainages 7200 - 6920 | 450 | no |  | 0
D1.6 | Phase 3 - Switch Narrow Lanes system on A Track (Eastbound)
D1.6.1 | Barrier removed from A Track in Items D1.4.5 & D1.4.6 |  |  |  |  | N/A | N/A
D1.7 | Install - Phase 4 - Narrow Lanes system on B Track (Westbound)
D1.7.1 | All barrier changes covered other phases. |  |  |  |  | N/A | N/A
D1.8 | Install - Phase 4 - Narrow Lanes system on A Track (Westbound)
D1.8.1 | Install 1357m temporary VRS (N2 / W1) in 4 section between Chainages 5850 - 6190, 6120 - 6350 (starts on J2 entry slip), 6370 - 6745, 6920 - 7332 | 1357 | m |  | 0 |  |  | 2 | Completed under carriageway closure
D1.8.2 | Install 4 no Crash Cushion | 4 | no |  | 0
D1.8.3 | Daily Hire of 1357m N2 W1 | 393 | Days |  | 0 | 2023-06-01 | 2024-06-28
D1.8.4 | Daily hire of 4No Crash cushion | 393 | Days |  | 0 | 2023-06-01 | 2024-06-28
D1.8.5 | Lift 1357m temporary VRS (N2 / W1) in 4 section between Chainages 5850 - 6190, 6120 - 6350 (starts on J2 entry slip), 6370 - 6745, 6920 - 7332 | 1357 | m |  | 0 | 2024-06-28 | 2024-06-30 | 2 | Completed under carriageway closure
D1.8.6 | lift 4 no Crash Cushion | 4 | no |  | 0
D1.9.1 | Install - Junction 2 - A Track Exit onto A643 Northbound
D1.8.1 | Install 260m temporary VRS (N2 / W1) on A Track (Eastbound) exit slip onto A643 Northbound | 260 | m |  | 0
D1.8.2 | Install 1 no Crash Cushion on A Track (Eastbound) exit slip | 1 | no |  | 0
D1.8.3 | Daily Hire of 260m N2 W1 | 215 | Days |  | 0 | 2023-01-12 | 2023-08-15
D1.8.4 | Daily hire of 1No Crash cushion | 215 | Days |  | 0 | 2023-01-12 | 2023-08-15
D1.9.1 | Install - Junction 2 - A643 Southbound onto A Track Entry slip
| Install 500m temporary VRS (N2 / W1) on A643 Southbound onto A Track (Eastbound) Entry slip | 500 | m |  | 0
| Install 1 no Crash Cushion on A643 Southbound | 1 | no |  | 0
| Daily Hire of 500m N2 W1 | 119 | Days |  | 0 | 2023-01-12 | 2023-05-11
| Daily hire of 1 No Crash cushion | 119 | Days |  | 0 | 2023-01-12 | 2023-05-11
D1.9.1 | Install - Junction 2 - Gyratory
| Install 400m temporary VRS (N2 / W1) on A643 Southbound onto A Track (Eastbound) Entry slip | 400 | m |  | 0
| Install 2 no Crash Cushion on A643 Southbound | 1 | no |  | 0
| Daily Hire of 400m N2 W1 | 153 | Days |  | 0 | 2023-01-12 | 2023-06-14
| Daily hire of 2 No Crash cushions | 153 | Days |  | 0 | 2023-01-12 | 2023-06-14
D1.9.1 | Install - Junction 2 - Phase change
| Lift 320m temporary VRS (N2 / W1) lift from A Track Entry slip | 320 | m |  | 0
| Lift 400m temporary VRS (N2 / W1) lift from Gyratory | 400 | m |  | 0
| lift 2 no Crash Cushion | 2 | no |  | 0
| Install 475m temporary VRS (N2 / W1) on A Track (Eastbound) Entry slip, B Track Entry slip and Gyratory in 4 sections | 475 | m |  | 0
| Install 4 no Crash Cushions | 4 | no |  | 0
| Daily Hire of 475m N2 W1 | 96 | Days |  | 0 | 2023-05-11 | 2023-08-15
| Daily hire of 4 No Crash cushions | 96 | Days |  | 0 | 2023-05-11 | 2023-08-15
D1.9.1 | Install - Junction 2 - Phase change
| Lift 260m temporary VRS (N2 / W1) lift from A Track Entry slip onto A643 Northbound | 260 | m |  | 0
| Lift 180m temporary VRS (N2 / W1) lift from A643 Southbound | 180 | m |  | 0
| Lift 180m temporary VRS (N2 / W1) lift from Gyratory | 180 | m |  | 0
| Lift 180m temporary VRS (N2 / W1) lift from A Track (Eastbound) Entry slip | 180 | m |  | 0
| Lift 115m temporary VRS (N2 / W1) lift from B Track (Eastbound) Entry slip | 115 | m |  | 0
| lift 5 no Crash Cushion | 5 | no |  | 0
| Install temporary VRS (N2 / W1) on B Track (Westbound) 150m on Exit slip & 160m Entry Slip | 310 | m |  | 0
| Install 2 no Crash Cushions | 2 | no |  | 0
| Install 100m temporary VRS (N2 / W1) on A643 Southbound | 100 | m |  | 0
| Install 80m temporary VRS (N2 / W1) on A643 Northbound | 80 | m |  | 0
| Install 2 no Crash Cushions | 2 | no |  | 0
| Daily Hire of 490m N2 W1 | 15 | Days |  | 0 | 2023-08-16 | 2023-08-31
| Daily hire of 4 No Crash cushions | 15 | Days |  | 0 | 2023-08-16 | 2023-08-31
| Lift temporary VRS (N2 / W1) on B Track (Westbound) 150m on Exit slip & 160m Entry Slip | 310 | m |  | 0
| Lift 2 no Crash Cushions | 2 | no |  | 0
| Lift 100m temporary VRS (N2 / W1) on A643 Southbound | 100 | m |  | 0
| Lift 80m temporary VRS (N2 / W1) on A643 Northbound | 80 | m |  | 0
| Lift 2 no Crash Cushions | 2 | no |  | 0
D1.9.1 | Additional Items
D1.9.1 | Minimum Visit charge to laterally move temporary VRS when installing or removing M621 Gantries (1 crew) | 15 | no |  | 0 | TBC | TBC |  | Depending on work method - May not be required
0
Temporary Barrier to include reflectors

## E - Maintenance Crews
E) M621 J1 to J7 - Traffic Management Package - Maintenance Crews
Description |  | Quantity | Unit | Rate | Total | Start Date | End Date | No of Shifts allowed | Notes
E | M621 - 2 man Maintenance Crew
E1.1 | Dayshift | 752 | Days |  | 0 | 2022-06-07 | 2024-06-28 | 752 | Allow Foreman, Operative & 3.5t Transit
E1.2 | Nightshift | 752 | Days |  | 0 | 2022-06-07 | 2024-06-28 | 752 | Allow Foreman, Operative & 3.5t Transit
0

## F - Tascar
F) M621 J1 to J7 - Traffic Management Package - TASCAR
Description |  | Quantity | Unit | Rate | Total | Start Date | End Date | Notes
F1 | M621 Eastbound carriageway (TASCAR)
F1.1 | Installation, calibration and commissioning of TASCAR and associated equipment as per Tascar Schedule | 1 | Item |  | 0 | NA | NA | 1 no live entry & exit & 4 dummy cameras - Locations TBC
The contractor is to include in his rate all civils works for installation of CCTV poles (Ground surveys/Excavations/back fills etc)
F1.2 | Hire and maintenance of TASCAR and associated equipment as per item F1.1 | 637 | Days |  | 0 | 2022-09-30 | 2024-06-28
F1.3 | Re - Calibration of TASCAR | 1 | Visits |  | 0 | Date TBC | Date TBC
F1.4 | Removal of TASCAR and associated equipment as per item F1.1 | 1 | Item |  | 0 | NA | NA | The contractor is to include in his rate all civils works for removal of Camera poles (Ground surveys/Excavations/back fills etc)
F2 | M621 Westbound carriageway (TASCAR)
F2.1 | Installation, calibration and commissioning of TASCAR and associated equipment as per Tascar Schedule | 1 | Item |  | 0 | NA | NA | 1 no live entry & exit & 4 dummy cameras - Location TBC
The contractor is to include in his rate all civils works for installation of CCTV poles (Ground surveys/Excavations/back fills etc)
F2.2 | Hire and maintenance of TASCAR and associated equipment as per item F2.1 | 752 | Days |  | 0 | 2022-06-07 | 2024-06-28
F2.3 | Re - Calibration of TASCAR | 1 | Visits |  | 0 | Date TBC | Date TBC
F2.4 | Removal of TASCAR and associated equipment as per item F2.1 | 1 | Item |  | 0 | NA | NA | The contractor is to include in his rate all civils works for removal of Camera poles (Ground surveys/Excavations/back fills etc)
F5 | Additional requirements
F5.1 | Installation of 1no additional Temporary Automated Speed Cameras | 0 | Item |  | 0 | N/A | N/A | This based on a Single live camera column including IR
F5.2 | Daily hire and maintenance of 1no additional Temporary Automated Speed Cameras | 0 | Days |  | 0 |  |  | This based on a Single live camera column including IR
F5.3 | Removal of 1no additional Temporary Automated Speed Cameras | 0 | Item |  | 0 | N/A | N/A | This based on a Single live camera column including IR
F5.4 | Relocation of a speed camera, pole, base, connection to accommodate change in construction phase | 0 | Visits |  | 0 | Date TBC | Date TBC | Based on a Live camera setup.
F5.5 | Additional visit to rectify connections/operations following damage/theft of cable or equipment | 0 | Visits |  | 0 | NA | NA | This is based on Days rates for attendance , Cable damage or theft will be calculated at a / m rate dependant on qty required. Rates are within support document.
F5.6 | Additional visit to reconnect Speed Camera to new power source following removal/relocation of existing power source | 0 | Item |  | 0 | N/A | N/A | This is based on Days rates for attendance , Cable damage or theft will be calculated at a / m rate dependant on qty required. Rates are within support document.
0
1, - all night time images to be acceptable by Safety Camera Partnership
2, - ERCU to be made available to Safety Camera Partnership (at cost to supplier not Keltbray )
3, - All software MUST be compatable with Safetycamera Partnerships requirments
4, - Any training required for Safety Camera Partnership to operate system is to be undertaken at no cost to Keltbray
5, - any development costs / on costs associated with ensuring Safety Camera Partnership are happy with images is to be bourne by supplier not Keltbray
6, - All columns to be installed prior to installation of TM to avoid programme issues when installing Traffic Management

## G - VMS & JTR.
G) M621 J1 to J7 - Traffic Management Package - VMS & JTR
Description |  | Quantity | Unit | Rate | Total | Start Date | End Date | Notes
G1 | Provision of Variable Message Signs
G1.1 | Install 14no Portable Mobile Variable Message Signs | 10 | Item |  | 0 | Date TBC | Date TBC | 3 per truck with Hiab
G1.2 | Daily hire of 14no Portable Mobile Variable Message Signs | 265 | Days |  | 0 | 2022-06-07 | 2023-02-27 | Price per VMS per day (£2,940 per week)
G1.3 | Remove 14 no Portable Mobile Variable Message Signs | 10 | Item |  | 0 | Date TBC | Date TBC | 3 per truck with Hiab
G2 | Provision of Journey Time Management System
G2.1 | Install JTM facility | 1 | Item |  | 0 | Date TBC | Date TBC | Web based software - No set up cost
G2.2 | Daily hire and maintenance of JTM facility (including monthly report) | 265 | Days |  | 0 | 2022-06-07 | 2023-02-27 | Price per route per day (2 ROUTES ALLOWED FOR) - M621 EB & WB
G2.3 | Removal of JTM Facility | 1 | Item |  | 0 | Date TBC | Date TBC | Web based system so no removal charge
G3 | Additional requirements
G3.1 | Provision of floating data for up to 2 Diversion Routes linked to Pvms |  | Days |  | 0 | 2022-06-07 | 2024-06-28 | Price per route per day - 2 No Diversion Routes
G3.2 | Install 6 No additional portable Variable Message Signs for Carriageway Closures |  | Item |  | 0 | Date TBC | Date TBC
G3.3 | Daily hire of 6 no Portable Mobile Variable Message Signs for carriageway closures |  | Days |  | 0 | 2022-06-07 | 2024-06-28 | Price per VMS per day (£1,260 per week)
G3.4 | Remove 6 no Portable Mobile Variable Message Signs for carriageway closures |  | Item |  | 0 | Date TBC | Date TBC | 3 per truck with Hiab
0
Perceived locations of Pvms
1) M1 NB prior to Junction 42
2) M62 WB prior to Junction 29
3) M62 EB prior to Junction 29
4) M1 NB prior to Junction 43
5) M621 WB prior to Junction 7
6) M1 SB prior to Junction 44
7) M1 SB prior to Junction 45
8) M62 EB prior to Junction 27
9) A650 EB prior to M62 Junction 27
10) A6110 SB approaching M621 Junction 1
11) A643 SB approaching M621 Junction 2
12) A61 SB approaching M621 Junction 4
13) M621 approaching Junction 6
14) M621 approaching Junction 2A Entry Slip
6 No on Diversion Routes (3 in each direction)

## H - Vehicle Recovery
H) M621 J1 to J7 - Traffic Management Package - Vehicle Recovery
Description |  | Quantity | Unit | Rate | Total | Start Date | End Date | Notes
H1 | Mobilisation of recovery bases
H1.1 | Mobilisation of Recovery Base 01 (1No IPV, 1No Heavy, 1No light) | 1 | Item |  | 0 | 2022-05-30 | 2022-06-06 | Located in Bobby Collins Way Compound
H1.2 | Mobilisation of Recovery Base 02 (1No IPV, 1No Heavy, 1No light) | 1 | Item |  | 0 | 2022-09-26 | 2022-09-29 | Located to be confirmed
H2 | Daily hire of recovery bases
H2.1 | Daily Hire of Recovery Vehicles at Base 01 (1No IPV, 1No Heavy, 1No light) | 265 | Days |  | 0 | 2022-06-07 | 2023-02-27 | Providing full welfare facilities for recovery personnel. Recovery contractor to provide generator power supply, water & waste water disposal. - Recovery in place 48hrs prior to TM being installed
H2.2 | Daily Hire of Recovery Vehicles at Base 02 (1No IPV, 1No Heavy, 1No light) | 150 | Days |  | 0 | 2022-09-30 | 2023-02-27 | Providing full welfare facilities for recovery personnel. Recovery contractor to provide generator power supply, water & waste water disposal. - Recovery in place 48hrs prior to TM being installed
F3 | Communication system
F3.1 | Provision of a licensed radio communication system throughout duration of the works to ensure effective 24/7 communication between recovery operators and Temporary CCTV Station | 265 | Days |  | 0 | 2022-06-07 | 2023-02-27 | As well as provision of usual mobile phone system
F4 | Additional requirements
F4.1 | Provision of 1no Specialist site based low loader for recovery of coaches/HGVs on a call out basis only | 265 | Days |  | 0 | 2022-06-07 | 2023-02-27 | Located at main works compound
F5 | De-mobilisation of recovery bases
F5.1 | De-mobilisation of Recovery Base 01 on completion of project | 1 | Item |  | 0 | 2023-02-27 | 2023-03-03 | Including cost for removal of all vehicles, welfare facilities and final site clearance of all equipment and debris
F5.2 | De-mobilisation of Recovery Base 02 on completion of project | 1 | Item |  | 0 | 2023-02-27 | 2023-03-03
0

## I - CCTV
I) M621 J1 to J7 - Traffic Management Package - CCTV
Description |  | Quantity | Unit | Rate | Total | Start Date | End Date | Notes
H1 | Installation of Temporary CCTV control room
H1.1 | Establish Temporary CCTV control room including all associated equipment for operational CCTV unit | 1 | Item |  | 0 | 2024-09-24 | 2023-02-27 | Control room based at Bobby Collins Way Compound . Buildings/Welfare/Power etc. provided by Keltbray (4 no 32ft x 12ft cabins with kitchen, toliets, air conditioning) will also act as recovery drop off point . Supplier to price for establishment of operational equipment
H1.2 | Hire and maintenance of Temporary CCTV control room and associated operational equipment | 265 | Days |  | 0 | 2022-06-07 | 2023-02-27
H1.3 | Provision of Temporary CCTV control room staff. 2no operators working 12hr shifts on a rota basis providing 24/7 coverage of CCTV room | 265 | Days |  | 0 | 2022-06-07 | 2023-02-27 | 17 / hour per operator (4 operators in total) 2022 rates used
H1.4 | Demobilise and remove Temporary CCTV control room including all associated equipment for operational CCTV unit | 1 | Item |  | 0 | N/A | N/A
H2 | Temporary CCTV system Item
H2.1 | Installation of 28 No solar powered towers fitted with PTZ cameras every 300m on M621 - assume all towers to be lifted into place with HIAB with TM provided for contractor, associated Civils work for towers to be undertaken by Keltbray | 28 | Item |  | 0 |  |  | CCTV capable of meeting criteria within appendix 1 /25.
Civils works associated with bases for towers to be provided by Keltbray
H2.2 | Daily hire of 28 No Temporary CCTV towers | 265 | Days |  | 0 | 2022-06-07 | 2023-02-27 | Towers at £50.00 / day each, rate to include PC with 4G dongle, viewing software, HDMI output and data package 30GB X2 (1 back to CCTV room, 1 to SW RCC) | compare with wired system
H3 | Removal of CCTV cameras
H3.1 | Removal of 28 no Temporary CCTV towers | 28 | Item |  | 0 | NA | NA | Civils works associated with removal of bases to be provided by Keltbray
H5 | Additional requirements
H5.1 | Additional visit to rectify connections/operations following damage/theft of equipment | 0 | Item |  | 0 | N/A | N/A
H5.2 | Relocation of 1no CCTV tower to accommodate change in construction work areas | 0 | Item |  | 0 | N/A | N/A
0

## J Additional Items
J) M621 J1 to J7 - Traffic Management Package - Additional Items
Description |  | Quantity | Unit | Rate | Total | Start Date | End Date | Notes
J1 | Lane closures / Additional Items
J1.1 | Install, maintain and remove overnight off peak lane closures for installation of Pvms | 27 | Number |  | 0 |  |  | IPV Dual crew
J1.2 | Install, maintain and remove overnight off peak lane closures for removal of Pvms | 27 | Number |  | 0 |  |  | IPV Dual crew
J1.3 | Install, maintain and remove overnight off peak lane 2 closure on A Track from 5/0 to 11/5 - 6.5km | 14 | Number |  | 0 |  |  | IPV Dual crew
J1.4 | Install, maintain and remove overnight off peak lane 1 closure on A Track from 5/0 to 11/5 - 6.5km | 20 | Number |  | 0 |  |  | IPV Dual crew
J1.5 | Install, maintain and remove overnight off peak lane 3 closure on B Track from 11/5 to 5/0 - 6.5km | 21 | Number |  | 0 |  |  | IPV Dual crew
J1.6 | Install, maintain and remove overnight off peak lane 1 closure on A Track from 7/2 to 8/5 - 1.3km | 5 | Number |  | 0 |  |  | IPV Dual crew
J1.7 | Install, maintain and remove overnight off peak lane 1 closure on B Track from 8/5 to 7/2 - 1.3km | 5 | Number |  | 0 |  |  | IPV Dual crew
J1.8 | Install, maintain and remove overnight A Track (Eastbound) full carriageway closure of the M621 Junction 1 to Junction 3 | 7 | Number |  | 0 |  |  | Allow for 3 IPV crews to install full carriageway closure
J1.9 | Install, maintain and remove overnight B Track (Westbound) full carriageway closure of the M621 Junction 4 to Junction 1 | 5 | Number |  | 0 |  |  | Allow for 3 IPV crews to install full carriageway closure
J1.10 | Install, maintain and remove overnight A Track (Eastbound) full carriageway closure of the M621 Junction 3 to Junction 7 | 5 | Number |  | 0 |  |  | Allow for 3 IPV crews to install full carriageway closure
J1.11 | Install, maintain and remove overnight B Track (Westbound) full carriageway closure of the M621 Junction 7 to Junction 3 | 5 | Number |  | 0 |  |  | Allow for 3 IPV crews to install full carriageway closure
J1.12 | Install, maintain and remove overnight full carriageway closure of the M621 from the M62 Junction 27 to M621 Junction 1 | 5 | Number |  | 0 |  |  | Allow for 3 IPV crews to install full carriageway closure
0

## K TM Staff Resource
K) M621 J1 to J7 - Traffic Management Package - TM Staff Resource
Description |  | Quantity | Unit | Rate | Total | Start Date | End Date | Notes
K1 | Traffic Management - Staff Resource
K1.1 | Provide 1no Traffic Safety and Control Officer - 12hr Dayshift | 752 | Shifts |  | 0 | 2022-06-07 | 2024-06-28 | TSCO on site 12hr day to deal with incidents/breakdowns etc
K1.3 | Provide 1no Traffic Safety and Control Officer - 12 hr Night shift | 752 | Shifts |  | 0 | 2022-06-07 | 2024-06-28 | TSCO on site 12hr night to deal with incidents/breakdowns etc
K1.4 | Provide TM Scheme Project Manager Mon-Fri office hours during scheme period | 788 | Days |  | 0 | 2022-05-02 | 2024-06-28 | Stakeholder and incident response co-ordination role
K1.5 | Provide TM Consultant (two days per month) office hours during scheme period | 56.3571 | Days |  | 0 | 2022-05-01 | 2024-06-28 | As required depending on scheme requirements
0