CONSULTANTS TO DELIVER A DIGITAL TRAINING PROGRAMME FOR A COHORT OF CEOS, DIRECTORS AND TRUSTEES FROM THE HERITAGE SECTOR

Organisation 	National Heritage Memorial Fund

Department 	BUSINESS DELIVERY DIVISION

Title of procurement	 - Delivery of a digital leadership programme  for senior leaders in the heritage sector

Brief description of supply 	Consultants to deliver a digital training programme for a cohort of CEO’s and Trustees from the Heritage Sector

Estimated value of tender 		        £50,000 exclusive of VAT

Estimated duration 	1 year

Name of NLHF Contact 	Harriet Hall

Timetable

Deadline by which to submit clarification questions to the Fund: 24th October by 5pm

The Fund will send answers to clarification questions by: 28th October by 5pm

Tender submission deadline: 8th November by 5pm 2019

Confirmation of contract: 15th November by 5pm

Completion of work: End May 2021

# Overview

The Heritage Lottery Fund, now the National Lottery Heritage Fund (the Fund) was set up in 1994 under the National Lottery Act and distributes money raised by the National Lottery to support projects involving the national, regional and local heritage of the United Kingdom. NLHF operate under the auspices of the National Heritage Memorial Fund (NHMF) and invests in the full breadth of the UK’s heritage.

Through our funding, we aim to make a lasting difference for heritage and people. This is reflected in the outcomes for heritage, people and communities which underpin our grant-making.

As part of its new Digital Campaign, the Fund requires a supplier to assist with the delivery of a workstream called Digital Development (Tranche 4). This document describes the work which we seek to be delivered.

Context

The Digital Campaign is a board-approved initiative being delivered by the Fund.

The goal of the digital campaign is this:

“Over two years the Fund will encourage the development of value-adding digital skills in heritage organisations by regularly communicating a series of simple, key messages, and by backing those messages with support in the form of funding, training and ‘how to’ materials.”

The digital campaign will deliver in this goal by delivering a series of workstreams that we are calling ‘tranches’. This document covers a piece of work that the Fund needs delivering that relates to Tranche 4.

About Tranche 4

In the discovery phase of the Digital Fund, we were informed that medium and large organisations often lack digital leadership skills amongst key senior staff, most notably trustees, chief executives and directors.  There was widespread support for the idea that the Fund might offer groups of such individuals a friendly, constructive opportunity to improve their own digital leadership skills, for the good of both their institutions and their customers.

We wish to contract a supplier to design and operate an up to one year-long cohort programme of around 12-16 individuals from medium and large UK heritage organisations, primarily at the trustee and chief executive level, but also with the possibility of key directors attending.

The cohort will meet several times during a period of between six and twelve months, and will focus on improving the digital leadership skills and understanding of its participants. Study will be concentrated on the ‘what’ of digital, rather than the ‘how’, helping leaders to understand what digital tools and approaches now exist, how they can both create and destroy value for heritage organisations. Topics on the agenda could include:

- Recruiting for digital

- Data driven decision making

- Organisational strategy and the role of digital within it

- User research practices

- Agile project management

- The role of audience data analysis

The Work to be Commissioned

We are seeking a supplier to plan and deliver a digital leadership skills cohort programme that will last between 6 and 12 months, and that will host between 12 and 16 trustees and director level staff from Britain’s heritage sector.

In order for the cohort to be successful, the structure and content of the programme will need to be researched and designed by the supplier, in consultation with both the Fund and the type of individual who may attend the cohort.

In practice this will mean that the supplier will have to:

- Research prospective members of the cohort, and discover what they might want from such a group.

- Design an engaging and challenging programme of meetings and activities

- Design an appropriate recruitment mechanism to encourage people to apply, in conjunction with the Fund.

- Arrange meetings and activities with cohort attendees.

- Deliver the programme for the cohort.

- Record and analyse the findings from the programme.

- Work with the Fund’s evaluation specialists to ensure that it is possible to assess the extent to which cohort member’s skills have evolved.

- Ensure that the meetings and communications are accessible.

- Work with the Welsh language specialists at the Fund to ensure that we comply with the Welsh Language Standards.

Timeframe and commitment

We require that the chosen supplier is available to:

- Start design and discovery no later than 6th January 2020 (earlier is acceptable).

- Be ready to open applications to the programme no later than 7th February 2020

- Deliver the first cohort meeting no later than 1st May 2020

- Deliver a minimum of 4 cohort gatherings over a period of at least 6 months.

The successful bidder will need to be willing to travel to conduct meetings at various locations within the UK that are currently TBD.

# Contract management

We expect the contracted work to begin no later than the 6th January 2020 and be completed by the end of May 2021.

The anticipated budget is £50,000 plus VAT, and must include all project expenses, with the exception of supplier travel and accommodation, which will be covered directly by the Fund in line with the Fund’s travel and expenses policy. We expect project expenses to include venue hire and the cost of running cohort events.

The contract will be let by the National Heritage Memorial Fund.

The payment schedule will be quarterly based upon evidence of work satisfactorily completed and signed off by the Fund. We will make an initial payment of 10% of the contract value after project initiation commences to cover initial costs, especially bookings.

The contract will be based on the NLHF standard terms and conditions which are attached.

The Digital Engagement will be managed on a day to day basis for NLHF by Harriet Hall.

# Award Criteria

A proposal for undertaking the work should include:

  - CVs of staff allocated to the project, together with their experience in carrying out similar projects.

  - The project manager / lead contact should be identified;

  - The allocation of days between members of the team should be clear;

  - The daily charging rate of individual staff involved;

  - A timescale for carrying out the project;

  - An overall cost for the work.

You must answer the specific questions in this ITT (set out below), we shall evaluate your response against them.

- Give us examples of at least two projects you have worked on previously that show that you have relevant experience. Please include a few details about what happened and what you learned.

- Describe to us how you would go about designing the structure of the programme, and some indicative types of gathering you might run (depending on what discovery reveals).

- Describe some of the main characteristics that people who have acquired digital leadership skills would display.

- Tell us what steps you would take to help ensure that we receive a good pool of diverse applicants from across the UK.

- Outline how you would evaluate the impact of this programme.

Your Bid will be scored out of 100%, 70% against service/ quality and 30% on price. Each question will be scored using the methodology in the table below.

## Questions scoring methodology

| Score | Word descriptor | Description |
| --- | --- | --- |
| 0 | Poor | No response or partial response and poor evidence provided in support of it. Does not give the NLHF confidence in the ability of the Bidder to deliver the Contract. |
| 1 | Weak | Response is supported by a weak standard of evidence in several areas giving rise to concern about the ability of the Bidder to deliver the Contract. |
| 2 | Satisfactory | Response is supported by a satisfactory standard of evidence in most areas but a few areas lacking detail/evidence giving rise to some concerns about the ability of the Bidder to deliver the Contract. |
| 3 | Good | Response is comprehensive and supported by good standard of evidence. Gives the NLHF confidence in the ability of the Bidder to deliver the contract. Meets the NLHF’s requirements. |
| 4 | Very good | Response is comprehensive and supported by a high standard of evidence. Gives the NLHF a high level of confidence in the ability of the Bidder to deliver the contract. May exceed the NLHF’s requirements in some respects. |
| 5 | Excellent | Response is very comprehensive and supported by a very high standard of evidence. Gives the NLHF a very high level of confidence the ability of the Bidder to deliver the contract. May exceed the NLHF’s requirements in most respects. |

Your price element 30% of your score will be marked as follows: -

- 30 marks will be awarded to the lowest priced bid and the remaining bidders will be allocated scores based on their deviation from this figure. Your fixed and total costs figure in your schedule of charges table will be used.

- For example, if the lowest price is £100 and the second lowest price is £108 then the lowest priced bidder gets 30% (full marks) for price and the second placed bidder gets 27.6% and so on. (8/100 x 30 = 2.4 marks; 30 - 2.4 = 27.6 marks)

- The scores for quality and price will be added together to obtain the overall score for each Bidder.

## Schedule of Charges

Please show in your tender submission, the number of staff and the amount of time that will be scheduled to work on the contract with the daily charging rate.

Please complete the table below providing a detailed breakdown of costs against each capitalised description, detailing a total and full ‘Firm Fixed Cost’ for each element of the service provision for the total contract period. Bidders may extend the tables to detail additional elements/costs if required.

VAT is chargeable on the services to be provided and this will be taken into account in the overall cost of this contract.

As part of our wider approach to corporate social responsibility the Fund prefers our business partners to have similar values to our own. We pay all of our staff the living wage (in London and the rest of the UK) and we would like our suppliers and contractors to do likewise. Please indicate if this is not the case within your response.

Bidders shall complete the schedule below, estimating the number of days, travel and subsistence costs associated with their tender submission.

| FIRM & FIXED COSTS | Post 1 @cost per day (No of days) e.g. Project Manager/ Director @ £2 | Post 2 @cost per day (No of days) e.g. Senior Consultant/manager/researcher @£1.5 | Post 3 @cost per day (No of days) Junior Consultant/equivalent e.g. £1 | Total days | Total fees |
| --- | --- | --- | --- | --- | --- |
| Inception meeting to agree plans and finalise requirements with the Fund | Example 0.5 | 1 | 1.5 | 3 | £4 |
| Estimated Expenses |  |  |  |  |  |
| Estimate event hosting costs |  |  |  |  |  |
| Other Costs [Add as necessary] |  |  |  |  |  |

| Cost Type | Value (£) |
| --- | --- |
| Sub - Total |  |
| VAT |  |
| Total* |  |

* (This must include all expenses as well as work costs; this figure will be used for the purposes of allocating your score for the price criterion and must cover the cost of meeting all our requirements set out in the ITT)

Please do not include supplier travel and accommodation expenses in these calculations, as they will be directly covered by the Fund. Please include an estimate of these travel and accommodation expenses in your proposal, outside of this table.

Notes: The Fund reserves the right to clarify quality and prices and to reject tenders that demonstrate an abnormally low quality response. NLHF also reserves the right to amend the timetable of work where required.

You should not submit additional assumptions with your pricing submission. If you submit assumptions you will be asked to withdraw them. Failure to withdraw them will lead to your exclusion from further participation in this competition.

# Procurement Process

The Fund reserves the right to reject abnormally low scoring tenders and the right not to appoint and to achieve the outcomes required through other methods.

The procurement timetable will be:

- Deadline for clarification questions: 24th October 2019

  - Please email to harriet.hall@heritagefund.org.uk

  - We shall anonymise questions and share clarification questions and answers with all bidders. Answers to questions will be uploaded to the Contract Finder website on the 28th October 2019

- Tender return deadline: 8th November 2019, close of play 5pm.

- We reserve the right to conduct telephone interviews with shortlisted bidders if required: potentially 12th / 13th November 2019

- Bidders will be notified of our procurement decision 15th November 2019

- We will seek to meet the successful bidder for an initiation meeting/call no earlier than 2nd December 2019 and no later than 24th December 2020.

Your tender proposals must be sent electronically via e-mail before the tender return deadline of 8th November 2019 before 5pm to the following contact:

Harriet Hall

National Lottery Heritage Fund

International House

St Katherine’s Way

London

E1W 1UN

harriet.hall@heritagefund.org.uk

Please visit the NLHF website for further information about the organisation.

# Appendix: Accessibility and formatting guidance

NLHF is committed to providing a website that is accessible to the widest possible audience. Our site is annually tested by accessibility auditors and we must meet a AA compliance level. Our accessibility testing encompasses not just site functionality and design but all of our content, including downloadable documents.

Reports and other documents created for NLHF (including the tender submissions) need to be clear, straightforward to use and ready to circulate internally, externally and online, as well as suitable for use by screen reading software. Best practice in accessibility is summarised below:

## Readability

In the final report, and all other documents that may be published online including the tender application consultants should ensure that:

- The size of the font is at least 11pt;

- There is a strong contrast between the background colour and the colour of the text. Black text on a white background provides the best contrast. This also applies to any shading used in tables and/or diagrams;

- Italics are only used when quoting book titles for citations and items on the reference list should be arranged alphabetically by author

- Colour formatting and use of photos should be of a resolution size that is easily printable and does not compromise the printability of the document.

For further guidance on ensuring readability of printed materials, please refer to the RNIB Clear Print guidelines. These can be found on the RNIB website.

## Accessibility

Reports should adhere to the following guidelines:

## Formatting

Headings and content in your document should be clearly identified and consistently formatted to allow easy navigation for users. Heading Styles should be used to convey both the structure of the document and the relationship between sections and sub-sections of the content. Heading styles should follow on from each other i.e. Heading 1 then Heading 2.

## Spacing

Screen readers audibly represent spaces, tabs and paragraph breaks within copy, so it is best practice to avoid the repetitive use of manually inserted spaces. Instead, indenting and formatting should be used to create whitespace (e.g., use a page break to start a new page, as opposed to multiple paragraph breaks).

## Alternative text

Alt text is additional information for images and tables. This extra information is essential for both document accessibility (screen reading software reads the Alt text aloud) and for the web. Alt text should be concise and descriptive, and should not begin with ‘Image of’ or ‘Picture of’.

## Images

These should be formatted in-line with text, to support screen readers. Crediting pictures may be necessary, usually in response to a direct request from a third party.

## Tables

These should be for used for presenting data and not for layout or design. They should be simple and include a descriptive title. The header row should be identified and there shouldn’t be more than one title row in a table. There should be no merged or blank cells.

## Additional documents

Any additional information, separate to the report, for example proformas and transcripts which may be used as standalone documents must be fully referenced to the piece of work being submitting and therefore dated, formatted and numbered appropriately.

## Acknowledgement

All reports should acknowledge NLHF. Our logo can be found on the NLHF website.

## Further resources

Please refer to the WCAG 2.0 article on PDF techniques for further information.

Submitting your report to NLHF

Please check the accessibility of your document using the Word accessibility checker before submitting: File – Info – Check for Issues – Check Accessibility.

Please submit your document as a Word file.

NLHF retains the right to amend documents in order to create accessible versions for publishing.