# SPECIFICATION

# South East Invest Lot 2

# Locate East Sussex

# ESSEX COUNTY COUNCIL

# Inward Investment Service

# SPECIFICATION

# Lot 2 – Locate East Sussex

# Issued 30th January 2017

# ECC Procurement Project 0409

Contents

1.	East Sussex	6

2	Introduction to the tender	8

3	Background	9

4	Scope of Lot 2	10

4.4	Part A  -  Locate East Sussex Core Inward Investment Service (“the Core Service”)	10

4.6	Part B - The ERDF funded Enhanced Inward Investment Service(“the Enhanced Service”)	11

5	Service Outputs and KPIs	17

6	Key Dates;	24

7	Statement of Technical Requirements	26

8	Authority Policies and Insurance requirements	27

9	E-Procurement Requirements	27

Definitions

“BIS” means the Department for Business, Innovation and Skills

“the Boroughs and Districts” – means the boroughs of Hastings and Eastbourne and the Districts of Wealden, Lewes and Rother.

“the Contract” means the contract between the County Council and the Contractor as set out in [insert] of the Tender Documents

“Core Service” means the Locate East Sussex services set out in Part A of this Specification

“the County Council” – means East Sussex County Council

“the County” – means the geographic area of the county of East Sussex (note this excludes Brighton and Hove which is a unitary authority.

“the  Contractor” – means the organisation that wins the tender for the Inward Investment Service

“CRM System” -  means the Evolutive Client Relationship Management software system that used to monitor the service outcomes

“DIT” – Department for International Trade

“ECC” Essex County Council – the Lead Partners of the ERDF bid.

“ESCC” East Sussex County Council

“Economic Development Officers Group” – means the group of economic development officers of the County Council and the partners that meets bi-monthly

“Enhanced Service” means the European Structural and Investment Funds (“ESIF”) Programme 2014-20  ERDF funded enhanced service and outputs as set out in Part B of this Specification

“Enterprise Zone” means the Enterprize Zone of Newhaven

“ERDF” – European Regional Development Fund

“ESIF” European Structural and Investment Funds (“ESIF”)

“Foreign Direct Investment” (‘FDI’) - is an investment made by a company or individual in one country in business interests in another country, in the form of either establishing business operations or acquiring business assets in the other country, such as ownership or controlling interest in a foreign company

“Foreign Inward Investment” (‘FII’) - is the injection of money from an external source into a region, in order to purchase capital goods for a branch of a corporation to locate or develop its presence in the region.

“Growth Corridors” means the three Growth Corridors set out in the East Sussex Growth Strategy

“Growth Strategy” – means the East Sussex Growth Strategy for the period 2014-2020

“IPA” –  means Investment Promotion Agency, that is the Inward Investment Service

“Inward Investment Service” – means the Locate East Sussex Service

“ITT” – means this Invitation to Tender

“KPIs” means Key Performance Indicators

“Lead Partner” means Essex County Council

“Locate East Sussex” (‘LES’) – means the Inward Investment service for East Sussex.

“Partners” means the County Council, the Borough Councils of Eastbourne and Hastings and the District Councils of Lewes, Rother and Wealden

“Potential Contractors” means any organisation bidding for the Inward Investment Services.  (Upon award of the Contract, references herein to “Potential Contractors” shall be read as a reference to the “the Contractor”)

“R&D” means Research and Development

“Requirements” means the County Council’s requirements for the Enhanced Service as set out at paragraph 4.9 of this Specification

“SELEP” – means South East Local Enterprise Partnership

“SEP” – means Strategic Economic Plan

“SMEs” means small and medium sized enterprises

“Tender Documents” means the tender documents published by ECC in relation to the procurement of the Inward Investment Services

“TES” – means Team East Sussex, the federated board for East Sussex which reports into the SELEP

“TUPE” – means Transfer of Undertaking (Protection of Employment) Regulations 2006 (TUPE) Regulations which implement the Acquired Rights Directive.

- East Sussex

  - This specification relates to the county of East Sussex only which is situated in the south east of England with Kent to the east, Brighton and West Sussex to the west and Surrey to the north. It has a population of nearly 544,000 in 241,000 households.  It has 22,520 live businesses and many more self-employed people.

  - East Sussex County Council is an upper tier authority.  It has close working partnerships with the five boroughs and districts of East Sussex, namely Eastbourne BC, Hastings BC, Wealden DC, Lewes DC and Rother DC as well as the Further Education colleges and two local universities of Sussex and Brighton.

  - The County Council is a partner in the South East Local Enterprise Partnership (“SE LEP”) along with Kent and Medway, Essex, Thurrock and Southend. This partnership takes the strategic lead for the area on economic growth. The SE LEP Strategic Economic Plan (“SEP”) outlines the growth objectives for the SE LEP area under the SE LEP Board. Link to SE LEP website: http://southeastlep.com.

  - Local Enterprise Partnerships are seen by the current government as the main ‘sub-regional’ vehicle through which most indirect government finance for economic growth flows. As part of this, the SEP outlines a Growth Deal for SE LEP which is financed, where government sees the maximum benefit, via the Local Growth Fund.  Given its geographical size, SE LEP has a federated operational model and for the purposes of the Growth Hub and this ITT, this federation consists of Essex, East Sussex, and Kent.

  - East Sussex County Council Plan

  - The County Council has identified four overarching priority outcomes: driving economic growth; keeping vulnerable people safe; helping people help themselves; and making best use of resources. Making best use of resources is the gateway priority through which any activity and accompanying resources must pass. The remaining three priority outcomes guide our activities, direct our resources and are reflected in our Council Plan activities and targets.

  - A thriving economy in East Sussex is key to the wellbeing of the County. Ensuring that local people have access to well-paid employment will have positive impacts on the health and the education outcomes of our young people, and will mean that they are less dependent on shrinking public sector resources. A growing economy will increase the resources we can raise locally to provide the services needed by the most vulnerable people in our society.

  - East Sussex Growth Strategy

  - The County Council with its local partners developed the East Sussex Growth Strategy for the period 2014-2020 (the “Growth Strategy”). The Growth Strategy is owned by TES. It sets out the vision for a more innovative, productive and faster growing East Sussex economy. We believe the County has a unique offer to make to investors, businesses and skilled workers; one that blends inspiring coastline and countryside and a business base of like-minded companies in growing sectors of the economy.

  - The strategy is built around three key pillars:  Business: Enabling business growth, particularly of ‘high value’ businesses; Place:  A significantly valued asset to the East Sussex economy; People: Meeting the skills needs of business and supporting residents to reach their full potential.

  - This Growth Strategy identifies the major economic opportunities across the County, and the collective actions that public and private sector partners will take to accelerate growth. By capitalising on the County’s strengths and unique characteristics, we will create a stronger, more diverse economy that will bring more jobs, particularly in higher value sectors. Our aim is to maximise the economic potential of every part of the County, recognising the different economic opportunities and challenges in our coastal communities and rural economy.

  - There are three growth corridors where there is the greatest capacity to unlock major new commercial and residential development. These are the:

A21 / A259 Hastings-Bexhill corridor, in particular the new developments on the Bexhill Hastings link road;

A22 / A26 / A27 Eastbourne – Polegate – Uckfield – Crowborough corridor; and

Newhaven Clean Tech and Maritime Corridor -  Also an Enterprise Zone and Port Gateway

  - Significant investment in education, business support, transport, infrastructure and the public realm has already taken place in these corridors and this momentum needs to be sustained to unlock further growth.

  - In the largely rural area, which includes the South Downs National Park and the High Weald Area of Outstanding Natural Beauty (“AONB”), a different approach is needed; one which strengthens and diversifies the economy whilst protecting and enhancing the outstanding natural environment. Our aim is to create networked and vibrant market towns and villages ready for knowledge-based entrepreneurs and manufacturing and engineering businesses. Encouragement of emerging land-based industries, such as viticulture, quality food and agritech, is needed, and the intensification, upgrading and new development of business premises is required to support manufacturing and office-based services.

  - Whilst each of these corridors has individual strengths, the Contractor should recognise that there are dependencies’ between corridors as well as strategic pressures that apply to all corridors. The County Council recognises that more can be achieved through working together across these corridors and therefore Potential Contractors should seek to achieve these greater synergies from the outset in order to realise the true potential of the County.

  - The Growth Strategy is currently being refreshed but is still relevant and  can be found at www.eastsussex.gov.uk/environment/planning/regeneration/growthstrategy

  - The Innovate East Sussex paper, produced in 2014 , sets out a framework and goals to achieve economic development benefits and support the creation of more efficient, responsive, cost-effective services. The document draws on the EU Smart Specialisation agenda and BIS and Innovate UK research over recent years, which aim to embed innovation to secure sustainable growth.

  - The vision for Innovate East Sussex is to make the County the location for innovation; where innovation is the natural order rather than something that happens better, faster and more often elsewhere. This is predicated on strong partnerships that will, on the one hand, stimulate and support innovation and on the other, work to remove barriers to it working.

  - The key findings of the paper should guide the support for innovation, high growth firms and sector support.

  - All the papers and relevant documents can be found at: https://www.eastsussex.gov.uk/environment/planning/regeneration/

  - The latest Economic Update for East Sussex can be found at: TES economic updates

- Introduction to the tender

  - The County Council is seeking a contractor to deliver the Locate East Sussex inward investment core service (“Core Services”), and the enhanced service funded by the European Regional Development fund project (“Enhanced Services”) as set out in this Specification on behalf of the County Council and its partners.

  - The Contract requires the Contractor to deliver the Inward Investment Services across the County running for a period of three (3) years, commencing in May 2017 for a set fee of £420,000 a year. There will be an option for the County Council to extend the Contract for one additional year, subject to funding at the end of the term.

  - Through the Contract, the Contractor will be expected to provide both a clear programme to attract inward investment and support incoming or growing businesses.

  - Provision will support both the attraction of new investment to the County as well as assisting existing East Sussex based businesses to develop and grow, providing signposting to linked providers, promoting affordable commercial space and developing strong linkages between SME’s and larger business to deliver further investment to the County.

- Background

  - As a part of its efforts to deliver sustainable Economic Growth for East Sussex Communities and Businesses, the County Council and its local Borough and District Council partners have had a long term priority to secure inward investment to the County as well as supporting and enhancing the development of SME’s.

  - The current Locate East Sussex (‘LES’) Service (“Current LES Services”) has been delivered under contract by the Lets Do Business Group (“LDBG”) since May 2013; this contract finishes in May 2017.  The Current LES Services are co-located with LDBG in St Leonards, East Sussex.

  - The County Council and the Boroughs and Districts will spend £210,000 on the Current LES Services in the financial year 2016/17.  The current LES Service has 3.5 FTE staff and the County Council advises that TUPE regulations will apply to these staff members.  Their terms are detailed in the TUPE Information supplied

  - The delivery targets for the last year of the Current LES contract are:

- 12 inward investments and 13 reinvestments;

- 50 jobs created; and

- 50 jobs safeguarded.

The investment targets were met in the preceding 12 months and the jobs created target was exceeded by 50%.

  - The Current LES Services promotes the County as a business location on behalf of the County Council and the Boroughs and Districts who jointly fund the Current LES Services and who work closely with Locate East Sussex.

  - At present, activities delivered by the Lets Do Business Group under the Current LES Services are predominantly reactive to business enquiries due to the level of funding and resource available with limited proactive targeting and sector-specific support available. Current activities include;

- Generic Investor Development, Targeting & support;

- A standalone Locate East Sussex Website (the domain name owned by the County Council);

- A property database sourced from Estates Gazette;

- Generic place marketing for the County as a business location;

- Signposting of businesses to other services, in particular the Growth Hub termed Business East Sussex (“BES”);

- Promoting and supporting applications to East Sussex business growth funding;

- Handling enquiries from potential investors when received and responding to these enquiries offering location selection support and property search services; and

- Promoting the County through press releases and social media of business success case studies and promoting premises.

- Attending business to business events and conferences to promote East Sussex.

  - Partners have undertaken a review to ensure that the current provision is fit for purpose. This has been undertaken through an evaluation of the Current LES Services as well as collaborating to develop this Specification for a revised and enhanced service. All of which ensures that it effectively aligns with the requirements and expectations of the market and will effectively deliver the Inward Investment support that Partners have identified as necessary to attract and support businesses to locate and grow in the County.

  - The review above concluded that whilst the Current LES Service has the right people and many of the right tools, it lacks the time and resources necessary to deliver the kind of comprehensive investor targeting strategy that will deliver greater inward investment for the region. The findings have informed the design of this Specification which seeks to provide an enhanced service offer (including innovation) and more responsiveness to the needs of its customers than the Current LES Service .

  - In addition to the strategic priorities driving delivery of the inward investment services, the County Council and Partners, recognise the need to secure a sufficient budget to enhance the reputation and the capacity of the Inward Investment Services over the three (3) year period of the Contract.  The County Council, together  with the lead partner Essex County Council (“ECC”) has identified the opportunity to access European Regional Development Fund (“ERDF”) monies to maximise available funding to deliver the Enhanced Service and better outputs and outcomes.

- Scope of Lot 2

  - This Specification relates to the administrative area of the County Council and is in two parts: Part A - the Core Service and Part B - the Enhanced Service.

  - The Contract requires a delivery Contractor to secure inward investment to attract high-value, high-quality investors to the County, creating and supporting  long-term, jobs, as well as adding value to local supply chains, providing partnering and collaboration opportunities between SMEs, increasing Research & Development (R &D) spend whilst developing both the talent base and new technologies in the County.

  - The Inward Investment Services will provide support to beneficiary SMEs in all sectors, but with a specific aim to encourage job growth and retention in sectors of specific relevance to the County namely;

    - Land-based– the developing specialist, high added-value food and drink production, including brewing and viticulture and food processing;

    - Healthcare – specifically in relation to the ageing population, including telehealth and telecare;

    - Advanced Manufacturing, Engineering and Electronics;

    - Construction;

    - Low carbon (including renewable energy);

    - Digital, creative, cultural and media; and

    - Financial and Business services.

  - Part A  -  Locate East Sussex Core Inward Investment Service (“the Core Service”)

  - The County Council and Partners require a Contractor to deliver the Core Service as currently provided, namely:

- Generic Investor Development, Targeting & support;

- A standalone ‘Locate East Sussex’ website (the domain name is owned by the County Council);

- A property database sourced from Estates Gazette (or other – please detail);

- Generic place marketing for the County as a business location;

- Signposting of businesses to other services, in particular the Growth Hub (BES);

- Promoting and supporting applications to East Sussex business growth funding;

- Handling enquiries from potential investors when received and responding to these enquiries offering location selection support and property search services; and

- Promoting the County through press releases and social media of business success case studies and promoting premises.

- Attendance / exhibiting at business to business events and conferences to promote East Sussex.

  - Part B - The ERDF funded Enhanced Inward Investment Service(“the Enhanced Service”)

  - The County Council and Partners have collaborated with ECC to develop a project, known as ‘South East Invest’ (“SEI”) that will create enhanced inward investment services in those counties, meeting SE LEP’s key priority of increasing trade and attracting investment. South East Invest seeks to enhance the capacity and expertise of services to develop long-term sustainability whilst ensuring SME’s in key sectors access support to re-locate and/or expand their operations and create a range of new businesses and jobs.

  - The successful Contractor will be expected to provide;

- Account management – detailing the number of existing and potential investors to be supported as well as providing intelligence in relation to the commercial property market, ensuring intelligence and engagements with customers and partners are recorded and monitored through 	the Evolutive Customer Relationship Management (the “CRM System”).

- Sector development and promotion activities – producing a plan which details activity (such as cluster mapping and proposition research and marketing) and the related forecast results and delivery plan.

- Marketing, and in particular Place Marketing (County and Local)

- Investor development support

- Enhanced local engagement and capacity – involvement of local public and private stakeholders in a successful investment attraction process

- Development and addition to the existing understanding of the County and its business environment - augmented with the Contractor’s own knowledge, experience and skills.

  - The successful Contractor will demonstrate:

- A comprehensive knowledge of inward investment services and the service requirements of the Enhanced Services;

- A clear understanding of individual markets / segments, an awareness of the issues and opportunities present in priority sectors, and how it will work with relevant networks and clusters ;

- A clear understanding of the support environment already in place in the County and an awareness of the importance / impact of being able to offer holistic support to clients;

- An ability to comply with ESIF requirements.

  - The Contractor will work with Partners to create additional local capacity to enable Foreign Direct Investment (“FDI”) and Foreign Inward Investment (“FII”) promotional and support activity, with the dual aims of attracting new innovative and potentially high growth SME’s or supporting local expansions by local and overseas owned companies. The Enhanced Services will also create capacity to exploit the new opportunities emerging around planned key employment sites.

  - The key features of the Enhanced Service (“the Requirements”) are as follows:

- Place Marketing of the County;

- Increased intelligence and data analysis;

- FDI focussed on key growth markets;

- Innovation and Supply Chain support;

- Business relocation after care service;

- ‘Soft-landing’ support; and

- Supply side marketing.

Further details of the Requirements are set out at paragraphs 4.12 to 4.21 below.

  - Requirement 1 - Place marketing (including Growth Corridors, the Enterprise Zone, the Port, Assisted Areas and cluster-marketing.) Current marketing of the County is focused on the County area as a generic destination; however, in addition to this the Contractor will be required to enhance the County’s attraction as an inward investment destination, alongside developing and delivering specific place marketing strategies, recognising the different economies and geographies across the East Sussex economy.

A minimum of 10% of the  annual contract value should be focussed on this requirement.

    - Provide market intelligence, materials and knowledge to develop a series of location-specific offers, which will build up to an offer across the County and support the communication of the whole County Council and SE LEP offer.

    - A place-marketing strategy based on the market specialisms and businesses environment in each growth area identified in the SEP and the Growth Strategy. A dedicated marketing resource will develop place-specific materials, media content and campaigns, targeted where appropriate at specific businesses / business sectors including our destination locations including the Growth Corridors, the Enterprise Zone, and Assisted Area Status plus linkages to the rest of the UK and Europe (Ports, Airports, Rail, Road connections to London as well as the private-sector property market and leisure offer).

    - A recognisable format will be utilised across the County with existing district and borough materials and products aligned to identical standards to promote a clear, recognisable image of the County to investors.

    - Specific focus will be made on the availability and strengths of sector-specific supply chains to develop the SME capacity, creating new jobs to support the location and development of trans-national / multi-national companies. To focus in particular on the high-technology clusters such as TEC 66 vacuum cluster, the Food and Drink sector including Viticulture and the renewable energy sector.

    - A place marketing offer that includes a comprehensive understanding of the business environment across the County including the skills available in the workforce both now and where enhanced future provision may be available.

    - Hosting and attending major conferences and events, and networking between SME’s and larger organisations of both new investors and existing supply chains, the Contractor will create the business environment necessary for further Inward Investment and will identify ways of taking the offer to the market, attending events briefings and sector based ‘open days’, and organising and hosting inward investment visits.

  - Requirement 2 - Developing an enhanced intelligence and data analysis programme. The Contractor will be expected to use data analysis and intelligence from both created data and engagements with partners specifically including the Districts and Boroughs to drive the location and creation of jobs into the County. This will be achieved by;

    - Working with partners and private-sector organisations to develop an understanding of the economy and seek to leverage subject matter expertise and develop partnerships and effective communication networks.

    - Developing an intelligence-led prospectus on the current and future programme of commercial property development in the County which can be used in the targeted promotion of sites and premises.

    - Understanding employment trends to give greater focus to marketing and promoting services to the appropriate businesses.

    - Providing intelligence around emerging industrial clusters.

    - Developing a comprehensive understanding of grants, loans and other funding sources available for investors.

    - Developing data and information sharing protocols between the BES Growth Hub and Partners. These protocols will reference the need to ensure that the data within the CRM Systems is robust and regularly updated.

    - Making available the CRM system to Partners tot facilitate the two-way updating of information regarding the latest site availability and investor approaches to ensure a consistent understanding and message is communicated. This is may require a data-sharing agreement being agreed the County Council, Partners and the Contractor

  - Requirement 3 - FDI and FII The following activities will be offered to encourage FDI/FII, focused on SME’s and the County Council’s key growth-markets;

    - The Contractor will deliver sufficient local capacity to enable FDI and FII (“FDII”) promotional and support activity not currently being undertaken by DIT or partners, with the dual aims of attracting new innovative and potentially high growth SME’s and / or supporting local expansions by overseas owned companies.

    - The Contractor should seek to leverage the resources, expertise, knowledge and capacity the Council  and Partners have to support FDI and FII to enhance the delivery of support to investors.

    - Using the outputs from the intelligence-led and sectoral focused marketing work referenced above and existing FDII networks, the Contractor will undertake focused investor identification and targeting to encourage re-location from businesses in the sectors of specific focus for the County Council.

    - The Contractor will develop the existing partnership with DIT and seek to collaborate to enhance the DIT Investment offer for the County, to avoid duplication and share leads as well as seeking to develop relationships to encourage greater marketing of the County on the international stage.

  - Requirement 4 - Innovation and targeting of pre-growth & high-growth companies & supply-chain support. This Requirement links directly to the ‘Innovation, Investment and Enterprise’ priority in the SE LEP ESIF strategy and the Innovate East Sussex paper. This will be delivered through:

    - Identifying and supporting the emerging innovation practices amongst high-growth and pre-high growth companies especially within the sectoral-specific growth locations.

    - Ensuring sufficient capacity exists in the Inward Investment Service to support engagement between investors and partners (specifically Universities and Business Development Programmes and the Growth-Hub) in sectoral specific growth locations to raise the number of high value jobs that add value to local supply chains.

    - Developing capacity in specific areas of market specialism to create further impact including opportunities for collaboration between Higher Education Institutions and investors.

  - Requirement 5 – Provide a retention programmme for businesses. The Contractor will maintain close contact with key businesses in the County:

    - The contractor will keep in touch with key businesses so that there is an early warning system for SMEs who may be considering re-location out of the area. This part of the Inward Investment Service will improve the retention rate of existing businesses by supporting them to find alternatives for their expansion within the area.

    - The Contractor will collaborate on key accounts with DIT to enable much wider coverage of retention activities.

    - The Contractor will provide support to key companies already located in the County, helping them to expand and grow operations and create jobs.

    - The Contractor will expand the current operations, widen the scope and increase the number of companies that will benefit from investor development support including overseas owned companies and those high value SME’s

    - The Contractor will maintain effective relationships with major employers and businesses to retain those businesses, identify growth opportunities and support to manage supply issues (skills, supply chain, premises etc.).

  - Requirement 6 - Soft Landing and After Care Support.  The contractor will   develop a package of soft landing support for Investors, and an aftercare programme, essential  if the County is to retain and grow the relocations secured by the Inward Investment Service. Recognising that within some partner organisations there is capacity and ongoing delivery of some of these services, the Contractor will be expected to:

    - Support to include market and local information and intelligence, a dedicated account manager, referrals to other business support organisations, sector bodies and intermediaries and networking opportunities and supported referrals to funding agencies.

    - Deliver investor development / aftercare activity focused on high value SMEs in the County, working with Partners to enhance and support the coordination of local approaches to ensure a consistent level and quality of support is provided across the County

    - Develop knowledge and sustainability of supply chains in key East Sussex growth sectors through engagements between businesses, local authorities and Higher Education institutions, as well as using them to attract other businesses whilst anchoring the original investor and creating sustainable new businesses

    - Compile follow-up visit programmes, liaising with all the relevant partners so that visits can meet the business client’s criteria and involve all internal and external partners from business, industry and academic institutions.

    - The Contractor will keep up-to-date information on all relevant sources of business funding to guide the investor and provide specialist advice and support on applications.

    - The Contractor will refer investors to relevant agencies to support staff recruitment and training.

  - Requirement 7 - Enhanced supply-side marketing. The Contractor will develop a coordinated supply-side marketing offer through engagements with partners and deploy this in their communication of the County to the market;

    - The Contractor will engage East Sussex partners including the County Council, various external regional and local partnerships (including Developers East Sussex and Business East Sussex), other EU ERDF business support funded projects (including the South East Business Boost (SEBB) project, LOCASE, KEEP+, EXEMPLAS etc) districts and boroughs, to support the development of  employment sites and enhance their offers and work with commercial agents and land owners, to produce authoritative intelligence on the development potential of sites coming forward.

    - The Contractor will work with these partners to understand and promote the offers available in their areas or organisation such as sites available for development, planning policies, financial incentives etc. as well as providing feedback from investors on the perceived gaps in suitable provision, raising  Partner’s awareness of areas of potential market failures as well as providing feedback on challenges from investors in delivering sites / growth.

  - Requirement 8 - Aligned working with the SE LEP Growth Hub Network The Inward Investment Services sit alongside the SE LEP Growth Hub network (having its own local core Growth Hub termed Business East Sussex) (BES) and also the part funded EU ERDF SEBB project.  The Contractor will collaborate with these services to ensure that all SMEs looking to locate anywhere within the SE LEP area receive a similar high-quality service to support their growth ambitions through access to financial support, signposting, networking and common place-marketing across the SE LEP area. All Potential Contractors will be expected to clearly demonstrate how they will deliver a pathway approach to businesses.

    - A clear distinction will be made regarding retention services offered to SME’s through this Requirement, including foreign owned businesses as well as those requiring specific tailored re-location and supply chain support, and the generic business support services that will be delivered to clients by SEBB. Collaborative working and referral protocols will be established with SEBB and partners, to ensure clients receive the most appropriate support.

    - The Contractor will ensure maximum opportunities for cross-referral between the initiatives exists, and clear distinctions between the services delivered are drawn, including usage of the linked CRM System across the two services to ensure completeness and to avoid any duplication of Growth Hub and SEBB activity but offer complementary provision.

  - Requirement 9 - Aligned working with the Foreign Inward Investment Kent Project and the Invest in Essex service and implementation of a strong partnership approach. In order to  maximise the benefits of alignment across the whole SE LEP area, the Contractor will be required to identify common ‘themes’ and areas for  collaboration between the Inward Investment Services and the Foreign Inward Investment Kent Project, Invest in Essex as well as other partners, including:

    - Opportunities to work together on FDII / Trade as a combined gateway and supporting each other on focus regions.

    - Develop close and coordinated links with DIT to generate leads, creating a common offer at business events, to enhance the promotion of the region on the international stage.

    - Develop greater coordination of how Partners promote the region.  The South East of England has a far greater marketing capacity than individual Local Authorities. Work will involve sharing resources to deliver this activity in the most resource-effective way.

    - The East Sussex Growth Corridors are an additional joint promotion opportunity, as are the Enterprise Zone at Newhaven (our Gateway Port) and also the Assisted Area in Hastings.

    - The Contractor will also work closely with other referral partners, including DIT, and business support organisations including the Chambers of Commerce, Higher Education and Further Education establishments, Institute of Directors and the Federation of Small Businesses, as well as employer and sector representative groups.

    - Referral protocols will be established between the other business support services, East Sussex local authorities and Higher Education partners.

    - The Contractor will be expected to evidence how they will strengthen relationships with the SE LEP, including developing robust referral protocols for businesses contacting the SE LEP seeking to Invest in the County.

    - As part of their tender response, Potential Contractors are required to demonstrate a clear methodology for partnership engagement and stakeholder engagement in order to ensure appropriate engagement is undertaken including presentation of intelligence and updates at partnership meetings.

  - Requirement 10 - Development of a sustainable service model.  Potential Contractors are required to identify how they will deliver the Inward Investment Services within the  levels of funding set out within this Specification.

    - The County Council expects the Contractors to identify how they will develop additional revenue streams from operation of the Inward Investment Services and set out a plan for how this will be utilised to deliver the Enhanced Service at the appropriate level and ensure the long-term sustainability of the Inward Investment Services.

    - The County Council and Partners have expressed an interest in developing a tailored service, specific to the requirement of their localities. The Contractors are therefore encouraged to outline how they will develop these relationships and generate income by offering additional services beyond the scope of those set out within this Specification.

    - Any additional services or outputs set out in any tender submission submitted by a the Contractor (“Contractor Designed Services”) will be incorporated into this Specification in the event of that the Contractor being selected.  The County Council will agree with the Contractor any KPIs or reporting requirements in relation to such Contractor Designed Services after award of the Contract but prior to commencement of the Inward Investment Services.  For the avoidance of doubt, any reference in this Specification to the Inward Investment Services shall include any Contractor Designed Services.

- Service Outputs and KPIs

  - The Core Service and the Enhanced Service have minimum outputs required.  Potential Contractors will be scored on how their service offering exceeds these targets as demonstrated by their Tender Submissions.

  - Potential Contractors will provide as part of their Tender Submission challenging Key Performance Indicators (“KPIs”) for the Inward Investment Services, which will include quantities and dates of outputs to be achieved and how they will evidence their achievement over the period of the Contract.

  - Baseline service levels (“Service Levels”) will be agreed between the Contractor and the County Council before the start of the Contract based on the submission and, where appropriate, will be reviewed during the first year of the Contract.

  - The Contractor will share supporting information and evidence in relation to performance against the Service Levels and KPIs with the County Council in accordance with the County Council’s ERDF application.  The Contractor shall report:

    - monthly to the County Council;

    - bi-monthly to the Economic Development Officers Group and Project Management Board;

    - quarterly to the Locate East Sussex (LES) Sponsors; and

    - as and when required to the TES Board.

  - The Contractor will utilise the CRM System for the recording and monitoring of Service Levels and activity delivered under the Contract. The CRM System will be accessible at all times by the County Council on behalf of the Partners in order to monitor performance and delivery of Service Levels and KPIs and to identify opportunities for collaboration or development of future, related initiatives or programmes.

  - The County Council will agree with the Contractor a performance regime prior to the commencement of the Contract which clearly demonstrates the Service Levels to be delivered across the life of the Contract.

    - In cases of poor performance against the Service Levels, a recovery plan must be put in place within the quarter following the poor performance. The County Council reserves the right to withhold payments in subsequent quarters in line with the clawback process which forms the basis of the ERDF contracts.

    - In extreme cases of continuous performance failure against one or more of the Service Levels or KPIs, the County Council in consultation with Partners may terminate the Contract in line with the terms and conditions set out therein.

  - By mutual agreement, the Service Levels may be modified during the term of the Contract. The performance measures will be reviewed at the end of each year of the Contract, and any adjustments to non-ERDF Service Levels will take effect three (3) months after such agreement.

  - The Contractors should note that the Inward Investment Services set out in this Specification represents the minimum acceptable standard and the Contractors are encouraged to outline how they will deliver outputs beyond those identified.

  - Core Service Minimum Outputs

| Number of investment success per year* | 12 |
| --- | --- |
| Number of re-investments per year* | 13 |
| Number of jobs created per year | 99 |
| Number of enquiries per year including property portal registrations | 200 |
| Number of business interactions a year ** | 200 |
| Number of website / social media contacts / hits per year | 7000 |
| Number of referrals to business funding | 30 |

*nb – the investments (from outside East Sussex) and re-investments are different from the ERDF outputs and do not require 12 hours support but do require a positive outcome. These can include the ERDF outputs that are successful.

** These are business enquiries that are responded to or contacts made at events or by phone.  The ones that progress will be counted again under the ERDF and Core outputs.

  - Enhanced Services – ERDF Minimum Outputs

  - The Contractor will deliver the Inward Investment Services on behalf of the County Council and Partners and will demonstrate how it will focus on working to secure inward investment, supporting the growth and development of supply chains and of SME’s through the activities described above in Part B of this Specification.

  - The ERDF outputs below (“Enhanced Service – Service Levels”) have been developed with Essex County Council and the County Council and have been verified as deliverable as part of the development process. The Enhanced Service – Service Levels (as set out below) have been agreed with the Department for Communities and Local Government (“DCLG”) and are fixed for the term of the Contract.  Non-delivery of any of the Enhanced Service – Service Levels is subject to claw-back or non-payment of funds. Potential Contractor should demonstrate in their Tender Submission how they will effectively deliver to these profiles and their protocol for managing under performance and claw-back.

  - The Enhanced Service – Service Levels will form the basis of the KPIs for the Enhanced Services which the Contractor will be measured against.

  - Minimum ERDF compliant requirements (“ERDF Outputs”)

The table below sets out the minimum output requirements of the Enhanced Service as set out in the ERDF bid that must be achieved by the Contractor.  Additional outputs including those for the Core Service to be proposed by the Prospective Contractor.

The definition of support to relocating businesses either from outside the County or within are defined below:

    - A minimum of twelve (12) hours support (advice, intelligence and visits to potential sites) for selected investors to plan and implement a re-location to the County, including property searches, site reports for clients looking for larger premises or sites, arranged / accompanied site visits as appropriate, assistance with negotiating terms, assistance with planning applications and recommendation of sources of support where appropriate, including sources of possible funding.

  - A minimum of twelve (12) hours support to selected businesses already in the County to develop an action plan to retain or grow jobs and support new product / service development and market entry.

  - ERDF can only assess new jobs created and not safeguarded or indirect jobs. This means that only new, permanent, paid jobs created as a result of the Enhanced Services will count towards the Enhanced Services – Service Levels. Evidence for such job creation shall be in the form of written confirmation by an enterprise, with job details and a schedule of jobs created.

  - Output Targets and Indicators– as set out in 2014-2020 European Growth Programme, Output Indicator Definitions Guidance for ERDF, Sept 2016.

|  | East Sussex targets per annum min ( 3 yr total) | Evidence required by DCLG |
| --- | --- | --- |
| C1; Number of enterprises receiving support | 18 (54) | Count criteria: Small and medium sized enterprises (SMEs); any support that is consistent with national eligibility rules and Operational Programme. Count threshold: Minimum 2 days (12 hours) active consultancy support; a specific business can only be counted once. Count exclusions: Travelling and preparation time; distribution of mail shots and brochures; activity already counted; any business ineligible for ERDF support. Verification evidence: Record of business (name, address, contact details, CRN); support claimed through hours supported (verified by business supported) |
| C4; Number of enterprises receiving non- financial support | 18 (54) | Count criteria: This is a subset of indicator C1 – therefore Count Criteria under C1 must be fulfilled. To register as non-financial support, the business must be provided with a service or services by the project with no direct payment of monies. Count threshold: This is a subset of indicator C1 – therefore Count threshold is as C1. Count exclusions: This is a subset of indicator C1 – therefore Count exclusions is as C1. Verification evidence In addition to Indicator C1,support claimed through hours supported – record, electronic or paper, of support over the minimum threshold (12 hours) verified by a senior member of staff in the enterprise assisted, including time period claimed. |
| C5; Number of new enterprises supported | 3 (9) | Count criteria: Same as C1 criteria, plus; a new business which is not trading and registered at Companies House for less than 12 months; a business locating in the Programme area for the first time (ie new to Programme area or branches of businesses which remain established elsewhere in the EU; or foreign direct investment bringing new enterprises to Programme area, both first time investment and subsequent expansions from outside the UK) Count threshold: Same as C1 criteria Count exclusions: Same as C01; the same business cannot be counted at different phases of its growth Verification evidence: Same as C01; evidence of new business requires company incorporation statement or letter or standard formed signed by business |
| C8; Employment increase in supported enterprises | 33 (99) | Count criteria: New, permanent, paid, FTE job created as a result of the activity supported by project; new means it did not exist with employer in England programme area before intervention; permanent means it should have intended life expectancy of at least 12 months. Count threshold: A job with an intended life expectancy of 12 months; date of creation is the day the new employee starts work in enterprise; minimum 36 hours per week threshold; part time jobs treated pro rata. Count exclusions: Jobs created directly to set up the project’s activities, including construction jobs. Verification evidence: Written confirmation from supported enterprise, including job details; additional information (age, gender, disability; ethnicity) |
| C28 Number of enterprises supported to introduce new to market products | 2 (7) | Count criteria: This is a subset of the indicator C1 - therefore Count Criteria under C1 must be fulfilled. Support must be for an enterprise to introduce one of the following: - Product - when it is either at pre-launch or launched to the market - Process - when it has been introduced into the business - Service - when it has been introduced to the market. The indicator measures if an enterprise receives support to develop a 'new to the market' product in any of its markets. It includes process innovation as long as the process contributes to the development of the product. A product is new to the market if there is no other product available on a market that offers the same functionality, or the design or technology that the new product uses is fundamentally different from the design or technology of already existing products. Products can be tangible or intangible (incl. services and processes). Supported operations that aimed to introduce new to the markets products, but did not succeed are still counted. If a product is new both to the market and to the firm, the enterprise should also be counted as supported to introduce new to the market products as well as supported to introduce new to the firm products. Enterprises included in this indicator should also be recorded as receiving one of grants or financial or non-financial support. The indicator applies to all sizes of enterprise, but eligibility rules or operation selection criteria may restrict the scope of activity. Count exclusions: This is a subset of indicator C1 – therefore Count exclusions is as C1. Operations without the aim of actually developing a product are excluded. If an enterprise introduces several products or receives support for several operations, it is still counted as one enterprise. In case of cooperation operations, the indicator measures all participating enterprises |
| C29; Number of enterprises supported to introduce new to the firm products | 1 (5) | Count threshold: This is a subset of indicator C1 – therefore Count threshold is as C1 The indicator measures if an enterprise is supported to develop a “new to the firm” product. It includes process innovation as long as the process contributes to the development of the product. Projects without the aim of actually developing a product are excluded. If an enterprise introduces several products or receives support for several operations, it is still counted as one enterprise. In case of cooperation operations, the indicator measures all participating enterprises to which the product is new. A product is new to the firm if the enterprise did not produce a product with the same functionality or the production technology is fundamentally different from the technology of already produced products. Products can be tangible or intangible (including services). Supported projects that aimed to introduce new to the firm products, but did not succeed are still counted. If a product is new both to the market and to the firm, the enterprise should be counted in both indicators. Enterprises included in this indicator should also be recorded as receiving one of grants or financial or non-financial support. The indicator applies to all sizes of enterprise but national eligibility rules or project selection criteria may restrict the scope of activity. Count threshold: Same as C1 criteria Count exclusions: Same as C1 criteria. Verification evidence: In addition to the evidence required for indicator C1: Products/processes services: Evidence might include the date a new or improved process became operational or the date the new product or service was launched from market information or marketing literature. |

Potential Contractors will be required to account within their Tender Submissions for how they will manage delivery against these outputs and the type, frequency and mechanisms they will put in place to record and share this data with the County Council and its Partners.

  - Service KPI’s & Monitoring Information.

  - The following table outlines the KPI’s and outputs for the Inward Invest  Core Services and the Enhanced Serivce  ERDF minimum requirements.  Potential Contractors are required to include the table in their Tender Submission and complete the final column with the additional stretch targets they expect to achieve.

| KPI per year | minimum ERDF Outputs (3 years) | Other annual outputs | Additional outputs proposed by the Contractors |
| --- | --- | --- | --- |
| C1No. of enterprises receiving support – 12 hours | 18 (54) |  |  |
| C5 No. of new enterprises supported | 3 (9) |  |  |
| C8 Employment increase in supported enterprises | 33 (99) |  |  |
| C28 No. of enterprises supported to introduce new to market products | 2 (7) |  |  |
| C29 No. of enterprises supported to introduce new to firm products | 1(5) |  |  |
| No of investment success per year* |  | 12 |  |
| No. of re-investments per year* |  | 13 |  |
| No. of business enquiries per year via internet, phone, registering on the property database |  | 200 |  |
| No of business interactions a year ** |  | 200 |  |
| No. of jobs created |  | 99 |  |
| No. of website / social media contacts / year |  | 7000 |  |
| No. of business referrals for funding |  | 30 |  |
| Additional KPIs suggested by contractor |  |  |  |

*NB – the investments (locating from outside East Sussex) and re-investments are different from the ERDF outputs and do not require 12 hours support but do require a positive outcome. They can also be included in C1 if the businesses received more than 12 hours support.

** These are business enquiries that are responded to or contacts made at events or by phone.  Some of these will progress and can be counted under other outputs again .

  - Performance Management Process

    - The Contractor and the County Council will jointly have access to the CRM System to enable continuous monitoring of the KPI’s and other activity monitoring that the Contractor is expected to complete as part of the Contract. The Contractor will be expected to enter into a Data-sharing agreement when finalised with the County and Partners.

    - All evidence relating to the achievement of the Inward Investment Services and the associated KPI’s (including paper forms) will be confirmed by businesses supported by the Contractor and will be stored in the CRM system. Progress towards the achievement of KPI’s will be recorded by the Contractor on the CRM.

    - Performance against the achievement of KPI’s will be undertaken by the County Council’s contract manager with monthly reports and regular contact between the Contractor’s representative and the County Council.  Progress reports are to be produced bi-monthly and presented to the East Sussex Economic Development Officers group meeting.

    - Enhanced progress reports are to be produced quarterly by the Contractor for presentation to the Locate East Sussex Sponsors Board, TES and for onward reporting to the project management board with the lead project partner -  ECC.

    - The monthly reporting will seek to review progress and identify mitigations or escalate as appropriate risks to the delivery of KPIs. The bi–monthly meetings will be utilised to inform the Partners of progress and ensure there is joint working and support to achieve outputs.  The quarterly reports are to evaluate the delivery of the Inward Investment Services against the KPIs and specifically the ERDF Outputs to allow the submission of quarterly returns and consider performance and any potential impacts on claw-back.

    - KPIs and monitoring information will be reviewed within the first three (3) months of the Contract between the County Council and the Contractor to confirm they effectively support the delivery of the required outputs of the Inward Investment Services and remain relevant to the Contractor’s activity. Thereafter, the KPIs and monitoring information will be reviewed by mutual agreement on an annual basis.  Any amendments to the KPIs (save for the ERDF Outputs which are fixed for the entire term of the Contract) will be based on latest performance information.

    - In the event of non-delivery against KPIs or Service Levels, in the first instance the contract manager will seek to work with the Contractor to identify the specific issues, develop understanding and seek to identify mitigations.

    - Should progress towards the delivery of a specific KPI be continuously below 80% of the minimum targets for the relevant quarter, ESCC will seek to work with the supplier to develop a recovery plan.

    - In the event that progress towards a specific KPI remains below 70% for two quarters, the County Council may withhold payment for the subsequent quarter’s activity.

    - Activity under the Contract is part-funded by ERDF monies, and there is a risk of claw-back of funding as a result of failure to deliver outputs. The County Council passes all liability for claw-back to the Contractor in the event of failure to deliver or appropriately evidence the delivery of outputs during the period of the Contract. This will be in line with the terms and conditions set-out in the contract between DCLG and ECC shown in Appendix 1

  - Potential Contractors will be required to outline in their Tender Submission how they will successfully deliver both parts of the Inward Investment Services (i.e. the Core Services and the Enhanced Services).

- Key Dates

  - Presentation by short-listed Contractors to ESCC and Partners at County Hall, Lewes  10th March.

  - Commencement date: 1 May 2017

  - Completion date: 30 April 2020 with optional extension to 30 April 2021.

  - The following table outlines the anticipated delivery milestones that the Contractor will be expected to deliver. In addition, as part of the evaluation of Tender Submissions, Potential Contractors will be expected to outline the anticipated milestones within the delivery plan.

| Milestone | Start Date | Completion Date |
| --- | --- | --- |
| ECC procurement process | January 2016 | February 2017 |
| Contracts signed with service delivery organisations and results/outputs agreed |  | April 2017 |
| Delivery Partner Partnership Agreements signed |  | April 2017 |
| First (quarterly) Steering Group meeting with strategic partners then continuing quarterly until completion | May 2017 | April 2020 |
| First (monthly) Operational Group Meeting, then continuing monthly until completion | May 2017 | April 2020 |
| Project start date; additional procurement / setting up operation teams and Steering Group meetings | May 1st 2017 | July 2017 |
| Memorandum of Understanding signed between referral partners (HEI’s, SEBB etc.) and the Contractor. |  | June 2017 |
| Marketing Plan Implementation | June 2017 | December 2019 |
| Client delivery commences | July 1st 2017 | April 30th 2020 |
| Mid-term project review (external) | September 2018 | November 2019 |
| Client activity ends |  | March 31st 2020 |
| Financial Completion |  | April 30th 2020 |
| End of project evaluation (external) | April 2020 | May 2020 |
| Project completion publicity | February 2020 | April 2020 |
| Milestone | Start Date | Completion Date |

  - Contract period

  - It is anticipated that the Contract shall commence on 1 May 2017 and will continue until 30 April 2020 for a period of 36 months unless terminated in accordance with the terms and conditions of the Contract.

  - Prior to the expiration of the Contract the County Council may, in its absolute discretion, notify the Contractor that it wishes to extend the Contract for a further period or periods of up to a maximum of one (1) year, dependant on the availability of funding.

  - Contract value

  - The value of the Contract for this Lot will be for a fixed-cost delivery totalling £420,000 per annum.

  - The Contract will be funded through contributions from the County Council, the Borough and Districts and the ERDF.  A copy of the ERDF “South East Invest” full application is available on the GOV website.

  - Funding Model

  - The annual budget for the Inward Investment Services is £420,000. This figure must cover all aspects of the service including all liabilities including redundancies and pensions.

  - 90% of this budget will be paid in twelve (12) equal monthly payments to the Contractor, with quarterly accruals taking place on the basis that the Contractor meets the volumetric requirements committed to as part of their Tender Submission.

  - 10% of the budget, in each calendar year, will be retained by the County Council until year end to mitigate the impacts of target volume below 70 of the KPIs not achieved and any claw-back as a result of underperformance against KPI’s. The Contractor will receive the remaining 10% in a single payment at year end in the event that all reporting is completed and all KPIs are satisfactorily met during that quarter.

- Statement of Technical Requirements

  - The Contractor will deliver a first class inward investment service for the County. The Inward Investment Services will have in place the vision and the leadership necessary to work alongside Partners to develop a clear strategy to market and promote the County as a premier inward investment destination in the country.

  - The Contractor will understand:

- the key issues that companies face when looking to relocate,

- the industrial and commercial property market appropriate to the subject matter of the Contract and its relevance to East Sussex localities,

- how to identify and develop leads,

- how to support companies during the relocation process,

- how to support relocated companies following relocation.

- the importance of marketing and branding of the service to businesses.

  - The Contractor will be able to think innovatively and demonstrate creativity, including working with partners to:

- identify the solutions required to create jobs through inward investment throughout the life of the Contract

- to increase the number of companies relocating to the County and / or making the decision to expand and grow; and

- foster the development / creation of new start-up businesses and supporting them to grow / expand.

  - The Contractor will be expected to deliver, alongside the County Council and Partners, specific outcomes that contribute to economic development of the County and in particular  demonstrate how they will address the place marketing and promotion of the County.

  - The Contractor will develop a programme of activity that delivers innovative and creative solutions to secure inward investment in the County by:

- Delivery of the Core Service and related outputs and outcomes; and

- Delivery of the Enhanced Services and related outputs and outcomes.

  - The Contractor will be expected to establish an office-based presence in the County that facilitates a responsive service to businesses and partners in all parts of the County, and includes the provision of suitable meeting space within the County that presents the County in the best light possible to investors.

  - The Contractor will seek to attract investors and undertake activity across the whole county; however, activity will be concentrated on areas of market specialisation, growth sectors and natural ‘clusters’ of industry that are extant within the county.

- TUPE

  - The view of the Council is that the Transfer of Undertaking (Protection of Employment) Regulations 2006 (TUPE) Regulations which implement the Acquired Rights Directive will apply to the Contract.  However, Potential Contractors should seek their own legal advice as to the applicability of TUPE and as to the effect of the TUPE clause contained in the terms and conditions of the Contract.

  - To facilitate the evaluation of Tender Submission on the basis that TUPE will apply, we have collated anonymised information pertaining to the employment of staff (including staffing costs and conditions of employment).

  - Potential Contractors will be provided with a copy of the anonymised TUPE data upon written confirmation that the Potential Contractor will only use the information provided for the purposes of preparing a Tender Submission, that the Potential Contractor will not disclose it to any third party and that the Potential Contractor will destroy such information once the tender process is concluded in the event it is not awarded the Contract. The anonymised TUPE data is provided on the basis that neither the County Council nor ECC give any warranties as to its accuracy and that neither the County Council nor ECC accept any liability for any inaccuracies contained therein.

  - To see the information  please provide your written undertaking that you agree to the above terms via ariba as soon as possible.

- Social Value – Employment and Skills Plan (ESP)

  - The Public Services (Social Value) Act 2012 requires public bodies in England and Wales, including local authorities, to consider how the services they commission and procure might improve the economic, social and environmental well-being of the area.

  - Employment and skills remain central to improving the health, wellbeing and life opportunities for individuals; the social cohesion of communities and the economic competitiveness of East Sussex. A skilled workforce will boost the productivity of our local businesses and provide more jobs for residents in our county.

  - All  existing and potential suppliers are encouraged to support the Council in improving the employment and skills development opportunities available locally for our residents and proactively address potential skills and labour shortages in the County.

  - Employment and Skills Plans (ESPs)

  - An ESP provides the opportunity for suppliers to make commitments to providing employment and skills development opportunities that are relevant and proportionate to the business, service and contract.

  - The contractor is required to complete the ESP table and provide a Method Statement that sets out how you intend to implement and deliver the commitments made in the ESP

  - When submitting an ESP as part of a tender requirement please note that only the commitments made as a result of winning the contract tendered will be considered (previous commitments made and delivered as part of other contracts will not be considered as relevant)

  - All commitments made within the ESP submitted will form part of the contractual agreement and will be monitored as Key Performance Indicators (KPIs). Suppliers will therefore be required to report on these KPIs on a quarterly basis throughout the life of the contract.

- E-Procurement Requirements

    - The County Council pays invoices by BACS using a purchase order system.  The Contractor must register as a Vendor prior to invoicing.  For further information go to https://www.eastsussex.gov.uk/business/doingbusiness/electronicprocurement/

  - The Contractor will be required to submit monthly electronic invoices from an agreed schedule of payments once the PO number has been issued.

# Appendix 1 – Draft ERDF Service agreement

# Appendix 2 – South East Invest Inward Investment Bid