## Sheet1
CLARIFICATION LOG
Tender: | Design and Build Tender: Our Past, Our Future: Royal Institution of Cornwall
Tender Reference: | 01/2024 (01)
Published Date: | 12.02.2024
Version number: | 0.5
Number | Clarification | Response | Reply date
1 | Have date(s) / times for the site visits been agreed? | Yes, the date and time of the site visits are, first site visit to be on 31st Jan between 9.00 am and 12pm and second site visit on 2nd Feb 1pm to 3pm | 2024-01-17
2 | If identified as a supplier for interview can you confirm if the interviews be conducted face to face? | Yes, for those suppliers shortlisted interviews are to be face to face at the Royal Cornwall Museum. | 2024-01-17
3 | Are you expecting a concept design to accompany the tender submission? | We are not expecting concept designs. We would like to see your approach to similar projects that will provide us with an idea of your design approach. If you do not have similar project experience, concept designs would be appreciated. | 2024-01-31
4 | We are based locally- do we need to attend the formal site visit or can we just review given that it’s on the public frontage? | You don't need to attend a formal site visit. However, staff will only be available to answer any queries on the dates and times specified. | 2024-01-31
5 | Are you able to share the museum's interpretation work. | Yes. Please see attached. This Interpretive Plan sets out the interpretive approach for the new Mineral Gallery at The Royal Cornwall Museum, showing the key themes that will run throughout the museum. It draws on the exhibition design brief and in turn will be used to inform the development and design of the gallery, it also supports, and is informed by current work by Counterculture to develop a Business Plan and to review audience development work. The museum entrance will be reconfigured as part of the later capital project. This will create a better physical entrance, but is also an opportunity to consider how visitors understand what the museum is and what to expect. An introduction to the museum through words and objects can help to show what the museum is, and will be able to use the current work to develop a clear identity for the museum. This could also reflect the ideas behind the narrative themes, which connect the museums stunning and eclectic collections. It is important that visitors understand from the beginning why this is a special and unique collection and museum. | 2024-02-06
6 | Is there lighting currently? | Yes | 2024-02-06
7 | Will lighting be required in the future? | Yes | 2024-02-06
8 | Are the sides of the buildings to be included? | Yes, to the left hand side of the building as you look at it is the entrance to the learning area. This area could be used for school visits in the future for them to sit and have lunch. The right hand side needs to include a bin storage area | 2024-02-06
9 | What sort of area are you looking for? | Welcoming, seating, open plan, sculptures, easy and low maintenance, community space. The design must compliment the building. The museum’s mission is to: provide a welcoming, dynamic and lively cultural hub centred around our collections, that inspires people to explore, thrive and have fun. This mission should be reflected in the landscaping. | 2024-02-06
10 | Is signage to be included. | Yes. The appointed designers should work closely with our marketing team to agree the signage to ensure it aligns with the rebranding guidelines. | 2024-02-06
11 | Who will liaise with the conservation officer? | This will be the responsibility of the appointed team. It will also be the responsibility of the team to have discussions with the planning authority in relation to the planning application. | 2024-02-06
12 | Will seating be required in the future for a café? | Yes. Please retain the space that is allocated now. The number of covers is to be maximised. | 2024-02-06
13 | Are the steps part of the Grade 2 listing? | We believe so. | 2024-02-06
14 | Where will the new entrance be in the future? | The new entrance will be subject to funding and won't happen for a couple of years. It is envisage to be as highlighted on the attached photograph: C4_New entrance markup.JPG | 2024-02-06
15 | Do you have measured survey details? | No. This is to be included in your costs. | 2024-02-06
16 | Given the other work that is taking place, who will undertake the Principal Designer and Principal Contractor roles? | The team will be expected to take on the role of Principal Designer and Principal Contractor for the project (with defined scope and site boundaries) and should be able to demonstrate their capability to dispense that responsibility and should cost for the time it will take. There may be times when more than one contractor is working on site at any given time. Each will have defined scope and boundaries. All contractors will be required to maintain safe access through the front door and fire escapes etc so, for example, the gallery contractor can still bring materials into the front door through the landscape site. | 2024-02-06
17 | Are you able to share the Museum's branding work. | This is still in development but will be shared as soon as possible to the successful team. | 2024-02-06
18 | Can you share the plans of the building. | Yes. Please see attached. | 2024-02-06
19 | This is a design and build tender so we, as the design team, have teamed up with a local landscape contractor company. Clearly we cannot put a price in for the build cost yet as we dont know what the scheme is going to be! The landscape contractor would be involved in the design stage to ensure that the build cost is within the contract values identified on the brief. That would be the most efficient way to get the project built due to the time limitations. However, will the procurement rules allow for a non tendered contract for the build component as we can only realistically price for the design stages at this stage of the works? Please can you confirm that it is a design and build but that for the purpose of the tender, the only cost you need is the design fee for all stages and for all the listed tasks ( eg design/ project management/ CDM/ Cost control?) . Build cost will be identified following design but that a tender is NOT required for the contractor element. | The RIC is seeking a design and build team - and will only contract with the lead organisation. We are not seeking a separate tender for the contractor element. The total overall maximum budget for the tender is £210k (including VAT) with the Construction aspects for the Works element being between £170k to £189k (including VAT). For evaluation purposes, the evaluation of bids will be based on the cost associated of the design element and overall costs. This must be within the overall budget envelope as above. | 2024-02-06
20 | What are your values? | Brave Using imagination, creativity and sideways thinking, we thrive on bringing people together for unexpected and unconventional experiences, conversations and interactions. We’re not afraid to stand up for what we believe in, for a better and fairer society for everyone. Welcoming Our spaces and team behaviours/ attitude are warm, safe, open and inclusive. We celebrate difference and work hard to listen and reflect what our diverse community needs – from calming corners to areas bustling with noise and energy – so everyone feels like they belong. Connected We’re in Cornwall and for Cornwall, but we also reach outwards – through stories, collaborations and exhibitions that are relevant in a much wider context, too. We use the expertise and insight from our collections and community to contribute to important conversations locally, nationally and internationally. Curious We’re always asking questions, exploring ideas and challenging ourselves to find new and better ways of doing things – never standing still or taking anything for granted. We’re a museum, but we’re continually re imagining what a museum can be – and the impact it can have. Committed We’re environmentally and socially responsible in everything we do, always looking for ways to reduce our environmental footprint and look after the community we serve. We’re not afraid to take a difficult path or change course if it brings us closer to achieving our purpose. | 2024-02-06
21 | We have one more question regarding the bid submission itself. We note that a lot of the questions you ask have a limit on how many words you would like us to write. If we struggle to answer the question as thoroughly as we would like to within 750 words, will we be automatically disqualified, will you only read the first 750 words or is this just a guideline so that you don’t receive pages and pages for each question. If for example we submit an answer with 850 words, what would happen? | Ideally the word count should be inline with what is stated or as near as possible. | 2024-02-13
22 | Further to question 4 above - are plans available of the building. | Further to question 4 above - building plans of the museaum are uploaded solely for information purposes : App_1 2012-0022-2 RCM Location codes Level 1 : App1_ 2012-0021-2 RCM Location codes Level 0 : App1_ 2012-0023-1 RCM Location codes Level 2 : App1_ 2012-0024-1 RCM Location codes Level 3 : App1_ 2012-0026-1 RCM Location codes Level 5 : App1_ 2012-0027-1 RCM Location codes Level 6 Along with Interpetation Strategy document and photo of front showing the area to be overhauled. | 2024-02-13
Clarifications will be published against the Contract Notice on Contracts Finder.
If interested in tendering for this project please ensure you add a "watch this notice" for alerts as from time to time additional information or clarifications may be published related to this tender.
It will be the responsibility of Bidders to ensure they are aware of all published clarifications and ensure that their bid has taken these into account.
In the event of any queries please contact: